## Sheet1
| Unnamed: 0.2 | Unnamed: 0.1 | Unnamed: 0 | Job Code | DESCRIPTION | CODE | Hierarchy | Concat | Order | Middle Part | Classification | Last Four | Code Final
0 | 0 | 0 | 0 | SA24M005 | Contractual Milestones |  | 1 | -1 | 0 |  |  | X
1 | 1 | 1 | 1 | SA24M005 | Portion- I |  | 2 | -1 | 0 |  |  | X
2 | 2 | 2 | 2 | SA24M005 | Complete Mobilization and Commence the work- Portion I |  | 0 | Contractual Milestones Portion- I Complete Mobilization and Commence the work- Portion I | 1 | CM00MW | L000 | 00L1 | L000CM00MW00L1
3 | 3 | 3 | 3 | SA24M005 | Technical Completion of the Project ( TCC )- Portion I |  | 0 | Contractual Milestones Portion- I Technical Completion of the Project ( TCC )- Portion I | 2 | CM00MW | L000 | 00L2 | L000CM00MW00L2
4 | 4 | 4 | 4 | SA24M005 | Preliminary Acceptance of the Project ( PAC )- Portion I |  | 0 | Contractual Milestones Portion- I Preliminary Acceptance of the Project ( PAC )- Portion I | 3 | CM00MW | L000 | 00L3 | L000CM00MW00L3
5 | 5 | 5 | 5 | SA24M005 | Final Acceptance of the Work ( FAC )- Portion I |  | 0 | Contractual Milestones Portion- I Final Acceptance of the Work ( FAC )- Portion I | 4 | CM00MW | L000 | 00L4 | L000CM00MW00L4
6 | 6 | 6 | 6 | SA24M005 | Portion- II |  | 2 | -1 | 0 |  |  | X
7 | 7 | 7 | 7 | SA24M005 | Complete Mobilization and Commence the work- Portion II |  | 0 | Contractual Milestones Portion- II Complete Mobilization and Commence the work- Portion II | 1 | CMOBW | L000 | 00L1 | L000CMOBW00L1
8 | 8 | 8 | 8 | SA24M005 | Technical Completion of the Project ( TCC )- Portion II |  | 0 | Contractual Milestones Portion- II Technical Completion of the Project ( TCC )- Portion II | 2 | CMOBW | L000 | 00L2 | L000CMOBW00L2
9 | 9 | 9 | 9 | SA24M005 | Preliminary Acceptance of the Project ( PAC )- Portion II |  | 0 | Contractual Milestones Portion- II Preliminary Acceptance of the Project ( PAC )- Portion II | 3 | CMOBW | L000 | 00L3 | L000CMOBW00L3
10 | 10 | 10 | 10 | SA24M005 | Final Acceptance of the Work ( FAC )- Portion II |  | 0 | Contractual Milestones Portion- II Final Acceptance of the Work ( FAC )- Portion II | 4 | CMOBW | L000 | 00L4 | L000CMOBW00L4
11 | 11 | 11 | 11 | SA24M005 | Internal Milestones |  | 1 | -1 | 0 |  |  | X
12 | 12 | 12 | 12 | SA24M005 | Contract Award Date |  | 0 | Internal Milestones Contract Award Date | 1 | IMILC | L000 | 00L1 | L000IMILC00L1
13 | 13 | 13 | 13 | SA24M005 | Engineering & Design Completion |  | 0 | Internal Milestones Engineering & Design Completion | 2 | IMILC | L000 | 00L2 | L000IMILC00L2
14 | 14 | 14 | 14 | SA24M005 | Equipment & Materials Delivery |  | 0 | Internal Milestones Equipment & Materials Delivery | 3 | IMILC | L000 | 00L3 | L000IMILC00L3
15 | 15 | 15 | 15 | SA24M005 | Completion of Civil Works |  | 0 | Internal Milestones Completion of Civil Works | 4 | IMILC | L000 | 00L4 | L000IMILC00L4
16 | 16 | 16 | 16 | SA24M005 | Completion of Installation Works |  | 0 | Internal Milestones Completion of Installation Works | 5 | IMILC | L000 | 00L5 | L000IMILC00L5
17 | 17 | 17 | 17 | SA24M005 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors |  | 1 | -1 | 0 |  |  | X
18 | 18 | 18 | 18 | SA24M005 | Main Station- North Qassim 380kV BSP (9061 BSP) |  | 2 | -1 | 0 |  |  | X
19 | 19 | 19 | 19 | SA24M005 | Preliminary Works |  | 3 | -1 | 0 |  |  | X
20 | 20 | 20 | 20 | SA24M005 | General Works |  | 4 | -1 | 0 |  |  | X
21 | 21 | 21 | 21 | SA24M005 | Kick off Meeting with Project Team |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Preliminary Works General Works Kick off Meeting with Project Team | 1 | #fSZX | E000 | 00E1 | E000#fSZX00E1
22 | 22 | 22 | 22 | SA24M005 | PQD for Design Agency - Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Preliminary Works General Works PQD for Design Agency - Submission | 2 | #fSZX | E000 | 00E2 | E000#fSZX00E2
23 | 23 | 23 | 23 | SA24M005 | PQD for Design Agency - Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Preliminary Works General Works PQD for Design Agency - Approval | 3 | #fSZX | E000 | 00E3 | E000#fSZX00E3
24 | 24 | 24 | 24 | SA24M005 | Finalization of Design Consultant |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Preliminary Works General Works Finalization of Design Consultant | 4 | #fSZX | E000 | 00E4 | E000#fSZX00E4
25 | 25 | 25 | 25 | SA24M005 | Submission of Comprehensive General Liability Insurance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Preliminary Works General Works Submission of Comprehensive General Liability Insurance | 5 | #fSZX | E000 | 00E5 | E000#fSZX00E5
26 | 26 | 26 | 26 | SA24M005 | Submission of Contractor's All Risk Insurance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Preliminary Works General Works Submission of Contractor's All Risk Insurance | 6 | #fSZX | E000 | 00E6 | E000#fSZX00E6
27 | 27 | 27 | 27 | SA24M005 | Submission of Medical Insurance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Preliminary Works General Works Submission of Medical Insurance | 7 | #fSZX | E000 | 00E7 | E000#fSZX00E7
28 | 28 | 28 | 28 | SA24M005 | Submission of Marine Insurance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Preliminary Works General Works Submission of Marine Insurance | 8 | #fSZX | E000 | 00E8 | E000#fSZX00E8
29 | 29 | 29 | 29 | SA24M005 | Submission of Automobile Insurance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Preliminary Works General Works Submission of Automobile Insurance | 9 | #fSZX | E000 | 00E9 | E000#fSZX00E9
30 | 30 | 30 | 30 | SA24M005 | Submission of Performance Security BG |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Preliminary Works General Works Submission of Performance Security BG | 10 | #fSZX | E000 | 0E10 | E000#fSZX0E10
31 | 31 | 31 | 31 | SA24M005 | Submission of Additional Performance Secutiies (if applicable) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Preliminary Works General Works Submission of Additional Performance Secutiies (if applicable) | 11 | #fSZX | E000 | 0E11 | E000#fSZX0E11
32 | 32 | 32 | 32 | SA24M005 | Obtaining Permits & Licenses in Contractor's Name |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Preliminary Works General Works Obtaining Permits & Licenses in Contractor's Name | 12 | #fSZX | E000 | 0E12 | E000#fSZX0E12
33 | 33 | 33 | 33 | SA24M005 | Obtaining Identification Cards from SEC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Preliminary Works General Works Obtaining Identification Cards from SEC | 13 | #fSZX | E000 | 0E13 | E000#fSZX0E13
34 | 34 | 34 | 34 | SA24M005 | Municipality Authorization (If applicable) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Preliminary Works General Works Municipality Authorization (If applicable) | 14 | #fSZX | E000 | 0E14 | E000#fSZX0E14
35 | 35 | 35 | 35 | SA24M005 | Other Licenses & Governmental approval (If applicable) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Preliminary Works General Works Other Licenses & Governmental approval (If applicable) | 15 | #fSZX | E000 | 0E15 | E000#fSZX0E15
36 | 36 | 36 | 36 | SA24M005 | Mobilization |  | 4 | -1 | 0 |  |  | X
37 | 37 | 37 | 37 | SA24M005 | Organization chart for Key Staffs - Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Preliminary Works Mobilization Organization chart for Key Staffs - Submission | 1 | PMOBK | E000 | 00E1 | E000PMOBK00E1
38 | 38 | 38 | 38 | SA24M005 | Organization chart for Key Staffs - Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Preliminary Works Mobilization Organization chart for Key Staffs - Approval | 2 | PMOBK | E000 | 00E2 | E000PMOBK00E2
39 | 39 | 39 | 39 | SA24M005 | Loss Prevention Program Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Preliminary Works Mobilization Loss Prevention Program Submission | 3 | PMOBK | E000 | 00E3 | E000PMOBK00E3
40 | 40 | 40 | 40 | SA24M005 | Loss Prevention Program Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Preliminary Works Mobilization Loss Prevention Program Approval | 4 | PMOBK | E000 | 00E4 | E000PMOBK00E4
41 | 41 | 41 | 41 | SA24M005 | PQP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Preliminary Works Mobilization PQP Submission | 5 | PMOBK | E000 | 00E5 | E000PMOBK00E5
42 | 42 | 42 | 42 | SA24M005 | PQP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Preliminary Works Mobilization PQP Approval | 6 | PMOBK | E000 | 00E6 | E000PMOBK00E6
43 | 43 | 43 | 43 | SA24M005 | Site Plot Handing Over |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Preliminary Works Mobilization Site Plot Handing Over | 7 | PMOBK | E000 | 00E7 | E000PMOBK00E7
44 | 44 | 44 | 44 | SA24M005 | Identification of Land for Temporary Site Facilities |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Preliminary Works Mobilization Identification of Land for Temporary Site Facilities | 8 | PMOBK | E000 | 00E8 | E000PMOBK00E8
45 | 45 | 45 | 45 | SA24M005 | Approval of Land for Temporary Site Facilities |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Preliminary Works Mobilization Approval of Land for Temporary Site Facilities | 9 | PMOBK | E000 | 00E9 | E000PMOBK00E9
46 | 46 | 46 | 46 | SA24M005 | Establishment of Temporary Site Facilities for SEC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Preliminary Works Mobilization Establishment of Temporary Site Facilities for SEC | 10 | PMOBK | E000 | 0E10 | E000PMOBK0E10
47 | 47 | 47 | 47 | SA24M005 | Establishment of Temporary site facilities & Laydown yard for L&T |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Preliminary Works Mobilization Establishment of Temporary site facilities & Laydown yard for L&T | 11 | PMOBK | E000 | 0E11 | E000PMOBK0E11
48 | 48 | 48 | 48 | SA24M005 | Labour and Other Resource Setup |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Preliminary Works Mobilization Labour and Other Resource Setup | 12 | PMOBK | E000 | 0E12 | E000PMOBK0E12
49 | 49 | 49 | 49 | SA24M005 | Establishment of Site Office |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Preliminary Works Mobilization Establishment of Site Office | 13 | PMOBK | E000 | 0E13 | E000PMOBK0E13
50 | 50 | 50 | 50 | SA24M005 | Arranging Vehicles for Company use |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Preliminary Works Mobilization Arranging Vehicles for Company use | 14 | PMOBK | E000 | 0E14 | E000PMOBK0E14
51 | 51 | 51 | 51 | SA24M005 | Preliminary Civil Works |  | 4 | -1 | 0 |  |  | X
52 | 52 | 52 | 52 | SA24M005 | Site Grading layout plan & Section submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Preliminary Works Preliminary Civil Works Site Grading layout plan & Section submission | 1 | PCW | E000 | 00E1 | E000PCW00E1
53 | 53 | 53 | 53 | SA24M005 | Site Grading layout plan & Section approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Preliminary Works Preliminary Civil Works Site Grading layout plan & Section approval | 2 | PCW | E000 | 00E2 | E000PCW00E2
54 | 54 | 54 | 54 | SA24M005 | Submission Exisitng nearby proposed road level |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Preliminary Works Preliminary Civil Works Submission Exisitng nearby proposed road level | 3 | PCW | E000 | 00E3 | E000PCW00E3
55 | 55 | 55 | 55 | SA24M005 | Approval by SEC for road level |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Preliminary Works Preliminary Civil Works Approval by SEC for road level | 4 | PCW | E000 | 00E4 | E000PCW00E4
56 | 56 | 56 | 56 | SA24M005 | PQD for Geo-technical Investigation - Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Preliminary Works Preliminary Civil Works PQD for Geo-technical Investigation - Submission | 5 | PCW | E000 | 00E5 | E000PCW00E5
57 | 57 | 57 | 57 | SA24M005 | PQD for Geo-technical Investigation - Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Preliminary Works Preliminary Civil Works PQD for Geo-technical Investigation - Approval | 6 | PCW | E000 | 00E6 | E000PCW00E6
58 | 58 | 58 | 58 | SA24M005 | Bore Hole, ERT & TRT Layout Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Preliminary Works Preliminary Civil Works Bore Hole, ERT & TRT Layout Submission | 7 | PCW | E000 | 00E7 | E000PCW00E7
59 | 59 | 59 | 59 | SA24M005 | Bore Hole, ERT & TRT Layout comments & Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Preliminary Works Preliminary Civil Works Bore Hole, ERT & TRT Layout comments & Approval | 8 | PCW | E000 | 00E8 | E000PCW00E8
60 | 60 | 60 | 60 | SA24M005 | PQD for RMC Vendor - Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Preliminary Works Preliminary Civil Works PQD for RMC Vendor - Submission | 9 | PCW | E000 | 00E9 | E000PCW00E9
61 | 61 | 61 | 61 | SA24M005 | PQD for RMC Vendor - Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Preliminary Works Preliminary Civil Works PQD for RMC Vendor - Approval | 10 | PCW | E000 | 0E10 | E000PCW0E10
62 | 62 | 62 | 62 | SA24M005 | Design & Engineering |  | 3 | -1 | 0 |  |  | X
63 | 63 | 63 | 63 | SA24M005 | Phase- I |  | 4 | -1 | 0 |  |  | X
64 | 64 | 64 | 64 | SA24M005 | Electrical |  | 5 | -1 | 0 |  |  | X
65 | 65 | 65 | 65 | SA24M005 | Drawing Control Sheet |  | 6 | -1 | 0 |  |  | X
66 | 66 | 66 | 66 | SA24M005 | Drafting / Preparation | E000E0DCS00E1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical Drawing Control Sheet Drafting / Preparation | 1 | E0DCS | E000 | 00E1 | E000#IomO00E1
67 | 67 | 67 | 67 | SA24M005 | Submission | E000E0DCS00E2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical Drawing Control Sheet Submission | 2 | E0DCS | E000 | 00E2 | E000#IomO00E2
68 | 68 | 68 | 68 | SA24M005 | Review / Evaluation | E000E0DCS00E3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical Drawing Control Sheet Review / Evaluation | 3 | E0DCS | E000 | 00E3 | E000#IomO00E3
69 | 69 | 69 | 69 | SA24M005 | Approval with Comments | E000E0DCS00E4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical Drawing Control Sheet Approval with Comments | 4 | E0DCS | E000 | 00E4 | E000#IomO00E4
70 | 70 | 70 | 70 | SA24M005 | FINAL Approval | E000E0DCS00E5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical Drawing Control Sheet FINAL Approval | 5 | E0DCS | E000 | 00E5 | E000#IomO00E5
71 | 71 | 71 | 71 | SA24M005 | List of Proposed Main Manufacturers for Major Materials |  | 6 | -1 | 0 |  |  | X | E000#IomO
72 | 72 | 72 | 72 | SA24M005 | Drafting / Preparation | E000E0MMM00E1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical List of Proposed Main Manufacturers for Major Materials Drafting / Preparation | 1 | E0MMM | E000 | 00E1 | E000E0MMM00E1
73 | 73 | 73 | 73 | SA24M005 | Submission | E000E0MMM00E2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical List of Proposed Main Manufacturers for Major Materials Submission | 2 | E0MMM | E000 | 00E2 | E000E0MMM00E2
74 | 74 | 74 | 74 | SA24M005 | Review / Evaluation | E000E0MMM00E3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical List of Proposed Main Manufacturers for Major Materials Review / Evaluation | 3 | E0MMM | E000 | 00E3 | E000E0MMM00E3
75 | 75 | 75 | 75 | SA24M005 | Approval with Comments | E000E0MMM00E4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical List of Proposed Main Manufacturers for Major Materials Approval with Comments | 4 | E0MMM | E000 | 00E4 | E000E0MMM00E4
76 | 76 | 76 | 76 | SA24M005 | FINAL Approval | E000E0MMM00E5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical List of Proposed Main Manufacturers for Major Materials FINAL Approval | 5 | E0MMM | E000 | 00E5 | E000E0MMM00E5
77 | 77 | 77 | 77 | SA24M005 | Overall Substation Layout (Equipment arrangement Plan & Sections) |  | 6 | -1 | 0 |  |  | X
78 | 78 | 78 | 78 | SA24M005 | Drafting / Preparation | E000E0SSL00E1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical Overall Substation Layout (Equipment arrangement Plan & Sections) Drafting / Preparation | 1 | E0SSL | E000 | 00E1 | E000E0SSL00E1
79 | 79 | 79 | 79 | SA24M005 | Submission | E000E0SSL00E2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical Overall Substation Layout (Equipment arrangement Plan & Sections) Submission | 2 | E0SSL | E000 | 00E2 | E000E0SSL00E2
80 | 80 | 80 | 80 | SA24M005 | Review / Evaluation | E000E0SSL00E3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical Overall Substation Layout (Equipment arrangement Plan & Sections) Review / Evaluation | 3 | E0SSL | E000 | 00E3 | E000E0SSL00E3
81 | 81 | 81 | 81 | SA24M005 | Approval with Comments | E000E0SSL00E4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical Overall Substation Layout (Equipment arrangement Plan & Sections) Approval with Comments | 4 | E0SSL | E000 | 00E4 | E000E0SSL00E4
82 | 82 | 82 | 82 | SA24M005 | FINAL Approval | E000E0SSL00E5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical Overall Substation Layout (Equipment arrangement Plan & Sections) FINAL Approval | 5 | E0SSL | E000 | 00E5 | E000E0SSL00E5
83 | 83 | 83 | 83 | SA24M005 | Soil resistivity measurement location |  | 6 | -1 | 0 |  |  | X
84 | 84 | 84 | 84 | SA24M005 | Drafting / Preparation | E000E0SRM00E1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical Soil resistivity measurement location Drafting / Preparation | 1 | E0SRM | E000 | 00E1 | E000E0SRM00E1
85 | 85 | 85 | 85 | SA24M005 | Submission | E000E0SRM00E2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical Soil resistivity measurement location Submission | 2 | E0SRM | E000 | 00E2 | E000E0SRM00E2
86 | 86 | 86 | 86 | SA24M005 | Review / Evaluation | E000E0SRM00E3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical Soil resistivity measurement location Review / Evaluation | 3 | E0SRM | E000 | 00E3 | E000E0SRM00E3
87 | 87 | 87 | 87 | SA24M005 | Approval with Comments | E000E0SRM00E4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical Soil resistivity measurement location Approval with Comments | 4 | E0SRM | E000 | 00E4 | E000E0SRM00E4
88 | 88 | 88 | 88 | SA24M005 | FINAL Approval | E000E0SRM00E5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical Soil resistivity measurement location FINAL Approval | 5 | E0SRM | E000 | 00E5 | E000E0SRM00E5
89 | 89 | 89 | 89 | SA24M005 | Soil resistivity report |  | 6 | -1 | 0 |  |  | X
90 | 90 | 90 | 90 | SA24M005 | Drafting / Preparation | E000E0SRP00E1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical Soil resistivity report Drafting / Preparation | 1 | E0SRP | E000 | 00E1 | E000E0SRP00E1
91 | 91 | 91 | 91 | SA24M005 | Submission | E000E0SRP00E2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical Soil resistivity report Submission | 2 | E0SRP | E000 | 00E2 | E000E0SRP00E2
92 | 92 | 92 | 92 | SA24M005 | Review / Evaluation | E000E0SRP00E3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical Soil resistivity report Review / Evaluation | 3 | E0SRP | E000 | 00E3 | E000E0SRP00E3
93 | 93 | 93 | 93 | SA24M005 | Approval with Comments | E000E0SRP00E4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical Soil resistivity report Approval with Comments | 4 | E0SRP | E000 | 00E4 | E000E0SRP00E4
94 | 94 | 94 | 94 | SA24M005 | FINAL Approval | E000E0SRP00E5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical Soil resistivity report FINAL Approval | 5 | E0SRP | E000 | 00E5 | E000E0SRP00E5
95 | 95 | 95 | 95 | SA24M005 | Quality Assurance and Quality Control Plan |  | 6 | -1 | 0 |  |  | X
96 | 96 | 96 | 96 | SA24M005 | Drafting / Preparation | E000EQAQC00E1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical Quality Assurance and Quality Control Plan Drafting / Preparation | 1 | EQAQC | E000 | 00E1 | E000#sCEz00E1
97 | 97 | 97 | 97 | SA24M005 | Submission | E000EQAQC00E2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical Quality Assurance and Quality Control Plan Submission | 2 | EQAQC | E000 | 00E2 | E000#sCEz00E2
98 | 98 | 98 | 98 | SA24M005 | Review / Evaluation | E000EQAQC00E3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical Quality Assurance and Quality Control Plan Review / Evaluation | 3 | EQAQC | E000 | 00E3 | E000#sCEz00E3
99 | 99 | 99 | 99 | SA24M005 | Approval with Comments | E000EQAQC00E4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical Quality Assurance and Quality Control Plan Approval with Comments | 4 | EQAQC | E000 | 00E4 | E000#sCEz00E4
100 | 100 | 100 | 100 | SA24M005 | FINAL Approval | E000EQAQC00E5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical Quality Assurance and Quality Control Plan FINAL Approval | 5 | EQAQC | E000 | 00E5 | E000#sCEz00E5
101 | 101 | 101 | 101 | SA24M005 | Main Single Line Diagrams |  | 6 | -1 | 0 |  |  | X | E000#sCEz
102 | 102 | 102 | 102 | SA24M005 | Drafting / Preparation | E000EMSLD00E1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical Main Single Line Diagrams Drafting / Preparation | 1 | EMSLD | E000 | 00E1 | E000EMSLD00E1
103 | 103 | 103 | 103 | SA24M005 | Submission | E000EMSLD00E2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical Main Single Line Diagrams Submission | 2 | EMSLD | E000 | 00E2 | E000EMSLD00E2
104 | 104 | 104 | 104 | SA24M005 | Review / Evaluation | E000EMSLD00E3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical Main Single Line Diagrams Review / Evaluation | 3 | EMSLD | E000 | 00E3 | E000EMSLD00E3
105 | 105 | 105 | 105 | SA24M005 | Approval with Comments | E000EMSLD00E4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical Main Single Line Diagrams Approval with Comments | 4 | EMSLD | E000 | 00E4 | E000EMSLD00E4
106 | 106 | 106 | 106 | SA24M005 | FINAL Approval | E000EMSLD00E5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical Main Single Line Diagrams FINAL Approval | 5 | EMSLD | E000 | 00E5 | E000EMSLD00E5
107 | 107 | 107 | 107 | SA24M005 | EHV BSP Gantry and/or HV SS (Gantry- OHTL) physical interfacing Connection Diagram |  | 6 | -1 | 0 |  |  | X
108 | 108 | 108 | 108 | SA24M005 | Drafting / Preparation | E000E0GAN00E1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical EHV BSP Gantry and/or HV SS (Gantry- OHTL) physical interfacing Connection Diagram Drafting / Preparation | 1 | E0GAN | E000 | 00E1 | E000#Oxzl00E1
109 | 109 | 109 | 109 | SA24M005 | Submission | E000E0GAN00E2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical EHV BSP Gantry and/or HV SS (Gantry- OHTL) physical interfacing Connection Diagram Submission | 2 | E0GAN | E000 | 00E2 | E000#Oxzl00E2
110 | 110 | 110 | 110 | SA24M005 | Review / Evaluation | E000E0GAN00E3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical EHV BSP Gantry and/or HV SS (Gantry- OHTL) physical interfacing Connection Diagram Review / Evaluation | 3 | E0GAN | E000 | 00E3 | E000#Oxzl00E3
111 | 111 | 111 | 111 | SA24M005 | Approval with Comments | E000E0GAN00E4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical EHV BSP Gantry and/or HV SS (Gantry- OHTL) physical interfacing Connection Diagram Approval with Comments | 4 | E0GAN | E000 | 00E4 | E000#Oxzl00E4
112 | 112 | 112 | 112 | SA24M005 | FINAL Approval | E000E0GAN00E5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical EHV BSP Gantry and/or HV SS (Gantry- OHTL) physical interfacing Connection Diagram FINAL Approval | 5 | E0GAN | E000 | 00E5 | E000#Oxzl00E5
113 | 113 | 113 | 113 | SA24M005 | HCIS Layout |  | 6 | -1 | 0 |  |  | X | E000#Oxzl
114 | 114 | 114 | 114 | SA24M005 | Drafting / Preparation | E000EHCIS00E1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical HCIS Layout Drafting / Preparation | 1 | EHCIS | E000 | 00E1 | E000EHCIS00E1
115 | 115 | 115 | 115 | SA24M005 | Submission | E000EHCIS00E2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical HCIS Layout Submission | 2 | EHCIS | E000 | 00E2 | E000EHCIS00E2
116 | 116 | 116 | 116 | SA24M005 | Review / Evaluation | E000EHCIS00E3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical HCIS Layout Review / Evaluation | 3 | EHCIS | E000 | 00E3 | E000EHCIS00E3
117 | 117 | 117 | 117 | SA24M005 | Approval with Comments | E000EHCIS00E4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical HCIS Layout Approval with Comments | 4 | EHCIS | E000 | 00E4 | E000EHCIS00E4
118 | 118 | 118 | 118 | SA24M005 | FINAL Approval | E000EHCIS00E5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical HCIS Layout FINAL Approval | 5 | EHCIS | E000 | 00E5 | E000EHCIS00E5
119 | 119 | 119 | 119 | SA24M005 | CCTV Details |  | 6 | -1 | 0 |  |  | X
120 | 120 | 120 | 120 | SA24M005 | Drafting / Preparation | E000ECCTV00E1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical CCTV Details Drafting / Preparation | 1 | ECCTV | E000 | 00E1 | E000#VlZt00E1
121 | 121 | 121 | 121 | SA24M005 | Submission | E000ECCTV00E2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical CCTV Details Submission | 2 | ECCTV | E000 | 00E2 | E000#VlZt00E2
122 | 122 | 122 | 122 | SA24M005 | Review / Evaluation | E000ECCTV00E3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical CCTV Details Review / Evaluation | 3 | ECCTV | E000 | 00E3 | E000#VlZt00E3
123 | 123 | 123 | 123 | SA24M005 | Approval with Comments | E000ECCTV00E4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical CCTV Details Approval with Comments | 4 | ECCTV | E000 | 00E4 | E000#VlZt00E4
124 | 124 | 124 | 124 | SA24M005 | FINAL Approval | E000ECCTV00E5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical CCTV Details FINAL Approval | 5 | ECCTV | E000 | 00E5 | E000#VlZt00E5
125 | 125 | 125 | 125 | SA24M005 | Surge Arrester- Insulation Coordination Study ICS |  | 6 | -1 | 0 |  |  | X | E000#VlZt
126 | 126 | 126 | 126 | SA24M005 | Drafting / Preparation | E000ESURG00E1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical Surge Arrester- Insulation Coordination Study ICS Drafting / Preparation | 1 | ESURG | E000 | 00E1 | E000#ofee00E1
127 | 127 | 127 | 127 | SA24M005 | Submission | E000ESURG00E2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical Surge Arrester- Insulation Coordination Study ICS Submission | 2 | ESURG | E000 | 00E2 | E000#ofee00E2
128 | 128 | 128 | 128 | SA24M005 | Review / Evaluation | E000ESURG00E3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical Surge Arrester- Insulation Coordination Study ICS Review / Evaluation | 3 | ESURG | E000 | 00E3 | E000#ofee00E3
129 | 129 | 129 | 129 | SA24M005 | Approval with Comments | E000ESURG00E4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical Surge Arrester- Insulation Coordination Study ICS Approval with Comments | 4 | ESURG | E000 | 00E4 | E000#ofee00E4
130 | 130 | 130 | 130 | SA24M005 | FINAL Approval | E000ESURG00E5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical Surge Arrester- Insulation Coordination Study ICS FINAL Approval | 5 | ESURG | E000 | 00E5 | E000#ofee00E5
131 | 131 | 131 | 131 | SA24M005 | Design of EHV Surge Arrestors |  | 6 | -1 | 0 |  |  | X | E000#ofee
132 | 132 | 132 | 132 | SA24M005 | Drafting / Preparation | E000E0SRG00E1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical Design of EHV Surge Arrestors Drafting / Preparation | 1 | E0SRG | E000 | 00E1 | E000E0SRG00E1
133 | 133 | 133 | 133 | SA24M005 | Submission | E000E0SRG00E2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical Design of EHV Surge Arrestors Submission | 2 | E0SRG | E000 | 00E2 | E000E0SRG00E2
134 | 134 | 134 | 134 | SA24M005 | Review / Evaluation | E000E0SRG00E3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical Design of EHV Surge Arrestors Review / Evaluation | 3 | E0SRG | E000 | 00E3 | E000E0SRG00E3
135 | 135 | 135 | 135 | SA24M005 | Approval with Comments | E000E0SRG00E4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical Design of EHV Surge Arrestors Approval with Comments | 4 | E0SRG | E000 | 00E4 | E000E0SRG00E4
136 | 136 | 136 | 136 | SA24M005 | FINAL Approval | E000E0SRG00E5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical Design of EHV Surge Arrestors FINAL Approval | 5 | E0SRG | E000 | 00E5 | E000E0SRG00E5
137 | 137 | 137 | 137 | SA24M005 | Design of HV Surge Arrestors |  | 6 | -1 | 0 |  |  | X
138 | 138 | 138 | 138 | SA24M005 | Drafting / Preparation | E000EHSRG00E1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical Design of HV Surge Arrestors Drafting / Preparation | 1 | EHSRG | E000 | 00E1 | E000EHSRG00E1
139 | 139 | 139 | 139 | SA24M005 | Submission | E000EHSRG00E2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical Design of HV Surge Arrestors Submission | 2 | EHSRG | E000 | 00E2 | E000EHSRG00E2
140 | 140 | 140 | 140 | SA24M005 | Review / Evaluation | E000EHSRG00E3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical Design of HV Surge Arrestors Review / Evaluation | 3 | EHSRG | E000 | 00E3 | E000EHSRG00E3
141 | 141 | 141 | 141 | SA24M005 | Approval with Comments | E000EHSRG00E4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical Design of HV Surge Arrestors Approval with Comments | 4 | EHSRG | E000 | 00E4 | E000EHSRG00E4
142 | 142 | 142 | 142 | SA24M005 | FINAL Approval | E000EHSRG00E5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Electrical Design of HV Surge Arrestors FINAL Approval | 5 | EHSRG | E000 | 00E5 | E000EHSRG00E5
143 | 143 | 143 | 143 | SA24M005 | Civil |  | 5 | -1 | 0 |  |  | X
144 | 144 | 144 | 144 | SA24M005 | 3D Presentation Of Substation |  | 6 | -1 | 0 |  |  | X
145 | 145 | 145 | 145 | SA24M005 | Drafting / Preparation | E000C03DP00E1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil 3D Presentation Of Substation Drafting / Preparation | 1 | C03DP | E000 | 00E1 | E000C03DP00E1
146 | 146 | 146 | 146 | SA24M005 | Submission | E000C03DP00E2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil 3D Presentation Of Substation Submission | 2 | C03DP | E000 | 00E2 | E000C03DP00E2
147 | 147 | 147 | 147 | SA24M005 | Review / Evaluation | E000C03DP00E3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil 3D Presentation Of Substation Review / Evaluation | 3 | C03DP | E000 | 00E3 | E000C03DP00E3
148 | 148 | 148 | 148 | SA24M005 | Approval with Comments | E000C03DP00E4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil 3D Presentation Of Substation Approval with Comments | 4 | C03DP | E000 | 00E4 | E000C03DP00E4
149 | 149 | 149 | 149 | SA24M005 | FINAL Approval | E000C03DP00E5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil 3D Presentation Of Substation FINAL Approval | 5 | C03DP | E000 | 00E5 | E000C03DP00E5
150 | 150 | 150 | 150 | SA24M005 | Temporary Project Sign Board |  | 6 | -1 | 0 |  |  | X
151 | 151 | 151 | 151 | SA24M005 | Drafting / Preparation | E000CTPSB00E1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Temporary Project Sign Board Drafting / Preparation | 1 | CTPSB | E000 | 00E1 | E000CTPSB00E1
152 | 152 | 152 | 152 | SA24M005 | Submission | E000CTPSB00E2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Temporary Project Sign Board Submission | 2 | CTPSB | E000 | 00E2 | E000CTPSB00E2
153 | 153 | 153 | 153 | SA24M005 | Review / Evaluation | E000CTPSB00E3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Temporary Project Sign Board Review / Evaluation | 3 | CTPSB | E000 | 00E3 | E000CTPSB00E3
154 | 154 | 154 | 154 | SA24M005 | Approval with Comments | E000CTPSB00E4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Temporary Project Sign Board Approval with Comments | 4 | CTPSB | E000 | 00E4 | E000CTPSB00E4
155 | 155 | 155 | 155 | SA24M005 | FINAL Approval | E000CTPSB00E5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Temporary Project Sign Board FINAL Approval | 5 | CTPSB | E000 | 00E5 | E000CTPSB00E5
156 | 156 | 156 | 156 | SA24M005 | Substation Permanent Sign Board |  | 6 | -1 | 0 |  |  | X
157 | 157 | 157 | 157 | SA24M005 | Drafting / Preparation | E000CSPSB00E1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Substation Permanent Sign Board Drafting / Preparation | 1 | CSPSB | E000 | 00E1 | E000CSPSB00E1
158 | 158 | 158 | 158 | SA24M005 | Submission | E000CSPSB00E2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Substation Permanent Sign Board Submission | 2 | CSPSB | E000 | 00E2 | E000CSPSB00E2
159 | 159 | 159 | 159 | SA24M005 | Review / Evaluation | E000CSPSB00E3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Substation Permanent Sign Board Review / Evaluation | 3 | CSPSB | E000 | 00E3 | E000CSPSB00E3
160 | 160 | 160 | 160 | SA24M005 | Approval with Comments | E000CSPSB00E4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Substation Permanent Sign Board Approval with Comments | 4 | CSPSB | E000 | 00E4 | E000CSPSB00E4
161 | 161 | 161 | 161 | SA24M005 | FINAL Approval | E000CSPSB00E5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Substation Permanent Sign Board FINAL Approval | 5 | CSPSB | E000 | 00E5 | E000CSPSB00E5
162 | 162 | 162 | 162 | SA24M005 | Borehole Location Plan |  | 6 | -1 | 0 |  |  | X
163 | 163 | 163 | 163 | SA24M005 | Drafting / Preparation | E000CBORL00E1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Borehole Location Plan Drafting / Preparation | 1 | CBORL | E000 | 00E1 | E000#sqAx00E1
164 | 164 | 164 | 164 | SA24M005 | Submission | E000CBORL00E2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Borehole Location Plan Submission | 2 | CBORL | E000 | 00E2 | E000#sqAx00E2
165 | 165 | 165 | 165 | SA24M005 | Review / Evaluation | E000CBORL00E3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Borehole Location Plan Review / Evaluation | 3 | CBORL | E000 | 00E3 | E000#sqAx00E3
166 | 166 | 166 | 166 | SA24M005 | Approval with Comments | E000CBORL00E4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Borehole Location Plan Approval with Comments | 4 | CBORL | E000 | 00E4 | E000#sqAx00E4
167 | 167 | 167 | 167 | SA24M005 | FINAL Approval | E000CBORL00E5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Borehole Location Plan FINAL Approval | 5 | CBORL | E000 | 00E5 | E000#sqAx00E5
168 | 168 | 168 | 168 | SA24M005 | Geotechnical /Soil Investigation Report |  | 6 | -1 | 0 |  |  | X | E000#sqAx
169 | 169 | 169 | 169 | SA24M005 | Drafting / Preparation | E000C0SIR00E1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Geotechnical /Soil Investigation Report Drafting / Preparation | 1 | C0SIR | E000 | 00E1 | E000#jbjk00E1
170 | 170 | 170 | 170 | SA24M005 | Submission | E000C0SIR00E2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Geotechnical /Soil Investigation Report Submission | 2 | C0SIR | E000 | 00E2 | E000#jbjk00E2
171 | 171 | 171 | 171 | SA24M005 | Review / Evaluation | E000C0SIR00E3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Geotechnical /Soil Investigation Report Review / Evaluation | 3 | C0SIR | E000 | 00E3 | E000#jbjk00E3
172 | 172 | 172 | 172 | SA24M005 | Approval with Comments | E000C0SIR00E4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Geotechnical /Soil Investigation Report Approval with Comments | 4 | C0SIR | E000 | 00E4 | E000#jbjk00E4
173 | 173 | 173 | 173 | SA24M005 | FINAL Approval | E000C0SIR00E5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Geotechnical /Soil Investigation Report FINAL Approval | 5 | C0SIR | E000 | 00E5 | E000#jbjk00E5
174 | 174 | 174 | 174 | SA24M005 | Soil Classification Test Result for Backfilling |  | 6 | -1 | 0 |  |  | X | E000#jbjk
175 | 175 | 175 | 175 | SA24M005 | Drafting / Preparation | E000CSCTR00E1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Soil Classification Test Result for Backfilling Drafting / Preparation | 1 | CSCTR | E000 | 00E1 | E000CSCTR00E1
176 | 176 | 176 | 176 | SA24M005 | Submission | E000CSCTR00E2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Soil Classification Test Result for Backfilling Submission | 2 | CSCTR | E000 | 00E2 | E000CSCTR00E2
177 | 177 | 177 | 177 | SA24M005 | Review / Evaluation | E000CSCTR00E3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Soil Classification Test Result for Backfilling Review / Evaluation | 3 | CSCTR | E000 | 00E3 | E000CSCTR00E3
178 | 178 | 178 | 178 | SA24M005 | Approval with Comments | E000CSCTR00E4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Soil Classification Test Result for Backfilling Approval with Comments | 4 | CSCTR | E000 | 00E4 | E000CSCTR00E4
179 | 179 | 179 | 179 | SA24M005 | FINAL Approval | E000CSCTR00E5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Soil Classification Test Result for Backfilling FINAL Approval | 5 | CSCTR | E000 | 00E5 | E000CSCTR00E5
180 | 180 | 180 | 180 | SA24M005 | Civil Design Criteria / Civil Design Philosophy |  | 6 | -1 | 0 |  |  | X
181 | 181 | 181 | 181 | SA24M005 | Drafting / Preparation | E000C0CDC00E1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Civil Design Criteria / Civil Design Philosophy Drafting / Preparation | 1 | C0CDC | E000 | 00E1 | E000C0CDC00E1
182 | 182 | 182 | 182 | SA24M005 | Submission | E000C0CDC00E2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Civil Design Criteria / Civil Design Philosophy Submission | 2 | C0CDC | E000 | 00E2 | E000C0CDC00E2
183 | 183 | 183 | 183 | SA24M005 | Review / Evaluation | E000C0CDC00E3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Civil Design Criteria / Civil Design Philosophy Review / Evaluation | 3 | C0CDC | E000 | 00E3 | E000C0CDC00E3
184 | 184 | 184 | 184 | SA24M005 | Approval with Comments | E000C0CDC00E4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Civil Design Criteria / Civil Design Philosophy Approval with Comments | 4 | C0CDC | E000 | 00E4 | E000C0CDC00E4
185 | 185 | 185 | 185 | SA24M005 | FINAL Approval | E000C0CDC00E5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Civil Design Criteria / Civil Design Philosophy FINAL Approval | 5 | C0CDC | E000 | 00E5 | E000C0CDC00E5
186 | 186 | 186 | 186 | SA24M005 | General Notes for Civil Works |  | 6 | -1 | 0 |  |  | X
187 | 187 | 187 | 187 | SA24M005 | Drafting / Preparation | E000CGNCW00E1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil General Notes for Civil Works Drafting / Preparation | 1 | CGNCW | E000 | 00E1 | E000CGNCW00E1
188 | 188 | 188 | 188 | SA24M005 | Submission | E000CGNCW00E2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil General Notes for Civil Works Submission | 2 | CGNCW | E000 | 00E2 | E000CGNCW00E2
189 | 189 | 189 | 189 | SA24M005 | Review / Evaluation | E000CGNCW00E3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil General Notes for Civil Works Review / Evaluation | 3 | CGNCW | E000 | 00E3 | E000CGNCW00E3
190 | 190 | 190 | 190 | SA24M005 | Approval with Comments | E000CGNCW00E4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil General Notes for Civil Works Approval with Comments | 4 | CGNCW | E000 | 00E4 | E000CGNCW00E4
191 | 191 | 191 | 191 | SA24M005 | FINAL Approval | E000CGNCW00E5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil General Notes for Civil Works FINAL Approval | 5 | CGNCW | E000 | 00E5 | E000CGNCW00E5
192 | 192 | 192 | 192 | SA24M005 | GIS Civil Work Requirements including GIB Support Locations |  | 6 | -1 | 0 |  |  | X
193 | 193 | 193 | 193 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil GIS Civil Work Requirements including GIB Support Locations Drafting / Preparation | 1 | CGISB | E000 | 00E1 | E000#bvDq00E1
194 | 194 | 194 | 194 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil GIS Civil Work Requirements including GIB Support Locations Submission | 2 | CGISB | E000 | 00E2 | E000#bvDq00E2
195 | 195 | 195 | 195 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil GIS Civil Work Requirements including GIB Support Locations Review / Evaluation | 3 | CGISB | E000 | 00E3 | E000#bvDq00E3
196 | 196 | 196 | 196 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil GIS Civil Work Requirements including GIB Support Locations Approval with Comments | 4 | CGISB | E000 | 00E4 | E000#bvDq00E4
197 | 197 | 197 | 197 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil GIS Civil Work Requirements including GIB Support Locations FINAL Approval | 5 | CGISB | E000 | 00E5 | E000#bvDq00E5
198 | 198 | 198 | 198 | SA24M005 | Topographic survey Layout Plan |  | 6 | -1 | 0 |  |  | X | E000#bvDq
199 | 199 | 199 | 199 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Topographic survey Layout Plan Drafting / Preparation | 1 | CTSR | E000 | 00E1 | E000CTSR00E1
200 | 200 | 200 | 200 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Topographic survey Layout Plan Submission | 2 | CTSR | E000 | 00E2 | E000CTSR00E2
201 | 201 | 201 | 201 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Topographic survey Layout Plan Review / Evaluation | 3 | CTSR | E000 | 00E3 | E000CTSR00E3
202 | 202 | 202 | 202 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Topographic survey Layout Plan Approval with Comments | 4 | CTSR | E000 | 00E4 | E000CTSR00E4
203 | 203 | 203 | 203 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Topographic survey Layout Plan FINAL Approval | 5 | CTSR | E000 | 00E5 | E000CTSR00E5
204 | 204 | 204 | 204 | SA24M005 | Site Grading Plan & Sections |  | 6 | -1 | 0 |  |  | X
205 | 205 | 205 | 205 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Site Grading Plan & Sections Drafting / Preparation | 1 | CSG | E000 | 00E1 | E000CSG00E1
206 | 206 | 206 | 206 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Site Grading Plan & Sections Submission | 2 | CSG | E000 | 00E2 | E000CSG00E2
207 | 207 | 207 | 207 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Site Grading Plan & Sections Review / Evaluation | 3 | CSG | E000 | 00E3 | E000CSG00E3
208 | 208 | 208 | 208 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Site Grading Plan & Sections Approval with Comments | 4 | CSG | E000 | 00E4 | E000CSG00E4
209 | 209 | 209 | 209 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Site Grading Plan & Sections FINAL Approval | 5 | CSG | E000 | 00E5 | E000CSG00E5
210 | 210 | 210 | 210 | SA24M005 | Site Development - Layout Plan & Sections Including Access Road to Substation Site Topographic Surve |  | 6 | -1 | 0 |  |  | X
211 | 211 | 211 | 211 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Site Development - Layout Plan & Sections Including Access Road to Substation Site Topographic Surve Drafting / Preparation | 1 | CSDEV | E000 | 00E1 | E000CSDEV00E1
212 | 212 | 212 | 212 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Site Development - Layout Plan & Sections Including Access Road to Substation Site Topographic Surve Submission | 2 | CSDEV | E000 | 00E2 | E000CSDEV00E2
213 | 213 | 213 | 213 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Site Development - Layout Plan & Sections Including Access Road to Substation Site Topographic Surve Review / Evaluation | 3 | CSDEV | E000 | 00E3 | E000CSDEV00E3
214 | 214 | 214 | 214 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Site Development - Layout Plan & Sections Including Access Road to Substation Site Topographic Surve Approval with Comments | 4 | CSDEV | E000 | 00E4 | E000CSDEV00E4
215 | 215 | 215 | 215 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Site Development - Layout Plan & Sections Including Access Road to Substation Site Topographic Surve FINAL Approval | 5 | CSDEV | E000 | 00E5 | E000CSDEV00E5
216 | 216 | 216 | 216 | SA24M005 | Site Topographic Survey & Site Grading Layout |  | 6 | -1 | 0 |  |  | X
217 | 217 | 217 | 217 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Site Topographic Survey & Site Grading Layout Drafting / Preparation | 1 | CS0TS | E000 | 00E1 | E000CS0TS00E1
218 | 218 | 218 | 218 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Site Topographic Survey & Site Grading Layout Submission | 2 | CS0TS | E000 | 00E2 | E000CS0TS00E2
219 | 219 | 219 | 219 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Site Topographic Survey & Site Grading Layout Review / Evaluation | 3 | CS0TS | E000 | 00E3 | E000CS0TS00E3
220 | 220 | 220 | 220 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Site Topographic Survey & Site Grading Layout Approval with Comments | 4 | CS0TS | E000 | 00E4 | E000CS0TS00E4
221 | 221 | 221 | 221 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Site Topographic Survey & Site Grading Layout FINAL Approval | 5 | CS0TS | E000 | 00E5 | E000CS0TS00E5
222 | 222 | 222 | 222 | SA24M005 | Roads Layout And Details |  | 6 | -1 | 0 |  |  | X
223 | 223 | 223 | 223 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Roads Layout And Details Drafting / Preparation | 1 | CROA | E000 | 00E1 | E000CROA00E1
224 | 224 | 224 | 224 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Roads Layout And Details Submission | 2 | CROA | E000 | 00E2 | E000CROA00E2
225 | 225 | 225 | 225 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Roads Layout And Details Review / Evaluation | 3 | CROA | E000 | 00E3 | E000CROA00E3
226 | 226 | 226 | 226 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Roads Layout And Details Approval with Comments | 4 | CROA | E000 | 00E4 | E000CROA00E4
227 | 227 | 227 | 227 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Roads Layout And Details FINAL Approval | 5 | CROA | E000 | 00E5 | E000CROA00E5
228 | 228 | 228 | 228 | SA24M005 | Layout and Details of HVAC PACU Pad Foundations |  | 6 | -1 | 0 |  |  | X
229 | 229 | 229 | 229 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Layout and Details of HVAC PACU Pad Foundations Drafting / Preparation | 1 | CHVAC | E000 | 00E1 | E000#dPWH00E1
230 | 230 | 230 | 230 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Layout and Details of HVAC PACU Pad Foundations Submission | 2 | CHVAC | E000 | 00E2 | E000#dPWH00E2
231 | 231 | 231 | 231 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Layout and Details of HVAC PACU Pad Foundations Review / Evaluation | 3 | CHVAC | E000 | 00E3 | E000#dPWH00E3
232 | 232 | 232 | 232 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Layout and Details of HVAC PACU Pad Foundations Approval with Comments | 4 | CHVAC | E000 | 00E4 | E000#dPWH00E4
233 | 233 | 233 | 233 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Civil Layout and Details of HVAC PACU Pad Foundations FINAL Approval | 5 | CHVAC | E000 | 00E5 | E000#dPWH00E5
234 | 234 | 234 | 234 | SA24M005 | Mechanical |  | 5 | -1 | 0 |  |  | X | E000#dPWH
235 | 235 | 235 | 235 | SA24M005 | Plumbing General Notes & Legend Drawings |  | 6 | -1 | 0 |  |  | X | E000#dPWH
236 | 236 | 236 | 236 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Mechanical Plumbing General Notes & Legend Drawings Drafting / Preparation | 1 | PLUMB | E000 | 00E1 | E000#bjmW00E1
237 | 237 | 237 | 237 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Mechanical Plumbing General Notes & Legend Drawings Submission | 2 | PLUMB | E000 | 00E2 | E000#bjmW00E2
238 | 238 | 238 | 238 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Mechanical Plumbing General Notes & Legend Drawings Review / Evaluation | 3 | PLUMB | E000 | 00E3 | E000#bjmW00E3
239 | 239 | 239 | 239 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Mechanical Plumbing General Notes & Legend Drawings Approval with Comments | 4 | PLUMB | E000 | 00E4 | E000#bjmW00E4
240 | 240 | 240 | 240 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Mechanical Plumbing General Notes & Legend Drawings FINAL Approval | 5 | PLUMB | E000 | 00E5 | E000#bjmW00E5
241 | 241 | 241 | 241 | SA24M005 | HVAC General Notes & Misc. Details |  | 6 | -1 | 0 |  |  | X | E000#bjmW
242 | 242 | 242 | 242 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Mechanical HVAC General Notes & Misc. Details Drafting / Preparation | 1 | MHVAC | E000 | 00E1 | E000#TmRQ00E1
243 | 243 | 243 | 243 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Mechanical HVAC General Notes & Misc. Details Submission | 2 | MHVAC | E000 | 00E2 | E000#TmRQ00E2
244 | 244 | 244 | 244 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Mechanical HVAC General Notes & Misc. Details Review / Evaluation | 3 | MHVAC | E000 | 00E3 | E000#TmRQ00E3
245 | 245 | 245 | 245 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Mechanical HVAC General Notes & Misc. Details Approval with Comments | 4 | MHVAC | E000 | 00E4 | E000#TmRQ00E4
246 | 246 | 246 | 246 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Mechanical HVAC General Notes & Misc. Details FINAL Approval | 5 | MHVAC | E000 | 00E5 | E000#TmRQ00E5
247 | 247 | 247 | 247 | SA24M005 | Safety and Loss Prevention Program |  | 6 | -1 | 0 |  |  | X | E000#TmRQ
248 | 248 | 248 | 248 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Mechanical Safety and Loss Prevention Program Drafting / Preparation | 1 | MSLPP | E000 | 00E1 | E000MSLPP00E1
249 | 249 | 249 | 249 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Mechanical Safety and Loss Prevention Program Submission | 2 | MSLPP | E000 | 00E2 | E000MSLPP00E2
250 | 250 | 250 | 250 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Mechanical Safety and Loss Prevention Program Review / Evaluation | 3 | MSLPP | E000 | 00E3 | E000MSLPP00E3
251 | 251 | 251 | 251 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Mechanical Safety and Loss Prevention Program Approval with Comments | 4 | MSLPP | E000 | 00E4 | E000MSLPP00E4
252 | 252 | 252 | 252 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Mechanical Safety and Loss Prevention Program FINAL Approval | 5 | MSLPP | E000 | 00E5 | E000MSLPP00E5
253 | 253 | 253 | 253 | SA24M005 | Protection |  | 5 | -1 | 0 |  |  | X
254 | 254 | 254 | 254 | SA24M005 | Protective Relays Manuals/Catalogue, Transient Fault Recorder & SOE Recorder Equipment Manuals/Catal |  | 6 | -1 | 0 |  |  | X
255 | 255 | 255 | 255 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Protection Protective Relays Manuals/Catalogue, Transient Fault Recorder & SOE Recorder Equipment Manuals/Catal Drafting / Preparation | 1 | PRTRF | E000 | 00E1 | E000PRTRF00E1
256 | 256 | 256 | 256 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Protection Protective Relays Manuals/Catalogue, Transient Fault Recorder & SOE Recorder Equipment Manuals/Catal Submission | 2 | PRTRF | E000 | 00E2 | E000PRTRF00E2
257 | 257 | 257 | 257 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Protection Protective Relays Manuals/Catalogue, Transient Fault Recorder & SOE Recorder Equipment Manuals/Catal Review / Evaluation | 3 | PRTRF | E000 | 00E3 | E000PRTRF00E3
258 | 258 | 258 | 258 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Protection Protective Relays Manuals/Catalogue, Transient Fault Recorder & SOE Recorder Equipment Manuals/Catal Approval with Comments | 4 | PRTRF | E000 | 00E4 | E000PRTRF00E4
259 | 259 | 259 | 259 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Protection Protective Relays Manuals/Catalogue, Transient Fault Recorder & SOE Recorder Equipment Manuals/Catal FINAL Approval | 5 | PRTRF | E000 | 00E5 | E000PRTRF00E5
260 | 260 | 260 | 260 | SA24M005 | Relay Application/Installation/Commissioning Manuals |  | 6 | -1 | 0 |  |  | X
261 | 261 | 261 | 261 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Protection Relay Application/Installation/Commissioning Manuals Drafting / Preparation | 1 | PRAYM | E000 | 00E1 | E000PRAYM00E1
262 | 262 | 262 | 262 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Protection Relay Application/Installation/Commissioning Manuals Submission | 2 | PRAYM | E000 | 00E2 | E000PRAYM00E2
263 | 263 | 263 | 263 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Protection Relay Application/Installation/Commissioning Manuals Review / Evaluation | 3 | PRAYM | E000 | 00E3 | E000PRAYM00E3
264 | 264 | 264 | 264 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Protection Relay Application/Installation/Commissioning Manuals Approval with Comments | 4 | PRAYM | E000 | 00E4 | E000PRAYM00E4
265 | 265 | 265 | 265 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Protection Relay Application/Installation/Commissioning Manuals FINAL Approval | 5 | PRAYM | E000 | 00E5 | E000PRAYM00E5
266 | 266 | 266 | 266 | SA24M005 | CT / VT SLD |  | 6 | -1 | 0 |  |  | X
267 | 267 | 267 | 267 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Protection CT / VT SLD Drafting / Preparation | 1 | CTVSL | E000 | 00E1 | E000CTVSL00E1
268 | 268 | 268 | 268 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Protection CT / VT SLD Submission | 2 | CTVSL | E000 | 00E2 | E000CTVSL00E2
269 | 269 | 269 | 269 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Protection CT / VT SLD Review / Evaluation | 3 | CTVSL | E000 | 00E3 | E000CTVSL00E3
270 | 270 | 270 | 270 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Protection CT / VT SLD Approval with Comments | 4 | CTVSL | E000 | 00E4 | E000CTVSL00E4
271 | 271 | 271 | 271 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Protection CT / VT SLD FINAL Approval | 5 | CTVSL | E000 | 00E5 | E000CTVSL00E5
272 | 272 | 272 | 272 | SA24M005 | CT/VT Performance Study |  | 6 | -1 | 0 |  |  | X
273 | 273 | 273 | 273 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Protection CT/VT Performance Study Drafting / Preparation | 1 | CTVPS | E000 | 00E1 | E000CTVPS00E1
274 | 274 | 274 | 274 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Protection CT/VT Performance Study Submission | 2 | CTVPS | E000 | 00E2 | E000CTVPS00E2
275 | 275 | 275 | 275 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Protection CT/VT Performance Study Review / Evaluation | 3 | CTVPS | E000 | 00E3 | E000CTVPS00E3
276 | 276 | 276 | 276 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Protection CT/VT Performance Study Approval with Comments | 4 | CTVPS | E000 | 00E4 | E000CTVPS00E4
277 | 277 | 277 | 277 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- I Protection CT/VT Performance Study FINAL Approval | 5 | CTVPS | E000 | 00E5 | E000CTVPS00E5
278 | 278 | 278 | 278 | SA24M005 | Phase- II |  | 4 | -1 | 0 |  |  | X
279 | 279 | 279 | 279 | SA24M005 | Electrical |  | 5 | -1 | 0 |  |  | X
280 | 280 | 280 | 280 | SA24M005 | EHV GIS Design- (Material Portion) |  | 6 | -1 | 0 |  |  | X
281 | 281 | 281 | 281 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical EHV GIS Design- (Material Portion) Drafting / Preparation | 1 | E0GIS | E000 | 00E1 | E000#dARI00E1
282 | 282 | 282 | 282 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical EHV GIS Design- (Material Portion) Submission | 2 | E0GIS | E000 | 00E2 | E000#dARI00E2
283 | 283 | 283 | 283 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical EHV GIS Design- (Material Portion) Review / Evaluation | 3 | E0GIS | E000 | 00E3 | E000#dARI00E3
284 | 284 | 284 | 284 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical EHV GIS Design- (Material Portion) Approval with Comments | 4 | E0GIS | E000 | 00E4 | E000#dARI00E4
285 | 285 | 285 | 285 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical EHV GIS Design- (Material Portion) FINAL Approval | 5 | E0GIS | E000 | 00E5 | E000#dARI00E5
286 | 286 | 286 | 286 | SA24M005 | EHV GIS Design- (Drawing Portion) |  | 6 | -1 | 0 |  |  | X | E000#dARI
287 | 287 | 287 | 287 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical EHV GIS Design- (Drawing Portion) Drafting / Preparation | 1 | E0GIS | E000 | 00E1 | E000#fYlJ00E1
288 | 288 | 288 | 288 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical EHV GIS Design- (Drawing Portion) Submission | 2 | E0GIS | E000 | 00E2 | E000#fYlJ00E2
289 | 289 | 289 | 289 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical EHV GIS Design- (Drawing Portion) Review / Evaluation | 3 | E0GIS | E000 | 00E3 | E000#fYlJ00E3
290 | 290 | 290 | 290 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical EHV GIS Design- (Drawing Portion) Approval with Comments | 4 | E0GIS | E000 | 00E4 | E000#fYlJ00E4
291 | 291 | 291 | 291 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical EHV GIS Design- (Drawing Portion) FINAL Approval | 5 | E0GIS | E000 | 00E5 | E000#fYlJ00E5
292 | 292 | 292 | 292 | SA24M005 | EHV Hybrid GIS Design |  | 6 | -1 | 0 |  |  | X | E000#fYlJ
293 | 293 | 293 | 293 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical EHV Hybrid GIS Design Drafting / Preparation | 1 | E0GIS | E000 | 00E1 | E000#BTBZ00E1
294 | 294 | 294 | 294 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical EHV Hybrid GIS Design Submission | 2 | E0GIS | E000 | 00E2 | E000#BTBZ00E2
295 | 295 | 295 | 295 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical EHV Hybrid GIS Design Review / Evaluation | 3 | E0GIS | E000 | 00E3 | E000#BTBZ00E3
296 | 296 | 296 | 296 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical EHV Hybrid GIS Design Approval with Comments | 4 | E0GIS | E000 | 00E4 | E000#BTBZ00E4
297 | 297 | 297 | 297 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical EHV Hybrid GIS Design FINAL Approval | 5 | E0GIS | E000 | 00E5 | E000#BTBZ00E5
298 | 298 | 298 | 298 | SA24M005 | EHV GIS- VT (PT) Sizing Calculation |  | 6 | -1 | 0 |  |  | X | E000#BTBZ
299 | 299 | 299 | 299 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical EHV GIS- VT (PT) Sizing Calculation Drafting / Preparation | 1 | E0GIS | E000 | 00E1 | E000#SVxl00E1
300 | 300 | 300 | 300 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical EHV GIS- VT (PT) Sizing Calculation Submission | 2 | E0GIS | E000 | 00E2 | E000#SVxl00E2
301 | 301 | 301 | 301 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical EHV GIS- VT (PT) Sizing Calculation Review / Evaluation | 3 | E0GIS | E000 | 00E3 | E000#SVxl00E3
302 | 302 | 302 | 302 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical EHV GIS- VT (PT) Sizing Calculation Approval with Comments | 4 | E0GIS | E000 | 00E4 | E000#SVxl00E4
303 | 303 | 303 | 303 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical EHV GIS- VT (PT) Sizing Calculation FINAL Approval | 5 | E0GIS | E000 | 00E5 | E000#SVxl00E5
304 | 304 | 304 | 304 | SA24M005 | EHV GIS- CT Sizing Calculation |  | 6 | -1 | 0 |  |  | X | E000#SVxl
305 | 305 | 305 | 305 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical EHV GIS- CT Sizing Calculation Drafting / Preparation | 1 | E0GIS | E000 | 00E1 | E000#PfOn00E1
306 | 306 | 306 | 306 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical EHV GIS- CT Sizing Calculation Submission | 2 | E0GIS | E000 | 00E2 | E000#PfOn00E2
307 | 307 | 307 | 307 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical EHV GIS- CT Sizing Calculation Review / Evaluation | 3 | E0GIS | E000 | 00E3 | E000#PfOn00E3
308 | 308 | 308 | 308 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical EHV GIS- CT Sizing Calculation Approval with Comments | 4 | E0GIS | E000 | 00E4 | E000#PfOn00E4
309 | 309 | 309 | 309 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical EHV GIS- CT Sizing Calculation FINAL Approval | 5 | E0GIS | E000 | 00E5 | E000#PfOn00E5
310 | 310 | 310 | 310 | SA24M005 | EHV GIS Design- LCC Mimic Diagram |  | 6 | -1 | 0 |  |  | X | E000#PfOn
311 | 311 | 311 | 311 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical EHV GIS Design- LCC Mimic Diagram Drafting / Preparation | 1 | E0GIS | E000 | 00E1 | E000#pVbn00E1
312 | 312 | 312 | 312 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical EHV GIS Design- LCC Mimic Diagram Submission | 2 | E0GIS | E000 | 00E2 | E000#pVbn00E2
313 | 313 | 313 | 313 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical EHV GIS Design- LCC Mimic Diagram Review / Evaluation | 3 | E0GIS | E000 | 00E3 | E000#pVbn00E3
314 | 314 | 314 | 314 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical EHV GIS Design- LCC Mimic Diagram Approval with Comments | 4 | E0GIS | E000 | 00E4 | E000#pVbn00E4
315 | 315 | 315 | 315 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical EHV GIS Design- LCC Mimic Diagram FINAL Approval | 5 | E0GIS | E000 | 00E5 | E000#pVbn00E5
316 | 316 | 316 | 316 | SA24M005 | EHV GIS Partial Discharge System |  | 6 | -1 | 0 |  |  | X | E000#pVbn
317 | 317 | 317 | 317 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical EHV GIS Partial Discharge System Drafting / Preparation | 1 | E0GIS | E000 | 00E1 | E000#hQMh00E1
318 | 318 | 318 | 318 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical EHV GIS Partial Discharge System Submission | 2 | E0GIS | E000 | 00E2 | E000#hQMh00E2
319 | 319 | 319 | 319 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical EHV GIS Partial Discharge System Review / Evaluation | 3 | E0GIS | E000 | 00E3 | E000#hQMh00E3
320 | 320 | 320 | 320 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical EHV GIS Partial Discharge System Approval with Comments | 4 | E0GIS | E000 | 00E4 | E000#hQMh00E4
321 | 321 | 321 | 321 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical EHV GIS Partial Discharge System FINAL Approval | 5 | E0GIS | E000 | 00E5 | E000#hQMh00E5
322 | 322 | 322 | 322 | SA24M005 | MV Switchgear Design |  | 6 | -1 | 0 |  |  | X | E000#hQMh
323 | 323 | 323 | 323 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical MV Switchgear Design Drafting / Preparation | 1 | EMSW | E000 | 00E1 | E000EMSW00E1
324 | 324 | 324 | 324 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical MV Switchgear Design Submission | 2 | EMSW | E000 | 00E2 | E000EMSW00E2
325 | 325 | 325 | 325 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical MV Switchgear Design Review / Evaluation | 3 | EMSW | E000 | 00E3 | E000EMSW00E3
326 | 326 | 326 | 326 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical MV Switchgear Design Approval with Comments | 4 | EMSW | E000 | 00E4 | E000EMSW00E4
327 | 327 | 327 | 327 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical MV Switchgear Design FINAL Approval | 5 | EMSW | E000 | 00E5 | E000EMSW00E5
328 | 328 | 328 | 328 | SA24M005 | MV SWGR- VT (PT) Sizing Calculation |  | 6 | -1 | 0 |  |  | X
329 | 329 | 329 | 329 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical MV SWGR- VT (PT) Sizing Calculation Drafting / Preparation | 1 | EMSWGR | E000 | 00E1 | E000EMSWGR00E1
330 | 330 | 330 | 330 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical MV SWGR- VT (PT) Sizing Calculation Submission | 2 | EMSWGR | E000 | 00E2 | E000EMSWGR00E2
331 | 331 | 331 | 331 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical MV SWGR- VT (PT) Sizing Calculation Review / Evaluation | 3 | EMSWGR | E000 | 00E3 | E000EMSWGR00E3
332 | 332 | 332 | 332 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical MV SWGR- VT (PT) Sizing Calculation Approval with Comments | 4 | EMSWGR | E000 | 00E4 | E000EMSWGR00E4
333 | 333 | 333 | 333 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical MV SWGR- VT (PT) Sizing Calculation FINAL Approval | 5 | EMSWGR | E000 | 00E5 | E000EMSWGR00E5
334 | 334 | 334 | 334 | SA24M005 | MV SWGR Metering List |  | 6 | -1 | 0 |  |  | X
335 | 335 | 335 | 335 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical MV SWGR Metering List Drafting / Preparation | 1 | E0SWGR | E000 | 00E1 | E000#vMqh00E1
336 | 336 | 336 | 336 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical MV SWGR Metering List Submission | 2 | E0SWGR | E000 | 00E2 | E000#vMqh00E2
337 | 337 | 337 | 337 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical MV SWGR Metering List Review / Evaluation | 3 | E0SWGR | E000 | 00E3 | E000#vMqh00E3
338 | 338 | 338 | 338 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical MV SWGR Metering List Approval with Comments | 4 | E0SWGR | E000 | 00E4 | E000#vMqh00E4
339 | 339 | 339 | 339 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical MV SWGR Metering List FINAL Approval | 5 | E0SWGR | E000 | 00E5 | E000#vMqh00E5
340 | 340 | 340 | 340 | SA24M005 | MV / LV Station Service Transformer Sizing Calculation |  | 6 | -1 | 0 |  |  | X | E000#vMqh
341 | 341 | 341 | 341 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical MV / LV Station Service Transformer Sizing Calculation Drafting / Preparation | 1 | EMVLV | E000 | 00E1 | E000#AhVI00E1
342 | 342 | 342 | 342 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical MV / LV Station Service Transformer Sizing Calculation Submission | 2 | EMVLV | E000 | 00E2 | E000#AhVI00E2
343 | 343 | 343 | 343 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical MV / LV Station Service Transformer Sizing Calculation Review / Evaluation | 3 | EMVLV | E000 | 00E3 | E000#AhVI00E3
344 | 344 | 344 | 344 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical MV / LV Station Service Transformer Sizing Calculation Approval with Comments | 4 | EMVLV | E000 | 00E4 | E000#AhVI00E4
345 | 345 | 345 | 345 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical MV / LV Station Service Transformer Sizing Calculation FINAL Approval | 5 | EMVLV | E000 | 00E5 | E000#AhVI00E5
346 | 346 | 346 | 346 | SA24M005 | MV / LV Technical Submittal of Station Service Transformer (SST) |  | 6 | -1 | 0 |  |  | X | E000#AhVI
347 | 347 | 347 | 347 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical MV / LV Technical Submittal of Station Service Transformer (SST) Drafting / Preparation | 1 | EMVLV | E000 | 00E1 | E000#BMJt00E1
348 | 348 | 348 | 348 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical MV / LV Technical Submittal of Station Service Transformer (SST) Submission | 2 | EMVLV | E000 | 00E2 | E000#BMJt00E2
349 | 349 | 349 | 349 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical MV / LV Technical Submittal of Station Service Transformer (SST) Review / Evaluation | 3 | EMVLV | E000 | 00E3 | E000#BMJt00E3
350 | 350 | 350 | 350 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical MV / LV Technical Submittal of Station Service Transformer (SST) Approval with Comments | 4 | EMVLV | E000 | 00E4 | E000#BMJt00E4
351 | 351 | 351 | 351 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical MV / LV Technical Submittal of Station Service Transformer (SST) FINAL Approval | 5 | EMVLV | E000 | 00E5 | E000#BMJt00E5
352 | 352 | 352 | 352 | SA24M005 | MV / LV Station Service Transformer (SST) Layout Plan , Section & Grounding |  | 6 | -1 | 0 |  |  | X | E000#BMJt
353 | 353 | 353 | 353 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical MV / LV Station Service Transformer (SST) Layout Plan , Section & Grounding Drafting / Preparation | 1 | EMVST | E000 | 00E1 | E000EMVST00E1
354 | 354 | 354 | 354 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical MV / LV Station Service Transformer (SST) Layout Plan , Section & Grounding Submission | 2 | EMVST | E000 | 00E2 | E000EMVST00E2
355 | 355 | 355 | 355 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical MV / LV Station Service Transformer (SST) Layout Plan , Section & Grounding Review / Evaluation | 3 | EMVST | E000 | 00E3 | E000EMVST00E3
356 | 356 | 356 | 356 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical MV / LV Station Service Transformer (SST) Layout Plan , Section & Grounding Approval with Comments | 4 | EMVST | E000 | 00E4 | E000EMVST00E4
357 | 357 | 357 | 357 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical MV / LV Station Service Transformer (SST) Layout Plan , Section & Grounding FINAL Approval | 5 | EMVST | E000 | 00E5 | E000EMVST00E5
358 | 358 | 358 | 358 | SA24M005 | 120MVAR EHV Bus Reactor Design- (Documents / Drawing Portion) |  | 6 | -1 | 0 |  |  | X
359 | 359 | 359 | 359 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical 120MVAR EHV Bus Reactor Design- (Documents / Drawing Portion) Drafting / Preparation | 1 | E0BR | E000 | 00E1 | E000#SZZJ00E1
360 | 360 | 360 | 360 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical 120MVAR EHV Bus Reactor Design- (Documents / Drawing Portion) Submission | 2 | E0BR | E000 | 00E2 | E000#SZZJ00E2
361 | 361 | 361 | 361 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical 120MVAR EHV Bus Reactor Design- (Documents / Drawing Portion) Review / Evaluation | 3 | E0BR | E000 | 00E3 | E000#SZZJ00E3
362 | 362 | 362 | 362 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical 120MVAR EHV Bus Reactor Design- (Documents / Drawing Portion) Approval with Comments | 4 | E0BR | E000 | 00E4 | E000#SZZJ00E4
363 | 363 | 363 | 363 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical 120MVAR EHV Bus Reactor Design- (Documents / Drawing Portion) FINAL Approval | 5 | E0BR | E000 | 00E5 | E000#SZZJ00E5
364 | 364 | 364 | 364 | SA24M005 | 120MVAR EHV Bus Reactor- Equipment Layout Plan and Section |  | 6 | -1 | 0 |  |  | X | E000#SZZJ
365 | 365 | 365 | 365 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical 120MVAR EHV Bus Reactor- Equipment Layout Plan and Section Drafting / Preparation | 1 | E0BR | E000 | 00E1 | E000#QfDo00E1
366 | 366 | 366 | 366 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical 120MVAR EHV Bus Reactor- Equipment Layout Plan and Section Submission | 2 | E0BR | E000 | 00E2 | E000#QfDo00E2
367 | 367 | 367 | 367 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical 120MVAR EHV Bus Reactor- Equipment Layout Plan and Section Review / Evaluation | 3 | E0BR | E000 | 00E3 | E000#QfDo00E3
368 | 368 | 368 | 368 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical 120MVAR EHV Bus Reactor- Equipment Layout Plan and Section Approval with Comments | 4 | E0BR | E000 | 00E4 | E000#QfDo00E4
369 | 369 | 369 | 369 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical 120MVAR EHV Bus Reactor- Equipment Layout Plan and Section FINAL Approval | 5 | E0BR | E000 | 00E5 | E000#QfDo00E5
370 | 370 | 370 | 370 | SA24M005 | 120MVAR EHV Bus Reactor- LCP Schematic Drawings |  | 6 | -1 | 0 |  |  | X | E000#QfDo
371 | 371 | 371 | 371 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical 120MVAR EHV Bus Reactor- LCP Schematic Drawings Drafting / Preparation | 1 | E0BR | E000 | 00E1 | E000#sVzQ00E1
372 | 372 | 372 | 372 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical 120MVAR EHV Bus Reactor- LCP Schematic Drawings Submission | 2 | E0BR | E000 | 00E2 | E000#sVzQ00E2
373 | 373 | 373 | 373 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical 120MVAR EHV Bus Reactor- LCP Schematic Drawings Review / Evaluation | 3 | E0BR | E000 | 00E3 | E000#sVzQ00E3
374 | 374 | 374 | 374 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical 120MVAR EHV Bus Reactor- LCP Schematic Drawings Approval with Comments | 4 | E0BR | E000 | 00E4 | E000#sVzQ00E4
375 | 375 | 375 | 375 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical 120MVAR EHV Bus Reactor- LCP Schematic Drawings FINAL Approval | 5 | E0BR | E000 | 00E5 | E000#sVzQ00E5
376 | 376 | 376 | 376 | SA24M005 | 120MVAR EHV Bus Reactor- Online DGA requirement |  | 6 | -1 | 0 |  |  | X | E000#sVzQ
377 | 377 | 377 | 377 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical 120MVAR EHV Bus Reactor- Online DGA requirement Drafting / Preparation | 1 | E0BR | E000 | 00E1 | E000#aVVH00E1
378 | 378 | 378 | 378 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical 120MVAR EHV Bus Reactor- Online DGA requirement Submission | 2 | E0BR | E000 | 00E2 | E000#aVVH00E2
379 | 379 | 379 | 379 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical 120MVAR EHV Bus Reactor- Online DGA requirement Review / Evaluation | 3 | E0BR | E000 | 00E3 | E000#aVVH00E3
380 | 380 | 380 | 380 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical 120MVAR EHV Bus Reactor- Online DGA requirement Approval with Comments | 4 | E0BR | E000 | 00E4 | E000#aVVH00E4
381 | 381 | 381 | 381 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical 120MVAR EHV Bus Reactor- Online DGA requirement FINAL Approval | 5 | E0BR | E000 | 00E5 | E000#aVVH00E5
382 | 382 | 382 | 382 | SA24M005 | 150MVAR EHV Line Reactor Design- (Documents / Drawing Portion) |  | 6 | -1 | 0 |  |  | X | E000#aVVH
383 | 383 | 383 | 383 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical 150MVAR EHV Line Reactor Design- (Documents / Drawing Portion) Drafting / Preparation | 1 | E0LRE | E000 | 00E1 | E000E0LRE00E1
384 | 384 | 384 | 384 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical 150MVAR EHV Line Reactor Design- (Documents / Drawing Portion) Submission | 2 | E0LRE | E000 | 00E2 | E000E0LRE00E2
385 | 385 | 385 | 385 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical 150MVAR EHV Line Reactor Design- (Documents / Drawing Portion) Review / Evaluation | 3 | E0LRE | E000 | 00E3 | E000E0LRE00E3
386 | 386 | 386 | 386 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical 150MVAR EHV Line Reactor Design- (Documents / Drawing Portion) Approval with Comments | 4 | E0LRE | E000 | 00E4 | E000E0LRE00E4
387 | 387 | 387 | 387 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical 150MVAR EHV Line Reactor Design- (Documents / Drawing Portion) FINAL Approval | 5 | E0LRE | E000 | 00E5 | E000E0LRE00E5
388 | 388 | 388 | 388 | SA24M005 | 150MVAR EHV Line Reactor- Equipment Layout Plan and Section |  | 6 | -1 | 0 |  |  | X
389 | 389 | 389 | 389 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical 150MVAR EHV Line Reactor- Equipment Layout Plan and Section Drafting / Preparation | 1 | E0EHLR | E000 | 00E1 | E000#RVjp00E1
390 | 390 | 390 | 390 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical 150MVAR EHV Line Reactor- Equipment Layout Plan and Section Submission | 2 | E0EHLR | E000 | 00E2 | E000#RVjp00E2
391 | 391 | 391 | 391 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical 150MVAR EHV Line Reactor- Equipment Layout Plan and Section Review / Evaluation | 3 | E0EHLR | E000 | 00E3 | E000#RVjp00E3
392 | 392 | 392 | 392 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical 150MVAR EHV Line Reactor- Equipment Layout Plan and Section Approval with Comments | 4 | E0EHLR | E000 | 00E4 | E000#RVjp00E4
393 | 393 | 393 | 393 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical 150MVAR EHV Line Reactor- Equipment Layout Plan and Section FINAL Approval | 5 | E0EHLR | E000 | 00E5 | E000#RVjp00E5
394 | 394 | 394 | 394 | SA24M005 | 150MVAR EHV Line Reactor- LCP Schematic Drawings |  | 6 | -1 | 0 |  |  | X | E000#RVjp
395 | 395 | 395 | 395 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical 150MVAR EHV Line Reactor- LCP Schematic Drawings Drafting / Preparation | 1 | E0LCR | E000 | 00E1 | E000E0LCR00E1
396 | 396 | 396 | 396 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical 150MVAR EHV Line Reactor- LCP Schematic Drawings Submission | 2 | E0LCR | E000 | 00E2 | E000E0LCR00E2
397 | 397 | 397 | 397 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical 150MVAR EHV Line Reactor- LCP Schematic Drawings Review / Evaluation | 3 | E0LCR | E000 | 00E3 | E000E0LCR00E3
398 | 398 | 398 | 398 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical 150MVAR EHV Line Reactor- LCP Schematic Drawings Approval with Comments | 4 | E0LCR | E000 | 00E4 | E000E0LCR00E4
399 | 399 | 399 | 399 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical 150MVAR EHV Line Reactor- LCP Schematic Drawings FINAL Approval | 5 | E0LCR | E000 | 00E5 | E000E0LCR00E5
400 | 400 | 400 | 400 | SA24M005 | 150MVAR EHV Line Reactor- Online DGA requirement |  | 6 | -1 | 0 |  |  | X
401 | 401 | 401 | 401 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical 150MVAR EHV Line Reactor- Online DGA requirement Drafting / Preparation | 1 | E0EHLR | E000 | 00E1 | E000#OeFp00E1
402 | 402 | 402 | 402 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical 150MVAR EHV Line Reactor- Online DGA requirement Submission | 2 | E0EHLR | E000 | 00E2 | E000#OeFp00E2
403 | 403 | 403 | 403 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical 150MVAR EHV Line Reactor- Online DGA requirement Review / Evaluation | 3 | E0EHLR | E000 | 00E3 | E000#OeFp00E3
404 | 404 | 404 | 404 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical 150MVAR EHV Line Reactor- Online DGA requirement Approval with Comments | 4 | E0EHLR | E000 | 00E4 | E000#OeFp00E4
405 | 405 | 405 | 405 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical 150MVAR EHV Line Reactor- Online DGA requirement FINAL Approval | 5 | E0EHLR | E000 | 00E5 | E000#OeFp00E5
406 | 406 | 406 | 406 | SA24M005 | EHV Neutral Grounding Reactor Study |  | 6 | -1 | 0 |  |  | X | E000#OeFp
407 | 407 | 407 | 407 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical EHV Neutral Grounding Reactor Study Drafting / Preparation | 1 | E00NR | E000 | 00E1 | E000E00NR00E1
408 | 408 | 408 | 408 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical EHV Neutral Grounding Reactor Study Submission | 2 | E00NR | E000 | 00E2 | E000E00NR00E2
409 | 409 | 409 | 409 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical EHV Neutral Grounding Reactor Study Review / Evaluation | 3 | E00NR | E000 | 00E3 | E000E00NR00E3
410 | 410 | 410 | 410 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical EHV Neutral Grounding Reactor Study Approval with Comments | 4 | E00NR | E000 | 00E4 | E000E00NR00E4
411 | 411 | 411 | 411 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical EHV Neutral Grounding Reactor Study FINAL Approval | 5 | E00NR | E000 | 00E5 | E000E00NR00E5
412 | 412 | 412 | 412 | SA24M005 | EHV Neutral Grounding Reactor (NGR) Design & Layout |  | 6 | -1 | 0 |  |  | X
413 | 413 | 413 | 413 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical EHV Neutral Grounding Reactor (NGR) Design & Layout Drafting / Preparation | 1 | E0NGR | E000 | 00E1 | E000E0NGR00E1
414 | 414 | 414 | 414 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical EHV Neutral Grounding Reactor (NGR) Design & Layout Submission | 2 | E0NGR | E000 | 00E2 | E000E0NGR00E2
415 | 415 | 415 | 415 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical EHV Neutral Grounding Reactor (NGR) Design & Layout Review / Evaluation | 3 | E0NGR | E000 | 00E3 | E000E0NGR00E3
416 | 416 | 416 | 416 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical EHV Neutral Grounding Reactor (NGR) Design & Layout Approval with Comments | 4 | E0NGR | E000 | 00E4 | E000E0NGR00E4
417 | 417 | 417 | 417 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical EHV Neutral Grounding Reactor (NGR) Design & Layout FINAL Approval | 5 | E0NGR | E000 | 00E5 | E000E0NGR00E5
418 | 418 | 418 | 418 | SA24M005 | Metering One Line Diagram (EHV / HV / MV) |  | 6 | -1 | 0 |  |  | X
419 | 419 | 419 | 419 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical Metering One Line Diagram (EHV / HV / MV) Drafting / Preparation | 1 | E0MLD | E000 | 00E1 | E000E0MLD00E1
420 | 420 | 420 | 420 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical Metering One Line Diagram (EHV / HV / MV) Submission | 2 | E0MLD | E000 | 00E2 | E000E0MLD00E2
421 | 421 | 421 | 421 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical Metering One Line Diagram (EHV / HV / MV) Review / Evaluation | 3 | E0MLD | E000 | 00E3 | E000E0MLD00E3
422 | 422 | 422 | 422 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical Metering One Line Diagram (EHV / HV / MV) Approval with Comments | 4 | E0MLD | E000 | 00E4 | E000E0MLD00E4
423 | 423 | 423 | 423 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical Metering One Line Diagram (EHV / HV / MV) FINAL Approval | 5 | E0MLD | E000 | 00E5 | E000E0MLD00E5
424 | 424 | 424 | 424 | SA24M005 | Panel wise Metering List |  | 6 | -1 | 0 |  |  | X
425 | 425 | 425 | 425 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical Panel wise Metering List Drafting / Preparation | 1 | E0PWM | E000 | 00E1 | E000E0PWM00E1
426 | 426 | 426 | 426 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical Panel wise Metering List Submission | 2 | E0PWM | E000 | 00E2 | E000E0PWM00E2
427 | 427 | 427 | 427 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical Panel wise Metering List Review / Evaluation | 3 | E0PWM | E000 | 00E3 | E000E0PWM00E3
428 | 428 | 428 | 428 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical Panel wise Metering List Approval with Comments | 4 | E0PWM | E000 | 00E4 | E000E0PWM00E4
429 | 429 | 429 | 429 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical Panel wise Metering List FINAL Approval | 5 | E0PWM | E000 | 00E5 | E000E0PWM00E5
430 | 430 | 430 | 430 | SA24M005 | CT Metering Sizing Calculation |  | 6 | -1 | 0 |  |  | X
431 | 431 | 431 | 431 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical CT Metering Sizing Calculation Drafting / Preparation | 1 | E0CTM | E000 | 00E1 | E000E0CTM00E1
432 | 432 | 432 | 432 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical CT Metering Sizing Calculation Submission | 2 | E0CTM | E000 | 00E2 | E000E0CTM00E2
433 | 433 | 433 | 433 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical CT Metering Sizing Calculation Review / Evaluation | 3 | E0CTM | E000 | 00E3 | E000E0CTM00E3
434 | 434 | 434 | 434 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical CT Metering Sizing Calculation Approval with Comments | 4 | E0CTM | E000 | 00E4 | E000E0CTM00E4
435 | 435 | 435 | 435 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical CT Metering Sizing Calculation FINAL Approval | 5 | E0CTM | E000 | 00E5 | E000E0CTM00E5
436 | 436 | 436 | 436 | SA24M005 | VT sizing calculation for metering system |  | 6 | -1 | 0 |  |  | X
437 | 437 | 437 | 437 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical VT sizing calculation for metering system Drafting / Preparation | 1 | EVTM | E000 | 00E1 | E000EVTM00E1
438 | 438 | 438 | 438 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical VT sizing calculation for metering system Submission | 2 | EVTM | E000 | 00E2 | E000EVTM00E2
439 | 439 | 439 | 439 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical VT sizing calculation for metering system Review / Evaluation | 3 | EVTM | E000 | 00E3 | E000EVTM00E3
440 | 440 | 440 | 440 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical VT sizing calculation for metering system Approval with Comments | 4 | EVTM | E000 | 00E4 | E000EVTM00E4
441 | 441 | 441 | 441 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical VT sizing calculation for metering system FINAL Approval | 5 | EVTM | E000 | 00E5 | E000EVTM00E5
442 | 442 | 442 | 442 | SA24M005 | Design Package for EHV Energy/Revenue Substation Permanent Sign Board |  | 6 | -1 | 0 |  |  | X
443 | 443 | 443 | 443 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical Design Package for EHV Energy/Revenue Substation Permanent Sign Board Drafting / Preparation | 1 | E0SB | E000 | 00E1 | E000E0SB00E1
444 | 444 | 444 | 444 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical Design Package for EHV Energy/Revenue Substation Permanent Sign Board Submission | 2 | E0SB | E000 | 00E2 | E000E0SB00E2
445 | 445 | 445 | 445 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical Design Package for EHV Energy/Revenue Substation Permanent Sign Board Review / Evaluation | 3 | E0SB | E000 | 00E3 | E000E0SB00E3
446 | 446 | 446 | 446 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical Design Package for EHV Energy/Revenue Substation Permanent Sign Board Approval with Comments | 4 | E0SB | E000 | 00E4 | E000E0SB00E4
447 | 447 | 447 | 447 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical Design Package for EHV Energy/Revenue Substation Permanent Sign Board FINAL Approval | 5 | E0SB | E000 | 00E5 | E000E0SB00E5
448 | 448 | 448 | 448 | SA24M005 | Design Package for HV Energy/Revenue Metering Panels |  | 6 | -1 | 0 |  |  | X
449 | 449 | 449 | 449 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical Design Package for HV Energy/Revenue Metering Panels Drafting / Preparation | 1 | EHVRM | E000 | 00E1 | E000EHVRM00E1
450 | 450 | 450 | 450 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical Design Package for HV Energy/Revenue Metering Panels Submission | 2 | EHVRM | E000 | 00E2 | E000EHVRM00E2
451 | 451 | 451 | 451 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical Design Package for HV Energy/Revenue Metering Panels Review / Evaluation | 3 | EHVRM | E000 | 00E3 | E000EHVRM00E3
452 | 452 | 452 | 452 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical Design Package for HV Energy/Revenue Metering Panels Approval with Comments | 4 | EHVRM | E000 | 00E4 | E000EHVRM00E4
453 | 453 | 453 | 453 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical Design Package for HV Energy/Revenue Metering Panels FINAL Approval | 5 | EHVRM | E000 | 00E5 | E000EHVRM00E5
454 | 454 | 454 | 454 | SA24M005 | Design Package for MV Energy/Revenue Metering Panels |  | 6 | -1 | 0 |  |  | X
455 | 455 | 455 | 455 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical Design Package for MV Energy/Revenue Metering Panels Drafting / Preparation | 1 | E0MVRM | E000 | 00E1 | E000E0MVRM00E1
456 | 456 | 456 | 456 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical Design Package for MV Energy/Revenue Metering Panels Submission | 2 | E0MVRM | E000 | 00E2 | E000E0MVRM00E2
457 | 457 | 457 | 457 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical Design Package for MV Energy/Revenue Metering Panels Review / Evaluation | 3 | E0MVRM | E000 | 00E3 | E000E0MVRM00E3
458 | 458 | 458 | 458 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical Design Package for MV Energy/Revenue Metering Panels Approval with Comments | 4 | E0MVRM | E000 | 00E4 | E000E0MVRM00E4
459 | 459 | 459 | 459 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical Design Package for MV Energy/Revenue Metering Panels FINAL Approval | 5 | E0MVRM | E000 | 00E5 | E000E0MVRM00E5
460 | 460 | 460 | 460 | SA24M005 | Control Scheme and Panels |  | 6 | -1 | 0 |  |  | X
461 | 461 | 461 | 461 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical Control Scheme and Panels Drafting / Preparation | 1 | ECSCM | E000 | 00E1 | E000ECSCM00E1
462 | 462 | 462 | 462 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical Control Scheme and Panels Submission | 2 | ECSCM | E000 | 00E2 | E000ECSCM00E2
463 | 463 | 463 | 463 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical Control Scheme and Panels Review / Evaluation | 3 | ECSCM | E000 | 00E3 | E000ECSCM00E3
464 | 464 | 464 | 464 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical Control Scheme and Panels Approval with Comments | 4 | ECSCM | E000 | 00E4 | E000ECSCM00E4
465 | 465 | 465 | 465 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical Control Scheme and Panels FINAL Approval | 5 | ECSCM | E000 | 00E5 | E000ECSCM00E5
466 | 466 | 466 | 466 | SA24M005 | Metering Panels |  | 6 | -1 | 0 |  |  | X
467 | 467 | 467 | 467 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical Metering Panels Drafting / Preparation | 1 | E0METP | E000 | 00E1 | E000E0METP00E1
468 | 468 | 468 | 468 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical Metering Panels Submission | 2 | E0METP | E000 | 00E2 | E000E0METP00E2
469 | 469 | 469 | 469 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical Metering Panels Review / Evaluation | 3 | E0METP | E000 | 00E3 | E000E0METP00E3
470 | 470 | 470 | 470 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical Metering Panels Approval with Comments | 4 | E0METP | E000 | 00E4 | E000E0METP00E4
471 | 471 | 471 | 471 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical Metering Panels FINAL Approval | 5 | E0METP | E000 | 00E5 | E000E0METP00E5
472 | 472 | 472 | 472 | SA24M005 | AMI Design Package |  | 6 | -1 | 0 |  |  | X
473 | 473 | 473 | 473 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical AMI Design Package Drafting / Preparation | 1 | EAMI | E000 | 00E1 | E000EAMI00E1
474 | 474 | 474 | 474 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical AMI Design Package Submission | 2 | EAMI | E000 | 00E2 | E000EAMI00E2
475 | 475 | 475 | 475 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical AMI Design Package Review / Evaluation | 3 | EAMI | E000 | 00E3 | E000EAMI00E3
476 | 476 | 476 | 476 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical AMI Design Package Approval with Comments | 4 | EAMI | E000 | 00E4 | E000EAMI00E4
477 | 477 | 477 | 477 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical AMI Design Package FINAL Approval | 5 | EAMI | E000 | 00E5 | E000EAMI00E5
478 | 478 | 478 | 478 | SA24M005 | Complete Design Package for Revenue Metering Panel (RMT 1_RMT6) |  | 6 | -1 | 0 |  |  | X
479 | 479 | 479 | 479 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical Complete Design Package for Revenue Metering Panel (RMT 1_RMT6) Drafting / Preparation | 1 | E0RMT | E000 | 00E1 | E000E0RMT00E1
480 | 480 | 480 | 480 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical Complete Design Package for Revenue Metering Panel (RMT 1_RMT6) Submission | 2 | E0RMT | E000 | 00E2 | E000E0RMT00E2
481 | 481 | 481 | 481 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical Complete Design Package for Revenue Metering Panel (RMT 1_RMT6) Review / Evaluation | 3 | E0RMT | E000 | 00E3 | E000E0RMT00E3
482 | 482 | 482 | 482 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical Complete Design Package for Revenue Metering Panel (RMT 1_RMT6) Approval with Comments | 4 | E0RMT | E000 | 00E4 | E000E0RMT00E4
483 | 483 | 483 | 483 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Electrical Complete Design Package for Revenue Metering Panel (RMT 1_RMT6) FINAL Approval | 5 | E0RMT | E000 | 00E5 | E000E0RMT00E5
484 | 484 | 484 | 484 | SA24M005 | Civil |  | 5 | -1 | 0 |  |  | X
485 | 485 | 485 | 485 | SA24M005 | Materials for Underground Waterproofing System |  | 6 | -1 | 0 |  |  | X
486 | 486 | 486 | 486 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Underground Waterproofing System Drafting / Preparation | 1 | C0UWS | E000 | 00E1 | E000C0UWS00E1
487 | 487 | 487 | 487 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Underground Waterproofing System Submission | 2 | C0UWS | E000 | 00E2 | E000C0UWS00E2
488 | 488 | 488 | 488 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Underground Waterproofing System Review / Evaluation | 3 | C0UWS | E000 | 00E3 | E000C0UWS00E3
489 | 489 | 489 | 489 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Underground Waterproofing System Approval with Comments | 4 | C0UWS | E000 | 00E4 | E000C0UWS00E4
490 | 490 | 490 | 490 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Underground Waterproofing System FINAL Approval | 5 | C0UWS | E000 | 00E5 | E000C0UWS00E5
491 | 491 | 491 | 491 | SA24M005 | Civil Material Submittal for Roof Waterproofing System |  | 6 | -1 | 0 |  |  | X
492 | 492 | 492 | 492 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Civil Material Submittal for Roof Waterproofing System Drafting / Preparation | 1 | CRMWS | E000 | 00E1 | E000CRMWS00E1
493 | 493 | 493 | 493 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Civil Material Submittal for Roof Waterproofing System Submission | 2 | CRMWS | E000 | 00E2 | E000CRMWS00E2
494 | 494 | 494 | 494 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Civil Material Submittal for Roof Waterproofing System Review / Evaluation | 3 | CRMWS | E000 | 00E3 | E000CRMWS00E3
495 | 495 | 495 | 495 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Civil Material Submittal for Roof Waterproofing System Approval with Comments | 4 | CRMWS | E000 | 00E4 | E000CRMWS00E4
496 | 496 | 496 | 496 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Civil Material Submittal for Roof Waterproofing System FINAL Approval | 5 | CRMWS | E000 | 00E5 | E000CRMWS00E5
497 | 497 | 497 | 497 | SA24M005 | Materials for Cementitous Membrane, Coal Tar Epoxy, and Polyurethane Waterproofing |  | 6 | -1 | 0 |  |  | X
498 | 498 | 498 | 498 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Cementitous Membrane, Coal Tar Epoxy, and Polyurethane Waterproofing Drafting / Preparation | 1 | CEMW | E000 | 00E1 | E000CEMW00E1
499 | 499 | 499 | 499 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Cementitous Membrane, Coal Tar Epoxy, and Polyurethane Waterproofing Submission | 2 | CEMW | E000 | 00E2 | E000CEMW00E2
500 | 500 | 500 | 500 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Cementitous Membrane, Coal Tar Epoxy, and Polyurethane Waterproofing Review / Evaluation | 3 | CEMW | E000 | 00E3 | E000CEMW00E3
501 | 501 | 501 | 501 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Cementitous Membrane, Coal Tar Epoxy, and Polyurethane Waterproofing Approval with Comments | 4 | CEMW | E000 | 00E4 | E000CEMW00E4
502 | 502 | 502 | 502 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Cementitous Membrane, Coal Tar Epoxy, and Polyurethane Waterproofing FINAL Approval | 5 | CEMW | E000 | 00E5 | E000CEMW00E5
503 | 503 | 503 | 503 | SA24M005 | Materials for Joint Filler and Sealant |  | 6 | -1 | 0 |  |  | X
504 | 504 | 504 | 504 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Joint Filler and Sealant Drafting / Preparation | 1 | CJF | E000 | 00E1 | E000CJF00E1
505 | 505 | 505 | 505 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Joint Filler and Sealant Submission | 2 | CJF | E000 | 00E2 | E000CJF00E2
506 | 506 | 506 | 506 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Joint Filler and Sealant Review / Evaluation | 3 | CJF | E000 | 00E3 | E000CJF00E3
507 | 507 | 507 | 507 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Joint Filler and Sealant Approval with Comments | 4 | CJF | E000 | 00E4 | E000CJF00E4
508 | 508 | 508 | 508 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Joint Filler and Sealant FINAL Approval | 5 | CJF | E000 | 00E5 | E000CJF00E5
509 | 509 | 509 | 509 | SA24M005 | Materials for Non Shrink Grout and Bonding Agent |  | 6 | -1 | 0 |  |  | X
510 | 510 | 510 | 510 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Non Shrink Grout and Bonding Agent Drafting / Preparation | 1 | C0NSG | E000 | 00E1 | E000C0NSG00E1
511 | 511 | 511 | 511 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Non Shrink Grout and Bonding Agent Submission | 2 | C0NSG | E000 | 00E2 | E000C0NSG00E2
512 | 512 | 512 | 512 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Non Shrink Grout and Bonding Agent Review / Evaluation | 3 | C0NSG | E000 | 00E3 | E000C0NSG00E3
513 | 513 | 513 | 513 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Non Shrink Grout and Bonding Agent Approval with Comments | 4 | C0NSG | E000 | 00E4 | E000C0NSG00E4
514 | 514 | 514 | 514 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Non Shrink Grout and Bonding Agent FINAL Approval | 5 | C0NSG | E000 | 00E5 | E000C0NSG00E5
515 | 515 | 515 | 515 | SA24M005 | Materials for Concrete Repair, Surfacer, Crack, Injections |  | 6 | -1 | 0 |  |  | X
516 | 516 | 516 | 516 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Concrete Repair, Surfacer, Crack, Injections Drafting / Preparation | 1 | C0CRM | E000 | 00E1 | E000#iLzP00E1
517 | 517 | 517 | 517 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Concrete Repair, Surfacer, Crack, Injections Submission | 2 | C0CRM | E000 | 00E2 | E000#iLzP00E2
518 | 518 | 518 | 518 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Concrete Repair, Surfacer, Crack, Injections Review / Evaluation | 3 | C0CRM | E000 | 00E3 | E000#iLzP00E3
519 | 519 | 519 | 519 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Concrete Repair, Surfacer, Crack, Injections Approval with Comments | 4 | C0CRM | E000 | 00E4 | E000#iLzP00E4
520 | 520 | 520 | 520 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Concrete Repair, Surfacer, Crack, Injections FINAL Approval | 5 | C0CRM | E000 | 00E5 | E000#iLzP00E5
521 | 521 | 521 | 521 | SA24M005 | Materials for Raised Floor System |  | 6 | -1 | 0 |  |  | X | E000#iLzP
522 | 522 | 522 | 522 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Raised Floor System Drafting / Preparation | 1 | CRMFS | E000 | 00E1 | E000CRMFS00E1
523 | 523 | 523 | 523 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Raised Floor System Submission | 2 | CRMFS | E000 | 00E2 | E000CRMFS00E2
524 | 524 | 524 | 524 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Raised Floor System Review / Evaluation | 3 | CRMFS | E000 | 00E3 | E000CRMFS00E3
525 | 525 | 525 | 525 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Raised Floor System Approval with Comments | 4 | CRMFS | E000 | 00E4 | E000CRMFS00E4
526 | 526 | 526 | 526 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Raised Floor System FINAL Approval | 5 | CRMFS | E000 | 00E5 | E000CRMFS00E5
527 | 527 | 527 | 527 | SA24M005 | Materials for Concrete Masonry Units |  | 6 | -1 | 0 |  |  | X
528 | 528 | 528 | 528 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Concrete Masonry Units Drafting / Preparation | 1 | CMCMU | E000 | 00E1 | E000CMCMU00E1
529 | 529 | 529 | 529 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Concrete Masonry Units Submission | 2 | CMCMU | E000 | 00E2 | E000CMCMU00E2
530 | 530 | 530 | 530 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Concrete Masonry Units Review / Evaluation | 3 | CMCMU | E000 | 00E3 | E000CMCMU00E3
531 | 531 | 531 | 531 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Concrete Masonry Units Approval with Comments | 4 | CMCMU | E000 | 00E4 | E000CMCMU00E4
532 | 532 | 532 | 532 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Concrete Masonry Units FINAL Approval | 5 | CMCMU | E000 | 00E5 | E000CMCMU00E5
533 | 533 | 533 | 533 | SA24M005 | Materials for Dry Wall System |  | 6 | -1 | 0 |  |  | X
534 | 534 | 534 | 534 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Dry Wall System Drafting / Preparation | 1 | CDWDS | E000 | 00E1 | E000CDWDS00E1
535 | 535 | 535 | 535 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Dry Wall System Submission | 2 | CDWDS | E000 | 00E2 | E000CDWDS00E2
536 | 536 | 536 | 536 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Dry Wall System Review / Evaluation | 3 | CDWDS | E000 | 00E3 | E000CDWDS00E3
537 | 537 | 537 | 537 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Dry Wall System Approval with Comments | 4 | CDWDS | E000 | 00E4 | E000CDWDS00E4
538 | 538 | 538 | 538 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Dry Wall System FINAL Approval | 5 | CDWDS | E000 | 00E5 | E000CDWDS00E5
539 | 539 | 539 | 539 | SA24M005 | Materials for Suspended Ceiling System |  | 6 | -1 | 0 |  |  | X
540 | 540 | 540 | 540 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Suspended Ceiling System Drafting / Preparation | 1 | MSCE | E000 | 00E1 | E000MSCE00E1
541 | 541 | 541 | 541 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Suspended Ceiling System Submission | 2 | MSCE | E000 | 00E2 | E000MSCE00E2
542 | 542 | 542 | 542 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Suspended Ceiling System Review / Evaluation | 3 | MSCE | E000 | 00E3 | E000MSCE00E3
543 | 543 | 543 | 543 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Suspended Ceiling System Approval with Comments | 4 | MSCE | E000 | 00E4 | E000MSCE00E4
544 | 544 | 544 | 544 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Suspended Ceiling System FINAL Approval | 5 | MSCE | E000 | 00E5 | E000MSCE00E5
545 | 545 | 545 | 545 | SA24M005 | Materials for Tiling System |  | 6 | -1 | 0 |  |  | X
546 | 546 | 546 | 546 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Tiling System Drafting / Preparation | 1 | CTILE | E000 | 00E1 | E000CTILE00E1
547 | 547 | 547 | 547 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Tiling System Submission | 2 | CTILE | E000 | 00E2 | E000CTILE00E2
548 | 548 | 548 | 548 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Tiling System Review / Evaluation | 3 | CTILE | E000 | 00E3 | E000CTILE00E3
549 | 549 | 549 | 549 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Tiling System Approval with Comments | 4 | CTILE | E000 | 00E4 | E000CTILE00E4
550 | 550 | 550 | 550 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Materials for Tiling System FINAL Approval | 5 | CTILE | E000 | 00E5 | E000CTILE00E5
551 | 551 | 551 | 551 | SA24M005 | Material for Painting System |  | 6 | -1 | 0 |  |  | X
552 | 552 | 552 | 552 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Material for Painting System Drafting / Preparation | 1 | C0MPS | E000 | 00E1 | E000C0MPS00E1
553 | 553 | 553 | 553 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Material for Painting System Submission | 2 | C0MPS | E000 | 00E2 | E000C0MPS00E2
554 | 554 | 554 | 554 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Material for Painting System Review / Evaluation | 3 | C0MPS | E000 | 00E3 | E000C0MPS00E3
555 | 555 | 555 | 555 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Material for Painting System Approval with Comments | 4 | C0MPS | E000 | 00E4 | E000C0MPS00E4
556 | 556 | 556 | 556 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Material for Painting System FINAL Approval | 5 | C0MPS | E000 | 00E5 | E000C0MPS00E5
557 | 557 | 557 | 557 | SA24M005 | Hollow Metal Doors Shop Drawings for Buildings Including Door Hardware |  | 6 | -1 | 0 |  |  | X
558 | 558 | 558 | 558 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Hollow Metal Doors Shop Drawings for Buildings Including Door Hardware Drafting / Preparation | 1 | CHMD | E000 | 00E1 | E000CHMD00E1
559 | 559 | 559 | 559 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Hollow Metal Doors Shop Drawings for Buildings Including Door Hardware Submission | 2 | CHMD | E000 | 00E2 | E000CHMD00E2
560 | 560 | 560 | 560 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Hollow Metal Doors Shop Drawings for Buildings Including Door Hardware Review / Evaluation | 3 | CHMD | E000 | 00E3 | E000CHMD00E3
561 | 561 | 561 | 561 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Hollow Metal Doors Shop Drawings for Buildings Including Door Hardware Approval with Comments | 4 | CHMD | E000 | 00E4 | E000CHMD00E4
562 | 562 | 562 | 562 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Hollow Metal Doors Shop Drawings for Buildings Including Door Hardware FINAL Approval | 5 | CHMD | E000 | 00E5 | E000CHMD00E5
563 | 563 | 563 | 563 | SA24M005 | PVC 200mm water stopper |  | 6 | -1 | 0 |  |  | X
564 | 564 | 564 | 564 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil PVC 200mm water stopper Drafting / Preparation | 1 | CPVCW | E000 | 00E1 | E000CPVCW00E1
565 | 565 | 565 | 565 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil PVC 200mm water stopper Submission | 2 | CPVCW | E000 | 00E2 | E000CPVCW00E2
566 | 566 | 566 | 566 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil PVC 200mm water stopper Review / Evaluation | 3 | CPVCW | E000 | 00E3 | E000CPVCW00E3
567 | 567 | 567 | 567 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil PVC 200mm water stopper Approval with Comments | 4 | CPVCW | E000 | 00E4 | E000CPVCW00E4
568 | 568 | 568 | 568 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil PVC 200mm water stopper FINAL Approval | 5 | CPVCW | E000 | 00E5 | E000CPVCW00E5
569 | 569 | 569 | 569 | SA24M005 | Ready Concrete Mix & Asphalt Design |  | 6 | -1 | 0 |  |  | X
570 | 570 | 570 | 570 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Ready Concrete Mix & Asphalt Design Drafting / Preparation | 1 | CRCMX | E000 | 00E1 | E000CRCMX00E1
571 | 571 | 571 | 571 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Ready Concrete Mix & Asphalt Design Submission | 2 | CRCMX | E000 | 00E2 | E000CRCMX00E2
572 | 572 | 572 | 572 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Ready Concrete Mix & Asphalt Design Review / Evaluation | 3 | CRCMX | E000 | 00E3 | E000CRCMX00E3
573 | 573 | 573 | 573 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Ready Concrete Mix & Asphalt Design Approval with Comments | 4 | CRCMX | E000 | 00E4 | E000CRCMX00E4
574 | 574 | 574 | 574 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Ready Concrete Mix & Asphalt Design FINAL Approval | 5 | CRCMX | E000 | 00E5 | E000CRCMX00E5
575 | 575 | 575 | 575 | SA24M005 | Ready Mix Concrete Supplier Design Mix for Cast-In-Suitu Concrete (A) |  | 6 | -1 | 0 |  |  | X
576 | 576 | 576 | 576 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Ready Mix Concrete Supplier Design Mix for Cast-In-Suitu Concrete (A) Drafting / Preparation | 1 | CRMC | E000 | 00E1 | E000#Ztdn00E1
577 | 577 | 577 | 577 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Ready Mix Concrete Supplier Design Mix for Cast-In-Suitu Concrete (A) Submission | 2 | CRMC | E000 | 00E2 | E000#Ztdn00E2
578 | 578 | 578 | 578 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Ready Mix Concrete Supplier Design Mix for Cast-In-Suitu Concrete (A) Review / Evaluation | 3 | CRMC | E000 | 00E3 | E000#Ztdn00E3
579 | 579 | 579 | 579 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Ready Mix Concrete Supplier Design Mix for Cast-In-Suitu Concrete (A) Approval with Comments | 4 | CRMC | E000 | 00E4 | E000#Ztdn00E4
580 | 580 | 580 | 580 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Ready Mix Concrete Supplier Design Mix for Cast-In-Suitu Concrete (A) FINAL Approval | 5 | CRMC | E000 | 00E5 | E000#Ztdn00E5
581 | 581 | 581 | 581 | SA24M005 | Ready Mix Concrete Supplier Design Mix for Cast-In-Suitu Concrete (B) |  | 6 | -1 | 0 |  |  | X | E000#Ztdn
582 | 582 | 582 | 582 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Ready Mix Concrete Supplier Design Mix for Cast-In-Suitu Concrete (B) Drafting / Preparation | 1 | CRMCS | E000 | 00E1 | E000CRMCS00E1
583 | 583 | 583 | 583 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Ready Mix Concrete Supplier Design Mix for Cast-In-Suitu Concrete (B) Submission | 2 | CRMCS | E000 | 00E2 | E000CRMCS00E2
584 | 584 | 584 | 584 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Ready Mix Concrete Supplier Design Mix for Cast-In-Suitu Concrete (B) Review / Evaluation | 3 | CRMCS | E000 | 00E3 | E000CRMCS00E3
585 | 585 | 585 | 585 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Ready Mix Concrete Supplier Design Mix for Cast-In-Suitu Concrete (B) Approval with Comments | 4 | CRMCS | E000 | 00E4 | E000CRMCS00E4
586 | 586 | 586 | 586 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Ready Mix Concrete Supplier Design Mix for Cast-In-Suitu Concrete (B) FINAL Approval | 5 | CRMCS | E000 | 00E5 | E000CRMCS00E5
587 | 587 | 587 | 587 | SA24M005 | Ready Mix Concrete Supplier Design Mix for Precast Concrete |  | 6 | -1 | 0 |  |  | X
588 | 588 | 588 | 588 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Ready Mix Concrete Supplier Design Mix for Precast Concrete Drafting / Preparation | 1 | CRMC | E000 | 00E1 | E000#wADi00E1
589 | 589 | 589 | 589 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Ready Mix Concrete Supplier Design Mix for Precast Concrete Submission | 2 | CRMC | E000 | 00E2 | E000#wADi00E2
590 | 590 | 590 | 590 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Ready Mix Concrete Supplier Design Mix for Precast Concrete Review / Evaluation | 3 | CRMC | E000 | 00E3 | E000#wADi00E3
591 | 591 | 591 | 591 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Ready Mix Concrete Supplier Design Mix for Precast Concrete Approval with Comments | 4 | CRMC | E000 | 00E4 | E000#wADi00E4
592 | 592 | 592 | 592 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Ready Mix Concrete Supplier Design Mix for Precast Concrete FINAL Approval | 5 | CRMC | E000 | 00E5 | E000#wADi00E5
593 | 593 | 593 | 593 | SA24M005 | Concrete Mix Design |  | 6 | -1 | 0 |  |  | X | E000#wADi
594 | 594 | 594 | 594 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Concrete Mix Design Drafting / Preparation | 1 | C0CMD | E000 | 00E1 | E000C0CMD00E1
595 | 595 | 595 | 595 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Concrete Mix Design Submission | 2 | C0CMD | E000 | 00E2 | E000C0CMD00E2
596 | 596 | 596 | 596 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Concrete Mix Design Review / Evaluation | 3 | C0CMD | E000 | 00E3 | E000C0CMD00E3
597 | 597 | 597 | 597 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Concrete Mix Design Approval with Comments | 4 | C0CMD | E000 | 00E4 | E000C0CMD00E4
598 | 598 | 598 | 598 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Civil Concrete Mix Design FINAL Approval | 5 | C0CMD | E000 | 00E5 | E000C0CMD00E5
599 | 599 | 599 | 599 | SA24M005 | Mechanical |  | 5 | -1 | 0 |  |  | X
600 | 600 | 600 | 600 | SA24M005 | EHV GIS Room- Technical Submittal for EOT Crane |  | 6 | -1 | 0 |  |  | X
601 | 601 | 601 | 601 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Mechanical EHV GIS Room- Technical Submittal for EOT Crane Drafting / Preparation | 1 | E0GIS | E000 | 00E1 | E000#ciMI00E1
602 | 602 | 602 | 602 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Mechanical EHV GIS Room- Technical Submittal for EOT Crane Submission | 2 | E0GIS | E000 | 00E2 | E000#ciMI00E2
603 | 603 | 603 | 603 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Mechanical EHV GIS Room- Technical Submittal for EOT Crane Review / Evaluation | 3 | E0GIS | E000 | 00E3 | E000#ciMI00E3
604 | 604 | 604 | 604 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Mechanical EHV GIS Room- Technical Submittal for EOT Crane Approval with Comments | 4 | E0GIS | E000 | 00E4 | E000#ciMI00E4
605 | 605 | 605 | 605 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Mechanical EHV GIS Room- Technical Submittal for EOT Crane FINAL Approval | 5 | E0GIS | E000 | 00E5 | E000#ciMI00E5
606 | 606 | 606 | 606 | SA24M005 | Protection |  | 5 | -1 | 0 |  |  | X | E000#ciMI
607 | 607 | 607 | 607 | SA24M005 | Control and Protection Panel proposals |  | 6 | -1 | 0 |  |  | X | E000#ciMI
608 | 608 | 608 | 608 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Protection Control and Protection Panel proposals Drafting / Preparation | 1 | C0CPP | E000 | 00E1 | E000C0CPP00E1
609 | 609 | 609 | 609 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Protection Control and Protection Panel proposals Submission | 2 | C0CPP | E000 | 00E2 | E000C0CPP00E2
610 | 610 | 610 | 610 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Protection Control and Protection Panel proposals Review / Evaluation | 3 | C0CPP | E000 | 00E3 | E000C0CPP00E3
611 | 611 | 611 | 611 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Protection Control and Protection Panel proposals Approval with Comments | 4 | C0CPP | E000 | 00E4 | E000C0CPP00E4
612 | 612 | 612 | 612 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Protection Control and Protection Panel proposals FINAL Approval | 5 | C0CPP | E000 | 00E5 | E000C0CPP00E5
613 | 613 | 613 | 613 | SA24M005 | Relay and Protection Details |  | 6 | -1 | 0 |  |  | X
614 | 614 | 614 | 614 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Protection Relay and Protection Details Drafting / Preparation | 1 | PRPD | E000 | 00E1 | E000PRPD00E1
615 | 615 | 615 | 615 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Protection Relay and Protection Details Submission | 2 | PRPD | E000 | 00E2 | E000PRPD00E2
616 | 616 | 616 | 616 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Protection Relay and Protection Details Review / Evaluation | 3 | PRPD | E000 | 00E3 | E000PRPD00E3
617 | 617 | 617 | 617 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Protection Relay and Protection Details Approval with Comments | 4 | PRPD | E000 | 00E4 | E000PRPD00E4
618 | 618 | 618 | 618 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- II Protection Relay and Protection Details FINAL Approval | 5 | PRPD | E000 | 00E5 | E000PRPD00E5
619 | 619 | 619 | 619 | SA24M005 | Phase- III |  | 4 | -1 | 0 |  |  | X
620 | 620 | 620 | 620 | SA24M005 | Electrical |  | 5 | -1 | 0 |  |  | X
621 | 621 | 621 | 621 | SA24M005 | EHV GIS room- Equipment Layout plan & Sections |  | 6 | -1 | 0 |  |  | X
622 | 622 | 622 | 622 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical EHV GIS room- Equipment Layout plan & Sections Drafting / Preparation | 1 | E0GIS | E000 | 00E1 | E000#pKcD00E1
623 | 623 | 623 | 623 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical EHV GIS room- Equipment Layout plan & Sections Submission | 2 | E0GIS | E000 | 00E2 | E000#pKcD00E2
624 | 624 | 624 | 624 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical EHV GIS room- Equipment Layout plan & Sections Review / Evaluation | 3 | E0GIS | E000 | 00E3 | E000#pKcD00E3
625 | 625 | 625 | 625 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical EHV GIS room- Equipment Layout plan & Sections Approval with Comments | 4 | E0GIS | E000 | 00E4 | E000#pKcD00E4
626 | 626 | 626 | 626 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical EHV GIS room- Equipment Layout plan & Sections FINAL Approval | 5 | E0GIS | E000 | 00E5 | E000#pKcD00E5
627 | 627 | 627 | 627 | SA24M005 | EHV GIS room- LV Power & Control Cable Schedule |  | 6 | -1 | 0 |  |  | X | E000#pKcD
628 | 628 | 628 | 628 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical EHV GIS room- LV Power & Control Cable Schedule Drafting / Preparation | 1 | E0GIS | E000 | 00E1 | E000#ziEx00E1
629 | 629 | 629 | 629 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical EHV GIS room- LV Power & Control Cable Schedule Submission | 2 | E0GIS | E000 | 00E2 | E000#ziEx00E2
630 | 630 | 630 | 630 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical EHV GIS room- LV Power & Control Cable Schedule Review / Evaluation | 3 | E0GIS | E000 | 00E3 | E000#ziEx00E3
631 | 631 | 631 | 631 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical EHV GIS room- LV Power & Control Cable Schedule Approval with Comments | 4 | E0GIS | E000 | 00E4 | E000#ziEx00E4
632 | 632 | 632 | 632 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical EHV GIS room- LV Power & Control Cable Schedule FINAL Approval | 5 | E0GIS | E000 | 00E5 | E000#ziEx00E5
633 | 633 | 633 | 633 | SA24M005 | EHV GIS room- Wall Opening , Floor Cutout , Basement wall opening , cable sleeves & Rooftop Layout D |  | 6 | -1 | 0 |  |  | X | E000#ziEx
634 | 634 | 634 | 634 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical EHV GIS room- Wall Opening , Floor Cutout , Basement wall opening , cable sleeves & Rooftop Layout D Drafting / Preparation | 1 | E0GIS | E000 | 00E1 | E000#KEkU00E1
635 | 635 | 635 | 635 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical EHV GIS room- Wall Opening , Floor Cutout , Basement wall opening , cable sleeves & Rooftop Layout D Submission | 2 | E0GIS | E000 | 00E2 | E000#KEkU00E2
636 | 636 | 636 | 636 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical EHV GIS room- Wall Opening , Floor Cutout , Basement wall opening , cable sleeves & Rooftop Layout D Review / Evaluation | 3 | E0GIS | E000 | 00E3 | E000#KEkU00E3
637 | 637 | 637 | 637 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical EHV GIS room- Wall Opening , Floor Cutout , Basement wall opening , cable sleeves & Rooftop Layout D Approval with Comments | 4 | E0GIS | E000 | 00E4 | E000#KEkU00E4
638 | 638 | 638 | 638 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical EHV GIS room- Wall Opening , Floor Cutout , Basement wall opening , cable sleeves & Rooftop Layout D FINAL Approval | 5 | E0GIS | E000 | 00E5 | E000#KEkU00E5
639 | 639 | 639 | 639 | SA24M005 | EHV GIS room- LV Power & Control Cable Race Way Routing Layout Plan and Section |  | 6 | -1 | 0 |  |  | X | E000#KEkU
640 | 640 | 640 | 640 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical EHV GIS room- LV Power & Control Cable Race Way Routing Layout Plan and Section Drafting / Preparation | 1 | E0GIS | E000 | 00E1 | E000#Nwzs00E1
641 | 641 | 641 | 641 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical EHV GIS room- LV Power & Control Cable Race Way Routing Layout Plan and Section Submission | 2 | E0GIS | E000 | 00E2 | E000#Nwzs00E2
642 | 642 | 642 | 642 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical EHV GIS room- LV Power & Control Cable Race Way Routing Layout Plan and Section Review / Evaluation | 3 | E0GIS | E000 | 00E3 | E000#Nwzs00E3
643 | 643 | 643 | 643 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical EHV GIS room- LV Power & Control Cable Race Way Routing Layout Plan and Section Approval with Comments | 4 | E0GIS | E000 | 00E4 | E000#Nwzs00E4
644 | 644 | 644 | 644 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical EHV GIS room- LV Power & Control Cable Race Way Routing Layout Plan and Section FINAL Approval | 5 | E0GIS | E000 | 00E5 | E000#Nwzs00E5
645 | 645 | 645 | 645 | SA24M005 | EHV GIS room- Reinforcement Grounding |  | 6 | -1 | 0 |  |  | X | E000#Nwzs
646 | 646 | 646 | 646 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical EHV GIS room- Reinforcement Grounding Drafting / Preparation | 1 | E0GIS | E000 | 00E1 | E000#atis00E1
647 | 647 | 647 | 647 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical EHV GIS room- Reinforcement Grounding Submission | 2 | E0GIS | E000 | 00E2 | E000#atis00E2
648 | 648 | 648 | 648 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical EHV GIS room- Reinforcement Grounding Review / Evaluation | 3 | E0GIS | E000 | 00E3 | E000#atis00E3
649 | 649 | 649 | 649 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical EHV GIS room- Reinforcement Grounding Approval with Comments | 4 | E0GIS | E000 | 00E4 | E000#atis00E4
650 | 650 | 650 | 650 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical EHV GIS room- Reinforcement Grounding FINAL Approval | 5 | E0GIS | E000 | 00E5 | E000#atis00E5
651 | 651 | 651 | 651 | SA24M005 | EHV GIS room- Equipment grounding Layout and Details |  | 6 | -1 | 0 |  |  | X | E000#atis
652 | 652 | 652 | 652 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical EHV GIS room- Equipment grounding Layout and Details Drafting / Preparation | 1 | E0GIS | E000 | 00E1 | E000#fZan00E1
653 | 653 | 653 | 653 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical EHV GIS room- Equipment grounding Layout and Details Submission | 2 | E0GIS | E000 | 00E2 | E000#fZan00E2
654 | 654 | 654 | 654 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical EHV GIS room- Equipment grounding Layout and Details Review / Evaluation | 3 | E0GIS | E000 | 00E3 | E000#fZan00E3
655 | 655 | 655 | 655 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical EHV GIS room- Equipment grounding Layout and Details Approval with Comments | 4 | E0GIS | E000 | 00E4 | E000#fZan00E4
656 | 656 | 656 | 656 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical EHV GIS room- Equipment grounding Layout and Details FINAL Approval | 5 | E0GIS | E000 | 00E5 | E000#fZan00E5
657 | 657 | 657 | 657 | SA24M005 | Grounding Grid system Design Calculations |  | 6 | -1 | 0 |  |  | X | E000#fZan
658 | 658 | 658 | 658 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Grounding Grid system Design Calculations Drafting / Preparation | 1 | EGRND | E000 | 00E1 | E000#SaqZ00E1
659 | 659 | 659 | 659 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Grounding Grid system Design Calculations Submission | 2 | EGRND | E000 | 00E2 | E000#SaqZ00E2
660 | 660 | 660 | 660 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Grounding Grid system Design Calculations Review / Evaluation | 3 | EGRND | E000 | 00E3 | E000#SaqZ00E3
661 | 661 | 661 | 661 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Grounding Grid system Design Calculations Approval with Comments | 4 | EGRND | E000 | 00E4 | E000#SaqZ00E4
662 | 662 | 662 | 662 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Grounding Grid system Design Calculations FINAL Approval | 5 | EGRND | E000 | 00E5 | E000#SaqZ00E5
663 | 663 | 663 | 663 | SA24M005 | Grounding Grid Layout and Details |  | 6 | -1 | 0 |  |  | X | E000#SaqZ
664 | 664 | 664 | 664 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Grounding Grid Layout and Details Drafting / Preparation | 1 | EGRND | E000 | 00E1 | E000#LVfm00E1
665 | 665 | 665 | 665 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Grounding Grid Layout and Details Submission | 2 | EGRND | E000 | 00E2 | E000#LVfm00E2
666 | 666 | 666 | 666 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Grounding Grid Layout and Details Review / Evaluation | 3 | EGRND | E000 | 00E3 | E000#LVfm00E3
667 | 667 | 667 | 667 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Grounding Grid Layout and Details Approval with Comments | 4 | EGRND | E000 | 00E4 | E000#LVfm00E4
668 | 668 | 668 | 668 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Grounding Grid Layout and Details FINAL Approval | 5 | EGRND | E000 | 00E5 | E000#LVfm00E5
669 | 669 | 669 | 669 | SA24M005 | Reinforcement Bars, Pre cast Panels, Columns, etc. Grounding Layout And Details |  | 6 | -1 | 0 |  |  | X | E000#LVfm
670 | 670 | 670 | 670 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Reinforcement Bars, Pre cast Panels, Columns, etc. Grounding Layout And Details Drafting / Preparation | 1 | E0RBC | E000 | 00E1 | E000E0RBC00E1
671 | 671 | 671 | 671 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Reinforcement Bars, Pre cast Panels, Columns, etc. Grounding Layout And Details Submission | 2 | E0RBC | E000 | 00E2 | E000E0RBC00E2
672 | 672 | 672 | 672 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Reinforcement Bars, Pre cast Panels, Columns, etc. Grounding Layout And Details Review / Evaluation | 3 | E0RBC | E000 | 00E3 | E000E0RBC00E3
673 | 673 | 673 | 673 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Reinforcement Bars, Pre cast Panels, Columns, etc. Grounding Layout And Details Approval with Comments | 4 | E0RBC | E000 | 00E4 | E000E0RBC00E4
674 | 674 | 674 | 674 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Reinforcement Bars, Pre cast Panels, Columns, etc. Grounding Layout And Details FINAL Approval | 5 | E0RBC | E000 | 00E5 | E000E0RBC00E5
675 | 675 | 675 | 675 | SA24M005 | Outdoor Equipment & Miscellaneous Building , tunnel Reinforcement Grounding Layout & Details |  | 6 | -1 | 0 |  |  | X
676 | 676 | 676 | 676 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Outdoor Equipment & Miscellaneous Building , tunnel Reinforcement Grounding Layout & Details Drafting / Preparation | 1 | E0EQB | E000 | 00E1 | E000E0EQB00E1
677 | 677 | 677 | 677 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Outdoor Equipment & Miscellaneous Building , tunnel Reinforcement Grounding Layout & Details Submission | 2 | E0EQB | E000 | 00E2 | E000E0EQB00E2
678 | 678 | 678 | 678 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Outdoor Equipment & Miscellaneous Building , tunnel Reinforcement Grounding Layout & Details Review / Evaluation | 3 | E0EQB | E000 | 00E3 | E000E0EQB00E3
679 | 679 | 679 | 679 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Outdoor Equipment & Miscellaneous Building , tunnel Reinforcement Grounding Layout & Details Approval with Comments | 4 | E0EQB | E000 | 00E4 | E000E0EQB00E4
680 | 680 | 680 | 680 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Outdoor Equipment & Miscellaneous Building , tunnel Reinforcement Grounding Layout & Details FINAL Approval | 5 | E0EQB | E000 | 00E5 | E000E0EQB00E5
681 | 681 | 681 | 681 | SA24M005 | Technical submittal of Grounding Conductors/Cables & Accessories |  | 6 | -1 | 0 |  |  | X
682 | 682 | 682 | 682 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Technical submittal of Grounding Conductors/Cables & Accessories Drafting / Preparation | 1 | EGRND | E000 | 00E1 | E000#Smkf00E1
683 | 683 | 683 | 683 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Technical submittal of Grounding Conductors/Cables & Accessories Submission | 2 | EGRND | E000 | 00E2 | E000#Smkf00E2
684 | 684 | 684 | 684 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Technical submittal of Grounding Conductors/Cables & Accessories Review / Evaluation | 3 | EGRND | E000 | 00E3 | E000#Smkf00E3
685 | 685 | 685 | 685 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Technical submittal of Grounding Conductors/Cables & Accessories Approval with Comments | 4 | EGRND | E000 | 00E4 | E000#Smkf00E4
686 | 686 | 686 | 686 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Technical submittal of Grounding Conductors/Cables & Accessories FINAL Approval | 5 | EGRND | E000 | 00E5 | E000#Smkf00E5
687 | 687 | 687 | 687 | SA24M005 | AC One Line Diagram - Main and Sub LV AC Auxiliary System |  | 6 | -1 | 0 |  |  | X | E000#Smkf
688 | 688 | 688 | 688 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical AC One Line Diagram - Main and Sub LV AC Auxiliary System Drafting / Preparation | 1 | E0ACD | E000 | 00E1 | E000#doEr00E1
689 | 689 | 689 | 689 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical AC One Line Diagram - Main and Sub LV AC Auxiliary System Submission | 2 | E0ACD | E000 | 00E2 | E000#doEr00E2
690 | 690 | 690 | 690 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical AC One Line Diagram - Main and Sub LV AC Auxiliary System Review / Evaluation | 3 | E0ACD | E000 | 00E3 | E000#doEr00E3
691 | 691 | 691 | 691 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical AC One Line Diagram - Main and Sub LV AC Auxiliary System Approval with Comments | 4 | E0ACD | E000 | 00E4 | E000#doEr00E4
692 | 692 | 692 | 692 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical AC One Line Diagram - Main and Sub LV AC Auxiliary System FINAL Approval | 5 | E0ACD | E000 | 00E5 | E000#doEr00E5
693 | 693 | 693 | 693 | SA24M005 | DC One Line Diagram - Main and Sub DC Auxiliary System |  | 6 | -1 | 0 |  |  | X | E000#doEr
694 | 694 | 694 | 694 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical DC One Line Diagram - Main and Sub DC Auxiliary System Drafting / Preparation | 1 | E0DC1 | E000 | 00E1 | E000E0DC100E1
695 | 695 | 695 | 695 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical DC One Line Diagram - Main and Sub DC Auxiliary System Submission | 2 | E0DC1 | E000 | 00E2 | E000E0DC100E2
696 | 696 | 696 | 696 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical DC One Line Diagram - Main and Sub DC Auxiliary System Review / Evaluation | 3 | E0DC1 | E000 | 00E3 | E000E0DC100E3
697 | 697 | 697 | 697 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical DC One Line Diagram - Main and Sub DC Auxiliary System Approval with Comments | 4 | E0DC1 | E000 | 00E4 | E000E0DC100E4
698 | 698 | 698 | 698 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical DC One Line Diagram - Main and Sub DC Auxiliary System FINAL Approval | 5 | E0DC1 | E000 | 00E5 | E000E0DC100E5
699 | 699 | 699 | 699 | SA24M005 | Technical Submittal And Sizing Calculation For LV AC Power Cables And Circuit Breakers |  | 6 | -1 | 0 |  |  | X
700 | 700 | 700 | 700 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Technical Submittal And Sizing Calculation For LV AC Power Cables And Circuit Breakers Drafting / Preparation | 1 | E0LVC | E000 | 00E1 | E000#LonY00E1
701 | 701 | 701 | 701 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Technical Submittal And Sizing Calculation For LV AC Power Cables And Circuit Breakers Submission | 2 | E0LVC | E000 | 00E2 | E000#LonY00E2
702 | 702 | 702 | 702 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Technical Submittal And Sizing Calculation For LV AC Power Cables And Circuit Breakers Review / Evaluation | 3 | E0LVC | E000 | 00E3 | E000#LonY00E3
703 | 703 | 703 | 703 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Technical Submittal And Sizing Calculation For LV AC Power Cables And Circuit Breakers Approval with Comments | 4 | E0LVC | E000 | 00E4 | E000#LonY00E4
704 | 704 | 704 | 704 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Technical Submittal And Sizing Calculation For LV AC Power Cables And Circuit Breakers FINAL Approval | 5 | E0LVC | E000 | 00E5 | E000#LonY00E5
705 | 705 | 705 | 705 | SA24M005 | Technical Submittal And Sizing Calculation For LV DC Cables And Circuit Breakers |  | 6 | -1 | 0 |  |  | X | E000#LonY
706 | 706 | 706 | 706 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Technical Submittal And Sizing Calculation For LV DC Cables And Circuit Breakers Drafting / Preparation | 1 | E LVDC | E000 | 00E1 | E000E LVDC00E1
707 | 707 | 707 | 707 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Technical Submittal And Sizing Calculation For LV DC Cables And Circuit Breakers Submission | 2 | E LVDC | E000 | 00E2 | E000E LVDC00E2
708 | 708 | 708 | 708 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Technical Submittal And Sizing Calculation For LV DC Cables And Circuit Breakers Review / Evaluation | 3 | E LVDC | E000 | 00E3 | E000E LVDC00E3
709 | 709 | 709 | 709 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Technical Submittal And Sizing Calculation For LV DC Cables And Circuit Breakers Approval with Comments | 4 | E LVDC | E000 | 00E4 | E000E LVDC00E4
710 | 710 | 710 | 710 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Technical Submittal And Sizing Calculation For LV DC Cables And Circuit Breakers FINAL Approval | 5 | E LVDC | E000 | 00E5 | E000E LVDC00E5
711 | 711 | 711 | 711 | SA24M005 | Complete Design Submittal Package for DC Distribution Panels |  | 6 | -1 | 0 |  |  | X
712 | 712 | 712 | 712 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Complete Design Submittal Package for DC Distribution Panels Drafting / Preparation | 1 | E0DCDB | E000 | 00E1 | E000E0DCDB00E1
713 | 713 | 713 | 713 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Complete Design Submittal Package for DC Distribution Panels Submission | 2 | E0DCDB | E000 | 00E2 | E000E0DCDB00E2
714 | 714 | 714 | 714 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Complete Design Submittal Package for DC Distribution Panels Review / Evaluation | 3 | E0DCDB | E000 | 00E3 | E000E0DCDB00E3
715 | 715 | 715 | 715 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Complete Design Submittal Package for DC Distribution Panels Approval with Comments | 4 | E0DCDB | E000 | 00E4 | E000E0DCDB00E4
716 | 716 | 716 | 716 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Complete Design Submittal Package for DC Distribution Panels FINAL Approval | 5 | E0DCDB | E000 | 00E5 | E000E0DCDB00E5
717 | 717 | 717 | 717 | SA24M005 | Complete Design Submittal Package for AC Distribution Panels |  | 6 | -1 | 0 |  |  | X
718 | 718 | 718 | 718 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Complete Design Submittal Package for AC Distribution Panels Drafting / Preparation | 1 | E0ACDP | E000 | 00E1 | E000E0ACDP00E1
719 | 719 | 719 | 719 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Complete Design Submittal Package for AC Distribution Panels Submission | 2 | E0ACDP | E000 | 00E2 | E000E0ACDP00E2
720 | 720 | 720 | 720 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Complete Design Submittal Package for AC Distribution Panels Review / Evaluation | 3 | E0ACDP | E000 | 00E3 | E000E0ACDP00E3
721 | 721 | 721 | 721 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Complete Design Submittal Package for AC Distribution Panels Approval with Comments | 4 | E0ACDP | E000 | 00E4 | E000E0ACDP00E4
722 | 722 | 722 | 722 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Complete Design Submittal Package for AC Distribution Panels FINAL Approval | 5 | E0ACDP | E000 | 00E5 | E000E0ACDP00E5
723 | 723 | 723 | 723 | SA24M005 | 125V DC Battery & Battery Charger Sizing Calculation |  | 6 | -1 | 0 |  |  | X
724 | 724 | 724 | 724 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical 125V DC Battery & Battery Charger Sizing Calculation Drafting / Preparation | 1 | EBDCB | E000 | 00E1 | E000EBDCB00E1
725 | 725 | 725 | 725 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical 125V DC Battery & Battery Charger Sizing Calculation Submission | 2 | EBDCB | E000 | 00E2 | E000EBDCB00E2
726 | 726 | 726 | 726 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical 125V DC Battery & Battery Charger Sizing Calculation Review / Evaluation | 3 | EBDCB | E000 | 00E3 | E000EBDCB00E3
727 | 727 | 727 | 727 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical 125V DC Battery & Battery Charger Sizing Calculation Approval with Comments | 4 | EBDCB | E000 | 00E4 | E000EBDCB00E4
728 | 728 | 728 | 728 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical 125V DC Battery & Battery Charger Sizing Calculation FINAL Approval | 5 | EBDCB | E000 | 00E5 | E000EBDCB00E5
729 | 729 | 729 | 729 | SA24M005 | Complete Design Package of 125V DC Battery & Battery Charger |  | 6 | -1 | 0 |  |  | X
730 | 730 | 730 | 730 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Complete Design Package of 125V DC Battery & Battery Charger Drafting / Preparation | 1 | EBATB | E000 | 00E1 | E000EBATB00E1
731 | 731 | 731 | 731 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Complete Design Package of 125V DC Battery & Battery Charger Submission | 2 | EBATB | E000 | 00E2 | E000EBATB00E2
732 | 732 | 732 | 732 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Complete Design Package of 125V DC Battery & Battery Charger Review / Evaluation | 3 | EBATB | E000 | 00E3 | E000EBATB00E3
733 | 733 | 733 | 733 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Complete Design Package of 125V DC Battery & Battery Charger Approval with Comments | 4 | EBATB | E000 | 00E4 | E000EBATB00E4
734 | 734 | 734 | 734 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Electrical Complete Design Package of 125V DC Battery & Battery Charger FINAL Approval | 5 | EBATB | E000 | 00E5 | E000EBATB00E5
735 | 735 | 735 | 735 | SA24M005 | Civil |  | 5 | -1 | 0 |  |  | X
736 | 736 | 736 | 736 | SA24M005 | Layout & Details of GIB Support Foundations and Design Calculations |  | 6 | -1 | 0 |  |  | X
737 | 737 | 737 | 737 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Civil Layout & Details of GIB Support Foundations and Design Calculations Drafting / Preparation | 1 | CGISB | E000 | 00E1 | E000#pDTt00E1
738 | 738 | 738 | 738 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Civil Layout & Details of GIB Support Foundations and Design Calculations Submission | 2 | CGISB | E000 | 00E2 | E000#pDTt00E2
739 | 739 | 739 | 739 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Civil Layout & Details of GIB Support Foundations and Design Calculations Review / Evaluation | 3 | CGISB | E000 | 00E3 | E000#pDTt00E3
740 | 740 | 740 | 740 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Civil Layout & Details of GIB Support Foundations and Design Calculations Approval with Comments | 4 | CGISB | E000 | 00E4 | E000#pDTt00E4
741 | 741 | 741 | 741 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Civil Layout & Details of GIB Support Foundations and Design Calculations FINAL Approval | 5 | CGISB | E000 | 00E5 | E000#pDTt00E5
742 | 742 | 742 | 742 | SA24M005 | Layout , Details and Design Calculations of Lighting Poles and Lightning Mast Foundations |  | 6 | -1 | 0 |  |  | X | E000#pDTt
743 | 743 | 743 | 743 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Civil Layout , Details and Design Calculations of Lighting Poles and Lightning Mast Foundations Drafting / Preparation | 1 | CLPLM | E000 | 00E1 | E000CLPLM00E1
744 | 744 | 744 | 744 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Civil Layout , Details and Design Calculations of Lighting Poles and Lightning Mast Foundations Submission | 2 | CLPLM | E000 | 00E2 | E000CLPLM00E2
745 | 745 | 745 | 745 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Civil Layout , Details and Design Calculations of Lighting Poles and Lightning Mast Foundations Review / Evaluation | 3 | CLPLM | E000 | 00E3 | E000CLPLM00E3
746 | 746 | 746 | 746 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Civil Layout , Details and Design Calculations of Lighting Poles and Lightning Mast Foundations Approval with Comments | 4 | CLPLM | E000 | 00E4 | E000CLPLM00E4
747 | 747 | 747 | 747 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Civil Layout , Details and Design Calculations of Lighting Poles and Lightning Mast Foundations FINAL Approval | 5 | CLPLM | E000 | 00E5 | E000CLPLM00E5
748 | 748 | 748 | 748 | SA24M005 | Layout and Details of HGIS Support Foundations and Design Calculations |  | 6 | -1 | 0 |  |  | X
749 | 749 | 749 | 749 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Civil Layout and Details of HGIS Support Foundations and Design Calculations Drafting / Preparation | 1 | CHGIS | E000 | 00E1 | E000CHGIS00E1
750 | 750 | 750 | 750 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Civil Layout and Details of HGIS Support Foundations and Design Calculations Submission | 2 | CHGIS | E000 | 00E2 | E000CHGIS00E2
751 | 751 | 751 | 751 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Civil Layout and Details of HGIS Support Foundations and Design Calculations Review / Evaluation | 3 | CHGIS | E000 | 00E3 | E000CHGIS00E3
752 | 752 | 752 | 752 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Civil Layout and Details of HGIS Support Foundations and Design Calculations Approval with Comments | 4 | CHGIS | E000 | 00E4 | E000CHGIS00E4
753 | 753 | 753 | 753 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Civil Layout and Details of HGIS Support Foundations and Design Calculations FINAL Approval | 5 | CHGIS | E000 | 00E5 | E000CHGIS00E5
754 | 754 | 754 | 754 | SA24M005 | Mechanical |  | 5 | -1 | 0 |  |  | X
755 | 755 | 755 | 755 | SA24M005 | Fire Alarm/Fire Signaling System Subcontractor Prequalification |  | 6 | -1 | 0 |  |  | X
756 | 756 | 756 | 756 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Fire Alarm/Fire Signaling System Subcontractor Prequalification Drafting / Preparation | 1 | F0FSS | E000 | 00E1 | E000#oFkQ00E1
757 | 757 | 757 | 757 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Fire Alarm/Fire Signaling System Subcontractor Prequalification Submission | 2 | F0FSS | E000 | 00E2 | E000#oFkQ00E2
758 | 758 | 758 | 758 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Fire Alarm/Fire Signaling System Subcontractor Prequalification Review / Evaluation | 3 | F0FSS | E000 | 00E3 | E000#oFkQ00E3
759 | 759 | 759 | 759 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Fire Alarm/Fire Signaling System Subcontractor Prequalification Approval with Comments | 4 | F0FSS | E000 | 00E4 | E000#oFkQ00E4
760 | 760 | 760 | 760 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Fire Alarm/Fire Signaling System Subcontractor Prequalification FINAL Approval | 5 | F0FSS | E000 | 00E5 | E000#oFkQ00E5
761 | 761 | 761 | 761 | SA24M005 | Material Submittal for Pump House Monorail Crane |  | 6 | -1 | 0 |  |  | X | E000#oFkQ
762 | 762 | 762 | 762 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Material Submittal for Pump House Monorail Crane Drafting / Preparation | 1 | 0PHMC | E000 | 00E1 | E0000PHMC00E1
763 | 763 | 763 | 763 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Material Submittal for Pump House Monorail Crane Submission | 2 | 0PHMC | E000 | 00E2 | E0000PHMC00E2
764 | 764 | 764 | 764 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Material Submittal for Pump House Monorail Crane Review / Evaluation | 3 | 0PHMC | E000 | 00E3 | E0000PHMC00E3
765 | 765 | 765 | 765 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Material Submittal for Pump House Monorail Crane Approval with Comments | 4 | 0PHMC | E000 | 00E4 | E0000PHMC00E4
766 | 766 | 766 | 766 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Material Submittal for Pump House Monorail Crane FINAL Approval | 5 | 0PHMC | E000 | 00E5 | E0000PHMC00E5
767 | 767 | 767 | 767 | SA24M005 | Material Submittal for Plumbing System Pumps |  | 6 | -1 | 0 |  |  | X
768 | 768 | 768 | 768 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Material Submittal for Plumbing System Pumps Drafting / Preparation | 1 | MPLPS | E000 | 00E1 | E000MPLPS00E1
769 | 769 | 769 | 769 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Material Submittal for Plumbing System Pumps Submission | 2 | MPLPS | E000 | 00E2 | E000MPLPS00E2
770 | 770 | 770 | 770 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Material Submittal for Plumbing System Pumps Review / Evaluation | 3 | MPLPS | E000 | 00E3 | E000MPLPS00E3
771 | 771 | 771 | 771 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Material Submittal for Plumbing System Pumps Approval with Comments | 4 | MPLPS | E000 | 00E4 | E000MPLPS00E4
772 | 772 | 772 | 772 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Material Submittal for Plumbing System Pumps FINAL Approval | 5 | MPLPS | E000 | 00E5 | E000MPLPS00E5
773 | 773 | 773 | 773 | SA24M005 | Design Calculations for PUMPS |  | 6 | -1 | 0 |  |  | X
774 | 774 | 774 | 774 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Design Calculations for PUMPS Drafting / Preparation | 1 | MPUMP | E000 | 00E1 | E000MPUMP00E1
775 | 775 | 775 | 775 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Design Calculations for PUMPS Submission | 2 | MPUMP | E000 | 00E2 | E000MPUMP00E2
776 | 776 | 776 | 776 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Design Calculations for PUMPS Review / Evaluation | 3 | MPUMP | E000 | 00E3 | E000MPUMP00E3
777 | 777 | 777 | 777 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Design Calculations for PUMPS Approval with Comments | 4 | MPUMP | E000 | 00E4 | E000MPUMP00E4
778 | 778 | 778 | 778 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Design Calculations for PUMPS FINAL Approval | 5 | MPUMP | E000 | 00E5 | E000MPUMP00E5
779 | 779 | 779 | 779 | SA24M005 | Fire Alarm System Design for Substation |  | 6 | -1 | 0 |  |  | X
780 | 780 | 780 | 780 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Fire Alarm System Design for Substation Drafting / Preparation | 1 | F0FAS | E000 | 00E1 | E000#Dlnl00E1
781 | 781 | 781 | 781 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Fire Alarm System Design for Substation Submission | 2 | F0FAS | E000 | 00E2 | E000#Dlnl00E2
782 | 782 | 782 | 782 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Fire Alarm System Design for Substation Review / Evaluation | 3 | F0FAS | E000 | 00E3 | E000#Dlnl00E3
783 | 783 | 783 | 783 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Fire Alarm System Design for Substation Approval with Comments | 4 | F0FAS | E000 | 00E4 | E000#Dlnl00E4
784 | 784 | 784 | 784 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Fire Alarm System Design for Substation FINAL Approval | 5 | F0FAS | E000 | 00E5 | E000#Dlnl00E5
785 | 785 | 785 | 785 | SA24M005 | Technical Submittal for HVAC Package Air Conditioning Units for all rooms / Building(s) |  | 6 | -1 | 0 |  |  | X | E000#Dlnl
786 | 786 | 786 | 786 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Technical Submittal for HVAC Package Air Conditioning Units for all rooms / Building(s) Drafting / Preparation | 1 | MHVAC | E000 | 00E1 | E000#GUck00E1
787 | 787 | 787 | 787 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Technical Submittal for HVAC Package Air Conditioning Units for all rooms / Building(s) Submission | 2 | MHVAC | E000 | 00E2 | E000#GUck00E2
788 | 788 | 788 | 788 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Technical Submittal for HVAC Package Air Conditioning Units for all rooms / Building(s) Review / Evaluation | 3 | MHVAC | E000 | 00E3 | E000#GUck00E3
789 | 789 | 789 | 789 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Technical Submittal for HVAC Package Air Conditioning Units for all rooms / Building(s) Approval with Comments | 4 | MHVAC | E000 | 00E4 | E000#GUck00E4
790 | 790 | 790 | 790 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Technical Submittal for HVAC Package Air Conditioning Units for all rooms / Building(s) FINAL Approval | 5 | MHVAC | E000 | 00E5 | E000#GUck00E5
791 | 791 | 791 | 791 | SA24M005 | Technical Submittal for HVAC DDC Control Panel |  | 6 | -1 | 0 |  |  | X | E000#GUck
792 | 792 | 792 | 792 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Technical Submittal for HVAC DDC Control Panel Drafting / Preparation | 1 | MHVAC | E000 | 00E1 | E000#lHzj00E1
793 | 793 | 793 | 793 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Technical Submittal for HVAC DDC Control Panel Submission | 2 | MHVAC | E000 | 00E2 | E000#lHzj00E2
794 | 794 | 794 | 794 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Technical Submittal for HVAC DDC Control Panel Review / Evaluation | 3 | MHVAC | E000 | 00E3 | E000#lHzj00E3
795 | 795 | 795 | 795 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Technical Submittal for HVAC DDC Control Panel Approval with Comments | 4 | MHVAC | E000 | 00E4 | E000#lHzj00E4
796 | 796 | 796 | 796 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Technical Submittal for HVAC DDC Control Panel FINAL Approval | 5 | MHVAC | E000 | 00E5 | E000#lHzj00E5
797 | 797 | 797 | 797 | SA24M005 | Material Submittal for HVAC Installation Material |  | 6 | -1 | 0 |  |  | X | E000#lHzj
798 | 798 | 798 | 798 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Material Submittal for HVAC Installation Material Drafting / Preparation | 1 | MHVAC | E000 | 00E1 | E000#NExf00E1
799 | 799 | 799 | 799 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Material Submittal for HVAC Installation Material Submission | 2 | MHVAC | E000 | 00E2 | E000#NExf00E2
800 | 800 | 800 | 800 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Material Submittal for HVAC Installation Material Review / Evaluation | 3 | MHVAC | E000 | 00E3 | E000#NExf00E3
801 | 801 | 801 | 801 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Material Submittal for HVAC Installation Material Approval with Comments | 4 | MHVAC | E000 | 00E4 | E000#NExf00E4
802 | 802 | 802 | 802 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Material Submittal for HVAC Installation Material FINAL Approval | 5 | MHVAC | E000 | 00E5 | E000#NExf00E5
803 | 803 | 803 | 803 | SA24M005 | Technical Submittal for Ventilation Fans Material (Smoke Purge & Exhaust) |  | 6 | -1 | 0 |  |  | X | E000#NExf
804 | 804 | 804 | 804 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Technical Submittal for Ventilation Fans Material (Smoke Purge & Exhaust) Drafting / Preparation | 1 | TVENT | E000 | 00E1 | E000TVENT00E1
805 | 805 | 805 | 805 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Technical Submittal for Ventilation Fans Material (Smoke Purge & Exhaust) Submission | 2 | TVENT | E000 | 00E2 | E000TVENT00E2
806 | 806 | 806 | 806 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Technical Submittal for Ventilation Fans Material (Smoke Purge & Exhaust) Review / Evaluation | 3 | TVENT | E000 | 00E3 | E000TVENT00E3
807 | 807 | 807 | 807 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Technical Submittal for Ventilation Fans Material (Smoke Purge & Exhaust) Approval with Comments | 4 | TVENT | E000 | 00E4 | E000TVENT00E4
808 | 808 | 808 | 808 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Technical Submittal for Ventilation Fans Material (Smoke Purge & Exhaust) FINAL Approval | 5 | TVENT | E000 | 00E5 | E000TVENT00E5
809 | 809 | 809 | 809 | SA24M005 | Material Submittal for Electric Duct Heaters |  | 6 | -1 | 0 |  |  | X
810 | 810 | 810 | 810 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Material Submittal for Electric Duct Heaters Drafting / Preparation | 1 | E0EHD | E000 | 00E1 | E000E0EHD00E1
811 | 811 | 811 | 811 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Material Submittal for Electric Duct Heaters Submission | 2 | E0EHD | E000 | 00E2 | E000E0EHD00E2
812 | 812 | 812 | 812 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Material Submittal for Electric Duct Heaters Review / Evaluation | 3 | E0EHD | E000 | 00E3 | E000E0EHD00E3
813 | 813 | 813 | 813 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Material Submittal for Electric Duct Heaters Approval with Comments | 4 | E0EHD | E000 | 00E4 | E000E0EHD00E4
814 | 814 | 814 | 814 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Material Submittal for Electric Duct Heaters FINAL Approval | 5 | E0EHD | E000 | 00E5 | E000E0EHD00E5
815 | 815 | 815 | 815 | SA24M005 | Plumbing Bulk Materials |  | 6 | -1 | 0 |  |  | X
816 | 816 | 816 | 816 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Plumbing Bulk Materials Drafting / Preparation | 1 | PLUMB | E000 | 00E1 | E000#fZmf00E1
817 | 817 | 817 | 817 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Plumbing Bulk Materials Submission | 2 | PLUMB | E000 | 00E2 | E000#fZmf00E2
818 | 818 | 818 | 818 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Plumbing Bulk Materials Review / Evaluation | 3 | PLUMB | E000 | 00E3 | E000#fZmf00E3
819 | 819 | 819 | 819 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Plumbing Bulk Materials Approval with Comments | 4 | PLUMB | E000 | 00E4 | E000#fZmf00E4
820 | 820 | 820 | 820 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Plumbing Bulk Materials FINAL Approval | 5 | PLUMB | E000 | 00E5 | E000#fZmf00E5
821 | 821 | 821 | 821 | SA24M005 | Material Submittal for Toilet Fixture & Accessories Including Electrical Water Heater |  | 6 | -1 | 0 |  |  | X | E000#fZmf
822 | 822 | 822 | 822 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Material Submittal for Toilet Fixture & Accessories Including Electrical Water Heater Drafting / Preparation | 1 | 0TOFR | E000 | 00E1 | E0000TOFR00E1
823 | 823 | 823 | 823 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Material Submittal for Toilet Fixture & Accessories Including Electrical Water Heater Submission | 2 | 0TOFR | E000 | 00E2 | E0000TOFR00E2
824 | 824 | 824 | 824 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Material Submittal for Toilet Fixture & Accessories Including Electrical Water Heater Review / Evaluation | 3 | 0TOFR | E000 | 00E3 | E0000TOFR00E3
825 | 825 | 825 | 825 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Material Submittal for Toilet Fixture & Accessories Including Electrical Water Heater Approval with Comments | 4 | 0TOFR | E000 | 00E4 | E0000TOFR00E4
826 | 826 | 826 | 826 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Material Submittal for Toilet Fixture & Accessories Including Electrical Water Heater FINAL Approval | 5 | 0TOFR | E000 | 00E5 | E0000TOFR00E5
827 | 827 | 827 | 827 | SA24M005 | Imported Materials Submission for Fire Alarm System (FACP, Detectors and Devices,LIMs, Strobes, Alar |  | 6 | -1 | 0 |  |  | X
828 | 828 | 828 | 828 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Imported Materials Submission for Fire Alarm System (FACP, Detectors and Devices,LIMs, Strobes, Alar Drafting / Preparation | 1 | F0FAS | E000 | 00E1 | E000#YoFV00E1
829 | 829 | 829 | 829 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Imported Materials Submission for Fire Alarm System (FACP, Detectors and Devices,LIMs, Strobes, Alar Submission | 2 | F0FAS | E000 | 00E2 | E000#YoFV00E2
830 | 830 | 830 | 830 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Imported Materials Submission for Fire Alarm System (FACP, Detectors and Devices,LIMs, Strobes, Alar Review / Evaluation | 3 | F0FAS | E000 | 00E3 | E000#YoFV00E3
831 | 831 | 831 | 831 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Imported Materials Submission for Fire Alarm System (FACP, Detectors and Devices,LIMs, Strobes, Alar Approval with Comments | 4 | F0FAS | E000 | 00E4 | E000#YoFV00E4
832 | 832 | 832 | 832 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Imported Materials Submission for Fire Alarm System (FACP, Detectors and Devices,LIMs, Strobes, Alar FINAL Approval | 5 | F0FAS | E000 | 00E5 | E000#YoFV00E5
833 | 833 | 833 | 833 | SA24M005 | Imported Materials for Fire Suppression System (Novec Cylinders, Nitrogen Cylinders, Manifolds, Sole |  | 6 | -1 | 0 |  |  | X | E000#YoFV
834 | 834 | 834 | 834 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Imported Materials for Fire Suppression System (Novec Cylinders, Nitrogen Cylinders, Manifolds, Sole Drafting / Preparation | 1 | F0FSS | E000 | 00E1 | E000#KDLT00E1
835 | 835 | 835 | 835 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Imported Materials for Fire Suppression System (Novec Cylinders, Nitrogen Cylinders, Manifolds, Sole Submission | 2 | F0FSS | E000 | 00E2 | E000#KDLT00E2
836 | 836 | 836 | 836 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Imported Materials for Fire Suppression System (Novec Cylinders, Nitrogen Cylinders, Manifolds, Sole Review / Evaluation | 3 | F0FSS | E000 | 00E3 | E000#KDLT00E3
837 | 837 | 837 | 837 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Imported Materials for Fire Suppression System (Novec Cylinders, Nitrogen Cylinders, Manifolds, Sole Approval with Comments | 4 | F0FSS | E000 | 00E4 | E000#KDLT00E4
838 | 838 | 838 | 838 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Imported Materials for Fire Suppression System (Novec Cylinders, Nitrogen Cylinders, Manifolds, Sole FINAL Approval | 5 | F0FSS | E000 | 00E5 | E000#KDLT00E5
839 | 839 | 839 | 839 | SA24M005 | Local Materials for Fire Alarm System (Conduits, Wires, Junction Boxes, PVC Coated RGS Conduits) |  | 6 | -1 | 0 |  |  | X | E000#KDLT
840 | 840 | 840 | 840 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Local Materials for Fire Alarm System (Conduits, Wires, Junction Boxes, PVC Coated RGS Conduits) Drafting / Preparation | 1 | #zMYi | E000 | 00E1 | E000#zMYi00E1
841 | 841 | 841 | 841 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Local Materials for Fire Alarm System (Conduits, Wires, Junction Boxes, PVC Coated RGS Conduits) Submission | 2 | #zMYi | E000 | 00E2 | E000#zMYi00E2
842 | 842 | 842 | 842 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Local Materials for Fire Alarm System (Conduits, Wires, Junction Boxes, PVC Coated RGS Conduits) Review / Evaluation | 3 | #zMYi | E000 | 00E3 | E000#zMYi00E3
843 | 843 | 843 | 843 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Local Materials for Fire Alarm System (Conduits, Wires, Junction Boxes, PVC Coated RGS Conduits) Approval with Comments | 4 | #zMYi | E000 | 00E4 | E000#zMYi00E4
844 | 844 | 844 | 844 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Local Materials for Fire Alarm System (Conduits, Wires, Junction Boxes, PVC Coated RGS Conduits) FINAL Approval | 5 | #zMYi | E000 | 00E5 | E000#zMYi00E5
845 | 845 | 845 | 845 | SA24M005 | Local Materials for Fire Signaling System (Metallic Pipes, Supports, Hardware Items, SS Tubing) |  | 6 | -1 | 0 |  |  | X
846 | 846 | 846 | 846 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Local Materials for Fire Signaling System (Metallic Pipes, Supports, Hardware Items, SS Tubing) Drafting / Preparation | 1 | #HuJK | E000 | 00E1 | E000#HuJK00E1
847 | 847 | 847 | 847 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Local Materials for Fire Signaling System (Metallic Pipes, Supports, Hardware Items, SS Tubing) Submission | 2 | #HuJK | E000 | 00E2 | E000#HuJK00E2
848 | 848 | 848 | 848 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Local Materials for Fire Signaling System (Metallic Pipes, Supports, Hardware Items, SS Tubing) Review / Evaluation | 3 | #HuJK | E000 | 00E3 | E000#HuJK00E3
849 | 849 | 849 | 849 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Local Materials for Fire Signaling System (Metallic Pipes, Supports, Hardware Items, SS Tubing) Approval with Comments | 4 | #HuJK | E000 | 00E4 | E000#HuJK00E4
850 | 850 | 850 | 850 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Local Materials for Fire Signaling System (Metallic Pipes, Supports, Hardware Items, SS Tubing) FINAL Approval | 5 | #HuJK | E000 | 00E5 | E000#HuJK00E5
851 | 851 | 851 | 851 | SA24M005 | Materials Submission for Fire Extinguishers. |  | 6 | -1 | 0 |  |  | X
852 | 852 | 852 | 852 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Materials Submission for Fire Extinguishers. Drafting / Preparation | 1 | #xiwB | E000 | 00E1 | E000#xiwB00E1
853 | 853 | 853 | 853 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Materials Submission for Fire Extinguishers. Submission | 2 | #xiwB | E000 | 00E2 | E000#xiwB00E2
854 | 854 | 854 | 854 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Materials Submission for Fire Extinguishers. Review / Evaluation | 3 | #xiwB | E000 | 00E3 | E000#xiwB00E3
855 | 855 | 855 | 855 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Materials Submission for Fire Extinguishers. Approval with Comments | 4 | #xiwB | E000 | 00E4 | E000#xiwB00E4
856 | 856 | 856 | 856 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Mechanical Materials Submission for Fire Extinguishers. FINAL Approval | 5 | #xiwB | E000 | 00E5 | E000#xiwB00E5
857 | 857 | 857 | 857 | SA24M005 | Protection |  | 5 | -1 | 0 |  |  | X
858 | 858 | 858 | 858 | SA24M005 | Relay Setting Calculations along with all equipment related data Transformer data (turns, impedances |  | 6 | -1 | 0 |  |  | X
859 | 859 | 859 | 859 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Protection Relay Setting Calculations along with all equipment related data Transformer data (turns, impedances Drafting / Preparation | 1 | ## Transformer Relay Setting Calculations ### TRF | E000 | 00E1 | E000TRF00E1
860 | 860 | 860 | 860 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Protection Relay Setting Calculations along with all equipment related data Transformer data (turns, impedances Submission | 2 | ## Transformer Relay Setting Calculations ### TRF | E000 | 00E2 | E000TRF00E2
861 | 861 | 861 | 861 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Protection Relay Setting Calculations along with all equipment related data Transformer data (turns, impedances Review / Evaluation | 3 | ## Transformer Relay Setting Calculations ### TRF | E000 | 00E3 | E000TRF00E3
862 | 862 | 862 | 862 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Protection Relay Setting Calculations along with all equipment related data Transformer data (turns, impedances Approval with Comments | 4 | ## Transformer Relay Setting Calculations ### TRF | E000 | 00E4 | E000TRF00E4
863 | 863 | 863 | 863 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Protection Relay Setting Calculations along with all equipment related data Transformer data (turns, impedances FINAL Approval | 5 | ## Transformer Relay Setting Calculations ### TRF | E000 | 00E5 | E000TRF00E5
864 | 864 | 864 | 864 | SA24M005 | CT Calculations to support Burden Rating and Knee Point Voltage/Characteristics |  | 6 | -1 | 0 |  |  | X
865 | 865 | 865 | 865 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Protection CT Calculations to support Burden Rating and Knee Point Voltage/Characteristics Drafting / Preparation | 1 | CTCALC | E000 | 00E1 | E000CTCALC00E1
866 | 866 | 866 | 866 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Protection CT Calculations to support Burden Rating and Knee Point Voltage/Characteristics Submission | 2 | CTCALC | E000 | 00E2 | E000CTCALC00E2
867 | 867 | 867 | 867 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Protection CT Calculations to support Burden Rating and Knee Point Voltage/Characteristics Review / Evaluation | 3 | CTCALC | E000 | 00E3 | E000CTCALC00E3
868 | 868 | 868 | 868 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Protection CT Calculations to support Burden Rating and Knee Point Voltage/Characteristics Approval with Comments | 4 | CTCALC | E000 | 00E4 | E000CTCALC00E4
869 | 869 | 869 | 869 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Protection CT Calculations to support Burden Rating and Knee Point Voltage/Characteristics FINAL Approval | 5 | CTCALC | E000 | 00E5 | E000CTCALC00E5
870 | 870 | 870 | 870 | SA24M005 | VT Calculations to support Burden Rating |  | 6 | -1 | 0 |  |  | X
871 | 871 | 871 | 871 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Protection VT Calculations to support Burden Rating Drafting / Preparation | 1 | PVTC | E000 | 00E1 | E000PVTC00E1
872 | 872 | 872 | 872 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Protection VT Calculations to support Burden Rating Submission | 2 | PVTC | E000 | 00E2 | E000PVTC00E2
873 | 873 | 873 | 873 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Protection VT Calculations to support Burden Rating Review / Evaluation | 3 | PVTC | E000 | 00E3 | E000PVTC00E3
874 | 874 | 874 | 874 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Protection VT Calculations to support Burden Rating Approval with Comments | 4 | PVTC | E000 | 00E4 | E000PVTC00E4
875 | 875 | 875 | 875 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Protection VT Calculations to support Burden Rating FINAL Approval | 5 | PVTC | E000 | 00E5 | E000PVTC00E5
876 | 876 | 876 | 876 | SA24M005 | Relay Application and Relay Setting Calculations |  | 6 | -1 | 0 |  |  | X
877 | 877 | 877 | 877 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Protection Relay Application and Relay Setting Calculations Drafting / Preparation | 1 | PRARSC | E000 | 00E1 | E000PRARSC00E1
878 | 878 | 878 | 878 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Protection Relay Application and Relay Setting Calculations Submission | 2 | PRARSC | E000 | 00E2 | E000PRARSC00E2
879 | 879 | 879 | 879 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Protection Relay Application and Relay Setting Calculations Review / Evaluation | 3 | PRARSC | E000 | 00E3 | E000PRARSC00E3
880 | 880 | 880 | 880 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Protection Relay Application and Relay Setting Calculations Approval with Comments | 4 | PRARSC | E000 | 00E4 | E000PRARSC00E4
881 | 881 | 881 | 881 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Protection Relay Application and Relay Setting Calculations FINAL Approval | 5 | PRARSC | E000 | 00E5 | E000PRARSC00E5
882 | 882 | 882 | 882 | SA24M005 | MCCB Setting (AC / DC) |  | 6 | -1 | 0 |  |  | X
883 | 883 | 883 | 883 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Protection MCCB Setting (AC / DC) Drafting / Preparation | 1 | MCCB | E000 | 00E1 | E000MCCB00E1
884 | 884 | 884 | 884 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Protection MCCB Setting (AC / DC) Submission | 2 | MCCB | E000 | 00E2 | E000MCCB00E2
885 | 885 | 885 | 885 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Protection MCCB Setting (AC / DC) Review / Evaluation | 3 | MCCB | E000 | 00E3 | E000MCCB00E3
886 | 886 | 886 | 886 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Protection MCCB Setting (AC / DC) Approval with Comments | 4 | MCCB | E000 | 00E4 | E000MCCB00E4
887 | 887 | 887 | 887 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Protection MCCB Setting (AC / DC) FINAL Approval | 5 | MCCB | E000 | 00E5 | E000MCCB00E5
888 | 888 | 888 | 888 | SA24M005 | SAS |  | 5 | -1 | 0 |  |  | X
889 | 889 | 889 | 889 | SA24M005 | SCADA Drawing Standard Symbols |  | 6 | -1 | 0 |  |  | X
890 | 890 | 890 | 890 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SCADA Drawing Standard Symbols Drafting / Preparation | 1 | SCADA | E000 | 00E1 | E000#PJoZ00E1
891 | 891 | 891 | 891 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SCADA Drawing Standard Symbols Submission | 2 | SCADA | E000 | 00E2 | E000#PJoZ00E2
892 | 892 | 892 | 892 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SCADA Drawing Standard Symbols Review / Evaluation | 3 | SCADA | E000 | 00E3 | E000#PJoZ00E3
893 | 893 | 893 | 893 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SCADA Drawing Standard Symbols Approval with Comments | 4 | SCADA | E000 | 00E4 | E000#PJoZ00E4
894 | 894 | 894 | 894 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SCADA Drawing Standard Symbols FINAL Approval | 5 | SCADA | E000 | 00E5 | E000#PJoZ00E5
895 | 895 | 895 | 895 | SA24M005 | SAS (REFERENCE DESIGN PACKAGE FOR FAT WITNESSING INSPECTORS) |  | 6 | -1 | 0 |  |  | X | E000#PJoZ
896 | 896 | 896 | 896 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SAS (REFERENCE DESIGN PACKAGE FOR FAT WITNESSING INSPECTORS) Drafting / Preparation | 1 | 0SAS | E000 | 00E1 | E000#DtML00E1
897 | 897 | 897 | 897 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SAS (REFERENCE DESIGN PACKAGE FOR FAT WITNESSING INSPECTORS) Submission | 2 | 0SAS | E000 | 00E2 | E000#DtML00E2
898 | 898 | 898 | 898 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SAS (REFERENCE DESIGN PACKAGE FOR FAT WITNESSING INSPECTORS) Review / Evaluation | 3 | 0SAS | E000 | 00E3 | E000#DtML00E3
899 | 899 | 899 | 899 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SAS (REFERENCE DESIGN PACKAGE FOR FAT WITNESSING INSPECTORS) Approval with Comments | 4 | 0SAS | E000 | 00E4 | E000#DtML00E4
900 | 900 | 900 | 900 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SAS (REFERENCE DESIGN PACKAGE FOR FAT WITNESSING INSPECTORS) FINAL Approval | 5 | 0SAS | E000 | 00E5 | E000#DtML00E5
901 | 901 | 901 | 901 | SA24M005 | FOC, CABINETS AND ACCESSORIES FOR SAS SYSTEM |  | 6 | -1 | 0 |  |  | X | E000#DtML
902 | 902 | 902 | 902 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS FOC, CABINETS AND ACCESSORIES FOR SAS SYSTEM Drafting / Preparation | 1 | FSAS | E000 | 00E1 | E000#TmrQ00E1
903 | 903 | 903 | 903 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS FOC, CABINETS AND ACCESSORIES FOR SAS SYSTEM Submission | 2 | FSAS | E000 | 00E2 | E000#TmrQ00E2
904 | 904 | 904 | 904 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS FOC, CABINETS AND ACCESSORIES FOR SAS SYSTEM Review / Evaluation | 3 | FSAS | E000 | 00E3 | E000#TmrQ00E3
905 | 905 | 905 | 905 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS FOC, CABINETS AND ACCESSORIES FOR SAS SYSTEM Approval with Comments | 4 | FSAS | E000 | 00E4 | E000#TmrQ00E4
906 | 906 | 906 | 906 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS FOC, CABINETS AND ACCESSORIES FOR SAS SYSTEM FINAL Approval | 5 | FSAS | E000 | 00E5 | E000#TmrQ00E5
907 | 907 | 907 | 907 | SA24M005 | SAS Integration/Interfacing with power generation plant |  | 6 | -1 | 0 |  |  | X | E000#TmrQ
908 | 908 | 908 | 908 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SAS Integration/Interfacing with power generation plant Drafting / Preparation | 1 | PSAS | E000 | 00E1 | E000#bZWD00E1
909 | 909 | 909 | 909 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SAS Integration/Interfacing with power generation plant Submission | 2 | PSAS | E000 | 00E2 | E000#bZWD00E2
910 | 910 | 910 | 910 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SAS Integration/Interfacing with power generation plant Review / Evaluation | 3 | PSAS | E000 | 00E3 | E000#bZWD00E3
911 | 911 | 911 | 911 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SAS Integration/Interfacing with power generation plant Approval with Comments | 4 | PSAS | E000 | 00E4 | E000#bZWD00E4
912 | 912 | 912 | 912 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SAS Integration/Interfacing with power generation plant FINAL Approval | 5 | PSAS | E000 | 00E5 | E000#bZWD00E5
913 | 913 | 913 | 913 | SA24M005 | SAS MODIFICATION/EXPANSION DESIGN PACKAGE |  | 6 | -1 | 0 |  |  | X | E000#bZWD
914 | 914 | 914 | 914 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SAS MODIFICATION/EXPANSION DESIGN PACKAGE Drafting / Preparation | 1 | 0SASM | E000 | 00E1 | E0000SASM00E1
915 | 915 | 915 | 915 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SAS MODIFICATION/EXPANSION DESIGN PACKAGE Submission | 2 | 0SASM | E000 | 00E2 | E0000SASM00E2
916 | 916 | 916 | 916 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SAS MODIFICATION/EXPANSION DESIGN PACKAGE Review / Evaluation | 3 | 0SASM | E000 | 00E3 | E0000SASM00E3
917 | 917 | 917 | 917 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SAS MODIFICATION/EXPANSION DESIGN PACKAGE Approval with Comments | 4 | 0SASM | E000 | 00E4 | E0000SASM00E4
918 | 918 | 918 | 918 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SAS MODIFICATION/EXPANSION DESIGN PACKAGE FINAL Approval | 5 | 0SASM | E000 | 00E5 | E0000SASM00E5
919 | 919 | 919 | 919 | SA24M005 | SCADA Integration/Interfacing with power generation plant |  | 6 | -1 | 0 |  |  | X
920 | 920 | 920 | 920 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SCADA Integration/Interfacing with power generation plant Drafting / Preparation | 1 | SCADA | E000 | 00E1 | E000#roPP00E1
921 | 921 | 921 | 921 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SCADA Integration/Interfacing with power generation plant Submission | 2 | SCADA | E000 | 00E2 | E000#roPP00E2
922 | 922 | 922 | 922 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SCADA Integration/Interfacing with power generation plant Review / Evaluation | 3 | SCADA | E000 | 00E3 | E000#roPP00E3
923 | 923 | 923 | 923 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SCADA Integration/Interfacing with power generation plant Approval with Comments | 4 | SCADA | E000 | 00E4 | E000#roPP00E4
924 | 924 | 924 | 924 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SCADA Integration/Interfacing with power generation plant FINAL Approval | 5 | SCADA | E000 | 00E5 | E000#roPP00E5
925 | 925 | 925 | 925 | SA24M005 | SAS/SOE/ TRF/ DRF Annunciation Point List |  | 6 | -1 | 0 |  |  | X | E000#roPP
926 | 926 | 926 | 926 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SAS/SOE/ TRF/ DRF Annunciation Point List Drafting / Preparation | 1 | SASOAP | E000 | 00E1 | E000SASOAP00E1
927 | 927 | 927 | 927 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SAS/SOE/ TRF/ DRF Annunciation Point List Submission | 2 | SASOAP | E000 | 00E2 | E000SASOAP00E2
928 | 928 | 928 | 928 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SAS/SOE/ TRF/ DRF Annunciation Point List Review / Evaluation | 3 | SASOAP | E000 | 00E3 | E000SASOAP00E3
929 | 929 | 929 | 929 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SAS/SOE/ TRF/ DRF Annunciation Point List Approval with Comments | 4 | SASOAP | E000 | 00E4 | E000SASOAP00E4
930 | 930 | 930 | 930 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SAS/SOE/ TRF/ DRF Annunciation Point List FINAL Approval | 5 | SASOAP | E000 | 00E5 | E000SASOAP00E5
931 | 931 | 931 | 931 | SA24M005 | NEW DSM DESIGN PACKAGE |  | 6 | -1 | 0 |  |  | X
932 | 932 | 932 | 932 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS NEW DSM DESIGN PACKAGE Drafting / Preparation | 1 | NSDSM | E000 | 00E1 | E000#nORL00E1
933 | 933 | 933 | 933 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS NEW DSM DESIGN PACKAGE Submission | 2 | NSDSM | E000 | 00E2 | E000#nORL00E2
934 | 934 | 934 | 934 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS NEW DSM DESIGN PACKAGE Review / Evaluation | 3 | NSDSM | E000 | 00E3 | E000#nORL00E3
935 | 935 | 935 | 935 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS NEW DSM DESIGN PACKAGE Approval with Comments | 4 | NSDSM | E000 | 00E4 | E000#nORL00E4
936 | 936 | 936 | 936 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS NEW DSM DESIGN PACKAGE FINAL Approval | 5 | NSDSM | E000 | 00E5 | E000#nORL00E5
937 | 937 | 937 | 937 | SA24M005 | SCADA / SAS Single Line Diagram |  | 6 | -1 | 0 |  |  | X | E000#nORL
938 | 938 | 938 | 938 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SCADA / SAS Single Line Diagram Drafting / Preparation | 1 | SCADA | E000 | 00E1 | E000#tPMk00E1
939 | 939 | 939 | 939 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SCADA / SAS Single Line Diagram Submission | 2 | SCADA | E000 | 00E2 | E000#tPMk00E2
940 | 940 | 940 | 940 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SCADA / SAS Single Line Diagram Review / Evaluation | 3 | SCADA | E000 | 00E3 | E000#tPMk00E3
941 | 941 | 941 | 941 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SCADA / SAS Single Line Diagram Approval with Comments | 4 | SCADA | E000 | 00E4 | E000#tPMk00E4
942 | 942 | 942 | 942 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SCADA / SAS Single Line Diagram FINAL Approval | 5 | SCADA | E000 | 00E5 | E000#tPMk00E5
943 | 943 | 943 | 943 | SA24M005 | SCADA / SAS Interconnecting Diagram Status |  | 6 | -1 | 0 |  |  | X | E000#tPMk
944 | 944 | 944 | 944 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SCADA / SAS Interconnecting Diagram Status Drafting / Preparation | 1 | SCADA | E000 | 00E1 | E000#VbNX00E1
945 | 945 | 945 | 945 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SCADA / SAS Interconnecting Diagram Status Submission | 2 | SCADA | E000 | 00E2 | E000#VbNX00E2
946 | 946 | 946 | 946 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SCADA / SAS Interconnecting Diagram Status Review / Evaluation | 3 | SCADA | E000 | 00E3 | E000#VbNX00E3
947 | 947 | 947 | 947 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SCADA / SAS Interconnecting Diagram Status Approval with Comments | 4 | SCADA | E000 | 00E4 | E000#VbNX00E4
948 | 948 | 948 | 948 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SCADA / SAS Interconnecting Diagram Status FINAL Approval | 5 | SCADA | E000 | 00E5 | E000#VbNX00E5
949 | 949 | 949 | 949 | SA24M005 | SCADA / SAS Interconnecting Diagram Control |  | 6 | -1 | 0 |  |  | X | E000#VbNX
950 | 950 | 950 | 950 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SCADA / SAS Interconnecting Diagram Control Drafting / Preparation | 1 | SCADA / SAS | E000 | 00E1 | E000#TAnf00E1
951 | 951 | 951 | 951 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SCADA / SAS Interconnecting Diagram Control Submission | 2 | SCADA / SAS | E000 | 00E2 | E000#TAnf00E2
952 | 952 | 952 | 952 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SCADA / SAS Interconnecting Diagram Control Review / Evaluation | 3 | SCADA / SAS | E000 | 00E3 | E000#TAnf00E3
953 | 953 | 953 | 953 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SCADA / SAS Interconnecting Diagram Control Approval with Comments | 4 | SCADA / SAS | E000 | 00E4 | E000#TAnf00E4
954 | 954 | 954 | 954 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SCADA / SAS Interconnecting Diagram Control FINAL Approval | 5 | SCADA / SAS | E000 | 00E5 | E000#TAnf00E5
955 | 955 | 955 | 955 | SA24M005 | SCADA / SAS Interconnecting Diagram Analog |  | 6 | -1 | 0 |  |  | X | E000#TAnf
956 | 956 | 956 | 956 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SCADA / SAS Interconnecting Diagram Analog Drafting / Preparation | 1 | SCADA / SAS | E000 | 00E1 | E000#MTWj00E1
957 | 957 | 957 | 957 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SCADA / SAS Interconnecting Diagram Analog Submission | 2 | SCADA / SAS | E000 | 00E2 | E000#MTWj00E2
958 | 958 | 958 | 958 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SCADA / SAS Interconnecting Diagram Analog Review / Evaluation | 3 | SCADA / SAS | E000 | 00E3 | E000#MTWj00E3
959 | 959 | 959 | 959 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SCADA / SAS Interconnecting Diagram Analog Approval with Comments | 4 | SCADA / SAS | E000 | 00E4 | E000#MTWj00E4
960 | 960 | 960 | 960 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III SAS SCADA / SAS Interconnecting Diagram Analog FINAL Approval | 5 | SCADA / SAS | E000 | 00E5 | E000#MTWj00E5
961 | 961 | 961 | 961 | SA24M005 | Telecom |  | 5 | -1 | 0 |  |  | X | E000#MTWj
962 | 962 | 962 | 962 | SA24M005 | MPLS-TP |  | 6 | -1 | 0 |  |  | X | E000#MTWj
963 | 963 | 963 | 963 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom MPLS-TP Drafting / Preparation | 1 | MPLS-TP | E000 | 00E1 | E000#fYpj00E1
964 | 964 | 964 | 964 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom MPLS-TP Submission | 2 | MPLS-TP | E000 | 00E2 | E000#fYpj00E2
965 | 965 | 965 | 965 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom MPLS-TP Review / Evaluation | 3 | MPLS-TP | E000 | 00E3 | E000#fYpj00E3
966 | 966 | 966 | 966 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom MPLS-TP Approval with Comments | 4 | MPLS-TP | E000 | 00E4 | E000#fYpj00E4
967 | 967 | 967 | 967 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom MPLS-TP FINAL Approval | 5 | MPLS-TP | E000 | 00E5 | E000#fYpj00E5
968 | 968 | 968 | 968 | SA24M005 | RFTS |  | 6 | -1 | 0 |  |  | X | E000#fYpj
969 | 969 | 969 | 969 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom RFTS Drafting / Preparation | 1 | RFTS | E000 | 00E1 | E000RFTS00E1
970 | 970 | 970 | 970 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom RFTS Submission | 2 | RFTS | E000 | 00E2 | E000RFTS00E2
971 | 971 | 971 | 971 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom RFTS Review / Evaluation | 3 | RFTS | E000 | 00E3 | E000RFTS00E3
972 | 972 | 972 | 972 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom RFTS Approval with Comments | 4 | RFTS | E000 | 00E4 | E000RFTS00E4
973 | 973 | 973 | 973 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom RFTS FINAL Approval | 5 | RFTS | E000 | 00E5 | E000RFTS00E5
974 | 974 | 974 | 974 | SA24M005 | DXC & DVM FIBER OPTIC COMMUNICATION SYSTEM EQUIPMENT |  | 6 | -1 | 0 |  |  | X
975 | 975 | 975 | 975 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom DXC & DVM FIBER OPTIC COMMUNICATION SYSTEM EQUIPMENT Drafting / Preparation | 1 | TDXC | E000 | 00E1 | E000#osnv00E1
976 | 976 | 976 | 976 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom DXC & DVM FIBER OPTIC COMMUNICATION SYSTEM EQUIPMENT Submission | 2 | TDXC | E000 | 00E2 | E000#osnv00E2
977 | 977 | 977 | 977 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom DXC & DVM FIBER OPTIC COMMUNICATION SYSTEM EQUIPMENT Review / Evaluation | 3 | TDXC | E000 | 00E3 | E000#osnv00E3
978 | 978 | 978 | 978 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom DXC & DVM FIBER OPTIC COMMUNICATION SYSTEM EQUIPMENT Approval with Comments | 4 | TDXC | E000 | 00E4 | E000#osnv00E4
979 | 979 | 979 | 979 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom DXC & DVM FIBER OPTIC COMMUNICATION SYSTEM EQUIPMENT FINAL Approval | 5 | TDXC | E000 | 00E5 | E000#osnv00E5
980 | 980 | 980 | 980 | SA24M005 | COMMUNICATION ROOM EQUIPMENT LAYOUT AND FLOOR PLAN |  | 6 | -1 | 0 |  |  | X | E000#osnv
981 | 981 | 981 | 981 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom COMMUNICATION ROOM EQUIPMENT LAYOUT AND FLOOR PLAN Drafting / Preparation | 1 | TCRE | E000 | 00E1 | E000TCRE00E1
982 | 982 | 982 | 982 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom COMMUNICATION ROOM EQUIPMENT LAYOUT AND FLOOR PLAN Submission | 2 | TCRE | E000 | 00E2 | E000TCRE00E2
983 | 983 | 983 | 983 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom COMMUNICATION ROOM EQUIPMENT LAYOUT AND FLOOR PLAN Review / Evaluation | 3 | TCRE | E000 | 00E3 | E000TCRE00E3
984 | 984 | 984 | 984 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom COMMUNICATION ROOM EQUIPMENT LAYOUT AND FLOOR PLAN Approval with Comments | 4 | TCRE | E000 | 00E4 | E000TCRE00E4
985 | 985 | 985 | 985 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom COMMUNICATION ROOM EQUIPMENT LAYOUT AND FLOOR PLAN FINAL Approval | 5 | TCRE | E000 | 00E5 | E000TCRE00E5
986 | 986 | 986 | 986 | SA24M005 | COMMUNICATION ROOM CABLE RACEWAY ARRANGEMENT |  | 6 | -1 | 0 |  |  | X
987 | 987 | 987 | 987 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom COMMUNICATION ROOM CABLE RACEWAY ARRANGEMENT Drafting / Preparation | 1 | TC0CR | E000 | 00E1 | E000TC0CR00E1
988 | 988 | 988 | 988 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom COMMUNICATION ROOM CABLE RACEWAY ARRANGEMENT Submission | 2 | TC0CR | E000 | 00E2 | E000TC0CR00E2
989 | 989 | 989 | 989 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom COMMUNICATION ROOM CABLE RACEWAY ARRANGEMENT Review / Evaluation | 3 | TC0CR | E000 | 00E3 | E000TC0CR00E3
990 | 990 | 990 | 990 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom COMMUNICATION ROOM CABLE RACEWAY ARRANGEMENT Approval with Comments | 4 | TC0CR | E000 | 00E4 | E000TC0CR00E4
991 | 991 | 991 | 991 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom COMMUNICATION ROOM CABLE RACEWAY ARRANGEMENT FINAL Approval | 5 | TC0CR | E000 | 00E5 | E000TC0CR00E5
992 | 992 | 992 | 992 | SA24M005 | COMMUNICATION-GRADE DC POWER SYSTEM AND GROUNDING SYSTEM |  | 6 | -1 | 0 |  |  | X
993 | 993 | 993 | 993 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom COMMUNICATION-GRADE DC POWER SYSTEM AND GROUNDING SYSTEM Drafting / Preparation | 1 | COMMDC | E000 | 00E1 | E000#hPjS00E1
994 | 994 | 994 | 994 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom COMMUNICATION-GRADE DC POWER SYSTEM AND GROUNDING SYSTEM Submission | 2 | COMMDC | E000 | 00E2 | E000#hPjS00E2
995 | 995 | 995 | 995 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom COMMUNICATION-GRADE DC POWER SYSTEM AND GROUNDING SYSTEM Review / Evaluation | 3 | COMMDC | E000 | 00E3 | E000#hPjS00E3
996 | 996 | 996 | 996 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom COMMUNICATION-GRADE DC POWER SYSTEM AND GROUNDING SYSTEM Approval with Comments | 4 | COMMDC | E000 | 00E4 | E000#hPjS00E4
997 | 997 | 997 | 997 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom COMMUNICATION-GRADE DC POWER SYSTEM AND GROUNDING SYSTEM FINAL Approval | 5 | COMMDC | E000 | 00E5 | E000#hPjS00E5
998 | 998 | 998 | 998 | SA24M005 | FIBER OPTIC CABLE SLEEVES OPENING LAYOUT & ROUTE |  | 6 | -1 | 0 |  |  | X | E000#hPjS
999 | 999 | 999 | 999 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom FIBER OPTIC CABLE SLEEVES OPENING LAYOUT & ROUTE Drafting / Preparation | 1 | F0CBS | E000 | 00E1 | E000F0CBS00E1
1000 | 1000 | 1000 | 1000 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom FIBER OPTIC CABLE SLEEVES OPENING LAYOUT & ROUTE Submission | 2 | F0CBS | E000 | 00E2 | E000F0CBS00E2
1001 | 1001 | 1001 | 1001 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom FIBER OPTIC CABLE SLEEVES OPENING LAYOUT & ROUTE Review / Evaluation | 3 | F0CBS | E000 | 00E3 | E000F0CBS00E3
1002 | 1002 | 1002 | 1002 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom FIBER OPTIC CABLE SLEEVES OPENING LAYOUT & ROUTE Approval with Comments | 4 | F0CBS | E000 | 00E4 | E000F0CBS00E4
1003 | 1003 | 1003 | 1003 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom FIBER OPTIC CABLE SLEEVES OPENING LAYOUT & ROUTE FINAL Approval | 5 | F0CBS | E000 | 00E5 | E000F0CBS00E5
1004 | 1004 | 1004 | 1004 | SA24M005 | FIBER OPTIC ROUTE PLAN |  | 6 | -1 | 0 |  |  | X
1005 | 1005 | 1005 | 1005 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom FIBER OPTIC ROUTE PLAN Drafting / Preparation | 1 | F00RP | E000 | 00E1 | E000F00RP00E1
1006 | 1006 | 1006 | 1006 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom FIBER OPTIC ROUTE PLAN Submission | 2 | F00RP | E000 | 00E2 | E000F00RP00E2
1007 | 1007 | 1007 | 1007 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom FIBER OPTIC ROUTE PLAN Review / Evaluation | 3 | F00RP | E000 | 00E3 | E000F00RP00E3
1008 | 1008 | 1008 | 1008 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom FIBER OPTIC ROUTE PLAN Approval with Comments | 4 | F00RP | E000 | 00E4 | E000F00RP00E4
1009 | 1009 | 1009 | 1009 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom FIBER OPTIC ROUTE PLAN FINAL Approval | 5 | F00RP | E000 | 00E5 | E000F00RP00E5
1010 | 1010 | 1010 | 1010 | SA24M005 | AMI (COMMUNICATION PORTION ONLY) |  | 6 | -1 | 0 |  |  | X
1011 | 1011 | 1011 | 1011 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom AMI (COMMUNICATION PORTION ONLY) Drafting / Preparation | 1 | TAMI | E000 | 00E1 | E000#ULOj00E1
1012 | 1012 | 1012 | 1012 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom AMI (COMMUNICATION PORTION ONLY) Submission | 2 | TAMI | E000 | 00E2 | E000#ULOj00E2
1013 | 1013 | 1013 | 1013 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom AMI (COMMUNICATION PORTION ONLY) Review / Evaluation | 3 | TAMI | E000 | 00E3 | E000#ULOj00E3
1014 | 1014 | 1014 | 1014 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom AMI (COMMUNICATION PORTION ONLY) Approval with Comments | 4 | TAMI | E000 | 00E4 | E000#ULOj00E4
1015 | 1015 | 1015 | 1015 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom AMI (COMMUNICATION PORTION ONLY) FINAL Approval | 5 | TAMI | E000 | 00E5 | E000#ULOj00E5
1016 | 1016 | 1016 | 1016 | SA24M005 | 48V DC BATTERY CHARGER AND BATTERY BANK FOR COMMUNICATION-sizing calculations |  | 6 | -1 | 0 |  |  | X | E000#ULOj
1017 | 1017 | 1017 | 1017 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom 48V DC BATTERY CHARGER AND BATTERY BANK FOR COMMUNICATION-sizing calculations Drafting / Preparation | 1 | 4BATC | E000 | 00E1 | E0004BATC00E1
1018 | 1018 | 1018 | 1018 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom 48V DC BATTERY CHARGER AND BATTERY BANK FOR COMMUNICATION-sizing calculations Submission | 2 | 4BATC | E000 | 00E2 | E0004BATC00E2
1019 | 1019 | 1019 | 1019 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom 48V DC BATTERY CHARGER AND BATTERY BANK FOR COMMUNICATION-sizing calculations Review / Evaluation | 3 | 4BATC | E000 | 00E3 | E0004BATC00E3
1020 | 1020 | 1020 | 1020 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom 48V DC BATTERY CHARGER AND BATTERY BANK FOR COMMUNICATION-sizing calculations Approval with Comments | 4 | 4BATC | E000 | 00E4 | E0004BATC00E4
1021 | 1021 | 1021 | 1021 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom 48V DC BATTERY CHARGER AND BATTERY BANK FOR COMMUNICATION-sizing calculations FINAL Approval | 5 | 4BATC | E000 | 00E5 | E0004BATC00E5
1022 | 1022 | 1022 | 1022 | SA24M005 | PABX/IP TELEPHONY SYSTEM |  | 6 | -1 | 0 |  |  | X
1023 | 1023 | 1023 | 1023 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom PABX/IP TELEPHONY SYSTEM Drafting / Preparation | 1 | PTPBX | E000 | 00E1 | E000#dFgA00E1
1024 | 1024 | 1024 | 1024 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom PABX/IP TELEPHONY SYSTEM Submission | 2 | PTPBX | E000 | 00E2 | E000#dFgA00E2
1025 | 1025 | 1025 | 1025 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom PABX/IP TELEPHONY SYSTEM Review / Evaluation | 3 | PTPBX | E000 | 00E3 | E000#dFgA00E3
1026 | 1026 | 1026 | 1026 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom PABX/IP TELEPHONY SYSTEM Approval with Comments | 4 | PTPBX | E000 | 00E4 | E000#dFgA00E4
1027 | 1027 | 1027 | 1027 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom PABX/IP TELEPHONY SYSTEM FINAL Approval | 5 | PTPBX | E000 | 00E5 | E000#dFgA00E5
1028 | 1028 | 1028 | 1028 | SA24M005 | LAN/WAN SYSTEM |  | 6 | -1 | 0 |  |  | X | E000#dFgA
1029 | 1029 | 1029 | 1029 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom LAN/WAN SYSTEM Drafting / Preparation | 1 | TLANW | E000 | 00E1 | E000#WEZI00E1
1030 | 1030 | 1030 | 1030 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom LAN/WAN SYSTEM Submission | 2 | TLANW | E000 | 00E2 | E000#WEZI00E2
1031 | 1031 | 1031 | 1031 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom LAN/WAN SYSTEM Review / Evaluation | 3 | TLANW | E000 | 00E3 | E000#WEZI00E3
1032 | 1032 | 1032 | 1032 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom LAN/WAN SYSTEM Approval with Comments | 4 | TLANW | E000 | 00E4 | E000#WEZI00E4
1033 | 1033 | 1033 | 1033 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom LAN/WAN SYSTEM FINAL Approval | 5 | TLANW | E000 | 00E5 | E000#WEZI00E5
1034 | 1034 | 1034 | 1034 | SA24M005 | PROTECTION SIGNALING EQUIPMENT (PSE) |  | 6 | -1 | 0 |  |  | X | E000#WEZI
1035 | 1035 | 1035 | 1035 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom PROTECTION SIGNALING EQUIPMENT (PSE) Drafting / Preparation | 1 | PTSE | E000 | 00E1 | E000#gsLy00E1
1036 | 1036 | 1036 | 1036 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom PROTECTION SIGNALING EQUIPMENT (PSE) Submission | 2 | PTSE | E000 | 00E2 | E000#gsLy00E2
1037 | 1037 | 1037 | 1037 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom PROTECTION SIGNALING EQUIPMENT (PSE) Review / Evaluation | 3 | PTSE | E000 | 00E3 | E000#gsLy00E3
1038 | 1038 | 1038 | 1038 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom PROTECTION SIGNALING EQUIPMENT (PSE) Approval with Comments | 4 | PTSE | E000 | 00E4 | E000#gsLy00E4
1039 | 1039 | 1039 | 1039 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom PROTECTION SIGNALING EQUIPMENT (PSE) FINAL Approval | 5 | PTSE | E000 | 00E5 | E000#gsLy00E5
1040 | 1040 | 1040 | 1040 | SA24M005 | PDS SYSTEM OSP/ISP |  | 6 | -1 | 0 |  |  | X | E000#gsLy
1041 | 1041 | 1041 | 1041 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom PDS SYSTEM OSP/ISP Drafting / Preparation | 1 | PDSYS | E000 | 00E1 | E000PDSYS00E1
1042 | 1042 | 1042 | 1042 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom PDS SYSTEM OSP/ISP Submission | 2 | PDSYS | E000 | 00E2 | E000PDSYS00E2
1043 | 1043 | 1043 | 1043 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom PDS SYSTEM OSP/ISP Review / Evaluation | 3 | PDSYS | E000 | 00E3 | E000PDSYS00E3
1044 | 1044 | 1044 | 1044 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom PDS SYSTEM OSP/ISP Approval with Comments | 4 | PDSYS | E000 | 00E4 | E000PDSYS00E4
1045 | 1045 | 1045 | 1045 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom PDS SYSTEM OSP/ISP FINAL Approval | 5 | PDSYS | E000 | 00E5 | E000PDSYS00E5
1046 | 1046 | 1046 | 1046 | SA24M005 | TELECOM CABINET/DATA CABINET/OFMR/MDF |  | 6 | -1 | 0 |  |  | X
1047 | 1047 | 1047 | 1047 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom TELECOM CABINET/DATA CABINET/OFMR/MDF Drafting / Preparation | 1 | TCAB | E000 | 00E1 | E000#hdPi00E1
1048 | 1048 | 1048 | 1048 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom TELECOM CABINET/DATA CABINET/OFMR/MDF Submission | 2 | TCAB | E000 | 00E2 | E000#hdPi00E2
1049 | 1049 | 1049 | 1049 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom TELECOM CABINET/DATA CABINET/OFMR/MDF Review / Evaluation | 3 | TCAB | E000 | 00E3 | E000#hdPi00E3
1050 | 1050 | 1050 | 1050 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom TELECOM CABINET/DATA CABINET/OFMR/MDF Approval with Comments | 4 | TCAB | E000 | 00E4 | E000#hdPi00E4
1051 | 1051 | 1051 | 1051 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom TELECOM CABINET/DATA CABINET/OFMR/MDF FINAL Approval | 5 | TCAB | E000 | 00E5 | E000#hdPi00E5
1052 | 1052 | 1052 | 1052 | SA24M005 | COMMUNICATION (DUCT BANK / MANHOLE / HANDHOLE / CONDUIT) LAYOUT PLAN & Sections |  | 6 | -1 | 0 |  |  | X | E000#hdPi
1053 | 1053 | 1053 | 1053 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom COMMUNICATION (DUCT BANK / MANHOLE / HANDHOLE / CONDUIT) LAYOUT PLAN & Sections Drafting / Preparation | 1 | CTDBM | E000 | 00E1 | E000CTDBM00E1
1054 | 1054 | 1054 | 1054 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom COMMUNICATION (DUCT BANK / MANHOLE / HANDHOLE / CONDUIT) LAYOUT PLAN & Sections Submission | 2 | CTDBM | E000 | 00E2 | E000CTDBM00E2
1055 | 1055 | 1055 | 1055 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom COMMUNICATION (DUCT BANK / MANHOLE / HANDHOLE / CONDUIT) LAYOUT PLAN & Sections Review / Evaluation | 3 | CTDBM | E000 | 00E3 | E000CTDBM00E3
1056 | 1056 | 1056 | 1056 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom COMMUNICATION (DUCT BANK / MANHOLE / HANDHOLE / CONDUIT) LAYOUT PLAN & Sections Approval with Comments | 4 | CTDBM | E000 | 00E4 | E000CTDBM00E4
1057 | 1057 | 1057 | 1057 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom COMMUNICATION (DUCT BANK / MANHOLE / HANDHOLE / CONDUIT) LAYOUT PLAN & Sections FINAL Approval | 5 | CTDBM | E000 | 00E5 | E000CTDBM00E5
1058 | 1058 | 1058 | 1058 | SA24M005 | SPLICE CLOSURE/JOINT BOX |  | 6 | -1 | 0 |  |  | X
1059 | 1059 | 1059 | 1059 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom SPLICE CLOSURE/JOINT BOX Drafting / Preparation | 1 | SPLICEBX | E000 | 00E1 | E000SPLICEBX00E1
1060 | 1060 | 1060 | 1060 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom SPLICE CLOSURE/JOINT BOX Submission | 2 | SPLICEBX | E000 | 00E2 | E000SPLICEBX00E2
1061 | 1061 | 1061 | 1061 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom SPLICE CLOSURE/JOINT BOX Review / Evaluation | 3 | SPLICEBX | E000 | 00E3 | E000SPLICEBX00E3
1062 | 1062 | 1062 | 1062 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom SPLICE CLOSURE/JOINT BOX Approval with Comments | 4 | SPLICEBX | E000 | 00E4 | E000SPLICEBX00E4
1063 | 1063 | 1063 | 1063 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- III Telecom SPLICE CLOSURE/JOINT BOX FINAL Approval | 5 | SPLICEBX | E000 | 00E5 | E000SPLICEBX00E5
1064 | 1064 | 1064 | 1064 | SA24M005 | Phase- IV |  | 4 | -1 | 0 |  |  | X
1065 | 1065 | 1065 | 1065 | SA24M005 | Electrical |  | 5 | -1 | 0 |  |  | X
1066 | 1066 | 1066 | 1066 | SA24M005 | Single Building HV Substation- Electrical Equipment Layout plan & section |  | 6 | -1 | 0 |  |  | X
1067 | 1067 | 1067 | 1067 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Single Building HV Substation- Electrical Equipment Layout plan & section Drafting / Preparation | 1 | E0SBH | E000 | 00E1 | E000#bLMz00E1
1068 | 1068 | 1068 | 1068 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Single Building HV Substation- Electrical Equipment Layout plan & section Submission | 2 | E0SBH | E000 | 00E2 | E000#bLMz00E2
1069 | 1069 | 1069 | 1069 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Single Building HV Substation- Electrical Equipment Layout plan & section Review / Evaluation | 3 | E0SBH | E000 | 00E3 | E000#bLMz00E3
1070 | 1070 | 1070 | 1070 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Single Building HV Substation- Electrical Equipment Layout plan & section Approval with Comments | 4 | E0SBH | E000 | 00E4 | E000#bLMz00E4
1071 | 1071 | 1071 | 1071 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Single Building HV Substation- Electrical Equipment Layout plan & section FINAL Approval | 5 | E0SBH | E000 | 00E5 | E000#bLMz00E5
1072 | 1072 | 1072 | 1072 | SA24M005 | Single Building HV Substation- LV Power & Control Cable Schedule |  | 6 | -1 | 0 |  |  | X | E000#bLMz
1073 | 1073 | 1073 | 1073 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Single Building HV Substation- LV Power & Control Cable Schedule Drafting / Preparation | 1 | E0SBH | E000 | 00E1 | E000#jDHG00E1
1074 | 1074 | 1074 | 1074 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Single Building HV Substation- LV Power & Control Cable Schedule Submission | 2 | E0SBH | E000 | 00E2 | E000#jDHG00E2
1075 | 1075 | 1075 | 1075 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Single Building HV Substation- LV Power & Control Cable Schedule Review / Evaluation | 3 | E0SBH | E000 | 00E3 | E000#jDHG00E3
1076 | 1076 | 1076 | 1076 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Single Building HV Substation- LV Power & Control Cable Schedule Approval with Comments | 4 | E0SBH | E000 | 00E4 | E000#jDHG00E4
1077 | 1077 | 1077 | 1077 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Single Building HV Substation- LV Power & Control Cable Schedule FINAL Approval | 5 | E0SBH | E000 | 00E5 | E000#jDHG00E5
1078 | 1078 | 1078 | 1078 | SA24M005 | Single Building HV Substation- Wall Opening , Floor Cutout , Basement wall opening , cable sleeves & |  | 6 | -1 | 0 |  |  | X | E000#jDHG
1079 | 1079 | 1079 | 1079 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Single Building HV Substation- Wall Opening , Floor Cutout , Basement wall opening , cable sleeves & Drafting / Preparation | 1 | E0SBH | E000 | 00E1 | E000#bram00E1
1080 | 1080 | 1080 | 1080 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Single Building HV Substation- Wall Opening , Floor Cutout , Basement wall opening , cable sleeves & Submission | 2 | E0SBH | E000 | 00E2 | E000#bram00E2
1081 | 1081 | 1081 | 1081 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Single Building HV Substation- Wall Opening , Floor Cutout , Basement wall opening , cable sleeves & Review / Evaluation | 3 | E0SBH | E000 | 00E3 | E000#bram00E3
1082 | 1082 | 1082 | 1082 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Single Building HV Substation- Wall Opening , Floor Cutout , Basement wall opening , cable sleeves & Approval with Comments | 4 | E0SBH | E000 | 00E4 | E000#bram00E4
1083 | 1083 | 1083 | 1083 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Single Building HV Substation- Wall Opening , Floor Cutout , Basement wall opening , cable sleeves & FINAL Approval | 5 | E0SBH | E000 | 00E5 | E000#bram00E5
1084 | 1084 | 1084 | 1084 | SA24M005 | Single Building HV Substation- Power Cables Race Way -Cabling Plan, Section & Details |  | 6 | -1 | 0 |  |  | X | E000#bram
1085 | 1085 | 1085 | 1085 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Single Building HV Substation- Power Cables Race Way -Cabling Plan, Section & Details Drafting / Preparation | 1 | E0SBH | E000 | 00E1 | E000#ptdP00E1
1086 | 1086 | 1086 | 1086 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Single Building HV Substation- Power Cables Race Way -Cabling Plan, Section & Details Submission | 2 | E0SBH | E000 | 00E2 | E000#ptdP00E2
1087 | 1087 | 1087 | 1087 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Single Building HV Substation- Power Cables Race Way -Cabling Plan, Section & Details Review / Evaluation | 3 | E0SBH | E000 | 00E3 | E000#ptdP00E3
1088 | 1088 | 1088 | 1088 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Single Building HV Substation- Power Cables Race Way -Cabling Plan, Section & Details Approval with Comments | 4 | E0SBH | E000 | 00E4 | E000#ptdP00E4
1089 | 1089 | 1089 | 1089 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Single Building HV Substation- Power Cables Race Way -Cabling Plan, Section & Details FINAL Approval | 5 | E0SBH | E000 | 00E5 | E000#ptdP00E5
1090 | 1090 | 1090 | 1090 | SA24M005 | Single Building HV Substation- Control Cables Race Way -Cabling Plan, Section & Details |  | 6 | -1 | 0 |  |  | X | E000#ptdP
1091 | 1091 | 1091 | 1091 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Single Building HV Substation- Control Cables Race Way -Cabling Plan, Section & Details Drafting / Preparation | 1 | E0SBH | E000 | 00E1 | E000#dins00E1
1092 | 1092 | 1092 | 1092 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Single Building HV Substation- Control Cables Race Way -Cabling Plan, Section & Details Submission | 2 | E0SBH | E000 | 00E2 | E000#dins00E2
1093 | 1093 | 1093 | 1093 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Single Building HV Substation- Control Cables Race Way -Cabling Plan, Section & Details Review / Evaluation | 3 | E0SBH | E000 | 00E3 | E000#dins00E3
1094 | 1094 | 1094 | 1094 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Single Building HV Substation- Control Cables Race Way -Cabling Plan, Section & Details Approval with Comments | 4 | E0SBH | E000 | 00E4 | E000#dins00E4
1095 | 1095 | 1095 | 1095 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Single Building HV Substation- Control Cables Race Way -Cabling Plan, Section & Details FINAL Approval | 5 | E0SBH | E000 | 00E5 | E000#dins00E5
1096 | 1096 | 1096 | 1096 | SA24M005 | Single Building HV Substation- Indoor Auxiliary Power Layout and Details |  | 6 | -1 | 0 |  |  | X | E000#dins
1097 | 1097 | 1097 | 1097 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Single Building HV Substation- Indoor Auxiliary Power Layout and Details Drafting / Preparation | 1 | E0SBH | E000 | 00E1 | E000#Wvlb00E1
1098 | 1098 | 1098 | 1098 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Single Building HV Substation- Indoor Auxiliary Power Layout and Details Submission | 2 | E0SBH | E000 | 00E2 | E000#Wvlb00E2
1099 | 1099 | 1099 | 1099 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Single Building HV Substation- Indoor Auxiliary Power Layout and Details Review / Evaluation | 3 | E0SBH | E000 | 00E3 | E000#Wvlb00E3
1100 | 1100 | 1100 | 1100 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Single Building HV Substation- Indoor Auxiliary Power Layout and Details Approval with Comments | 4 | E0SBH | E000 | 00E4 | E000#Wvlb00E4
1101 | 1101 | 1101 | 1101 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Single Building HV Substation- Indoor Auxiliary Power Layout and Details FINAL Approval | 5 | E0SBH | E000 | 00E5 | E000#Wvlb00E5
1102 | 1102 | 1102 | 1102 | SA24M005 | Control Room /building- Equipment Layout Plan & Sections for Control Building (Aux Room, Battery Roo |  | 6 | -1 | 0 |  |  | X | E000#Wvlb
1103 | 1103 | 1103 | 1103 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Control Room /building- Equipment Layout Plan & Sections for Control Building (Aux Room, Battery Roo Drafting / Preparation | 1 | E0CRB | E000 | 00E1 | E000#gslS00E1
1104 | 1104 | 1104 | 1104 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Control Room /building- Equipment Layout Plan & Sections for Control Building (Aux Room, Battery Roo Submission | 2 | E0CRB | E000 | 00E2 | E000#gslS00E2
1105 | 1105 | 1105 | 1105 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Control Room /building- Equipment Layout Plan & Sections for Control Building (Aux Room, Battery Roo Review / Evaluation | 3 | E0CRB | E000 | 00E3 | E000#gslS00E3
1106 | 1106 | 1106 | 1106 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Control Room /building- Equipment Layout Plan & Sections for Control Building (Aux Room, Battery Roo Approval with Comments | 4 | E0CRB | E000 | 00E4 | E000#gslS00E4
1107 | 1107 | 1107 | 1107 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Control Room /building- Equipment Layout Plan & Sections for Control Building (Aux Room, Battery Roo FINAL Approval | 5 | E0CRB | E000 | 00E5 | E000#gslS00E5
1108 | 1108 | 1108 | 1108 | SA24M005 | Control Room /building- LV Power & Control Cable Schedule |  | 6 | -1 | 0 |  |  | X | E000#gslS
1109 | 1109 | 1109 | 1109 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Control Room /building- LV Power & Control Cable Schedule Drafting / Preparation | 1 | E0CRB | E000 | 00E1 | E000#sScH00E1
1110 | 1110 | 1110 | 1110 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Control Room /building- LV Power & Control Cable Schedule Submission | 2 | E0CRB | E000 | 00E2 | E000#sScH00E2
1111 | 1111 | 1111 | 1111 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Control Room /building- LV Power & Control Cable Schedule Review / Evaluation | 3 | E0CRB | E000 | 00E3 | E000#sScH00E3
1112 | 1112 | 1112 | 1112 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Control Room /building- LV Power & Control Cable Schedule Approval with Comments | 4 | E0CRB | E000 | 00E4 | E000#sScH00E4
1113 | 1113 | 1113 | 1113 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Control Room /building- LV Power & Control Cable Schedule FINAL Approval | 5 | E0CRB | E000 | 00E5 | E000#sScH00E5
1114 | 1114 | 1114 | 1114 | SA24M005 | LV Power & Control Cable Race Way Routing Layout Plan and Section for Control Building |  | 6 | -1 | 0 |  |  | X | E000#sScH
1115 | 1115 | 1115 | 1115 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical LV Power & Control Cable Race Way Routing Layout Plan and Section for Control Building Drafting / Preparation | 1 | E0LVC | E000 | 00E1 | E000#TmRv00E1
1116 | 1116 | 1116 | 1116 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical LV Power & Control Cable Race Way Routing Layout Plan and Section for Control Building Submission | 2 | E0LVC | E000 | 00E2 | E000#TmRv00E2
1117 | 1117 | 1117 | 1117 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical LV Power & Control Cable Race Way Routing Layout Plan and Section for Control Building Review / Evaluation | 3 | E0LVC | E000 | 00E3 | E000#TmRv00E3
1118 | 1118 | 1118 | 1118 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical LV Power & Control Cable Race Way Routing Layout Plan and Section for Control Building Approval with Comments | 4 | E0LVC | E000 | 00E4 | E000#TmRv00E4
1119 | 1119 | 1119 | 1119 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical LV Power & Control Cable Race Way Routing Layout Plan and Section for Control Building FINAL Approval | 5 | E0LVC | E000 | 00E5 | E000#TmRv00E5
1120 | 1120 | 1120 | 1120 | SA24M005 | Wall Opening , Floor Cutout , cable sleeves & Rooftop Layout Details - Control Building |  | 6 | -1 | 0 |  |  | X | E000#TmRv
1121 | 1121 | 1121 | 1121 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Wall Opening , Floor Cutout , cable sleeves & Rooftop Layout Details - Control Building Drafting / Preparation | 1 | EWOFC | E000 | 00E1 | E000EWOFC00E1
1122 | 1122 | 1122 | 1122 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Wall Opening , Floor Cutout , cable sleeves & Rooftop Layout Details - Control Building Submission | 2 | EWOFC | E000 | 00E2 | E000EWOFC00E2
1123 | 1123 | 1123 | 1123 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Wall Opening , Floor Cutout , cable sleeves & Rooftop Layout Details - Control Building Review / Evaluation | 3 | EWOFC | E000 | 00E3 | E000EWOFC00E3
1124 | 1124 | 1124 | 1124 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Wall Opening , Floor Cutout , cable sleeves & Rooftop Layout Details - Control Building Approval with Comments | 4 | EWOFC | E000 | 00E4 | E000EWOFC00E4
1125 | 1125 | 1125 | 1125 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Wall Opening , Floor Cutout , cable sleeves & Rooftop Layout Details - Control Building FINAL Approval | 5 | EWOFC | E000 | 00E5 | E000EWOFC00E5
1126 | 1126 | 1126 | 1126 | SA24M005 | Reinforcement Grounding for Control Building |  | 6 | -1 | 0 |  |  | X
1127 | 1127 | 1127 | 1127 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Reinforcement Grounding for Control Building Drafting / Preparation | 1 | E0GRC | E000 | 00E1 | E000E0GRC00E1
1128 | 1128 | 1128 | 1128 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Reinforcement Grounding for Control Building Submission | 2 | E0GRC | E000 | 00E2 | E000E0GRC00E2
1129 | 1129 | 1129 | 1129 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Reinforcement Grounding for Control Building Review / Evaluation | 3 | E0GRC | E000 | 00E3 | E000E0GRC00E3
1130 | 1130 | 1130 | 1130 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Reinforcement Grounding for Control Building Approval with Comments | 4 | E0GRC | E000 | 00E4 | E000E0GRC00E4
1131 | 1131 | 1131 | 1131 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Reinforcement Grounding for Control Building FINAL Approval | 5 | E0GRC | E000 | 00E5 | E000E0GRC00E5
1132 | 1132 | 1132 | 1132 | SA24M005 | Equipment Building Indoor Equipment Grounding Layout & Sections |  | 6 | -1 | 0 |  |  | X
1133 | 1133 | 1133 | 1133 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Equipment Building Indoor Equipment Grounding Layout & Sections Drafting / Preparation | 1 | EQB0E0GL | E000 | 00E1 | E000EQB0E0GL00E1
1134 | 1134 | 1134 | 1134 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Equipment Building Indoor Equipment Grounding Layout & Sections Submission | 2 | EQB0E0GL | E000 | 00E2 | E000EQB0E0GL00E2
1135 | 1135 | 1135 | 1135 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Equipment Building Indoor Equipment Grounding Layout & Sections Review / Evaluation | 3 | EQB0E0GL | E000 | 00E3 | E000EQB0E0GL00E3
1136 | 1136 | 1136 | 1136 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Equipment Building Indoor Equipment Grounding Layout & Sections Approval with Comments | 4 | EQB0E0GL | E000 | 00E4 | E000EQB0E0GL00E4
1137 | 1137 | 1137 | 1137 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Equipment Building Indoor Equipment Grounding Layout & Sections FINAL Approval | 5 | EQB0E0GL | E000 | 00E5 | E000EQB0E0GL00E5
1138 | 1138 | 1138 | 1138 | SA24M005 | Heat Dissipation Calculation for Control Building |  | 6 | -1 | 0 |  |  | X
1139 | 1139 | 1139 | 1139 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Heat Dissipation Calculation for Control Building Drafting / Preparation | 1 | EHCDB | E000 | 00E1 | E000EHCDB00E1
1140 | 1140 | 1140 | 1140 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Heat Dissipation Calculation for Control Building Submission | 2 | EHCDB | E000 | 00E2 | E000EHCDB00E2
1141 | 1141 | 1141 | 1141 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Heat Dissipation Calculation for Control Building Review / Evaluation | 3 | EHCDB | E000 | 00E3 | E000EHCDB00E3
1142 | 1142 | 1142 | 1142 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Heat Dissipation Calculation for Control Building Approval with Comments | 4 | EHCDB | E000 | 00E4 | E000EHCDB00E4
1143 | 1143 | 1143 | 1143 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Heat Dissipation Calculation for Control Building FINAL Approval | 5 | EHCDB | E000 | 00E5 | E000EHCDB00E5
1144 | 1144 | 1144 | 1144 | SA24M005 | LV Power & Control Cable Schedule |  | 6 | -1 | 0 |  |  | X
1145 | 1145 | 1145 | 1145 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical LV Power & Control Cable Schedule Drafting / Preparation | 1 | E0LVC | E000 | 00E1 | E000#ZoRW00E1
1146 | 1146 | 1146 | 1146 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical LV Power & Control Cable Schedule Submission | 2 | E0LVC | E000 | 00E2 | E000#ZoRW00E2
1147 | 1147 | 1147 | 1147 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical LV Power & Control Cable Schedule Review / Evaluation | 3 | E0LVC | E000 | 00E3 | E000#ZoRW00E3
1148 | 1148 | 1148 | 1148 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical LV Power & Control Cable Schedule Approval with Comments | 4 | E0LVC | E000 | 00E4 | E000#ZoRW00E4
1149 | 1149 | 1149 | 1149 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical LV Power & Control Cable Schedule FINAL Approval | 5 | E0LVC | E000 | 00E5 | E000#ZoRW00E5
1150 | 1150 | 1150 | 1150 | SA24M005 | Calculation of Cable tray Fill Ratio |  | 6 | -1 | 0 |  |  | X | E000#ZoRW
1151 | 1151 | 1151 | 1151 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Calculation of Cable tray Fill Ratio Drafting / Preparation | 1 | ECBLT | E000 | 00E1 | E000ECBLT00E1
1152 | 1152 | 1152 | 1152 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Calculation of Cable tray Fill Ratio Submission | 2 | ECBLT | E000 | 00E2 | E000ECBLT00E2
1153 | 1153 | 1153 | 1153 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Calculation of Cable tray Fill Ratio Review / Evaluation | 3 | ECBLT | E000 | 00E3 | E000ECBLT00E3
1154 | 1154 | 1154 | 1154 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Calculation of Cable tray Fill Ratio Approval with Comments | 4 | ECBLT | E000 | 00E4 | E000ECBLT00E4
1155 | 1155 | 1155 | 1155 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Calculation of Cable tray Fill Ratio FINAL Approval | 5 | ECBLT | E000 | 00E5 | E000ECBLT00E5
1156 | 1156 | 1156 | 1156 | SA24M005 | Technical Submittal for LV Power Cables |  | 6 | -1 | 0 |  |  | X
1157 | 1157 | 1157 | 1157 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Technical Submittal for LV Power Cables FINAL Approval | 1 | E0LVC | E000 | 00E1 | E000#Pvoj00E1
1158 | 1158 | 1158 | 1158 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Technical Submittal for LV Power Cables Drafting / Preparation | 2 | E0LVC | E000 | 00E2 | E000#Pvoj00E2
1159 | 1159 | 1159 | 1159 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Technical Submittal for LV Power Cables Submission | 3 | E0LVC | E000 | 00E3 | E000#Pvoj00E3
1160 | 1160 | 1160 | 1160 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Technical Submittal for LV Power Cables Review / Evaluation | 4 | E0LVC | E000 | 00E4 | E000#Pvoj00E4
1161 | 1161 | 1161 | 1161 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Technical Submittal for LV Power Cables Approval with Comments | 5 | E0LVC | E000 | 00E5 | E000#Pvoj00E5
1162 | 1162 | 1162 | 1162 | SA24M005 | Technical Submittal for LV Control Cables |  | 6 | -1 | 0 |  |  | X | E000#Pvoj
1163 | 1163 | 1163 | 1163 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Technical Submittal for LV Control Cables Drafting / Preparation | 1 | E0LVC | E000 | 00E1 | E000#LvAc00E1
1164 | 1164 | 1164 | 1164 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Technical Submittal for LV Control Cables Submission | 2 | E0LVC | E000 | 00E2 | E000#LvAc00E2
1165 | 1165 | 1165 | 1165 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Technical Submittal for LV Control Cables Review / Evaluation | 3 | E0LVC | E000 | 00E3 | E000#LvAc00E3
1166 | 1166 | 1166 | 1166 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Technical Submittal for LV Control Cables Approval with Comments | 4 | E0LVC | E000 | 00E4 | E000#LvAc00E4
1167 | 1167 | 1167 | 1167 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Technical Submittal for LV Control Cables FINAL Approval | 5 | E0LVC | E000 | 00E5 | E000#LvAc00E5
1168 | 1168 | 1168 | 1168 | SA24M005 | Technical Submittal for lighting wires |  | 6 | -1 | 0 |  |  | X | E000#LvAc
1169 | 1169 | 1169 | 1169 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Technical Submittal for lighting wires Drafting / Preparation | 1 | E0LGW | E000 | 00E1 | E000E0LGW00E1
1170 | 1170 | 1170 | 1170 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Technical Submittal for lighting wires Submission | 2 | E0LGW | E000 | 00E2 | E000E0LGW00E2
1171 | 1171 | 1171 | 1171 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Technical Submittal for lighting wires Review / Evaluation | 3 | E0LGW | E000 | 00E3 | E000E0LGW00E3
1172 | 1172 | 1172 | 1172 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Technical Submittal for lighting wires Approval with Comments | 4 | E0LGW | E000 | 00E4 | E000E0LGW00E4
1173 | 1173 | 1173 | 1173 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Technical Submittal for lighting wires FINAL Approval | 5 | E0LGW | E000 | 00E5 | E000E0LGW00E5
1174 | 1174 | 1174 | 1174 | SA24M005 | LV Power Cables Raceway Cabling Plan, Section And Details |  | 6 | -1 | 0 |  |  | X
1175 | 1175 | 1175 | 1175 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical LV Power Cables Raceway Cabling Plan, Section And Details Drafting / Preparation | 1 | LVPC | E000 | 00E1 | E000LVPC00E1
1176 | 1176 | 1176 | 1176 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical LV Power Cables Raceway Cabling Plan, Section And Details Submission | 2 | LVPC | E000 | 00E2 | E000LVPC00E2
1177 | 1177 | 1177 | 1177 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical LV Power Cables Raceway Cabling Plan, Section And Details Review / Evaluation | 3 | LVPC | E000 | 00E3 | E000LVPC00E3
1178 | 1178 | 1178 | 1178 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical LV Power Cables Raceway Cabling Plan, Section And Details Approval with Comments | 4 | LVPC | E000 | 00E4 | E000LVPC00E4
1179 | 1179 | 1179 | 1179 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical LV Power Cables Raceway Cabling Plan, Section And Details FINAL Approval | 5 | LVPC | E000 | 00E5 | E000LVPC00E5
1180 | 1180 | 1180 | 1180 | SA24M005 | Control Cables Raceway Cabling Plan, Section And Details |  | 6 | -1 | 0 |  |  | X
1181 | 1181 | 1181 | 1181 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Control Cables Raceway Cabling Plan, Section And Details Drafting / Preparation | 1 | E0CCR | E000 | 00E1 | E000E0CCR00E1
1182 | 1182 | 1182 | 1182 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Control Cables Raceway Cabling Plan, Section And Details Submission | 2 | E0CCR | E000 | 00E2 | E000E0CCR00E2
1183 | 1183 | 1183 | 1183 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Control Cables Raceway Cabling Plan, Section And Details Review / Evaluation | 3 | E0CCR | E000 | 00E3 | E000E0CCR00E3
1184 | 1184 | 1184 | 1184 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Control Cables Raceway Cabling Plan, Section And Details Approval with Comments | 4 | E0CCR | E000 | 00E4 | E000E0CCR00E4
1185 | 1185 | 1185 | 1185 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Control Cables Raceway Cabling Plan, Section And Details FINAL Approval | 5 | E0CCR | E000 | 00E5 | E000E0CCR00E5
1186 | 1186 | 1186 | 1186 | SA24M005 | Technical Submittal for Cable raceways (Ladders and Trays) for MV, LV & Control, Cables) |  | 6 | -1 | 0 |  |  | X
1187 | 1187 | 1187 | 1187 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Technical Submittal for Cable raceways (Ladders and Trays) for MV, LV & Control, Cables) Drafting / Preparation | 1 | ECRCW | E000 | 00E1 | E000ECRCW00E1
1188 | 1188 | 1188 | 1188 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Technical Submittal for Cable raceways (Ladders and Trays) for MV, LV & Control, Cables) Submission | 2 | ECRCW | E000 | 00E2 | E000ECRCW00E2
1189 | 1189 | 1189 | 1189 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Technical Submittal for Cable raceways (Ladders and Trays) for MV, LV & Control, Cables) Review / Evaluation | 3 | ECRCW | E000 | 00E3 | E000ECRCW00E3
1190 | 1190 | 1190 | 1190 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Technical Submittal for Cable raceways (Ladders and Trays) for MV, LV & Control, Cables) Approval with Comments | 4 | ECRCW | E000 | 00E4 | E000ECRCW00E4
1191 | 1191 | 1191 | 1191 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Technical Submittal for Cable raceways (Ladders and Trays) for MV, LV & Control, Cables) FINAL Approval | 5 | ECRCW | E000 | 00E5 | E000ECRCW00E5
1192 | 1192 | 1192 | 1192 | SA24M005 | Cable Tray System |  | 6 | -1 | 0 |  |  | X
1193 | 1193 | 1193 | 1193 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Cable Tray System Drafting / Preparation | 1 | E0CABT | E000 | 00E1 | E000E0CABT00E1
1194 | 1194 | 1194 | 1194 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Cable Tray System Submission | 2 | E0CABT | E000 | 00E2 | E000E0CABT00E2
1195 | 1195 | 1195 | 1195 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Cable Tray System Review / Evaluation | 3 | E0CABT | E000 | 00E3 | E000E0CABT00E3
1196 | 1196 | 1196 | 1196 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Cable Tray System Approval with Comments | 4 | E0CABT | E000 | 00E4 | E000E0CABT00E4
1197 | 1197 | 1197 | 1197 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Cable Tray System FINAL Approval | 5 | E0CABT | E000 | 00E5 | E000E0CABT00E5
1198 | 1198 | 1198 | 1198 | SA24M005 | MV Power Cable -Technical Submittal and Sizing Calculations |  | 6 | -1 | 0 |  |  | X
1199 | 1199 | 1199 | 1199 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical MV Power Cable -Technical Submittal and Sizing Calculations Drafting / Preparation | 1 | E0PMC | E000 | 00E1 | E000E0PMC00E1
1200 | 1200 | 1200 | 1200 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical MV Power Cable -Technical Submittal and Sizing Calculations Submission | 2 | E0PMC | E000 | 00E2 | E000E0PMC00E2
1201 | 1201 | 1201 | 1201 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical MV Power Cable -Technical Submittal and Sizing Calculations Review / Evaluation | 3 | E0PMC | E000 | 00E3 | E000E0PMC00E3
1202 | 1202 | 1202 | 1202 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical MV Power Cable -Technical Submittal and Sizing Calculations Approval with Comments | 4 | E0PMC | E000 | 00E4 | E000E0PMC00E4
1203 | 1203 | 1203 | 1203 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical MV Power Cable -Technical Submittal and Sizing Calculations FINAL Approval | 5 | E0PMC | E000 | 00E5 | E000E0PMC00E5
1204 | 1204 | 1204 | 1204 | SA24M005 | MV Power Cable -Design Documents / Drawings for Cable Sealing Ends & Termination kits |  | 6 | -1 | 0 |  |  | X
1205 | 1205 | 1205 | 1205 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical MV Power Cable -Design Documents / Drawings for Cable Sealing Ends & Termination kits Drafting / Preparation | 1 | E0POWC | E000 | 00E1 | E000#PsgT00E1
1206 | 1206 | 1206 | 1206 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical MV Power Cable -Design Documents / Drawings for Cable Sealing Ends & Termination kits Submission | 2 | E0POWC | E000 | 00E2 | E000#PsgT00E2
1207 | 1207 | 1207 | 1207 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical MV Power Cable -Design Documents / Drawings for Cable Sealing Ends & Termination kits Review / Evaluation | 3 | E0POWC | E000 | 00E3 | E000#PsgT00E3
1208 | 1208 | 1208 | 1208 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical MV Power Cable -Design Documents / Drawings for Cable Sealing Ends & Termination kits Approval with Comments | 4 | E0POWC | E000 | 00E4 | E000#PsgT00E4
1209 | 1209 | 1209 | 1209 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical MV Power Cable -Design Documents / Drawings for Cable Sealing Ends & Termination kits FINAL Approval | 5 | E0POWC | E000 | 00E5 | E000#PsgT00E5
1210 | 1210 | 1210 | 1210 | SA24M005 | Indoor , Outdoor , Power & Control cable tunnels , Basement & Yard Lighting Design calculations |  | 6 | -1 | 0 |  |  | X | E000#PsgT
1211 | 1211 | 1211 | 1211 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Indoor , Outdoor , Power & Control cable tunnels , Basement & Yard Lighting Design calculations Drafting / Preparation | 1 | #IPMk | E000 | 00E1 | E000#IPMk00E1
1212 | 1212 | 1212 | 1212 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Indoor , Outdoor , Power & Control cable tunnels , Basement & Yard Lighting Design calculations Submission | 2 | #IPMk | E000 | 00E2 | E000#IPMk00E2
1213 | 1213 | 1213 | 1213 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Indoor , Outdoor , Power & Control cable tunnels , Basement & Yard Lighting Design calculations Review / Evaluation | 3 | #IPMk | E000 | 00E3 | E000#IPMk00E3
1214 | 1214 | 1214 | 1214 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Indoor , Outdoor , Power & Control cable tunnels , Basement & Yard Lighting Design calculations Approval with Comments | 4 | #IPMk | E000 | 00E4 | E000#IPMk00E4
1215 | 1215 | 1215 | 1215 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Indoor , Outdoor , Power & Control cable tunnels , Basement & Yard Lighting Design calculations FINAL Approval | 5 | #IPMk | E000 | 00E5 | E000#IPMk00E5
1216 | 1216 | 1216 | 1216 | SA24M005 | AC and DC Lighting One Line Diagram |  | 6 | -1 | 0 |  |  | X
1217 | 1217 | 1217 | 1217 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical AC and DC Lighting One Line Diagram Drafting / Preparation | 1 | E0ACD | E000 | 00E1 | E000#bgTS00E1
1218 | 1218 | 1218 | 1218 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical AC and DC Lighting One Line Diagram Submission | 2 | E0ACD | E000 | 00E2 | E000#bgTS00E2
1219 | 1219 | 1219 | 1219 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical AC and DC Lighting One Line Diagram Review / Evaluation | 3 | E0ACD | E000 | 00E3 | E000#bgTS00E3
1220 | 1220 | 1220 | 1220 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical AC and DC Lighting One Line Diagram Approval with Comments | 4 | E0ACD | E000 | 00E4 | E000#bgTS00E4
1221 | 1221 | 1221 | 1221 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical AC and DC Lighting One Line Diagram FINAL Approval | 5 | E0ACD | E000 | 00E5 | E000#bgTS00E5
1222 | 1222 | 1222 | 1222 | SA24M005 | AC & DC Lighting CB & cable Sizing Calculations |  | 6 | -1 | 0 |  |  | X | E000#bgTS
1223 | 1223 | 1223 | 1223 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical AC & DC Lighting CB & cable Sizing Calculations Drafting / Preparation | 1 | EALCB | E000 | 00E1 | E000EALCB00E1
1224 | 1224 | 1224 | 1224 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical AC & DC Lighting CB & cable Sizing Calculations Submission | 2 | EALCB | E000 | 00E2 | E000EALCB00E2
1225 | 1225 | 1225 | 1225 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical AC & DC Lighting CB & cable Sizing Calculations Review / Evaluation | 3 | EALCB | E000 | 00E3 | E000EALCB00E3
1226 | 1226 | 1226 | 1226 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical AC & DC Lighting CB & cable Sizing Calculations Approval with Comments | 4 | EALCB | E000 | 00E4 | E000EALCB00E4
1227 | 1227 | 1227 | 1227 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical AC & DC Lighting CB & cable Sizing Calculations FINAL Approval | 5 | EALCB | E000 | 00E5 | E000EALCB00E5
1228 | 1228 | 1228 | 1228 | SA24M005 | AC , DC Panel board schedules and Control Circuit Diagram |  | 6 | -1 | 0 |  |  | X
1229 | 1229 | 1229 | 1229 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical AC , DC Panel board schedules and Control Circuit Diagram Drafting / Preparation | 1 | E0ACDC | E000 | 00E1 | E000E0ACDC00E1
1230 | 1230 | 1230 | 1230 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical AC , DC Panel board schedules and Control Circuit Diagram Submission | 2 | E0ACDC | E000 | 00E2 | E000E0ACDC00E2
1231 | 1231 | 1231 | 1231 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical AC , DC Panel board schedules and Control Circuit Diagram Review / Evaluation | 3 | E0ACDC | E000 | 00E3 | E000E0ACDC00E3
1232 | 1232 | 1232 | 1232 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical AC , DC Panel board schedules and Control Circuit Diagram Approval with Comments | 4 | E0ACDC | E000 | 00E4 | E000E0ACDC00E4
1233 | 1233 | 1233 | 1233 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical AC , DC Panel board schedules and Control Circuit Diagram FINAL Approval | 5 | E0ACDC | E000 | 00E5 | E000E0ACDC00E5
1234 | 1234 | 1234 | 1234 | SA24M005 | Indoor [GIS , Control,etc] rooms- Lighting & Receptacles Layout & Details |  | 6 | -1 | 0 |  |  | X
1235 | 1235 | 1235 | 1235 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Indoor [GIS , Control,etc] rooms- Lighting & Receptacles Layout & Details Drafting / Preparation | 1 | E0GIS | E000 | 00E1 | E000#vtYa00E1
1236 | 1236 | 1236 | 1236 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Indoor [GIS , Control,etc] rooms- Lighting & Receptacles Layout & Details Submission | 2 | E0GIS | E000 | 00E2 | E000#vtYa00E2
1237 | 1237 | 1237 | 1237 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Indoor [GIS , Control,etc] rooms- Lighting & Receptacles Layout & Details Review / Evaluation | 3 | E0GIS | E000 | 00E3 | E000#vtYa00E3
1238 | 1238 | 1238 | 1238 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Indoor [GIS , Control,etc] rooms- Lighting & Receptacles Layout & Details Approval with Comments | 4 | E0GIS | E000 | 00E4 | E000#vtYa00E4
1239 | 1239 | 1239 | 1239 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Indoor [GIS , Control,etc] rooms- Lighting & Receptacles Layout & Details FINAL Approval | 5 | E0GIS | E000 | 00E5 | E000#vtYa00E5
1240 | 1240 | 1240 | 1240 | SA24M005 | Outdoor Lighting/Power Layout & Details (including Power & Control cable tunnels, Security Lighting |  | 6 | -1 | 0 |  |  | X | E000#vtYa
1241 | 1241 | 1241 | 1241 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Outdoor Lighting/Power Layout & Details (including Power & Control cable tunnels, Security Lighting Drafting / Preparation | 1 | E0LGP | E000 | 00E1 | E000E0LGP00E1
1242 | 1242 | 1242 | 1242 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Outdoor Lighting/Power Layout & Details (including Power & Control cable tunnels, Security Lighting Submission | 2 | E0LGP | E000 | 00E2 | E000E0LGP00E2
1243 | 1243 | 1243 | 1243 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Outdoor Lighting/Power Layout & Details (including Power & Control cable tunnels, Security Lighting Review / Evaluation | 3 | E0LGP | E000 | 00E3 | E000E0LGP00E3
1244 | 1244 | 1244 | 1244 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Outdoor Lighting/Power Layout & Details (including Power & Control cable tunnels, Security Lighting Approval with Comments | 4 | E0LGP | E000 | 00E4 | E000E0LGP00E4
1245 | 1245 | 1245 | 1245 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Outdoor Lighting/Power Layout & Details (including Power & Control cable tunnels, Security Lighting FINAL Approval | 5 | E0LGP | E000 | 00E5 | E000E0LGP00E5
1246 | 1246 | 1246 | 1246 | SA24M005 | Lighting poles / Mast / Security lighting pole details |  | 6 | -1 | 0 |  |  | X
1247 | 1247 | 1247 | 1247 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Lighting poles / Mast / Security lighting pole details Drafting / Preparation | 1 | LGPM | E000 | 00E1 | E000LGPM00E1
1248 | 1248 | 1248 | 1248 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Lighting poles / Mast / Security lighting pole details Submission | 2 | LGPM | E000 | 00E2 | E000LGPM00E2
1249 | 1249 | 1249 | 1249 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Lighting poles / Mast / Security lighting pole details Review / Evaluation | 3 | LGPM | E000 | 00E3 | E000LGPM00E3
1250 | 1250 | 1250 | 1250 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Lighting poles / Mast / Security lighting pole details Approval with Comments | 4 | LGPM | E000 | 00E4 | E000LGPM00E4
1251 | 1251 | 1251 | 1251 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Lighting poles / Mast / Security lighting pole details FINAL Approval | 5 | LGPM | E000 | 00E5 | E000LGPM00E5
1252 | 1252 | 1252 | 1252 | SA24M005 | Technical submittal for Indoor & Outdoor Lighting Fixures |  | 6 | -1 | 0 |  |  | X
1253 | 1253 | 1253 | 1253 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Technical submittal for Indoor & Outdoor Lighting Fixures Drafting / Preparation | 1 | E0LGF | E000 | 00E1 | E000E0LGF00E1
1254 | 1254 | 1254 | 1254 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Technical submittal for Indoor & Outdoor Lighting Fixures Submission | 2 | E0LGF | E000 | 00E2 | E000E0LGF00E2
1255 | 1255 | 1255 | 1255 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Technical submittal for Indoor & Outdoor Lighting Fixures Review / Evaluation | 3 | E0LGF | E000 | 00E3 | E000E0LGF00E3
1256 | 1256 | 1256 | 1256 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Technical submittal for Indoor & Outdoor Lighting Fixures Approval with Comments | 4 | E0LGF | E000 | 00E4 | E000E0LGF00E4
1257 | 1257 | 1257 | 1257 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Technical submittal for Indoor & Outdoor Lighting Fixures FINAL Approval | 5 | E0LGF | E000 | 00E5 | E000E0LGF00E5
1258 | 1258 | 1258 | 1258 | SA24M005 | Industrial security system lighting layout |  | 6 | -1 | 0 |  |  | X
1259 | 1259 | 1259 | 1259 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Industrial security system lighting layout Drafting / Preparation | 1 | E0ISS | E000 | 00E1 | E000E0ISS00E1
1260 | 1260 | 1260 | 1260 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Industrial security system lighting layout Submission | 2 | E0ISS | E000 | 00E2 | E000E0ISS00E2
1261 | 1261 | 1261 | 1261 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Industrial security system lighting layout Review / Evaluation | 3 | E0ISS | E000 | 00E3 | E000E0ISS00E3
1262 | 1262 | 1262 | 1262 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Industrial security system lighting layout Approval with Comments | 4 | E0ISS | E000 | 00E4 | E000E0ISS00E4
1263 | 1263 | 1263 | 1263 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Industrial security system lighting layout FINAL Approval | 5 | E0ISS | E000 | 00E5 | E000E0ISS00E5
1264 | 1264 | 1264 | 1264 | SA24M005 | Receptacles Socket Layout (Outdoor Area) |  | 6 | -1 | 0 |  |  | X
1265 | 1265 | 1265 | 1265 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Receptacles Socket Layout (Outdoor Area) Drafting / Preparation | 1 | ERECP | E000 | 00E1 | E000ERECP00E1
1266 | 1266 | 1266 | 1266 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Receptacles Socket Layout (Outdoor Area) Submission | 2 | ERECP | E000 | 00E2 | E000ERECP00E2
1267 | 1267 | 1267 | 1267 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Receptacles Socket Layout (Outdoor Area) Review / Evaluation | 3 | ERECP | E000 | 00E3 | E000ERECP00E3
1268 | 1268 | 1268 | 1268 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Receptacles Socket Layout (Outdoor Area) Approval with Comments | 4 | ERECP | E000 | 00E4 | E000ERECP00E4
1269 | 1269 | 1269 | 1269 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Receptacles Socket Layout (Outdoor Area) FINAL Approval | 5 | ERECP | E000 | 00E5 | E000ERECP00E5
1270 | 1270 | 1270 | 1270 | SA24M005 | Technical Submittal of Power Receptacles, Push buttons and Switches |  | 6 | -1 | 0 |  |  | X
1271 | 1271 | 1271 | 1271 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Technical Submittal of Power Receptacles, Push buttons and Switches Drafting / Preparation | 1 | EPRPS | E000 | 00E1 | E000EPRPS00E1
1272 | 1272 | 1272 | 1272 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Technical Submittal of Power Receptacles, Push buttons and Switches Submission | 2 | EPRPS | E000 | 00E2 | E000EPRPS00E2
1273 | 1273 | 1273 | 1273 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Technical Submittal of Power Receptacles, Push buttons and Switches Review / Evaluation | 3 | EPRPS | E000 | 00E3 | E000EPRPS00E3
1274 | 1274 | 1274 | 1274 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Technical Submittal of Power Receptacles, Push buttons and Switches Approval with Comments | 4 | EPRPS | E000 | 00E4 | E000EPRPS00E4
1275 | 1275 | 1275 | 1275 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Technical Submittal of Power Receptacles, Push buttons and Switches FINAL Approval | 5 | EPRPS | E000 | 00E5 | E000EPRPS00E5
1276 | 1276 | 1276 | 1276 | SA24M005 | Installation Drawing Details & Wiring Diagrams for Indoor and Outdoor CCTV system |  | 6 | -1 | 0 |  |  | X
1277 | 1277 | 1277 | 1277 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Installation Drawing Details & Wiring Diagrams for Indoor and Outdoor CCTV system Drafting / Preparation | 1 | E0CTV | E000 | 00E1 | E000E0CTV00E1
1278 | 1278 | 1278 | 1278 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Installation Drawing Details & Wiring Diagrams for Indoor and Outdoor CCTV system Submission | 2 | E0CTV | E000 | 00E2 | E000E0CTV00E2
1279 | 1279 | 1279 | 1279 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Installation Drawing Details & Wiring Diagrams for Indoor and Outdoor CCTV system Review / Evaluation | 3 | E0CTV | E000 | 00E3 | E000E0CTV00E3
1280 | 1280 | 1280 | 1280 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Installation Drawing Details & Wiring Diagrams for Indoor and Outdoor CCTV system Approval with Comments | 4 | E0CTV | E000 | 00E4 | E000E0CTV00E4
1281 | 1281 | 1281 | 1281 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Installation Drawing Details & Wiring Diagrams for Indoor and Outdoor CCTV system FINAL Approval | 5 | E0CTV | E000 | 00E5 | E000E0CTV00E5
1282 | 1282 | 1282 | 1282 | SA24M005 | Material submittal for CCTV |  | 6 | -1 | 0 |  |  | X
1283 | 1283 | 1283 | 1283 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Material submittal for CCTV Drafting / Preparation | 1 | ECCTV | E000 | 00E1 | E000#Aioe00E1
1284 | 1284 | 1284 | 1284 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Material submittal for CCTV Submission | 2 | ECCTV | E000 | 00E2 | E000#Aioe00E2
1285 | 1285 | 1285 | 1285 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Material submittal for CCTV Review / Evaluation | 3 | ECCTV | E000 | 00E3 | E000#Aioe00E3
1286 | 1286 | 1286 | 1286 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Material submittal for CCTV Approval with Comments | 4 | ECCTV | E000 | 00E4 | E000#Aioe00E4
1287 | 1287 | 1287 | 1287 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Material submittal for CCTV FINAL Approval | 5 | ECCTV | E000 | 00E5 | E000#Aioe00E5
1288 | 1288 | 1288 | 1288 | SA24M005 | Equipment Layout Plan & Sections- IPP ROOM |  | 6 | -1 | 0 |  |  | X | E000#Aioe
1289 | 1289 | 1289 | 1289 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Equipment Layout Plan & Sections- IPP ROOM Drafting / Preparation | 1 | EQIPP | E000 | 00E1 | E000EQIPP00E1
1290 | 1290 | 1290 | 1290 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Equipment Layout Plan & Sections- IPP ROOM Submission | 2 | EQIPP | E000 | 00E2 | E000EQIPP00E2
1291 | 1291 | 1291 | 1291 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Equipment Layout Plan & Sections- IPP ROOM Review / Evaluation | 3 | EQIPP | E000 | 00E3 | E000EQIPP00E3
1292 | 1292 | 1292 | 1292 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Equipment Layout Plan & Sections- IPP ROOM Approval with Comments | 4 | EQIPP | E000 | 00E4 | E000EQIPP00E4
1293 | 1293 | 1293 | 1293 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Equipment Layout Plan & Sections- IPP ROOM FINAL Approval | 5 | EQIPP | E000 | 00E5 | E000EQIPP00E5
1294 | 1294 | 1294 | 1294 | SA24M005 | LV Power & Control Cable Race Way Routing Layout Plan and Section for IPP Room |  | 6 | -1 | 0 |  |  | X
1295 | 1295 | 1295 | 1295 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical LV Power & Control Cable Race Way Routing Layout Plan and Section for IPP Room Drafting / Preparation | 1 | E0LVC | E000 | 00E1 | E000#wNGV00E1
1296 | 1296 | 1296 | 1296 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical LV Power & Control Cable Race Way Routing Layout Plan and Section for IPP Room Submission | 2 | E0LVC | E000 | 00E2 | E000#wNGV00E2
1297 | 1297 | 1297 | 1297 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical LV Power & Control Cable Race Way Routing Layout Plan and Section for IPP Room Review / Evaluation | 3 | E0LVC | E000 | 00E3 | E000#wNGV00E3
1298 | 1298 | 1298 | 1298 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical LV Power & Control Cable Race Way Routing Layout Plan and Section for IPP Room Approval with Comments | 4 | E0LVC | E000 | 00E4 | E000#wNGV00E4
1299 | 1299 | 1299 | 1299 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical LV Power & Control Cable Race Way Routing Layout Plan and Section for IPP Room FINAL Approval | 5 | E0LVC | E000 | 00E5 | E000#wNGV00E5
1300 | 1300 | 1300 | 1300 | SA24M005 | Wall Opening , Floor Cutout , cable sleeves & Rooftop Layout Details - IPP Room |  | 6 | -1 | 0 |  |  | X | E000#wNGV
1301 | 1301 | 1301 | 1301 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Wall Opening , Floor Cutout , cable sleeves & Rooftop Layout Details - IPP Room Drafting / Preparation | 1 | E0WFR | E000 | 00E1 | E000E0WFR00E1
1302 | 1302 | 1302 | 1302 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Wall Opening , Floor Cutout , cable sleeves & Rooftop Layout Details - IPP Room Submission | 2 | E0WFR | E000 | 00E2 | E000E0WFR00E2
1303 | 1303 | 1303 | 1303 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Wall Opening , Floor Cutout , cable sleeves & Rooftop Layout Details - IPP Room Review / Evaluation | 3 | E0WFR | E000 | 00E3 | E000E0WFR00E3
1304 | 1304 | 1304 | 1304 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Wall Opening , Floor Cutout , cable sleeves & Rooftop Layout Details - IPP Room Approval with Comments | 4 | E0WFR | E000 | 00E4 | E000E0WFR00E4
1305 | 1305 | 1305 | 1305 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Wall Opening , Floor Cutout , cable sleeves & Rooftop Layout Details - IPP Room FINAL Approval | 5 | E0WFR | E000 | 00E5 | E000E0WFR00E5
1306 | 1306 | 1306 | 1306 | SA24M005 | Reinforcement Grounding for IPP Room |  | 6 | -1 | 0 |  |  | X
1307 | 1307 | 1307 | 1307 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Reinforcement Grounding for IPP Room Drafting / Preparation | 1 | EGRND | E000 | 00E1 | E000#lDiK00E1
1308 | 1308 | 1308 | 1308 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Reinforcement Grounding for IPP Room Submission | 2 | EGRND | E000 | 00E2 | E000#lDiK00E2
1309 | 1309 | 1309 | 1309 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Reinforcement Grounding for IPP Room Review / Evaluation | 3 | EGRND | E000 | 00E3 | E000#lDiK00E3
1310 | 1310 | 1310 | 1310 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Reinforcement Grounding for IPP Room Approval with Comments | 4 | EGRND | E000 | 00E4 | E000#lDiK00E4
1311 | 1311 | 1311 | 1311 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Reinforcement Grounding for IPP Room FINAL Approval | 5 | EGRND | E000 | 00E5 | E000#lDiK00E5
1312 | 1312 | 1312 | 1312 | SA24M005 | Equipment Building Indoor Equipment Grounding Layout & Sections- IPP ROOM |  | 6 | -1 | 0 |  |  | X | E000#lDiK
1313 | 1313 | 1313 | 1313 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Equipment Building Indoor Equipment Grounding Layout & Sections- IPP ROOM Drafting / Preparation | 1 | EQB0IPP | E000 | 00E1 | E000EQB0IPP00E1
1314 | 1314 | 1314 | 1314 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Equipment Building Indoor Equipment Grounding Layout & Sections- IPP ROOM Submission | 2 | EQB0IPP | E000 | 00E2 | E000EQB0IPP00E2
1315 | 1315 | 1315 | 1315 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Equipment Building Indoor Equipment Grounding Layout & Sections- IPP ROOM Review / Evaluation | 3 | EQB0IPP | E000 | 00E3 | E000EQB0IPP00E3
1316 | 1316 | 1316 | 1316 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Equipment Building Indoor Equipment Grounding Layout & Sections- IPP ROOM Approval with Comments | 4 | EQB0IPP | E000 | 00E4 | E000EQB0IPP00E4
1317 | 1317 | 1317 | 1317 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Equipment Building Indoor Equipment Grounding Layout & Sections- IPP ROOM FINAL Approval | 5 | EQB0IPP | E000 | 00E5 | E000EQB0IPP00E5
1318 | 1318 | 1318 | 1318 | SA24M005 | Heat Dissipation Calculation- IPP ROOM |  | 6 | -1 | 0 |  |  | X
1319 | 1319 | 1319 | 1319 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Heat Dissipation Calculation- IPP ROOM Drafting / Preparation | 1 | E0HRM | E000 | 00E1 | E000E0HRM00E1
1320 | 1320 | 1320 | 1320 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Heat Dissipation Calculation- IPP ROOM Submission | 2 | E0HRM | E000 | 00E2 | E000E0HRM00E2
1321 | 1321 | 1321 | 1321 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Heat Dissipation Calculation- IPP ROOM Review / Evaluation | 3 | E0HRM | E000 | 00E3 | E000E0HRM00E3
1322 | 1322 | 1322 | 1322 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Heat Dissipation Calculation- IPP ROOM Approval with Comments | 4 | E0HRM | E000 | 00E4 | E000E0HRM00E4
1323 | 1323 | 1323 | 1323 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Electrical Heat Dissipation Calculation- IPP ROOM FINAL Approval | 5 | E0HRM | E000 | 00E5 | E000E0HRM00E5
1324 | 1324 | 1324 | 1324 | SA24M005 | Civil |  | 5 | -1 | 0 |  |  | X
1325 | 1325 | 1325 | 1325 | SA24M005 | EHV GIS Room- Architectural Plan & Details |  | 6 | -1 | 0 |  |  | X
1326 | 1326 | 1326 | 1326 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Architectural Plan & Details Drafting / Preparation | 1 | E0GIS | E000 | 00E1 | E000#syJA00E1
1327 | 1327 | 1327 | 1327 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Architectural Plan & Details Submission | 2 | E0GIS | E000 | 00E2 | E000#syJA00E2
1328 | 1328 | 1328 | 1328 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Architectural Plan & Details Review / Evaluation | 3 | E0GIS | E000 | 00E3 | E000#syJA00E3
1329 | 1329 | 1329 | 1329 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Architectural Plan & Details Approval with Comments | 4 | E0GIS | E000 | 00E4 | E000#syJA00E4
1330 | 1330 | 1330 | 1330 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Architectural Plan & Details FINAL Approval | 5 | E0GIS | E000 | 00E5 | E000#syJA00E5
1331 | 1331 | 1331 | 1331 | SA24M005 | EHV GIS Room- Layout & Details of Openings and Sleeves in Walls |  | 6 | -1 | 0 |  |  | X | E000#syJA
1332 | 1332 | 1332 | 1332 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Layout & Details of Openings and Sleeves in Walls Drafting / Preparation | 1 | E0GIS | E000 | 00E1 | E000#UOKw00E1
1333 | 1333 | 1333 | 1333 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Layout & Details of Openings and Sleeves in Walls Submission | 2 | E0GIS | E000 | 00E2 | E000#UOKw00E2
1334 | 1334 | 1334 | 1334 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Layout & Details of Openings and Sleeves in Walls Review / Evaluation | 3 | E0GIS | E000 | 00E3 | E000#UOKw00E3
1335 | 1335 | 1335 | 1335 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Layout & Details of Openings and Sleeves in Walls Approval with Comments | 4 | E0GIS | E000 | 00E4 | E000#UOKw00E4
1336 | 1336 | 1336 | 1336 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Layout & Details of Openings and Sleeves in Walls FINAL Approval | 5 | E0GIS | E000 | 00E5 | E000#UOKw00E5
1337 | 1337 | 1337 | 1337 | SA24M005 | EHV GIS Room- Building Analysis and Design Calculations , Substructure & Column Reinforcement Detail |  | 6 | -1 | 0 |  |  | X | E000#UOKw
1338 | 1338 | 1338 | 1338 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Building Analysis and Design Calculations , Substructure & Column Reinforcement Detail Drafting / Preparation | 1 | E0GIS | E000 | 00E1 | E000#XQXL00E1
1339 | 1339 | 1339 | 1339 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Building Analysis and Design Calculations , Substructure & Column Reinforcement Detail Submission | 2 | E0GIS | E000 | 00E2 | E000#XQXL00E2
1340 | 1340 | 1340 | 1340 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Building Analysis and Design Calculations , Substructure & Column Reinforcement Detail Review / Evaluation | 3 | E0GIS | E000 | 00E3 | E000#XQXL00E3
1341 | 1341 | 1341 | 1341 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Building Analysis and Design Calculations , Substructure & Column Reinforcement Detail Approval with Comments | 4 | E0GIS | E000 | 00E4 | E000#XQXL00E4
1342 | 1342 | 1342 | 1342 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Building Analysis and Design Calculations , Substructure & Column Reinforcement Detail FINAL Approval | 5 | E0GIS | E000 | 00E5 | E000#XQXL00E5
1343 | 1343 | 1343 | 1343 | SA24M005 | EHV GIS Room- Slab and Beam Framing Plan, Ground Floor Openings and Reinforcement Details |  | 6 | -1 | 0 |  |  | X | E000#XQXL
1344 | 1344 | 1344 | 1344 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Slab and Beam Framing Plan, Ground Floor Openings and Reinforcement Details Drafting / Preparation | 1 | E0GIS | E000 | 00E1 | E000#CYWB00E1
1345 | 1345 | 1345 | 1345 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Slab and Beam Framing Plan, Ground Floor Openings and Reinforcement Details Submission | 2 | E0GIS | E000 | 00E2 | E000#CYWB00E2
1346 | 1346 | 1346 | 1346 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Slab and Beam Framing Plan, Ground Floor Openings and Reinforcement Details Review / Evaluation | 3 | E0GIS | E000 | 00E3 | E000#CYWB00E3
1347 | 1347 | 1347 | 1347 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Slab and Beam Framing Plan, Ground Floor Openings and Reinforcement Details Approval with Comments | 4 | E0GIS | E000 | 00E4 | E000#CYWB00E4
1348 | 1348 | 1348 | 1348 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Slab and Beam Framing Plan, Ground Floor Openings and Reinforcement Details FINAL Approval | 5 | E0GIS | E000 | 00E5 | E000#CYWB00E5
1349 | 1349 | 1349 | 1349 | SA24M005 | EHV GIS Room- Stair Rebar Details |  | 6 | -1 | 0 |  |  | X | E000#CYWB
1350 | 1350 | 1350 | 1350 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Stair Rebar Details Drafting / Preparation | 1 | E0GIS | E000 | 00E1 | E000#cpfN00E1
1351 | 1351 | 1351 | 1351 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Stair Rebar Details Submission | 2 | E0GIS | E000 | 00E2 | E000#cpfN00E2
1352 | 1352 | 1352 | 1352 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Stair Rebar Details Review / Evaluation | 3 | E0GIS | E000 | 00E3 | E000#cpfN00E3
1353 | 1353 | 1353 | 1353 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Stair Rebar Details Approval with Comments | 4 | E0GIS | E000 | 00E4 | E000#cpfN00E4
1354 | 1354 | 1354 | 1354 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Stair Rebar Details FINAL Approval | 5 | E0GIS | E000 | 00E5 | E000#cpfN00E5
1355 | 1355 | 1355 | 1355 | SA24M005 | EHV GIS Room- Precast Super Structure Elements Design & Details |  | 6 | -1 | 0 |  |  | X | E000#cpfN
1356 | 1356 | 1356 | 1356 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Precast Super Structure Elements Design & Details Drafting / Preparation | 1 | E0GIS | E000 | 00E1 | E000#nrro00E1
1357 | 1357 | 1357 | 1357 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Precast Super Structure Elements Design & Details Submission | 2 | E0GIS | E000 | 00E2 | E000#nrro00E2
1358 | 1358 | 1358 | 1358 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Precast Super Structure Elements Design & Details Review / Evaluation | 3 | E0GIS | E000 | 00E3 | E000#nrro00E3
1359 | 1359 | 1359 | 1359 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Precast Super Structure Elements Design & Details Approval with Comments | 4 | E0GIS | E000 | 00E4 | E000#nrro00E4
1360 | 1360 | 1360 | 1360 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Precast Super Structure Elements Design & Details FINAL Approval | 5 | E0GIS | E000 | 00E5 | E000#nrro00E5
1361 | 1361 | 1361 | 1361 | SA24M005 | EHV GIS Room- Roof Level Reinforcement Details |  | 6 | -1 | 0 |  |  | X | E000#nrro
1362 | 1362 | 1362 | 1362 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Roof Level Reinforcement Details Drafting / Preparation | 1 | E0GIS | E000 | 00E1 | E000#GygG00E1
1363 | 1363 | 1363 | 1363 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Roof Level Reinforcement Details Submission | 2 | E0GIS | E000 | 00E2 | E000#GygG00E2
1364 | 1364 | 1364 | 1364 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Roof Level Reinforcement Details Review / Evaluation | 3 | E0GIS | E000 | 00E3 | E000#GygG00E3
1365 | 1365 | 1365 | 1365 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Roof Level Reinforcement Details Approval with Comments | 4 | E0GIS | E000 | 00E4 | E000#GygG00E4
1366 | 1366 | 1366 | 1366 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Roof Level Reinforcement Details FINAL Approval | 5 | E0GIS | E000 | 00E5 | E000#GygG00E5
1367 | 1367 | 1367 | 1367 | SA24M005 | EHV GIS Room- Crane Girder (Crane Runway Beam) Calculations, Plan and Details |  | 6 | -1 | 0 |  |  | X | E000#GygG
1368 | 1368 | 1368 | 1368 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Crane Girder (Crane Runway Beam) Calculations, Plan and Details Drafting / Preparation | 1 | E0GIS | E000 | 00E1 | E000#Fhju00E1
1369 | 1369 | 1369 | 1369 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Crane Girder (Crane Runway Beam) Calculations, Plan and Details Submission | 2 | E0GIS | E000 | 00E2 | E000#Fhju00E2
1370 | 1370 | 1370 | 1370 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Crane Girder (Crane Runway Beam) Calculations, Plan and Details Review / Evaluation | 3 | E0GIS | E000 | 00E3 | E000#Fhju00E3
1371 | 1371 | 1371 | 1371 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Crane Girder (Crane Runway Beam) Calculations, Plan and Details Approval with Comments | 4 | E0GIS | E000 | 00E4 | E000#Fhju00E4
1372 | 1372 | 1372 | 1372 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Crane Girder (Crane Runway Beam) Calculations, Plan and Details FINAL Approval | 5 | E0GIS | E000 | 00E5 | E000#Fhju00E5
1373 | 1373 | 1373 | 1373 | SA24M005 | EHV GIS Room- Access Ladder Details for Roofs and Cranes |  | 6 | -1 | 0 |  |  | X | E000#Fhju
1374 | 1374 | 1374 | 1374 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Access Ladder Details for Roofs and Cranes Drafting / Preparation | 1 | E0GIS | E000 | 00E1 | E000#olYn00E1
1375 | 1375 | 1375 | 1375 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Access Ladder Details for Roofs and Cranes Submission | 2 | E0GIS | E000 | 00E2 | E000#olYn00E2
1376 | 1376 | 1376 | 1376 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Access Ladder Details for Roofs and Cranes Review / Evaluation | 3 | E0GIS | E000 | 00E3 | E000#olYn00E3
1377 | 1377 | 1377 | 1377 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Access Ladder Details for Roofs and Cranes Approval with Comments | 4 | E0GIS | E000 | 00E4 | E000#olYn00E4
1378 | 1378 | 1378 | 1378 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Access Ladder Details for Roofs and Cranes FINAL Approval | 5 | E0GIS | E000 | 00E5 | E000#olYn00E5
1379 | 1379 | 1379 | 1379 | SA24M005 | EHV GIS Room- Steps, Ramps, Walkways & Loading Platforms Layout & Details |  | 6 | -1 | 0 |  |  | X | E000#olYn
1380 | 1380 | 1380 | 1380 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Steps, Ramps, Walkways & Loading Platforms Layout & Details Drafting / Preparation | 1 | E0GIS | E000 | 00E1 | E000#GGgJ00E1
1381 | 1381 | 1381 | 1381 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Steps, Ramps, Walkways & Loading Platforms Layout & Details Submission | 2 | E0GIS | E000 | 00E2 | E000#GGgJ00E2
1382 | 1382 | 1382 | 1382 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Steps, Ramps, Walkways & Loading Platforms Layout & Details Review / Evaluation | 3 | E0GIS | E000 | 00E3 | E000#GGgJ00E3
1383 | 1383 | 1383 | 1383 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Steps, Ramps, Walkways & Loading Platforms Layout & Details Approval with Comments | 4 | E0GIS | E000 | 00E4 | E000#GGgJ00E4
1384 | 1384 | 1384 | 1384 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Steps, Ramps, Walkways & Loading Platforms Layout & Details FINAL Approval | 5 | E0GIS | E000 | 00E5 | E000#GGgJ00E5
1385 | 1385 | 1385 | 1385 | SA24M005 | EHV GIS Room- Design Calculations , Layout and Details of HVAC PACU Pad Foundations |  | 6 | -1 | 0 |  |  | X | E000#GGgJ
1386 | 1386 | 1386 | 1386 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Design Calculations , Layout and Details of HVAC PACU Pad Foundations Drafting / Preparation | 1 | E0GIS | E000 | 00E1 | E000#GwbC00E1
1387 | 1387 | 1387 | 1387 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Design Calculations , Layout and Details of HVAC PACU Pad Foundations Submission | 2 | E0GIS | E000 | 00E2 | E000#GwbC00E2
1388 | 1388 | 1388 | 1388 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Design Calculations , Layout and Details of HVAC PACU Pad Foundations Review / Evaluation | 3 | E0GIS | E000 | 00E3 | E000#GwbC00E3
1389 | 1389 | 1389 | 1389 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Design Calculations , Layout and Details of HVAC PACU Pad Foundations Approval with Comments | 4 | E0GIS | E000 | 00E4 | E000#GwbC00E4
1390 | 1390 | 1390 | 1390 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil EHV GIS Room- Design Calculations , Layout and Details of HVAC PACU Pad Foundations FINAL Approval | 5 | E0GIS | E000 | 00E5 | E000#GwbC00E5
1391 | 1391 | 1391 | 1391 | SA24M005 | Bus-Reactors- Design Calculation and Reinforcement Details of Foundations and Firewall |  | 6 | -1 | 0 |  |  | X | E000#GwbC
1392 | 1392 | 1392 | 1392 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil Bus-Reactors- Design Calculation and Reinforcement Details of Foundations and Firewall Drafting / Preparation | 1 | C0BRF | E000 | 00E1 | E000C0BRF00E1
1393 | 1393 | 1393 | 1393 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil Bus-Reactors- Design Calculation and Reinforcement Details of Foundations and Firewall Submission | 2 | C0BRF | E000 | 00E2 | E000C0BRF00E2
1394 | 1394 | 1394 | 1394 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil Bus-Reactors- Design Calculation and Reinforcement Details of Foundations and Firewall Review / Evaluation | 3 | C0BRF | E000 | 00E3 | E000C0BRF00E3
1395 | 1395 | 1395 | 1395 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil Bus-Reactors- Design Calculation and Reinforcement Details of Foundations and Firewall Approval with Comments | 4 | C0BRF | E000 | 00E4 | E000C0BRF00E4
1396 | 1396 | 1396 | 1396 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil Bus-Reactors- Design Calculation and Reinforcement Details of Foundations and Firewall FINAL Approval | 5 | C0BRF | E000 | 00E5 | E000C0BRF00E5
1397 | 1397 | 1397 | 1397 | SA24M005 | Bus-Reactors- Layout & details of transformer steel grating |  | 6 | -1 | 0 |  |  | X
1398 | 1398 | 1398 | 1398 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil Bus-Reactors- Layout & details of transformer steel grating Drafting / Preparation | 1 | C0BRT | E000 | 00E1 | E000C0BRT00E1
1399 | 1399 | 1399 | 1399 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil Bus-Reactors- Layout & details of transformer steel grating Submission | 2 | C0BRT | E000 | 00E2 | E000C0BRT00E2
1400 | 1400 | 1400 | 1400 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil Bus-Reactors- Layout & details of transformer steel grating Review / Evaluation | 3 | C0BRT | E000 | 00E3 | E000C0BRT00E3
1401 | 1401 | 1401 | 1401 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil Bus-Reactors- Layout & details of transformer steel grating Approval with Comments | 4 | C0BRT | E000 | 00E4 | E000C0BRT00E4
1402 | 1402 | 1402 | 1402 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil Bus-Reactors- Layout & details of transformer steel grating FINAL Approval | 5 | C0BRT | E000 | 00E5 | E000C0BRT00E5
1403 | 1403 | 1403 | 1403 | SA24M005 | Line-Reactors- Design Calculation and Reinforcement Details of Foundations and Firewall |  | 6 | -1 | 0 |  |  | X
1404 | 1404 | 1404 | 1404 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil Line-Reactors- Design Calculation and Reinforcement Details of Foundations and Firewall Drafting / Preparation | 1 | CLINE-REACTORS | E000 | 00E1 | E000CLINE-REACTORS00E1
1405 | 1405 | 1405 | 1405 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil Line-Reactors- Design Calculation and Reinforcement Details of Foundations and Firewall Submission | 2 | CLINE-REACTORS | E000 | 00E2 | E000CLINE-REACTORS00E2
1406 | 1406 | 1406 | 1406 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil Line-Reactors- Design Calculation and Reinforcement Details of Foundations and Firewall Review / Evaluation | 3 | CLINE-REACTORS | E000 | 00E3 | E000CLINE-REACTORS00E3
1407 | 1407 | 1407 | 1407 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil Line-Reactors- Design Calculation and Reinforcement Details of Foundations and Firewall Approval with Comments | 4 | CLINE-REACTORS | E000 | 00E4 | E000CLINE-REACTORS00E4
1408 | 1408 | 1408 | 1408 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil Line-Reactors- Design Calculation and Reinforcement Details of Foundations and Firewall FINAL Approval | 5 | CLINE-REACTORS | E000 | 00E5 | E000CLINE-REACTORS00E5
1409 | 1409 | 1409 | 1409 | SA24M005 | Line-Reactors- Layout & details of transformer steel grating |  | 6 | -1 | 0 |  |  | X
1410 | 1410 | 1410 | 1410 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil Line-Reactors- Layout & details of transformer steel grating Drafting / Preparation | 1 | CLINE-REAC | E000 | 00E1 | E000CLINE-REAC00E1
1411 | 1411 | 1411 | 1411 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil Line-Reactors- Layout & details of transformer steel grating Submission | 2 | CLINE-REAC | E000 | 00E2 | E000CLINE-REAC00E2
1412 | 1412 | 1412 | 1412 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil Line-Reactors- Layout & details of transformer steel grating Review / Evaluation | 3 | CLINE-REAC | E000 | 00E3 | E000CLINE-REAC00E3
1413 | 1413 | 1413 | 1413 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil Line-Reactors- Layout & details of transformer steel grating Approval with Comments | 4 | CLINE-REAC | E000 | 00E4 | E000CLINE-REAC00E4
1414 | 1414 | 1414 | 1414 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil Line-Reactors- Layout & details of transformer steel grating FINAL Approval | 5 | CLINE-REAC | E000 | 00E5 | E000CLINE-REAC00E5
1415 | 1415 | 1415 | 1415 | SA24M005 | Oil Tank Design Calculation & Details |  | 6 | -1 | 0 |  |  | X
1416 | 1416 | 1416 | 1416 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil Oil Tank Design Calculation & Details Drafting / Preparation | 1 | COTDC | E000 | 00E1 | E000COTDC00E1
1417 | 1417 | 1417 | 1417 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil Oil Tank Design Calculation & Details Submission | 2 | COTDC | E000 | 00E2 | E000COTDC00E2
1418 | 1418 | 1418 | 1418 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil Oil Tank Design Calculation & Details Review / Evaluation | 3 | COTDC | E000 | 00E3 | E000COTDC00E3
1419 | 1419 | 1419 | 1419 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil Oil Tank Design Calculation & Details Approval with Comments | 4 | COTDC | E000 | 00E4 | E000COTDC00E4
1420 | 1420 | 1420 | 1420 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil Oil Tank Design Calculation & Details FINAL Approval | 5 | COTDC | E000 | 00E5 | E000COTDC00E5
1421 | 1421 | 1421 | 1421 | SA24M005 | Design Calculation and Reinforcement Details of NGR Foundation |  | 6 | -1 | 0 |  |  | X
1422 | 1422 | 1422 | 1422 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil Design Calculation and Reinforcement Details of NGR Foundation Drafting / Preparation | 1 | C0NGR | E000 | 00E1 | E000C0NGR00E1
1423 | 1423 | 1423 | 1423 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil Design Calculation and Reinforcement Details of NGR Foundation Submission | 2 | C0NGR | E000 | 00E2 | E000C0NGR00E2
1424 | 1424 | 1424 | 1424 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil Design Calculation and Reinforcement Details of NGR Foundation Review / Evaluation | 3 | C0NGR | E000 | 00E3 | E000C0NGR00E3
1425 | 1425 | 1425 | 1425 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil Design Calculation and Reinforcement Details of NGR Foundation Approval with Comments | 4 | C0NGR | E000 | 00E4 | E000C0NGR00E4
1426 | 1426 | 1426 | 1426 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil Design Calculation and Reinforcement Details of NGR Foundation FINAL Approval | 5 | C0NGR | E000 | 00E5 | E000C0NGR00E5
1427 | 1427 | 1427 | 1427 | SA24M005 | All Outdoor Cable Tunnel -design Calculations, sections and Reinforcement Details |  | 6 | -1 | 0 |  |  | X
1428 | 1428 | 1428 | 1428 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil All Outdoor Cable Tunnel -design Calculations, sections and Reinforcement Details Drafting / Preparation | 1 | AOCR0 | E000 | 00E1 | E000AOCR000E1
1429 | 1429 | 1429 | 1429 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil All Outdoor Cable Tunnel -design Calculations, sections and Reinforcement Details Submission | 2 | AOCR0 | E000 | 00E2 | E000AOCR000E2
1430 | 1430 | 1430 | 1430 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil All Outdoor Cable Tunnel -design Calculations, sections and Reinforcement Details Review / Evaluation | 3 | AOCR0 | E000 | 00E3 | E000AOCR000E3
1431 | 1431 | 1431 | 1431 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil All Outdoor Cable Tunnel -design Calculations, sections and Reinforcement Details Approval with Comments | 4 | AOCR0 | E000 | 00E4 | E000AOCR000E4
1432 | 1432 | 1432 | 1432 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil All Outdoor Cable Tunnel -design Calculations, sections and Reinforcement Details FINAL Approval | 5 | AOCR0 | E000 | 00E5 | E000AOCR000E5
1433 | 1433 | 1433 | 1433 | SA24M005 | Layout, Calculations & reinforcement Details of Trenches, Electrical DuctBanks, Wing walls, Manholes |  | 6 | -1 | 0 |  |  | X
1434 | 1434 | 1434 | 1434 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil Layout, Calculations & reinforcement Details of Trenches, Electrical DuctBanks, Wing walls, Manholes Drafting / Preparation | 1 | E0TRB | E000 | 00E1 | E000E0TRB00E1
1435 | 1435 | 1435 | 1435 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil Layout, Calculations & reinforcement Details of Trenches, Electrical DuctBanks, Wing walls, Manholes Submission | 2 | E0TRB | E000 | 00E2 | E000E0TRB00E2
1436 | 1436 | 1436 | 1436 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil Layout, Calculations & reinforcement Details of Trenches, Electrical DuctBanks, Wing walls, Manholes Review / Evaluation | 3 | E0TRB | E000 | 00E3 | E000E0TRB00E3
1437 | 1437 | 1437 | 1437 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil Layout, Calculations & reinforcement Details of Trenches, Electrical DuctBanks, Wing walls, Manholes Approval with Comments | 4 | E0TRB | E000 | 00E4 | E000E0TRB00E4
1438 | 1438 | 1438 | 1438 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil Layout, Calculations & reinforcement Details of Trenches, Electrical DuctBanks, Wing walls, Manholes FINAL Approval | 5 | E0TRB | E000 | 00E5 | E000E0TRB00E5
1439 | 1439 | 1439 | 1439 | SA24M005 | Layout & Detail Design Calculation of Communication Duct Bank (Structural Package) |  | 6 | -1 | 0 |  |  | X
1440 | 1440 | 1440 | 1440 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil Layout & Detail Design Calculation of Communication Duct Bank (Structural Package) Drafting / Preparation | 1 | C0CDB | E000 | 00E1 | E000C0CDB00E1
1441 | 1441 | 1441 | 1441 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil Layout & Detail Design Calculation of Communication Duct Bank (Structural Package) Submission | 2 | C0CDB | E000 | 00E2 | E000C0CDB00E2
1442 | 1442 | 1442 | 1442 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil Layout & Detail Design Calculation of Communication Duct Bank (Structural Package) Review / Evaluation | 3 | C0CDB | E000 | 00E3 | E000C0CDB00E3
1443 | 1443 | 1443 | 1443 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil Layout & Detail Design Calculation of Communication Duct Bank (Structural Package) Approval with Comments | 4 | C0CDB | E000 | 00E4 | E000C0CDB00E4
1444 | 1444 | 1444 | 1444 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil Layout & Detail Design Calculation of Communication Duct Bank (Structural Package) FINAL Approval | 5 | C0CDB | E000 | 00E5 | E000C0CDB00E5
1445 | 1445 | 1445 | 1445 | SA24M005 | Asphalt Mix Design |  | 6 | -1 | 0 |  |  | X
1446 | 1446 | 1446 | 1446 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil Asphalt Mix Design Drafting / Preparation | 1 | CASMD | E000 | 00E1 | E000CASMD00E1
1447 | 1447 | 1447 | 1447 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil Asphalt Mix Design Submission | 2 | CASMD | E000 | 00E2 | E000CASMD00E2
1448 | 1448 | 1448 | 1448 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil Asphalt Mix Design Review / Evaluation | 3 | CASMD | E000 | 00E3 | E000CASMD00E3
1449 | 1449 | 1449 | 1449 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil Asphalt Mix Design Approval with Comments | 4 | CASMD | E000 | 00E4 | E000CASMD00E4
1450 | 1450 | 1450 | 1450 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Civil Asphalt Mix Design FINAL Approval | 5 | CASMD | E000 | 00E5 | E000CASMD00E5
1451 | 1451 | 1451 | 1451 | SA24M005 | Mechanical |  | 5 | -1 | 0 |  |  | X
1452 | 1452 | 1452 | 1452 | SA24M005 | EHV GIS Room- HVAC System Design Calculation and Drawing |  | 6 | -1 | 0 |  |  | X
1453 | 1453 | 1453 | 1453 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Mechanical EHV GIS Room- HVAC System Design Calculation and Drawing Drafting / Preparation | 1 | E0GIS | E000 | 00E1 | E000#TFiE00E1
1454 | 1454 | 1454 | 1454 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Mechanical EHV GIS Room- HVAC System Design Calculation and Drawing Submission | 2 | E0GIS | E000 | 00E2 | E000#TFiE00E2
1455 | 1455 | 1455 | 1455 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Mechanical EHV GIS Room- HVAC System Design Calculation and Drawing Review / Evaluation | 3 | E0GIS | E000 | 00E3 | E000#TFiE00E3
1456 | 1456 | 1456 | 1456 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Mechanical EHV GIS Room- HVAC System Design Calculation and Drawing Approval with Comments | 4 | E0GIS | E000 | 00E4 | E000#TFiE00E4
1457 | 1457 | 1457 | 1457 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Mechanical EHV GIS Room- HVAC System Design Calculation and Drawing FINAL Approval | 5 | E0GIS | E000 | 00E5 | E000#TFiE00E5
1458 | 1458 | 1458 | 1458 | SA24M005 | EHV GIS Room- Plumbing Design Calculations & Drawings |  | 6 | -1 | 0 |  |  | X | E000#TFiE
1459 | 1459 | 1459 | 1459 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Mechanical EHV GIS Room- Plumbing Design Calculations & Drawings Drafting / Preparation | 1 | E0GIS | E000 | 00E1 | E000#xCGq00E1
1460 | 1460 | 1460 | 1460 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Mechanical EHV GIS Room- Plumbing Design Calculations & Drawings Submission | 2 | E0GIS | E000 | 00E2 | E000#xCGq00E2
1461 | 1461 | 1461 | 1461 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Mechanical EHV GIS Room- Plumbing Design Calculations & Drawings Review / Evaluation | 3 | E0GIS | E000 | 00E3 | E000#xCGq00E3
1462 | 1462 | 1462 | 1462 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Mechanical EHV GIS Room- Plumbing Design Calculations & Drawings Approval with Comments | 4 | E0GIS | E000 | 00E4 | E000#xCGq00E4
1463 | 1463 | 1463 | 1463 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Mechanical EHV GIS Room- Plumbing Design Calculations & Drawings FINAL Approval | 5 | E0GIS | E000 | 00E5 | E000#xCGq00E5
1464 | 1464 | 1464 | 1464 | SA24M005 | EHV GIS Room- Material Submittal for HVAC Control Panel |  | 6 | -1 | 0 |  |  | X | E000#xCGq
1465 | 1465 | 1465 | 1465 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Mechanical EHV GIS Room- Material Submittal for HVAC Control Panel Drafting / Preparation | 1 | E0GIS | E000 | 00E1 | E000#KwdK00E1
1466 | 1466 | 1466 | 1466 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Mechanical EHV GIS Room- Material Submittal for HVAC Control Panel Submission | 2 | E0GIS | E000 | 00E2 | E000#KwdK00E2
1467 | 1467 | 1467 | 1467 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Mechanical EHV GIS Room- Material Submittal for HVAC Control Panel Review / Evaluation | 3 | E0GIS | E000 | 00E3 | E000#KwdK00E3
1468 | 1468 | 1468 | 1468 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Mechanical EHV GIS Room- Material Submittal for HVAC Control Panel Approval with Comments | 4 | E0GIS | E000 | 00E4 | E000#KwdK00E4
1469 | 1469 | 1469 | 1469 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Mechanical EHV GIS Room- Material Submittal for HVAC Control Panel FINAL Approval | 5 | E0GIS | E000 | 00E5 | E000#KwdK00E5
1470 | 1470 | 1470 | 1470 | SA24M005 | EHV GIS Room- Fire Protection Design Calculations & Drawings |  | 6 | -1 | 0 |  |  | X | E000#KwdK
1471 | 1471 | 1471 | 1471 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Mechanical EHV GIS Room- Fire Protection Design Calculations & Drawings Drafting / Preparation | 1 | E0GIS | E000 | 00E1 | E000#pnkT00E1
1472 | 1472 | 1472 | 1472 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Mechanical EHV GIS Room- Fire Protection Design Calculations & Drawings Submission | 2 | E0GIS | E000 | 00E2 | E000#pnkT00E2
1473 | 1473 | 1473 | 1473 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Mechanical EHV GIS Room- Fire Protection Design Calculations & Drawings Review / Evaluation | 3 | E0GIS | E000 | 00E3 | E000#pnkT00E3
1474 | 1474 | 1474 | 1474 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Mechanical EHV GIS Room- Fire Protection Design Calculations & Drawings Approval with Comments | 4 | E0GIS | E000 | 00E4 | E000#pnkT00E4
1475 | 1475 | 1475 | 1475 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Mechanical EHV GIS Room- Fire Protection Design Calculations & Drawings FINAL Approval | 5 | E0GIS | E000 | 00E5 | E000#pnkT00E5
1476 | 1476 | 1476 | 1476 | SA24M005 | Oil Filled Equipment (Plumbing & Drainage) System Design Calculation & Drawings |  | 6 | -1 | 0 |  |  | X | E000#pnkT
1477 | 1477 | 1477 | 1477 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Mechanical Oil Filled Equipment (Plumbing & Drainage) System Design Calculation & Drawings Drafting / Preparation | 1 | OFEQ | E000 | 00E1 | E000OFEQ00E1
1478 | 1478 | 1478 | 1478 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Mechanical Oil Filled Equipment (Plumbing & Drainage) System Design Calculation & Drawings Submission | 2 | OFEQ | E000 | 00E2 | E000OFEQ00E2
1479 | 1479 | 1479 | 1479 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Mechanical Oil Filled Equipment (Plumbing & Drainage) System Design Calculation & Drawings Review / Evaluation | 3 | OFEQ | E000 | 00E3 | E000OFEQ00E3
1480 | 1480 | 1480 | 1480 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Mechanical Oil Filled Equipment (Plumbing & Drainage) System Design Calculation & Drawings Approval with Comments | 4 | OFEQ | E000 | 00E4 | E000OFEQ00E4
1481 | 1481 | 1481 | 1481 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Mechanical Oil Filled Equipment (Plumbing & Drainage) System Design Calculation & Drawings FINAL Approval | 5 | OFEQ | E000 | 00E5 | E000OFEQ00E5
1482 | 1482 | 1482 | 1482 | SA24M005 | Technical Data of Transformer & Reactor Oil Pit Pump |  | 6 | -1 | 0 |  |  | X
1483 | 1483 | 1483 | 1483 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Mechanical Technical Data of Transformer & Reactor Oil Pit Pump Drafting / Preparation | 1 | 0TRF0 | E000 | 00E1 | E0000TRF000E1
1484 | 1484 | 1484 | 1484 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Mechanical Technical Data of Transformer & Reactor Oil Pit Pump Submission | 2 | 0TRF0 | E000 | 00E2 | E0000TRF000E2
1485 | 1485 | 1485 | 1485 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Mechanical Technical Data of Transformer & Reactor Oil Pit Pump Review / Evaluation | 3 | 0TRF0 | E000 | 00E3 | E0000TRF000E3
1486 | 1486 | 1486 | 1486 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Mechanical Technical Data of Transformer & Reactor Oil Pit Pump Approval with Comments | 4 | 0TRF0 | E000 | 00E4 | E0000TRF000E4
1487 | 1487 | 1487 | 1487 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Mechanical Technical Data of Transformer & Reactor Oil Pit Pump FINAL Approval | 5 | 0TRF0 | E000 | 00E5 | E0000TRF000E5
1488 | 1488 | 1488 | 1488 | SA24M005 | Material Submission for Safety and First Aid Equipment As per TES-P-119.21, Rev. 01 clause 3.8.6.10 |  | 6 | -1 | 0 |  |  | X
1489 | 1489 | 1489 | 1489 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Mechanical Material Submission for Safety and First Aid Equipment As per TES-P-119.21, Rev. 01 clause 3.8.6.10 Drafting / Preparation | 1 | MSFAE | E000 | 00E1 | E000MSFAE00E1
1490 | 1490 | 1490 | 1490 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Mechanical Material Submission for Safety and First Aid Equipment As per TES-P-119.21, Rev. 01 clause 3.8.6.10 Submission | 2 | MSFAE | E000 | 00E2 | E000MSFAE00E2
1491 | 1491 | 1491 | 1491 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Mechanical Material Submission for Safety and First Aid Equipment As per TES-P-119.21, Rev. 01 clause 3.8.6.10 Review / Evaluation | 3 | MSFAE | E000 | 00E3 | E000MSFAE00E3
1492 | 1492 | 1492 | 1492 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Mechanical Material Submission for Safety and First Aid Equipment As per TES-P-119.21, Rev. 01 clause 3.8.6.10 Approval with Comments | 4 | MSFAE | E000 | 00E4 | E000MSFAE00E4
1493 | 1493 | 1493 | 1493 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Mechanical Material Submission for Safety and First Aid Equipment As per TES-P-119.21, Rev. 01 clause 3.8.6.10 FINAL Approval | 5 | MSFAE | E000 | 00E5 | E000MSFAE00E5
1494 | 1494 | 1494 | 1494 | SA24M005 | Protection |  | 5 | -1 | 0 |  |  | X
1495 | 1495 | 1495 | 1495 | SA24M005 | Abbreviations, Symbols and Legend |  | 6 | -1 | 0 |  |  | X
1496 | 1496 | 1496 | 1496 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection Abbreviations, Symbols and Legend Drafting / Preparation | 1 | P0ASL | E000 | 00E1 | E000P0ASL00E1
1497 | 1497 | 1497 | 1497 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection Abbreviations, Symbols and Legend Submission | 2 | P0ASL | E000 | 00E2 | E000P0ASL00E2
1498 | 1498 | 1498 | 1498 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection Abbreviations, Symbols and Legend Review / Evaluation | 3 | P0ASL | E000 | 00E3 | E000P0ASL00E3
1499 | 1499 | 1499 | 1499 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection Abbreviations, Symbols and Legend Approval with Comments | 4 | P0ASL | E000 | 00E4 | E000P0ASL00E4
1500 | 1500 | 1500 | 1500 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection Abbreviations, Symbols and Legend FINAL Approval | 5 | P0ASL | E000 | 00E5 | E000P0ASL00E5
1501 | 1501 | 1501 | 1501 | SA24M005 | Switching One-Line Diagram |  | 6 | -1 | 0 |  |  | X
1502 | 1502 | 1502 | 1502 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection Switching One-Line Diagram Drafting / Preparation | 1 | PSOLD | E000 | 00E1 | E000PSOLD00E1
1503 | 1503 | 1503 | 1503 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection Switching One-Line Diagram Submission | 2 | PSOLD | E000 | 00E2 | E000PSOLD00E2
1504 | 1504 | 1504 | 1504 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection Switching One-Line Diagram Review / Evaluation | 3 | PSOLD | E000 | 00E3 | E000PSOLD00E3
1505 | 1505 | 1505 | 1505 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection Switching One-Line Diagram Approval with Comments | 4 | PSOLD | E000 | 00E4 | E000PSOLD00E4
1506 | 1506 | 1506 | 1506 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection Switching One-Line Diagram FINAL Approval | 5 | PSOLD | E000 | 00E5 | E000PSOLD00E5
1507 | 1507 | 1507 | 1507 | SA24M005 | Relaying and Metering One-Line Diagram |  | 6 | -1 | 0 |  |  | X
1508 | 1508 | 1508 | 1508 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection Relaying and Metering One-Line Diagram Drafting / Preparation | 1 | PRLGM | E000 | 00E1 | E000PRLGM00E1
1509 | 1509 | 1509 | 1509 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection Relaying and Metering One-Line Diagram Submission | 2 | PRLGM | E000 | 00E2 | E000PRLGM00E2
1510 | 1510 | 1510 | 1510 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection Relaying and Metering One-Line Diagram Review / Evaluation | 3 | PRLGM | E000 | 00E3 | E000PRLGM00E3
1511 | 1511 | 1511 | 1511 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection Relaying and Metering One-Line Diagram Approval with Comments | 4 | PRLGM | E000 | 00E4 | E000PRLGM00E4
1512 | 1512 | 1512 | 1512 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection Relaying and Metering One-Line Diagram FINAL Approval | 5 | PRLGM | E000 | 00E5 | E000PRLGM00E5
1513 | 1513 | 1513 | 1513 | SA24M005 | Panel Wiring Diagrams for Relay & Fault Recorder |  | 6 | -1 | 0 |  |  | X
1514 | 1514 | 1514 | 1514 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection Panel Wiring Diagrams for Relay & Fault Recorder Drafting / Preparation | 1 | PWDPF | E000 | 00E1 | E000PWDPF00E1
1515 | 1515 | 1515 | 1515 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection Panel Wiring Diagrams for Relay & Fault Recorder Submission | 2 | PWDPF | E000 | 00E2 | E000PWDPF00E2
1516 | 1516 | 1516 | 1516 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection Panel Wiring Diagrams for Relay & Fault Recorder Review / Evaluation | 3 | PWDPF | E000 | 00E3 | E000PWDPF00E3
1517 | 1517 | 1517 | 1517 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection Panel Wiring Diagrams for Relay & Fault Recorder Approval with Comments | 4 | PWDPF | E000 | 00E4 | E000PWDPF00E4
1518 | 1518 | 1518 | 1518 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection Panel Wiring Diagrams for Relay & Fault Recorder FINAL Approval | 5 | PWDPF | E000 | 00E5 | E000PWDPF00E5
1519 | 1519 | 1519 | 1519 | SA24M005 | Interlocking scheme |  | 6 | -1 | 0 |  |  | X
1520 | 1520 | 1520 | 1520 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection Interlocking scheme Drafting / Preparation | 1 | PINTL | E000 | 00E1 | E000PINTL00E1
1521 | 1521 | 1521 | 1521 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection Interlocking scheme Submission | 2 | PINTL | E000 | 00E2 | E000PINTL00E2
1522 | 1522 | 1522 | 1522 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection Interlocking scheme Review / Evaluation | 3 | PINTL | E000 | 00E3 | E000PINTL00E3
1523 | 1523 | 1523 | 1523 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection Interlocking scheme Approval with Comments | 4 | PINTL | E000 | 00E4 | E000PINTL00E4
1524 | 1524 | 1524 | 1524 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection Interlocking scheme FINAL Approval | 5 | PINTL | E000 | 00E5 | E000PINTL00E5
1525 | 1525 | 1525 | 1525 | SA24M005 | 380kV Under Ground Cable Protection Without Shunt Reactor. |  | 6 | -1 | 0 |  |  | X
1526 | 1526 | 1526 | 1526 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection 380kV Under Ground Cable Protection Without Shunt Reactor. Drafting / Preparation | 1 | 0UCPSR | E000 | 00E1 | E0000UCPSR00E1
1527 | 1527 | 1527 | 1527 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection 380kV Under Ground Cable Protection Without Shunt Reactor. Submission | 2 | 0UCPSR | E000 | 00E2 | E0000UCPSR00E2
1528 | 1528 | 1528 | 1528 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection 380kV Under Ground Cable Protection Without Shunt Reactor. Review / Evaluation | 3 | 0UCPSR | E000 | 00E3 | E0000UCPSR00E3
1529 | 1529 | 1529 | 1529 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection 380kV Under Ground Cable Protection Without Shunt Reactor. Approval with Comments | 4 | 0UCPSR | E000 | 00E4 | E0000UCPSR00E4
1530 | 1530 | 1530 | 1530 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection 380kV Under Ground Cable Protection Without Shunt Reactor. FINAL Approval | 5 | 0UCPSR | E000 | 00E5 | E0000UCPSR00E5
1531 | 1531 | 1531 | 1531 | SA24M005 | 380kV OHL Protection without Shunt Reactor |  | 6 | -1 | 0 |  |  | X
1532 | 1532 | 1532 | 1532 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection 380kV OHL Protection without Shunt Reactor Drafting / Preparation | 1 | POWSR | E000 | 00E1 | E000POWSR00E1
1533 | 1533 | 1533 | 1533 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection 380kV OHL Protection without Shunt Reactor Submission | 2 | POWSR | E000 | 00E2 | E000POWSR00E2
1534 | 1534 | 1534 | 1534 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection 380kV OHL Protection without Shunt Reactor Review / Evaluation | 3 | POWSR | E000 | 00E3 | E000POWSR00E3
1535 | 1535 | 1535 | 1535 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection 380kV OHL Protection without Shunt Reactor Approval with Comments | 4 | POWSR | E000 | 00E4 | E000POWSR00E4
1536 | 1536 | 1536 | 1536 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection 380kV OHL Protection without Shunt Reactor FINAL Approval | 5 | POWSR | E000 | 00E5 | E000POWSR00E5
1537 | 1537 | 1537 | 1537 | SA24M005 | 380kV OHL Protection with Shunt Reactor |  | 6 | -1 | 0 |  |  | X
1538 | 1538 | 1538 | 1538 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection 380kV OHL Protection with Shunt Reactor Drafting / Preparation | 1 | POHLSR | E000 | 00E1 | E000POHLSR00E1
1539 | 1539 | 1539 | 1539 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection 380kV OHL Protection with Shunt Reactor Submission | 2 | POHLSR | E000 | 00E2 | E000POHLSR00E2
1540 | 1540 | 1540 | 1540 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection 380kV OHL Protection with Shunt Reactor Review / Evaluation | 3 | POHLSR | E000 | 00E3 | E000POHLSR00E3
1541 | 1541 | 1541 | 1541 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection 380kV OHL Protection with Shunt Reactor Approval with Comments | 4 | POHLSR | E000 | 00E4 | E000POHLSR00E4
1542 | 1542 | 1542 | 1542 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection 380kV OHL Protection with Shunt Reactor FINAL Approval | 5 | POHLSR | E000 | 00E5 | E000POHLSR00E5
1543 | 1543 | 1543 | 1543 | SA24M005 | 380kV Bus Shunt Reactor . |  | 6 | -1 | 0 |  |  | X
1544 | 1544 | 1544 | 1544 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection 380kV Bus Shunt Reactor . Drafting / Preparation | 1 | 00BSR | E000 | 00E1 | E00000BSR00E1
1545 | 1545 | 1545 | 1545 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection 380kV Bus Shunt Reactor . Submission | 2 | 00BSR | E000 | 00E2 | E00000BSR00E2
1546 | 1546 | 1546 | 1546 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection 380kV Bus Shunt Reactor . Review / Evaluation | 3 | 00BSR | E000 | 00E3 | E00000BSR00E3
1547 | 1547 | 1547 | 1547 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection 380kV Bus Shunt Reactor . Approval with Comments | 4 | 00BSR | E000 | 00E4 | E00000BSR00E4
1548 | 1548 | 1548 | 1548 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection 380kV Bus Shunt Reactor . FINAL Approval | 5 | 00BSR | E000 | 00E5 | E00000BSR00E5
1549 | 1549 | 1549 | 1549 | SA24M005 | 380 kV Circuit Breaker Fail Protection. |  | 6 | -1 | 0 |  |  | X
1550 | 1550 | 1550 | 1550 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection 380 kV Circuit Breaker Fail Protection. Drafting / Preparation | 1 | PCBRF | E000 | 00E1 | E000PCBRF00E1
1551 | 1551 | 1551 | 1551 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection 380 kV Circuit Breaker Fail Protection. Submission | 2 | PCBRF | E000 | 00E2 | E000PCBRF00E2
1552 | 1552 | 1552 | 1552 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection 380 kV Circuit Breaker Fail Protection. Review / Evaluation | 3 | PCBRF | E000 | 00E3 | E000PCBRF00E3
1553 | 1553 | 1553 | 1553 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection 380 kV Circuit Breaker Fail Protection. Approval with Comments | 4 | PCBRF | E000 | 00E4 | E000PCBRF00E4
1554 | 1554 | 1554 | 1554 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection 380 kV Circuit Breaker Fail Protection. FINAL Approval | 5 | PCBRF | E000 | 00E5 | E000PCBRF00E5
1555 | 1555 | 1555 | 1555 | SA24M005 | 380 kV Bus Bar Protection. |  | 6 | -1 | 0 |  |  | X
1556 | 1556 | 1556 | 1556 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection 380 kV Bus Bar Protection. Drafting / Preparation | 1 | 0BBAR | E000 | 00E1 | E0000BBAR00E1
1557 | 1557 | 1557 | 1557 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection 380 kV Bus Bar Protection. Submission | 2 | 0BBAR | E000 | 00E2 | E0000BBAR00E2
1558 | 1558 | 1558 | 1558 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection 380 kV Bus Bar Protection. Review / Evaluation | 3 | 0BBAR | E000 | 00E3 | E0000BBAR00E3
1559 | 1559 | 1559 | 1559 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection 380 kV Bus Bar Protection. Approval with Comments | 4 | 0BBAR | E000 | 00E4 | E0000BBAR00E4
1560 | 1560 | 1560 | 1560 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection 380 kV Bus Bar Protection. FINAL Approval | 5 | 0BBAR | E000 | 00E5 | E0000BBAR00E5
1561 | 1561 | 1561 | 1561 | SA24M005 | 13.8kV, Bus Bar Protection. |  | 6 | -1 | 0 |  |  | X
1562 | 1562 | 1562 | 1562 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection 13.8kV, Bus Bar Protection. Drafting / Preparation | 1 | 0BBRP | E000 | 00E1 | E0000BBRP00E1
1563 | 1563 | 1563 | 1563 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection 13.8kV, Bus Bar Protection. Submission | 2 | 0BBRP | E000 | 00E2 | E0000BBRP00E2
1564 | 1564 | 1564 | 1564 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection 13.8kV, Bus Bar Protection. Review / Evaluation | 3 | 0BBRP | E000 | 00E3 | E0000BBRP00E3
1565 | 1565 | 1565 | 1565 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection 13.8kV, Bus Bar Protection. Approval with Comments | 4 | 0BBRP | E000 | 00E4 | E0000BBRP00E4
1566 | 1566 | 1566 | 1566 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection 13.8kV, Bus Bar Protection. FINAL Approval | 5 | 0BBRP | E000 | 00E5 | E0000BBRP00E5
1567 | 1567 | 1567 | 1567 | SA24M005 | 13.8kV, 7MVAR Shunt Capacitor Bank Protection |  | 6 | -1 | 0 |  |  | X
1568 | 1568 | 1568 | 1568 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection 13.8kV, 7MVAR Shunt Capacitor Bank Protection Drafting / Preparation | 1 | 0SHCB | E000 | 00E1 | E0000SHCB00E1
1569 | 1569 | 1569 | 1569 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection 13.8kV, 7MVAR Shunt Capacitor Bank Protection Submission | 2 | 0SHCB | E000 | 00E2 | E0000SHCB00E2
1570 | 1570 | 1570 | 1570 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection 13.8kV, 7MVAR Shunt Capacitor Bank Protection Review / Evaluation | 3 | 0SHCB | E000 | 00E3 | E0000SHCB00E3
1571 | 1571 | 1571 | 1571 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection 13.8kV, 7MVAR Shunt Capacitor Bank Protection Approval with Comments | 4 | 0SHCB | E000 | 00E4 | E0000SHCB00E4
1572 | 1572 | 1572 | 1572 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection 13.8kV, 7MVAR Shunt Capacitor Bank Protection FINAL Approval | 5 | 0SHCB | E000 | 00E5 | E0000SHCB00E5
1573 | 1573 | 1573 | 1573 | SA24M005 | 13.8 kV Feeder Protection. |  | 6 | -1 | 0 |  |  | X
1574 | 1574 | 1574 | 1574 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection 13.8 kV Feeder Protection. Drafting / Preparation | 1 | PFDR | E000 | 00E1 | E000PFDR00E1
1575 | 1575 | 1575 | 1575 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection 13.8 kV Feeder Protection. Submission | 2 | PFDR | E000 | 00E2 | E000PFDR00E2
1576 | 1576 | 1576 | 1576 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection 13.8 kV Feeder Protection. Review / Evaluation | 3 | PFDR | E000 | 00E3 | E000PFDR00E3
1577 | 1577 | 1577 | 1577 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection 13.8 kV Feeder Protection. Approval with Comments | 4 | PFDR | E000 | 00E4 | E000PFDR00E4
1578 | 1578 | 1578 | 1578 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Protection 13.8 kV Feeder Protection. FINAL Approval | 5 | PFDR | E000 | 00E5 | E000PFDR00E5
1579 | 1579 | 1579 | 1579 | SA24M005 | SAS |  | 5 | -1 | 0 |  |  | X
1580 | 1580 | 1580 | 1580 | SA24M005 | SAS (REFERENCE DESIGN PACKAGE FOR FAT WITNESSING INSPECTORS) |  | 6 | -1 | 0 |  |  | X
1581 | 1581 | 1581 | 1581 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV SAS SAS (REFERENCE DESIGN PACKAGE FOR FAT WITNESSING INSPECTORS) Drafting / Preparation | 1 | 0SAS | E000 | 00E1 | E000#WuXP00E1
1582 | 1582 | 1582 | 1582 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV SAS SAS (REFERENCE DESIGN PACKAGE FOR FAT WITNESSING INSPECTORS) Submission | 2 | 0SAS | E000 | 00E2 | E000#WuXP00E2
1583 | 1583 | 1583 | 1583 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV SAS SAS (REFERENCE DESIGN PACKAGE FOR FAT WITNESSING INSPECTORS) Review / Evaluation | 3 | 0SAS | E000 | 00E3 | E000#WuXP00E3
1584 | 1584 | 1584 | 1584 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV SAS SAS (REFERENCE DESIGN PACKAGE FOR FAT WITNESSING INSPECTORS) Approval with Comments | 4 | 0SAS | E000 | 00E4 | E000#WuXP00E4
1585 | 1585 | 1585 | 1585 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV SAS SAS (REFERENCE DESIGN PACKAGE FOR FAT WITNESSING INSPECTORS) FINAL Approval | 5 | 0SAS | E000 | 00E5 | E000#WuXP00E5
1586 | 1586 | 1586 | 1586 | SA24M005 | FOC, CABINETS AND ACCESSORIES FOR SAS SYSTEM |  | 6 | -1 | 0 |  |  | X | E000#WuXP
1587 | 1587 | 1587 | 1587 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV SAS FOC, CABINETS AND ACCESSORIES FOR SAS SYSTEM Drafting / Preparation | 1 | FSAS | E000 | 00E1 | E000#REhu00E1
1588 | 1588 | 1588 | 1588 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV SAS FOC, CABINETS AND ACCESSORIES FOR SAS SYSTEM Submission | 2 | FSAS | E000 | 00E2 | E000#REhu00E2
1589 | 1589 | 1589 | 1589 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV SAS FOC, CABINETS AND ACCESSORIES FOR SAS SYSTEM Review / Evaluation | 3 | FSAS | E000 | 00E3 | E000#REhu00E3
1590 | 1590 | 1590 | 1590 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV SAS FOC, CABINETS AND ACCESSORIES FOR SAS SYSTEM Approval with Comments | 4 | FSAS | E000 | 00E4 | E000#REhu00E4
1591 | 1591 | 1591 | 1591 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV SAS FOC, CABINETS AND ACCESSORIES FOR SAS SYSTEM FINAL Approval | 5 | FSAS | E000 | 00E5 | E000#REhu00E5
1592 | 1592 | 1592 | 1592 | SA24M005 | SAS MAINTENANCE LAPTOP |  | 6 | -1 | 0 |  |  | X | E000#REhu
1593 | 1593 | 1593 | 1593 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV SAS SAS MAINTENANCE LAPTOP Drafting / Preparation | 1 | 0SASL | E000 | 00E1 | E0000SASL00E1
1594 | 1594 | 1594 | 1594 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV SAS SAS MAINTENANCE LAPTOP Submission | 2 | 0SASL | E000 | 00E2 | E0000SASL00E2
1595 | 1595 | 1595 | 1595 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV SAS SAS MAINTENANCE LAPTOP Review / Evaluation | 3 | 0SASL | E000 | 00E3 | E0000SASL00E3
1596 | 1596 | 1596 | 1596 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV SAS SAS MAINTENANCE LAPTOP Approval with Comments | 4 | 0SASL | E000 | 00E4 | E0000SASL00E4
1597 | 1597 | 1597 | 1597 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV SAS SAS MAINTENANCE LAPTOP FINAL Approval | 5 | 0SASL | E000 | 00E5 | E0000SASL00E5
1598 | 1598 | 1598 | 1598 | SA24M005 | SAS Integration/Interfacing with power generation plant |  | 6 | -1 | 0 |  |  | X
1599 | 1599 | 1599 | 1599 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV SAS SAS Integration/Interfacing with power generation plant Drafting / Preparation | 1 | PSAS | E000 | 00E1 | E000#aurt00E1
1600 | 1600 | 1600 | 1600 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV SAS SAS Integration/Interfacing with power generation plant Submission | 2 | PSAS | E000 | 00E2 | E000#aurt00E2
1601 | 1601 | 1601 | 1601 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV SAS SAS Integration/Interfacing with power generation plant Review / Evaluation | 3 | PSAS | E000 | 00E3 | E000#aurt00E3
1602 | 1602 | 1602 | 1602 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV SAS SAS Integration/Interfacing with power generation plant Approval with Comments | 4 | PSAS | E000 | 00E4 | E000#aurt00E4
1603 | 1603 | 1603 | 1603 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV SAS SAS Integration/Interfacing with power generation plant FINAL Approval | 5 | PSAS | E000 | 00E5 | E000#aurt00E5
1604 | 1604 | 1604 | 1604 | SA24M005 | SCADA Integration/Interfacing with power generation plant |  | 6 | -1 | 0 |  |  | X | E000#aurt
1605 | 1605 | 1605 | 1605 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV SAS SCADA Integration/Interfacing with power generation plant Drafting / Preparation | 1 | SCADA | E000 | 00E1 | E000#PXpl00E1
1606 | 1606 | 1606 | 1606 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV SAS SCADA Integration/Interfacing with power generation plant Submission | 2 | SCADA | E000 | 00E2 | E000#PXpl00E2
1607 | 1607 | 1607 | 1607 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV SAS SCADA Integration/Interfacing with power generation plant Review / Evaluation | 3 | SCADA | E000 | 00E3 | E000#PXpl00E3
1608 | 1608 | 1608 | 1608 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV SAS SCADA Integration/Interfacing with power generation plant Approval with Comments | 4 | SCADA | E000 | 00E4 | E000#PXpl00E4
1609 | 1609 | 1609 | 1609 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV SAS SCADA Integration/Interfacing with power generation plant FINAL Approval | 5 | SCADA | E000 | 00E5 | E000#PXpl00E5
1610 | 1610 | 1610 | 1610 | SA24M005 | NEW DSM |  | 6 | -1 | 0 |  |  | X | E000#PXpl
1611 | 1611 | 1611 | 1611 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV SAS NEW DSM Drafting / Preparation | 1 | NSDSM | E000 | 00E1 | E000#YEeU00E1
1612 | 1612 | 1612 | 1612 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV SAS NEW DSM Submission | 2 | NSDSM | E000 | 00E2 | E000#YEeU00E2
1613 | 1613 | 1613 | 1613 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV SAS NEW DSM Review / Evaluation | 3 | NSDSM | E000 | 00E3 | E000#YEeU00E3
1614 | 1614 | 1614 | 1614 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV SAS NEW DSM Approval with Comments | 4 | NSDSM | E000 | 00E4 | E000#YEeU00E4
1615 | 1615 | 1615 | 1615 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV SAS NEW DSM FINAL Approval | 5 | NSDSM | E000 | 00E5 | E000#YEeU00E5
1616 | 1616 | 1616 | 1616 | SA24M005 | Telecom |  | 5 | -1 | 0 |  |  | X | E000#YEeU
1617 | 1617 | 1617 | 1617 | SA24M005 | PDS SYSTEM OSP/ISP |  | 6 | -1 | 0 |  |  | X | E000#YEeU
1618 | 1618 | 1618 | 1618 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom PDS SYSTEM OSP/ISP Drafting / Preparation | 1 | PDSTR | E000 | 00E1 | E000PDSTR00E1
1619 | 1619 | 1619 | 1619 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom PDS SYSTEM OSP/ISP Submission | 2 | PDSTR | E000 | 00E2 | E000PDSTR00E2
1620 | 1620 | 1620 | 1620 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom PDS SYSTEM OSP/ISP Review / Evaluation | 3 | PDSTR | E000 | 00E3 | E000PDSTR00E3
1621 | 1621 | 1621 | 1621 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom PDS SYSTEM OSP/ISP Approval with Comments | 4 | PDSTR | E000 | 00E4 | E000PDSTR00E4
1622 | 1622 | 1622 | 1622 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom PDS SYSTEM OSP/ISP FINAL Approval | 5 | PDSTR | E000 | 00E5 | E000PDSTR00E5
1623 | 1623 | 1623 | 1623 | SA24M005 | TELECOM CABINET/DATA CABINET/OFMR/MDF |  | 6 | -1 | 0 |  |  | X
1624 | 1624 | 1624 | 1624 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom TELECOM CABINET/DATA CABINET/OFMR/MDF Drafting / Preparation | 1 | TCAB | E000 | 00E1 | E000#Troo00E1
1625 | 1625 | 1625 | 1625 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom TELECOM CABINET/DATA CABINET/OFMR/MDF Submission | 2 | TCAB | E000 | 00E2 | E000#Troo00E2
1626 | 1626 | 1626 | 1626 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom TELECOM CABINET/DATA CABINET/OFMR/MDF Review / Evaluation | 3 | TCAB | E000 | 00E3 | E000#Troo00E3
1627 | 1627 | 1627 | 1627 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom TELECOM CABINET/DATA CABINET/OFMR/MDF Approval with Comments | 4 | TCAB | E000 | 00E4 | E000#Troo00E4
1628 | 1628 | 1628 | 1628 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom TELECOM CABINET/DATA CABINET/OFMR/MDF FINAL Approval | 5 | TCAB | E000 | 00E5 | E000#Troo00E5
1629 | 1629 | 1629 | 1629 | SA24M005 | COMMUNICATION (DUCT BANK / MANHOLE / HANDHOLE / CONDUIT) |  | 6 | -1 | 0 |  |  | X | E000#Troo
1630 | 1630 | 1630 | 1630 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom COMMUNICATION (DUCT BANK / MANHOLE / HANDHOLE / CONDUIT) Drafting / Preparation | 1 | COMDB | E000 | 00E1 | E000COMDB00E1
1631 | 1631 | 1631 | 1631 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom COMMUNICATION (DUCT BANK / MANHOLE / HANDHOLE / CONDUIT) Submission | 2 | COMDB | E000 | 00E2 | E000COMDB00E2
1632 | 1632 | 1632 | 1632 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom COMMUNICATION (DUCT BANK / MANHOLE / HANDHOLE / CONDUIT) Review / Evaluation | 3 | COMDB | E000 | 00E3 | E000COMDB00E3
1633 | 1633 | 1633 | 1633 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom COMMUNICATION (DUCT BANK / MANHOLE / HANDHOLE / CONDUIT) Approval with Comments | 4 | COMDB | E000 | 00E4 | E000COMDB00E4
1634 | 1634 | 1634 | 1634 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom COMMUNICATION (DUCT BANK / MANHOLE / HANDHOLE / CONDUIT) FINAL Approval | 5 | COMDB | E000 | 00E5 | E000COMDB00E5
1635 | 1635 | 1635 | 1635 | SA24M005 | MPLS-TP |  | 6 | -1 | 0 |  |  | X
1636 | 1636 | 1636 | 1636 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom MPLS-TP Drafting / Preparation | 1 | MPLS-TP | E000 | 00E1 | E000#XnTF00E1
1637 | 1637 | 1637 | 1637 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom MPLS-TP Submission | 2 | MPLS-TP | E000 | 00E2 | E000#XnTF00E2
1638 | 1638 | 1638 | 1638 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom MPLS-TP Review / Evaluation | 3 | MPLS-TP | E000 | 00E3 | E000#XnTF00E3
1639 | 1639 | 1639 | 1639 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom MPLS-TP Approval with Comments | 4 | MPLS-TP | E000 | 00E4 | E000#XnTF00E4
1640 | 1640 | 1640 | 1640 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom MPLS-TP FINAL Approval | 5 | MPLS-TP | E000 | 00E5 | E000#XnTF00E5
1641 | 1641 | 1641 | 1641 | SA24M005 | DXC & DVM FIBER OPTIC COMMUNICATION SYSTEM EQUIPMENT |  | 6 | -1 | 0 |  |  | X | E000#XnTF
1642 | 1642 | 1642 | 1642 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom DXC & DVM FIBER OPTIC COMMUNICATION SYSTEM EQUIPMENT Drafting / Preparation | 1 | TDXC | E000 | 00E1 | E000#pylY00E1
1643 | 1643 | 1643 | 1643 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom DXC & DVM FIBER OPTIC COMMUNICATION SYSTEM EQUIPMENT Submission | 2 | TDXC | E000 | 00E2 | E000#pylY00E2
1644 | 1644 | 1644 | 1644 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom DXC & DVM FIBER OPTIC COMMUNICATION SYSTEM EQUIPMENT Review / Evaluation | 3 | TDXC | E000 | 00E3 | E000#pylY00E3
1645 | 1645 | 1645 | 1645 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom DXC & DVM FIBER OPTIC COMMUNICATION SYSTEM EQUIPMENT Approval with Comments | 4 | TDXC | E000 | 00E4 | E000#pylY00E4
1646 | 1646 | 1646 | 1646 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom DXC & DVM FIBER OPTIC COMMUNICATION SYSTEM EQUIPMENT FINAL Approval | 5 | TDXC | E000 | 00E5 | E000#pylY00E5
1647 | 1647 | 1647 | 1647 | SA24M005 | COMMUNICATION-GRADE DC POWER SYSTEM AND GROUNDING SYSTEM |  | 6 | -1 | 0 |  |  | X | E000#pylY
1648 | 1648 | 1648 | 1648 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom COMMUNICATION-GRADE DC POWER SYSTEM AND GROUNDING SYSTEM Drafting / Preparation | 1 | COMMDC | E000 | 00E1 | E000#jmUw00E1
1649 | 1649 | 1649 | 1649 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom COMMUNICATION-GRADE DC POWER SYSTEM AND GROUNDING SYSTEM Submission | 2 | COMMDC | E000 | 00E2 | E000#jmUw00E2
1650 | 1650 | 1650 | 1650 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom COMMUNICATION-GRADE DC POWER SYSTEM AND GROUNDING SYSTEM Review / Evaluation | 3 | COMMDC | E000 | 00E3 | E000#jmUw00E3
1651 | 1651 | 1651 | 1651 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom COMMUNICATION-GRADE DC POWER SYSTEM AND GROUNDING SYSTEM Approval with Comments | 4 | COMMDC | E000 | 00E4 | E000#jmUw00E4
1652 | 1652 | 1652 | 1652 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom COMMUNICATION-GRADE DC POWER SYSTEM AND GROUNDING SYSTEM FINAL Approval | 5 | COMMDC | E000 | 00E5 | E000#jmUw00E5
1653 | 1653 | 1653 | 1653 | SA24M005 | SPLICE CLOSURE/JOINT BOX |  | 6 | -1 | 0 |  |  | X | E000#jmUw
1654 | 1654 | 1654 | 1654 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom SPLICE CLOSURE/JOINT BOX Drafting / Preparation | 1 | SPLICE CLOSURE/JOINT BOX | E000 | 00E1 | E000SPLICE CLOSURE/JOINT BOX00E1
1655 | 1655 | 1655 | 1655 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom SPLICE CLOSURE/JOINT BOX Submission | 2 | SPLICE CLOSURE/JOINT BOX | E000 | 00E2 | E000SPLICE CLOSURE/JOINT BOX00E2
1656 | 1656 | 1656 | 1656 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom SPLICE CLOSURE/JOINT BOX Review / Evaluation | 3 | SPLICE CLOSURE/JOINT BOX | E000 | 00E3 | E000SPLICE CLOSURE/JOINT BOX00E3
1657 | 1657 | 1657 | 1657 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom SPLICE CLOSURE/JOINT BOX Approval with Comments | 4 | SPLICE CLOSURE/JOINT BOX | E000 | 00E4 | E000SPLICE CLOSURE/JOINT BOX00E4
1658 | 1658 | 1658 | 1658 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom SPLICE CLOSURE/JOINT BOX FINAL Approval | 5 | SPLICE CLOSURE/JOINT BOX | E000 | 00E5 | E000SPLICE CLOSURE/JOINT BOX00E5
1659 | 1659 | 1659 | 1659 | SA24M005 | AMI (COMMUNICATION PORTION ONLY) |  | 6 | -1 | 0 |  |  | X
1660 | 1660 | 1660 | 1660 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom AMI (COMMUNICATION PORTION ONLY) Drafting / Preparation | 1 | TAMI | E000 | 00E1 | E000#KIJz00E1
1661 | 1661 | 1661 | 1661 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom AMI (COMMUNICATION PORTION ONLY) Submission | 2 | TAMI | E000 | 00E2 | E000#KIJz00E2
1662 | 1662 | 1662 | 1662 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom AMI (COMMUNICATION PORTION ONLY) Review / Evaluation | 3 | TAMI | E000 | 00E3 | E000#KIJz00E3
1663 | 1663 | 1663 | 1663 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom AMI (COMMUNICATION PORTION ONLY) Approval with Comments | 4 | TAMI | E000 | 00E4 | E000#KIJz00E4
1664 | 1664 | 1664 | 1664 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom AMI (COMMUNICATION PORTION ONLY) FINAL Approval | 5 | TAMI | E000 | 00E5 | E000#KIJz00E5
1665 | 1665 | 1665 | 1665 | SA24M005 | BATTERY CHARGER AND BATTERY BANK FOR COMMUNICATION |  | 6 | -1 | 0 |  |  | X | E000#KIJz
1666 | 1666 | 1666 | 1666 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom BATTERY CHARGER AND BATTERY BANK FOR COMMUNICATION Drafting / Preparation | 1 | TBATB | E000 | 00E1 | E000#BHue00E1
1667 | 1667 | 1667 | 1667 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom BATTERY CHARGER AND BATTERY BANK FOR COMMUNICATION Submission | 2 | TBATB | E000 | 00E2 | E000#BHue00E2
1668 | 1668 | 1668 | 1668 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom BATTERY CHARGER AND BATTERY BANK FOR COMMUNICATION Review / Evaluation | 3 | TBATB | E000 | 00E3 | E000#BHue00E3
1669 | 1669 | 1669 | 1669 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom BATTERY CHARGER AND BATTERY BANK FOR COMMUNICATION Approval with Comments | 4 | TBATB | E000 | 00E4 | E000#BHue00E4
1670 | 1670 | 1670 | 1670 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom BATTERY CHARGER AND BATTERY BANK FOR COMMUNICATION FINAL Approval | 5 | TBATB | E000 | 00E5 | E000#BHue00E5
1671 | 1671 | 1671 | 1671 | SA24M005 | PABX/IP TELEPHONY SYSTEM |  | 6 | -1 | 0 |  |  | X | E000#BHue
1672 | 1672 | 1672 | 1672 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom PABX/IP TELEPHONY SYSTEM Drafting / Preparation | 1 | PTPBX | E000 | 00E1 | E000#xNgu00E1
1673 | 1673 | 1673 | 1673 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom PABX/IP TELEPHONY SYSTEM Submission | 2 | PTPBX | E000 | 00E2 | E000#xNgu00E2
1674 | 1674 | 1674 | 1674 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom PABX/IP TELEPHONY SYSTEM Review / Evaluation | 3 | PTPBX | E000 | 00E3 | E000#xNgu00E3
1675 | 1675 | 1675 | 1675 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom PABX/IP TELEPHONY SYSTEM Approval with Comments | 4 | PTPBX | E000 | 00E4 | E000#xNgu00E4
1676 | 1676 | 1676 | 1676 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom PABX/IP TELEPHONY SYSTEM FINAL Approval | 5 | PTPBX | E000 | 00E5 | E000#xNgu00E5
1677 | 1677 | 1677 | 1677 | SA24M005 | LAN/WAN SYSTEM |  | 6 | -1 | 0 |  |  | X | E000#xNgu
1678 | 1678 | 1678 | 1678 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom LAN/WAN SYSTEM Drafting / Preparation | 1 | TLANW | E000 | 00E1 | E000#kwpW00E1
1679 | 1679 | 1679 | 1679 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom LAN/WAN SYSTEM Submission | 2 | TLANW | E000 | 00E2 | E000#kwpW00E2
1680 | 1680 | 1680 | 1680 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom LAN/WAN SYSTEM Review / Evaluation | 3 | TLANW | E000 | 00E3 | E000#kwpW00E3
1681 | 1681 | 1681 | 1681 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom LAN/WAN SYSTEM Approval with Comments | 4 | TLANW | E000 | 00E4 | E000#kwpW00E4
1682 | 1682 | 1682 | 1682 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom LAN/WAN SYSTEM FINAL Approval | 5 | TLANW | E000 | 00E5 | E000#kwpW00E5
1683 | 1683 | 1683 | 1683 | SA24M005 | PROTECTION SIGNALING EQUIPMENT (PSE) |  | 6 | -1 | 0 |  |  | X | E000#kwpW
1684 | 1684 | 1684 | 1684 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom PROTECTION SIGNALING EQUIPMENT (PSE) Drafting / Preparation | 1 | PTSE | E000 | 00E1 | E000#NJNn00E1
1685 | 1685 | 1685 | 1685 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom PROTECTION SIGNALING EQUIPMENT (PSE) Submission | 2 | PTSE | E000 | 00E2 | E000#NJNn00E2
1686 | 1686 | 1686 | 1686 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom PROTECTION SIGNALING EQUIPMENT (PSE) Review / Evaluation | 3 | PTSE | E000 | 00E3 | E000#NJNn00E3
1687 | 1687 | 1687 | 1687 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom PROTECTION SIGNALING EQUIPMENT (PSE) Approval with Comments | 4 | PTSE | E000 | 00E4 | E000#NJNn00E4
1688 | 1688 | 1688 | 1688 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- IV Telecom PROTECTION SIGNALING EQUIPMENT (PSE) FINAL Approval | 5 | PTSE | E000 | 00E5 | E000#NJNn00E5
1689 | 1689 | 1689 | 1689 | SA24M005 | Phase- V |  | 4 | -1 | 0 |  |  | X | E000#NJNn
1690 | 1690 | 1690 | 1690 | SA24M005 | Electrical |  | 5 | -1 | 0 |  |  | X | E000#NJNn
1691 | 1691 | 1691 | 1691 | SA24M005 | Material submittal for EHV / HV / MV Power Cable Clamps / Cable supports |  | 6 | -1 | 0 |  |  | X | E000#NJNn
1692 | 1692 | 1692 | 1692 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical Material submittal for EHV / HV / MV Power Cable Clamps / Cable supports Drafting / Preparation | 1 | E0POWC | E000 | 00E1 | E000#YmIB00E1
1693 | 1693 | 1693 | 1693 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical Material submittal for EHV / HV / MV Power Cable Clamps / Cable supports Submission | 2 | E0POWC | E000 | 00E2 | E000#YmIB00E2
1694 | 1694 | 1694 | 1694 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical Material submittal for EHV / HV / MV Power Cable Clamps / Cable supports Review / Evaluation | 3 | E0POWC | E000 | 00E3 | E000#YmIB00E3
1695 | 1695 | 1695 | 1695 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical Material submittal for EHV / HV / MV Power Cable Clamps / Cable supports Approval with Comments | 4 | E0POWC | E000 | 00E4 | E000#YmIB00E4
1696 | 1696 | 1696 | 1696 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical Material submittal for EHV / HV / MV Power Cable Clamps / Cable supports FINAL Approval | 5 | E0POWC | E000 | 00E5 | E000#YmIB00E5
1697 | 1697 | 1697 | 1697 | SA24M005 | All Outdoor Tunnel Layout Cabling Plan & Section for Power Cables |  | 6 | -1 | 0 |  |  | X | E000#YmIB
1698 | 1698 | 1698 | 1698 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical All Outdoor Tunnel Layout Cabling Plan & Section for Power Cables Drafting / Preparation | 1 | E0TUN | E000 | 00E1 | E000E0TUN00E1
1699 | 1699 | 1699 | 1699 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical All Outdoor Tunnel Layout Cabling Plan & Section for Power Cables Submission | 2 | E0TUN | E000 | 00E2 | E000E0TUN00E2
1700 | 1700 | 1700 | 1700 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical All Outdoor Tunnel Layout Cabling Plan & Section for Power Cables Review / Evaluation | 3 | E0TUN | E000 | 00E3 | E000E0TUN00E3
1701 | 1701 | 1701 | 1701 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical All Outdoor Tunnel Layout Cabling Plan & Section for Power Cables Approval with Comments | 4 | E0TUN | E000 | 00E4 | E000E0TUN00E4
1702 | 1702 | 1702 | 1702 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical All Outdoor Tunnel Layout Cabling Plan & Section for Power Cables FINAL Approval | 5 | E0TUN | E000 | 00E5 | E000E0TUN00E5
1703 | 1703 | 1703 | 1703 | SA24M005 | All Outdoor Tunnel Layout Cabling Plan & Section for Control Cables |  | 6 | -1 | 0 |  |  | X
1704 | 1704 | 1704 | 1704 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical All Outdoor Tunnel Layout Cabling Plan & Section for Control Cables Drafting / Preparation | 1 | E0CTL | E000 | 00E1 | E000E0CTL00E1
1705 | 1705 | 1705 | 1705 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical All Outdoor Tunnel Layout Cabling Plan & Section for Control Cables Submission | 2 | E0CTL | E000 | 00E2 | E000E0CTL00E2
1706 | 1706 | 1706 | 1706 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical All Outdoor Tunnel Layout Cabling Plan & Section for Control Cables Review / Evaluation | 3 | E0CTL | E000 | 00E3 | E000E0CTL00E3
1707 | 1707 | 1707 | 1707 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical All Outdoor Tunnel Layout Cabling Plan & Section for Control Cables Approval with Comments | 4 | E0CTL | E000 | 00E4 | E000E0CTL00E4
1708 | 1708 | 1708 | 1708 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical All Outdoor Tunnel Layout Cabling Plan & Section for Control Cables FINAL Approval | 5 | E0CTL | E000 | 00E5 | E000E0CTL00E5
1709 | 1709 | 1709 | 1709 | SA24M005 | Equipment Grounding Layout for all Outdoor Cable Tunnels |  | 6 | -1 | 0 |  |  | X
1710 | 1710 | 1710 | 1710 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical Equipment Grounding Layout for all Outdoor Cable Tunnels Drafting / Preparation | 1 | EQGRND | E000 | 00E1 | E000EQGRND00E1
1711 | 1711 | 1711 | 1711 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical Equipment Grounding Layout for all Outdoor Cable Tunnels Submission | 2 | EQGRND | E000 | 00E2 | E000EQGRND00E2
1712 | 1712 | 1712 | 1712 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical Equipment Grounding Layout for all Outdoor Cable Tunnels Review / Evaluation | 3 | EQGRND | E000 | 00E3 | E000EQGRND00E3
1713 | 1713 | 1713 | 1713 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical Equipment Grounding Layout for all Outdoor Cable Tunnels Approval with Comments | 4 | EQGRND | E000 | 00E4 | E000EQGRND00E4
1714 | 1714 | 1714 | 1714 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical Equipment Grounding Layout for all Outdoor Cable Tunnels FINAL Approval | 5 | EQGRND | E000 | 00E5 | E000EQGRND00E5
1715 | 1715 | 1715 | 1715 | SA24M005 | Trench / Duct Bank / Manhole / handhole / Conduit Layout Plan details and Sections |  | 6 | -1 | 0 |  |  | X
1716 | 1716 | 1716 | 1716 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical Trench / Duct Bank / Manhole / handhole / Conduit Layout Plan details and Sections Drafting / Preparation | 1 | E0TDB | E000 | 00E1 | E000E0TDB00E1
1717 | 1717 | 1717 | 1717 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical Trench / Duct Bank / Manhole / handhole / Conduit Layout Plan details and Sections Submission | 2 | E0TDB | E000 | 00E2 | E000E0TDB00E2
1718 | 1718 | 1718 | 1718 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical Trench / Duct Bank / Manhole / handhole / Conduit Layout Plan details and Sections Review / Evaluation | 3 | E0TDB | E000 | 00E3 | E000E0TDB00E3
1719 | 1719 | 1719 | 1719 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical Trench / Duct Bank / Manhole / handhole / Conduit Layout Plan details and Sections Approval with Comments | 4 | E0TDB | E000 | 00E4 | E000E0TDB00E4
1720 | 1720 | 1720 | 1720 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical Trench / Duct Bank / Manhole / handhole / Conduit Layout Plan details and Sections FINAL Approval | 5 | E0TDB | E000 | 00E5 | E000E0TDB00E5
1721 | 1721 | 1721 | 1721 | SA24M005 | Shielding/Lightning System Design Calculations |  | 6 | -1 | 0 |  |  | X
1722 | 1722 | 1722 | 1722 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical Shielding/Lightning System Design Calculations Drafting / Preparation | 1 | E0SLS | E000 | 00E1 | E000E0SLS00E1
1723 | 1723 | 1723 | 1723 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical Shielding/Lightning System Design Calculations Submission | 2 | E0SLS | E000 | 00E2 | E000E0SLS00E2
1724 | 1724 | 1724 | 1724 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical Shielding/Lightning System Design Calculations Review / Evaluation | 3 | E0SLS | E000 | 00E3 | E000E0SLS00E3
1725 | 1725 | 1725 | 1725 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical Shielding/Lightning System Design Calculations Approval with Comments | 4 | E0SLS | E000 | 00E4 | E000E0SLS00E4
1726 | 1726 | 1726 | 1726 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical Shielding/Lightning System Design Calculations FINAL Approval | 5 | E0SLS | E000 | 00E5 | E000E0SLS00E5
1727 | 1727 | 1727 | 1727 | SA24M005 | Shielding/Lightning Layout & Details |  | 6 | -1 | 0 |  |  | X
1728 | 1728 | 1728 | 1728 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical Shielding/Lightning Layout & Details Drafting / Preparation | 1 | E0SHL | E000 | 00E1 | E000E0SHL00E1
1729 | 1729 | 1729 | 1729 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical Shielding/Lightning Layout & Details Submission | 2 | E0SHL | E000 | 00E2 | E000E0SHL00E2
1730 | 1730 | 1730 | 1730 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical Shielding/Lightning Layout & Details Review / Evaluation | 3 | E0SHL | E000 | 00E3 | E000E0SHL00E3
1731 | 1731 | 1731 | 1731 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical Shielding/Lightning Layout & Details Approval with Comments | 4 | E0SHL | E000 | 00E4 | E000E0SHL00E4
1732 | 1732 | 1732 | 1732 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical Shielding/Lightning Layout & Details FINAL Approval | 5 | E0SHL | E000 | 00E5 | E000E0SHL00E5
1733 | 1733 | 1733 | 1733 | SA24M005 | Shielding Masts, Air terminals, etc. Material submittal |  | 6 | -1 | 0 |  |  | X
1734 | 1734 | 1734 | 1734 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical Shielding Masts, Air terminals, etc. Material submittal Drafting / Preparation | 1 | E0ASM | E000 | 00E1 | E000E0ASM00E1
1735 | 1735 | 1735 | 1735 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical Shielding Masts, Air terminals, etc. Material submittal Submission | 2 | E0ASM | E000 | 00E2 | E000E0ASM00E2
1736 | 1736 | 1736 | 1736 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical Shielding Masts, Air terminals, etc. Material submittal Review / Evaluation | 3 | E0ASM | E000 | 00E3 | E000E0ASM00E3
1737 | 1737 | 1737 | 1737 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical Shielding Masts, Air terminals, etc. Material submittal Approval with Comments | 4 | E0ASM | E000 | 00E4 | E000E0ASM00E4
1738 | 1738 | 1738 | 1738 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical Shielding Masts, Air terminals, etc. Material submittal FINAL Approval | 5 | E0ASM | E000 | 00E5 | E000E0ASM00E5
1739 | 1739 | 1739 | 1739 | SA24M005 | EHV- OHTL Gantry Area Layout Plan & Sections |  | 6 | -1 | 0 |  |  | X
1740 | 1740 | 1740 | 1740 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical EHV- OHTL Gantry Area Layout Plan & Sections Drafting / Preparation | 1 | E0G0A | E000 | 00E1 | E000E0G0A00E1
1741 | 1741 | 1741 | 1741 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical EHV- OHTL Gantry Area Layout Plan & Sections Submission | 2 | E0G0A | E000 | 00E2 | E000E0G0A00E2
1742 | 1742 | 1742 | 1742 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical EHV- OHTL Gantry Area Layout Plan & Sections Review / Evaluation | 3 | E0G0A | E000 | 00E3 | E000E0G0A00E3
1743 | 1743 | 1743 | 1743 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical EHV- OHTL Gantry Area Layout Plan & Sections Approval with Comments | 4 | E0G0A | E000 | 00E4 | E000E0G0A00E4
1744 | 1744 | 1744 | 1744 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical EHV- OHTL Gantry Area Layout Plan & Sections FINAL Approval | 5 | E0G0A | E000 | 00E5 | E000E0G0A00E5
1745 | 1745 | 1745 | 1745 | SA24M005 | EHV GIB Layout |  | 6 | -1 | 0 |  |  | X
1746 | 1746 | 1746 | 1746 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical EHV GIB Layout Drafting / Preparation | 1 | E0GIB | E000 | 00E1 | E000E0GIB00E1
1747 | 1747 | 1747 | 1747 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical EHV GIB Layout Submission | 2 | E0GIB | E000 | 00E2 | E000E0GIB00E2
1748 | 1748 | 1748 | 1748 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical EHV GIB Layout Review / Evaluation | 3 | E0GIB | E000 | 00E3 | E000E0GIB00E3
1749 | 1749 | 1749 | 1749 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical EHV GIB Layout Approval with Comments | 4 | E0GIB | E000 | 00E4 | E000E0GIB00E4
1750 | 1750 | 1750 | 1750 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical EHV GIB Layout FINAL Approval | 5 | E0GIB | E000 | 00E5 | E000E0GIB00E5
1751 | 1751 | 1751 | 1751 | SA24M005 | EHV- Connector Hardware at Gantry Tower |  | 6 | -1 | 0 |  |  | X
1752 | 1752 | 1752 | 1752 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical EHV- Connector Hardware at Gantry Tower Drafting / Preparation | 1 | E0CNH | E000 | 00E1 | E000E0CNH00E1
1753 | 1753 | 1753 | 1753 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical EHV- Connector Hardware at Gantry Tower Submission | 2 | E0CNH | E000 | 00E2 | E000E0CNH00E2
1754 | 1754 | 1754 | 1754 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical EHV- Connector Hardware at Gantry Tower Review / Evaluation | 3 | E0CNH | E000 | 00E3 | E000E0CNH00E3
1755 | 1755 | 1755 | 1755 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical EHV- Connector Hardware at Gantry Tower Approval with Comments | 4 | E0CNH | E000 | 00E4 | E000E0CNH00E4
1756 | 1756 | 1756 | 1756 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical EHV- Connector Hardware at Gantry Tower FINAL Approval | 5 | E0CNH | E000 | 00E5 | E000E0CNH00E5
1757 | 1757 | 1757 | 1757 | SA24M005 | EHV- GIS/AIR Termination Design |  | 6 | -1 | 0 |  |  | X
1758 | 1758 | 1758 | 1758 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical EHV- GIS/AIR Termination Design Drafting / Preparation | 1 | E0GIS | E000 | 00E1 | E000#IBGk00E1
1759 | 1759 | 1759 | 1759 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical EHV- GIS/AIR Termination Design Submission | 2 | E0GIS | E000 | 00E2 | E000#IBGk00E2
1760 | 1760 | 1760 | 1760 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical EHV- GIS/AIR Termination Design Review / Evaluation | 3 | E0GIS | E000 | 00E3 | E000#IBGk00E3
1761 | 1761 | 1761 | 1761 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical EHV- GIS/AIR Termination Design Approval with Comments | 4 | E0GIS | E000 | 00E4 | E000#IBGk00E4
1762 | 1762 | 1762 | 1762 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical EHV- GIS/AIR Termination Design FINAL Approval | 5 | E0GIS | E000 | 00E5 | E000#IBGk00E5
1763 | 1763 | 1763 | 1763 | SA24M005 | EHV- Design of Free Standing Current Transformers |  | 6 | -1 | 0 |  |  | X | E000#IBGk
1764 | 1764 | 1764 | 1764 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical EHV- Design of Free Standing Current Transformers Drafting / Preparation | 1 | E0STRF | E000 | 00E1 | E000E0STRF00E1
1765 | 1765 | 1765 | 1765 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical EHV- Design of Free Standing Current Transformers Submission | 2 | E0STRF | E000 | 00E2 | E000E0STRF00E2
1766 | 1766 | 1766 | 1766 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical EHV- Design of Free Standing Current Transformers Review / Evaluation | 3 | E0STRF | E000 | 00E3 | E000E0STRF00E3
1767 | 1767 | 1767 | 1767 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical EHV- Design of Free Standing Current Transformers Approval with Comments | 4 | E0STRF | E000 | 00E4 | E000E0STRF00E4
1768 | 1768 | 1768 | 1768 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical EHV- Design of Free Standing Current Transformers FINAL Approval | 5 | E0STRF | E000 | 00E5 | E000E0STRF00E5
1769 | 1769 | 1769 | 1769 | SA24M005 | EHV- Design of Free Standing Voltage Transformers |  | 6 | -1 | 0 |  |  | X
1770 | 1770 | 1770 | 1770 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical EHV- Design of Free Standing Voltage Transformers Drafting / Preparation | 1 | E0FVT | E000 | 00E1 | E000E0FVT00E1
1771 | 1771 | 1771 | 1771 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical EHV- Design of Free Standing Voltage Transformers Submission | 2 | E0FVT | E000 | 00E2 | E000E0FVT00E2
1772 | 1772 | 1772 | 1772 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical EHV- Design of Free Standing Voltage Transformers Review / Evaluation | 3 | E0FVT | E000 | 00E3 | E000E0FVT00E3
1773 | 1773 | 1773 | 1773 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical EHV- Design of Free Standing Voltage Transformers Approval with Comments | 4 | E0FVT | E000 | 00E4 | E000E0FVT00E4
1774 | 1774 | 1774 | 1774 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical EHV- Design of Free Standing Voltage Transformers FINAL Approval | 5 | E0FVT | E000 | 00E5 | E000E0FVT00E5
1775 | 1775 | 1775 | 1775 | SA24M005 | EHV- Design and Material Submittal of bus bar and their supporting Structures |  | 6 | -1 | 0 |  |  | X
1776 | 1776 | 1776 | 1776 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical EHV- Design and Material Submittal of bus bar and their supporting Structures Drafting / Preparation | 1 | E0BUS | E000 | 00E1 | E000E0BUS00E1
1777 | 1777 | 1777 | 1777 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical EHV- Design and Material Submittal of bus bar and their supporting Structures Submission | 2 | E0BUS | E000 | 00E2 | E000E0BUS00E2
1778 | 1778 | 1778 | 1778 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical EHV- Design and Material Submittal of bus bar and their supporting Structures Review / Evaluation | 3 | E0BUS | E000 | 00E3 | E000E0BUS00E3
1779 | 1779 | 1779 | 1779 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical EHV- Design and Material Submittal of bus bar and their supporting Structures Approval with Comments | 4 | E0BUS | E000 | 00E4 | E000E0BUS00E4
1780 | 1780 | 1780 | 1780 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Electrical EHV- Design and Material Submittal of bus bar and their supporting Structures FINAL Approval | 5 | E0BUS | E000 | 00E5 | E000E0BUS00E5
1781 | 1781 | 1781 | 1781 | SA24M005 | Civil |  | 5 | -1 | 0 |  |  | X
1782 | 1782 | 1782 | 1782 | SA24M005 | Architectural Plan & Details for Control Building |  | 6 | -1 | 0 |  |  | X
1783 | 1783 | 1783 | 1783 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Architectural Plan & Details for Control Building Drafting / Preparation | 1 | C0CB | E000 | 00E1 | E000C0CB00E1
1784 | 1784 | 1784 | 1784 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Architectural Plan & Details for Control Building Submission | 2 | C0CB | E000 | 00E2 | E000C0CB00E2
1785 | 1785 | 1785 | 1785 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Architectural Plan & Details for Control Building Review / Evaluation | 3 | C0CB | E000 | 00E3 | E000C0CB00E3
1786 | 1786 | 1786 | 1786 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Architectural Plan & Details for Control Building Approval with Comments | 4 | C0CB | E000 | 00E4 | E000C0CB00E4
1787 | 1787 | 1787 | 1787 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Architectural Plan & Details for Control Building FINAL Approval | 5 | C0CB | E000 | 00E5 | E000C0CB00E5
1788 | 1788 | 1788 | 1788 | SA24M005 | Basement Wall Openings Reinforcement Details - Control Building |  | 6 | -1 | 0 |  |  | X
1789 | 1789 | 1789 | 1789 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Basement Wall Openings Reinforcement Details - Control Building Drafting / Preparation | 1 | CBW0 | E000 | 00E1 | E000CBW000E1
1790 | 1790 | 1790 | 1790 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Basement Wall Openings Reinforcement Details - Control Building Submission | 2 | CBW0 | E000 | 00E2 | E000CBW000E2
1791 | 1791 | 1791 | 1791 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Basement Wall Openings Reinforcement Details - Control Building Review / Evaluation | 3 | CBW0 | E000 | 00E3 | E000CBW000E3
1792 | 1792 | 1792 | 1792 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Basement Wall Openings Reinforcement Details - Control Building Approval with Comments | 4 | CBW0 | E000 | 00E4 | E000CBW000E4
1793 | 1793 | 1793 | 1793 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Basement Wall Openings Reinforcement Details - Control Building FINAL Approval | 5 | CBW0 | E000 | 00E5 | E000CBW000E5
1794 | 1794 | 1794 | 1794 | SA24M005 | Building Analysis and Design Calculations, Substructure & Column Reinforcement Details |  | 6 | -1 | 0 |  |  | X
1795 | 1795 | 1795 | 1795 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Building Analysis and Design Calculations, Substructure & Column Reinforcement Details Drafting / Preparation | 1 | CBADC | E000 | 00E1 | E000CBADC00E1
1796 | 1796 | 1796 | 1796 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Building Analysis and Design Calculations, Substructure & Column Reinforcement Details Submission | 2 | CBADC | E000 | 00E2 | E000CBADC00E2
1797 | 1797 | 1797 | 1797 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Building Analysis and Design Calculations, Substructure & Column Reinforcement Details Review / Evaluation | 3 | CBADC | E000 | 00E3 | E000CBADC00E3
1798 | 1798 | 1798 | 1798 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Building Analysis and Design Calculations, Substructure & Column Reinforcement Details Approval with Comments | 4 | CBADC | E000 | 00E4 | E000CBADC00E4
1799 | 1799 | 1799 | 1799 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Building Analysis and Design Calculations, Substructure & Column Reinforcement Details FINAL Approval | 5 | CBADC | E000 | 00E5 | E000CBADC00E5
1800 | 1800 | 1800 | 1800 | SA24M005 | Staircase Reinforcement Details Control Building |  | 6 | -1 | 0 |  |  | X
1801 | 1801 | 1801 | 1801 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Staircase Reinforcement Details Control Building Drafting / Preparation | 1 | CSTRC | E000 | 00E1 | E000#EyBy00E1
1802 | 1802 | 1802 | 1802 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Staircase Reinforcement Details Control Building Submission | 2 | CSTRC | E000 | 00E2 | E000#EyBy00E2
1803 | 1803 | 1803 | 1803 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Staircase Reinforcement Details Control Building Review / Evaluation | 3 | CSTRC | E000 | 00E3 | E000#EyBy00E3
1804 | 1804 | 1804 | 1804 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Staircase Reinforcement Details Control Building Approval with Comments | 4 | CSTRC | E000 | 00E4 | E000#EyBy00E4
1805 | 1805 | 1805 | 1805 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Staircase Reinforcement Details Control Building FINAL Approval | 5 | CSTRC | E000 | 00E5 | E000#EyBy00E5
1806 | 1806 | 1806 | 1806 | SA24M005 | Slab and Beam Framing Plan, Slab Openings and Reinforcement Details Ground Floor Control Building |  | 6 | -1 | 0 |  |  | X | E000#EyBy
1807 | 1807 | 1807 | 1807 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Slab and Beam Framing Plan, Slab Openings and Reinforcement Details Ground Floor Control Building Drafting / Preparation | 1 | CSBFR | E000 | 00E1 | E000CSBFR00E1
1808 | 1808 | 1808 | 1808 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Slab and Beam Framing Plan, Slab Openings and Reinforcement Details Ground Floor Control Building Submission | 2 | CSBFR | E000 | 00E2 | E000CSBFR00E2
1809 | 1809 | 1809 | 1809 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Slab and Beam Framing Plan, Slab Openings and Reinforcement Details Ground Floor Control Building Review / Evaluation | 3 | CSBFR | E000 | 00E3 | E000CSBFR00E3
1810 | 1810 | 1810 | 1810 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Slab and Beam Framing Plan, Slab Openings and Reinforcement Details Ground Floor Control Building Approval with Comments | 4 | CSBFR | E000 | 00E4 | E000CSBFR00E4
1811 | 1811 | 1811 | 1811 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Slab and Beam Framing Plan, Slab Openings and Reinforcement Details Ground Floor Control Building FINAL Approval | 5 | CSBFR | E000 | 00E5 | E000CSBFR00E5
1812 | 1812 | 1812 | 1812 | SA24M005 | Slab and Beam Framing Plan, Slab Openings and Reinforcement Details Intermediate / First Floor Contr |  | 6 | -1 | 0 |  |  | X
1813 | 1813 | 1813 | 1813 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Slab and Beam Framing Plan, Slab Openings and Reinforcement Details Intermediate / First Floor Contr Drafting / Preparation | 1 | CSBFR01F | E000 | 00E1 | E000CSBFR01F00E1
1814 | 1814 | 1814 | 1814 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Slab and Beam Framing Plan, Slab Openings and Reinforcement Details Intermediate / First Floor Contr Submission | 2 | CSBFR01F | E000 | 00E2 | E000CSBFR01F00E2
1815 | 1815 | 1815 | 1815 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Slab and Beam Framing Plan, Slab Openings and Reinforcement Details Intermediate / First Floor Contr Review / Evaluation | 3 | CSBFR01F | E000 | 00E3 | E000CSBFR01F00E3
1816 | 1816 | 1816 | 1816 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Slab and Beam Framing Plan, Slab Openings and Reinforcement Details Intermediate / First Floor Contr Approval with Comments | 4 | CSBFR01F | E000 | 00E4 | E000CSBFR01F00E4
1817 | 1817 | 1817 | 1817 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Slab and Beam Framing Plan, Slab Openings and Reinforcement Details Intermediate / First Floor Contr FINAL Approval | 5 | CSBFR01F | E000 | 00E5 | E000CSBFR01F00E5
1818 | 1818 | 1818 | 1818 | SA24M005 | Steps, Ramps, Walkways & Loading Platforms Layout & Details - Control Building |  | 6 | -1 | 0 |  |  | X
1819 | 1819 | 1819 | 1819 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Steps, Ramps, Walkways & Loading Platforms Layout & Details - Control Building Drafting / Preparation | 1 | CSTRW | E000 | 00E1 | E000CSTRW00E1
1820 | 1820 | 1820 | 1820 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Steps, Ramps, Walkways & Loading Platforms Layout & Details - Control Building Submission | 2 | CSTRW | E000 | 00E2 | E000CSTRW00E2
1821 | 1821 | 1821 | 1821 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Steps, Ramps, Walkways & Loading Platforms Layout & Details - Control Building Review / Evaluation | 3 | CSTRW | E000 | 00E3 | E000CSTRW00E3
1822 | 1822 | 1822 | 1822 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Steps, Ramps, Walkways & Loading Platforms Layout & Details - Control Building Approval with Comments | 4 | CSTRW | E000 | 00E4 | E000CSTRW00E4
1823 | 1823 | 1823 | 1823 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Steps, Ramps, Walkways & Loading Platforms Layout & Details - Control Building FINAL Approval | 5 | CSTRW | E000 | 00E5 | E000CSTRW00E5
1824 | 1824 | 1824 | 1824 | SA24M005 | Roof Level Reinforcement Details |  | 6 | -1 | 0 |  |  | X
1825 | 1825 | 1825 | 1825 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Roof Level Reinforcement Details Drafting / Preparation | 1 | CROLR | E000 | 00E1 | E000CROLR00E1
1826 | 1826 | 1826 | 1826 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Roof Level Reinforcement Details Submission | 2 | CROLR | E000 | 00E2 | E000CROLR00E2
1827 | 1827 | 1827 | 1827 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Roof Level Reinforcement Details Review / Evaluation | 3 | CROLR | E000 | 00E3 | E000CROLR00E3
1828 | 1828 | 1828 | 1828 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Roof Level Reinforcement Details Approval with Comments | 4 | CROLR | E000 | 00E4 | E000CROLR00E4
1829 | 1829 | 1829 | 1829 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Roof Level Reinforcement Details FINAL Approval | 5 | CROLR | E000 | 00E5 | E000CROLR00E5
1830 | 1830 | 1830 | 1830 | SA24M005 | Precast Super Structure Elements Design & Details (Precast Slab) Control Building |  | 6 | -1 | 0 |  |  | X
1831 | 1831 | 1831 | 1831 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Precast Super Structure Elements Design & Details (Precast Slab) Control Building Drafting / Preparation | 1 | PCSB | E000 | 00E1 | E000PCSB00E1
1832 | 1832 | 1832 | 1832 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Precast Super Structure Elements Design & Details (Precast Slab) Control Building Submission | 2 | PCSB | E000 | 00E2 | E000PCSB00E2
1833 | 1833 | 1833 | 1833 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Precast Super Structure Elements Design & Details (Precast Slab) Control Building Review / Evaluation | 3 | PCSB | E000 | 00E3 | E000PCSB00E3
1834 | 1834 | 1834 | 1834 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Precast Super Structure Elements Design & Details (Precast Slab) Control Building Approval with Comments | 4 | PCSB | E000 | 00E4 | E000PCSB00E4
1835 | 1835 | 1835 | 1835 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Precast Super Structure Elements Design & Details (Precast Slab) Control Building FINAL Approval | 5 | PCSB | E000 | 00E5 | E000PCSB00E5
1836 | 1836 | 1836 | 1836 | SA24M005 | Raised Floor / False Ceiling Layout and Details - Control Building |  | 6 | -1 | 0 |  |  | X
1837 | 1837 | 1837 | 1837 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Raised Floor / False Ceiling Layout and Details - Control Building Drafting / Preparation | 1 | CRAISED | E000 | 00E1 | E000CRAISED00E1
1838 | 1838 | 1838 | 1838 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Raised Floor / False Ceiling Layout and Details - Control Building Submission | 2 | CRAISED | E000 | 00E2 | E000CRAISED00E2
1839 | 1839 | 1839 | 1839 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Raised Floor / False Ceiling Layout and Details - Control Building Review / Evaluation | 3 | CRAISED | E000 | 00E3 | E000CRAISED00E3
1840 | 1840 | 1840 | 1840 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Raised Floor / False Ceiling Layout and Details - Control Building Approval with Comments | 4 | CRAISED | E000 | 00E4 | E000CRAISED00E4
1841 | 1841 | 1841 | 1841 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Raised Floor / False Ceiling Layout and Details - Control Building FINAL Approval | 5 | CRAISED | E000 | 00E5 | E000CRAISED00E5
1842 | 1842 | 1842 | 1842 | SA24M005 | Control Building Access Ladder Details for Roofs |  | 6 | -1 | 0 |  |  | X
1843 | 1843 | 1843 | 1843 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Control Building Access Ladder Details for Roofs Drafting / Preparation | 1 | C0CBAL | E000 | 00E1 | E000C0CBAL00E1
1844 | 1844 | 1844 | 1844 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Control Building Access Ladder Details for Roofs Submission | 2 | C0CBAL | E000 | 00E2 | E000C0CBAL00E2
1845 | 1845 | 1845 | 1845 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Control Building Access Ladder Details for Roofs Review / Evaluation | 3 | C0CBAL | E000 | 00E3 | E000C0CBAL00E3
1846 | 1846 | 1846 | 1846 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Control Building Access Ladder Details for Roofs Approval with Comments | 4 | C0CBAL | E000 | 00E4 | E000C0CBAL00E4
1847 | 1847 | 1847 | 1847 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Control Building Access Ladder Details for Roofs FINAL Approval | 5 | C0CBAL | E000 | 00E5 | E000C0CBAL00E5
1848 | 1848 | 1848 | 1848 | SA24M005 | Design Calculations, Layout and Details of Soak Pit and Neutralization Dry Pit |  | 6 | -1 | 0 |  |  | X
1849 | 1849 | 1849 | 1849 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Design Calculations, Layout and Details of Soak Pit and Neutralization Dry Pit Drafting / Preparation | 1 | CSOAK | E000 | 00E1 | E000CSOAK00E1
1850 | 1850 | 1850 | 1850 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Design Calculations, Layout and Details of Soak Pit and Neutralization Dry Pit Submission | 2 | CSOAK | E000 | 00E2 | E000CSOAK00E2
1851 | 1851 | 1851 | 1851 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Design Calculations, Layout and Details of Soak Pit and Neutralization Dry Pit Review / Evaluation | 3 | CSOAK | E000 | 00E3 | E000CSOAK00E3
1852 | 1852 | 1852 | 1852 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Design Calculations, Layout and Details of Soak Pit and Neutralization Dry Pit Approval with Comments | 4 | CSOAK | E000 | 00E4 | E000CSOAK00E4
1853 | 1853 | 1853 | 1853 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Design Calculations, Layout and Details of Soak Pit and Neutralization Dry Pit FINAL Approval | 5 | CSOAK | E000 | 00E5 | E000CSOAK00E5
1854 | 1854 | 1854 | 1854 | SA24M005 | Design Calculations, Layout and Details of Septic Tank and Underground Water Tank |  | 6 | -1 | 0 |  |  | X
1855 | 1855 | 1855 | 1855 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Design Calculations, Layout and Details of Septic Tank and Underground Water Tank Drafting / Preparation | 1 | CSTUW | E000 | 00E1 | E000CSTUW00E1
1856 | 1856 | 1856 | 1856 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Design Calculations, Layout and Details of Septic Tank and Underground Water Tank Submission | 2 | CSTUW | E000 | 00E2 | E000CSTUW00E2
1857 | 1857 | 1857 | 1857 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Design Calculations, Layout and Details of Septic Tank and Underground Water Tank Review / Evaluation | 3 | CSTUW | E000 | 00E3 | E000CSTUW00E3
1858 | 1858 | 1858 | 1858 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Design Calculations, Layout and Details of Septic Tank and Underground Water Tank Approval with Comments | 4 | CSTUW | E000 | 00E4 | E000CSTUW00E4
1859 | 1859 | 1859 | 1859 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Design Calculations, Layout and Details of Septic Tank and Underground Water Tank FINAL Approval | 5 | CSTUW | E000 | 00E5 | E000CSTUW00E5
1860 | 1860 | 1860 | 1860 | SA24M005 | Control Room/Building- Design Calculations , Layout and Details of HVAC PACU Pad Foundations |  | 6 | -1 | 0 |  |  | X
1861 | 1861 | 1861 | 1861 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Control Room/Building- Design Calculations , Layout and Details of HVAC PACU Pad Foundations Drafting / Preparation | 1 | C0CRB | E000 | 00E1 | E000C0CRB00E1
1862 | 1862 | 1862 | 1862 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Control Room/Building- Design Calculations , Layout and Details of HVAC PACU Pad Foundations Submission | 2 | C0CRB | E000 | 00E2 | E000C0CRB00E2
1863 | 1863 | 1863 | 1863 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Control Room/Building- Design Calculations , Layout and Details of HVAC PACU Pad Foundations Review / Evaluation | 3 | C0CRB | E000 | 00E3 | E000C0CRB00E3
1864 | 1864 | 1864 | 1864 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Control Room/Building- Design Calculations , Layout and Details of HVAC PACU Pad Foundations Approval with Comments | 4 | C0CRB | E000 | 00E4 | E000C0CRB00E4
1865 | 1865 | 1865 | 1865 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Control Room/Building- Design Calculations , Layout and Details of HVAC PACU Pad Foundations FINAL Approval | 5 | C0CRB | E000 | 00E5 | E000C0CRB00E5
1866 | 1866 | 1866 | 1866 | SA24M005 | Steel Support Structure For Surge Arrestor Design Calculations & Detail Drawings |  | 6 | -1 | 0 |  |  | X
1867 | 1867 | 1867 | 1867 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Steel Support Structure For Surge Arrestor Design Calculations & Detail Drawings Drafting / Preparation | 1 | CSURG | E000 | 00E1 | E000#gmTD00E1
1868 | 1868 | 1868 | 1868 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Steel Support Structure For Surge Arrestor Design Calculations & Detail Drawings Submission | 2 | CSURG | E000 | 00E2 | E000#gmTD00E2
1869 | 1869 | 1869 | 1869 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Steel Support Structure For Surge Arrestor Design Calculations & Detail Drawings Review / Evaluation | 3 | CSURG | E000 | 00E3 | E000#gmTD00E3
1870 | 1870 | 1870 | 1870 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Steel Support Structure For Surge Arrestor Design Calculations & Detail Drawings Approval with Comments | 4 | CSURG | E000 | 00E4 | E000#gmTD00E4
1871 | 1871 | 1871 | 1871 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Steel Support Structure For Surge Arrestor Design Calculations & Detail Drawings FINAL Approval | 5 | CSURG | E000 | 00E5 | E000#gmTD00E5
1872 | 1872 | 1872 | 1872 | SA24M005 | Design Calculations And Drawings Of Surge Arrestor Foundation |  | 6 | -1 | 0 |  |  | X | E000#gmTD
1873 | 1873 | 1873 | 1873 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Design Calculations And Drawings Of Surge Arrestor Foundation Drafting / Preparation | 1 | CSURG | E000 | 00E1 | E000#CGTo00E1
1874 | 1874 | 1874 | 1874 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Design Calculations And Drawings Of Surge Arrestor Foundation Submission | 2 | CSURG | E000 | 00E2 | E000#CGTo00E2
1875 | 1875 | 1875 | 1875 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Design Calculations And Drawings Of Surge Arrestor Foundation Review / Evaluation | 3 | CSURG | E000 | 00E3 | E000#CGTo00E3
1876 | 1876 | 1876 | 1876 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Design Calculations And Drawings Of Surge Arrestor Foundation Approval with Comments | 4 | CSURG | E000 | 00E4 | E000#CGTo00E4
1877 | 1877 | 1877 | 1877 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Design Calculations And Drawings Of Surge Arrestor Foundation FINAL Approval | 5 | CSURG | E000 | 00E5 | E000#CGTo00E5
1878 | 1878 | 1878 | 1878 | SA24M005 | “CT" Steel Support Structure Design Calculations & Detail Drawings |  | 6 | -1 | 0 |  |  | X | E000#CGTo
1879 | 1879 | 1879 | 1879 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil “CT" Steel Support Structure Design Calculations & Detail Drawings Drafting / Preparation | 1 | CTSSS | E000 | 00E1 | E000#qfaE00E1
1880 | 1880 | 1880 | 1880 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil “CT" Steel Support Structure Design Calculations & Detail Drawings Submission | 2 | CTSSS | E000 | 00E2 | E000#qfaE00E2
1881 | 1881 | 1881 | 1881 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil “CT" Steel Support Structure Design Calculations & Detail Drawings Review / Evaluation | 3 | CTSSS | E000 | 00E3 | E000#qfaE00E3
1882 | 1882 | 1882 | 1882 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil “CT" Steel Support Structure Design Calculations & Detail Drawings Approval with Comments | 4 | CTSSS | E000 | 00E4 | E000#qfaE00E4
1883 | 1883 | 1883 | 1883 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil “CT" Steel Support Structure Design Calculations & Detail Drawings FINAL Approval | 5 | CTSSS | E000 | 00E5 | E000#qfaE00E5
1884 | 1884 | 1884 | 1884 | SA24M005 | Design Calculations And Drawings Of "CT" Steel Support Structure Foundation |  | 6 | -1 | 0 |  |  | X | E000#qfaE
1885 | 1885 | 1885 | 1885 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Design Calculations And Drawings Of "CT" Steel Support Structure Foundation Drafting / Preparation | 1 | CTSSS | E000 | 00E1 | E000#hsEU00E1
1886 | 1886 | 1886 | 1886 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Design Calculations And Drawings Of "CT" Steel Support Structure Foundation Submission | 2 | CTSSS | E000 | 00E2 | E000#hsEU00E2
1887 | 1887 | 1887 | 1887 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Design Calculations And Drawings Of "CT" Steel Support Structure Foundation Review / Evaluation | 3 | CTSSS | E000 | 00E3 | E000#hsEU00E3
1888 | 1888 | 1888 | 1888 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Design Calculations And Drawings Of "CT" Steel Support Structure Foundation Approval with Comments | 4 | CTSSS | E000 | 00E4 | E000#hsEU00E4
1889 | 1889 | 1889 | 1889 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Design Calculations And Drawings Of "CT" Steel Support Structure Foundation FINAL Approval | 5 | CTSSS | E000 | 00E5 | E000#hsEU00E5
1890 | 1890 | 1890 | 1890 | SA24M005 | Steel Support Structures (NGR) Drawings & Design Calculations at Reactors Area |  | 6 | -1 | 0 |  |  | X | E000#hsEU
1891 | 1891 | 1891 | 1891 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Steel Support Structures (NGR) Drawings & Design Calculations at Reactors Area Drafting / Preparation | 1 | CSTRS | E000 | 00E1 | E000CSTRS00E1
1892 | 1892 | 1892 | 1892 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Steel Support Structures (NGR) Drawings & Design Calculations at Reactors Area Submission | 2 | CSTRS | E000 | 00E2 | E000CSTRS00E2
1893 | 1893 | 1893 | 1893 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Steel Support Structures (NGR) Drawings & Design Calculations at Reactors Area Review / Evaluation | 3 | CSTRS | E000 | 00E3 | E000CSTRS00E3
1894 | 1894 | 1894 | 1894 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Steel Support Structures (NGR) Drawings & Design Calculations at Reactors Area Approval with Comments | 4 | CSTRS | E000 | 00E4 | E000CSTRS00E4
1895 | 1895 | 1895 | 1895 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Steel Support Structures (NGR) Drawings & Design Calculations at Reactors Area FINAL Approval | 5 | CSTRS | E000 | 00E5 | E000CSTRS00E5
1896 | 1896 | 1896 | 1896 | SA24M005 | Fabrication Drawings for Steel Lattice Structures. |  | 6 | -1 | 0 |  |  | X
1897 | 1897 | 1897 | 1897 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Fabrication Drawings for Steel Lattice Structures. Drafting / Preparation | 1 | C0SLS | E000 | 00E1 | E000C0SLS00E1
1898 | 1898 | 1898 | 1898 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Fabrication Drawings for Steel Lattice Structures. Submission | 2 | C0SLS | E000 | 00E2 | E000C0SLS00E2
1899 | 1899 | 1899 | 1899 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Fabrication Drawings for Steel Lattice Structures. Review / Evaluation | 3 | C0SLS | E000 | 00E3 | E000C0SLS00E3
1900 | 1900 | 1900 | 1900 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Fabrication Drawings for Steel Lattice Structures. Approval with Comments | 4 | C0SLS | E000 | 00E4 | E000C0SLS00E4
1901 | 1901 | 1901 | 1901 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Fabrication Drawings for Steel Lattice Structures. FINAL Approval | 5 | C0SLS | E000 | 00E5 | E000C0SLS00E5
1902 | 1902 | 1902 | 1902 | SA24M005 | Power Cables Steel Support drawings |  | 6 | -1 | 0 |  |  | X
1903 | 1903 | 1903 | 1903 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Power Cables Steel Support drawings Drafting / Preparation | 1 | #jiXl | E000 | 00E1 | E000#jiXl00E1
1904 | 1904 | 1904 | 1904 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Power Cables Steel Support drawings Submission | 2 | #jiXl | E000 | 00E2 | E000#jiXl00E2
1905 | 1905 | 1905 | 1905 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Power Cables Steel Support drawings Review / Evaluation | 3 | #jiXl | E000 | 00E3 | E000#jiXl00E3
1906 | 1906 | 1906 | 1906 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Power Cables Steel Support drawings Approval with Comments | 4 | #jiXl | E000 | 00E4 | E000#jiXl00E4
1907 | 1907 | 1907 | 1907 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil Power Cables Steel Support drawings FINAL Approval | 5 | #jiXl | E000 | 00E5 | E000#jiXl00E5
1908 | 1908 | 1908 | 1908 | SA24M005 | EHV Gantry- Steel Structural Gantries Drawings & Design Calculations |  | 6 | -1 | 0 |  |  | X
1909 | 1909 | 1909 | 1909 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil EHV Gantry- Steel Structural Gantries Drawings & Design Calculations Drafting / Preparation | 1 | E0GAN | E000 | 00E1 | E000#yTTN00E1
1910 | 1910 | 1910 | 1910 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil EHV Gantry- Steel Structural Gantries Drawings & Design Calculations Submission | 2 | E0GAN | E000 | 00E2 | E000#yTTN00E2
1911 | 1911 | 1911 | 1911 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil EHV Gantry- Steel Structural Gantries Drawings & Design Calculations Review / Evaluation | 3 | E0GAN | E000 | 00E3 | E000#yTTN00E3
1912 | 1912 | 1912 | 1912 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil EHV Gantry- Steel Structural Gantries Drawings & Design Calculations Approval with Comments | 4 | E0GAN | E000 | 00E4 | E000#yTTN00E4
1913 | 1913 | 1913 | 1913 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil EHV Gantry- Steel Structural Gantries Drawings & Design Calculations FINAL Approval | 5 | E0GAN | E000 | 00E5 | E000#yTTN00E5
1914 | 1914 | 1914 | 1914 | SA24M005 | EHV Gantry- Design Calculations, Layout & Details of Gantry Foundations |  | 6 | -1 | 0 |  |  | X | E000#yTTN
1915 | 1915 | 1915 | 1915 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil EHV Gantry- Design Calculations, Layout & Details of Gantry Foundations Drafting / Preparation | 1 | E0GAN | E000 | 00E1 | E000#rDUb00E1
1916 | 1916 | 1916 | 1916 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil EHV Gantry- Design Calculations, Layout & Details of Gantry Foundations Submission | 2 | E0GAN | E000 | 00E2 | E000#rDUb00E2
1917 | 1917 | 1917 | 1917 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil EHV Gantry- Design Calculations, Layout & Details of Gantry Foundations Review / Evaluation | 3 | E0GAN | E000 | 00E3 | E000#rDUb00E3
1918 | 1918 | 1918 | 1918 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil EHV Gantry- Design Calculations, Layout & Details of Gantry Foundations Approval with Comments | 4 | E0GAN | E000 | 00E4 | E000#rDUb00E4
1919 | 1919 | 1919 | 1919 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil EHV Gantry- Design Calculations, Layout & Details of Gantry Foundations FINAL Approval | 5 | E0GAN | E000 | 00E5 | E000#rDUb00E5
1920 | 1920 | 1920 | 1920 | SA24M005 | EHV Gantry- Gantry Steel Structure Fabrication / shop & erection Drawings |  | 6 | -1 | 0 |  |  | X | E000#rDUb
1921 | 1921 | 1921 | 1921 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil EHV Gantry- Gantry Steel Structure Fabrication / shop & erection Drawings Drafting / Preparation | 1 | E0GAN | E000 | 00E1 | E000#LBlV00E1
1922 | 1922 | 1922 | 1922 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil EHV Gantry- Gantry Steel Structure Fabrication / shop & erection Drawings Submission | 2 | E0GAN | E000 | 00E2 | E000#LBlV00E2
1923 | 1923 | 1923 | 1923 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil EHV Gantry- Gantry Steel Structure Fabrication / shop & erection Drawings Review / Evaluation | 3 | E0GAN | E000 | 00E3 | E000#LBlV00E3
1924 | 1924 | 1924 | 1924 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil EHV Gantry- Gantry Steel Structure Fabrication / shop & erection Drawings Approval with Comments | 4 | E0GAN | E000 | 00E4 | E000#LBlV00E4
1925 | 1925 | 1925 | 1925 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Civil EHV Gantry- Gantry Steel Structure Fabrication / shop & erection Drawings FINAL Approval | 5 | E0GAN | E000 | 00E5 | E000#LBlV00E5
1926 | 1926 | 1926 | 1926 | SA24M005 | Mechanical |  | 5 | -1 | 0 |  |  | X | E000#LBlV
1927 | 1927 | 1927 | 1927 | SA24M005 | HVAC System Design Calculation and Drawings for Control Building Including Ventilation in Battery Ro |  | 6 | -1 | 0 |  |  | X | E000#LBlV
1928 | 1928 | 1928 | 1928 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical HVAC System Design Calculation and Drawings for Control Building Including Ventilation in Battery Ro Drafting / Preparation | 1 | MHVAC | E000 | 00E1 | E000#nzvX00E1
1929 | 1929 | 1929 | 1929 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical HVAC System Design Calculation and Drawings for Control Building Including Ventilation in Battery Ro Submission | 2 | MHVAC | E000 | 00E2 | E000#nzvX00E2
1930 | 1930 | 1930 | 1930 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical HVAC System Design Calculation and Drawings for Control Building Including Ventilation in Battery Ro Review / Evaluation | 3 | MHVAC | E000 | 00E3 | E000#nzvX00E3
1931 | 1931 | 1931 | 1931 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical HVAC System Design Calculation and Drawings for Control Building Including Ventilation in Battery Ro Approval with Comments | 4 | MHVAC | E000 | 00E4 | E000#nzvX00E4
1932 | 1932 | 1932 | 1932 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical HVAC System Design Calculation and Drawings for Control Building Including Ventilation in Battery Ro FINAL Approval | 5 | MHVAC | E000 | 00E5 | E000#nzvX00E5
1933 | 1933 | 1933 | 1933 | SA24M005 | Plumbing Design Calculation and Drawings forControl Building |  | 6 | -1 | 0 |  |  | X | E000#nzvX
1934 | 1934 | 1934 | 1934 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Plumbing Design Calculation and Drawings forControl Building Drafting / Preparation | 1 | PLUMB | E000 | 00E1 | E000#fyUR00E1
1935 | 1935 | 1935 | 1935 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Plumbing Design Calculation and Drawings forControl Building Submission | 2 | PLUMB | E000 | 00E2 | E000#fyUR00E2
1936 | 1936 | 1936 | 1936 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Plumbing Design Calculation and Drawings forControl Building Review / Evaluation | 3 | PLUMB | E000 | 00E3 | E000#fyUR00E3
1937 | 1937 | 1937 | 1937 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Plumbing Design Calculation and Drawings forControl Building Approval with Comments | 4 | PLUMB | E000 | 00E4 | E000#fyUR00E4
1938 | 1938 | 1938 | 1938 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Plumbing Design Calculation and Drawings forControl Building FINAL Approval | 5 | PLUMB | E000 | 00E5 | E000#fyUR00E5
1939 | 1939 | 1939 | 1939 | SA24M005 | Material Submittal for HVAC Control Panel for Control Building |  | 6 | -1 | 0 |  |  | X | E000#fyUR
1940 | 1940 | 1940 | 1940 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Material Submittal for HVAC Control Panel for Control Building Drafting / Preparation | 1 | MHVAC | E000 | 00E1 | E000#CAwM00E1
1941 | 1941 | 1941 | 1941 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Material Submittal for HVAC Control Panel for Control Building Submission | 2 | MHVAC | E000 | 00E2 | E000#CAwM00E2
1942 | 1942 | 1942 | 1942 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Material Submittal for HVAC Control Panel for Control Building Review / Evaluation | 3 | MHVAC | E000 | 00E3 | E000#CAwM00E3
1943 | 1943 | 1943 | 1943 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Material Submittal for HVAC Control Panel for Control Building Approval with Comments | 4 | MHVAC | E000 | 00E4 | E000#CAwM00E4
1944 | 1944 | 1944 | 1944 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Material Submittal for HVAC Control Panel for Control Building FINAL Approval | 5 | MHVAC | E000 | 00E5 | E000#CAwM00E5
1945 | 1945 | 1945 | 1945 | SA24M005 | Fire Protection Design Calculations and Drawings for Control Building |  | 6 | -1 | 0 |  |  | X | E000#CAwM
1946 | 1946 | 1946 | 1946 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Fire Protection Design Calculations and Drawings for Control Building Drafting / Preparation | 1 | FPRC | E000 | 00E1 | E000FPRC00E1
1947 | 1947 | 1947 | 1947 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Fire Protection Design Calculations and Drawings for Control Building Submission | 2 | FPRC | E000 | 00E2 | E000FPRC00E2
1948 | 1948 | 1948 | 1948 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Fire Protection Design Calculations and Drawings for Control Building Review / Evaluation | 3 | FPRC | E000 | 00E3 | E000FPRC00E3
1949 | 1949 | 1949 | 1949 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Fire Protection Design Calculations and Drawings for Control Building Approval with Comments | 4 | FPRC | E000 | 00E4 | E000FPRC00E4
1950 | 1950 | 1950 | 1950 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Fire Protection Design Calculations and Drawings for Control Building FINAL Approval | 5 | FPRC | E000 | 00E5 | E000FPRC00E5
1951 | 1951 | 1951 | 1951 | SA24M005 | Complete HVAC System Design Calculation and drawings for Single Building HV Substation |  | 6 | -1 | 0 |  |  | X
1952 | 1952 | 1952 | 1952 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Complete HVAC System Design Calculation and drawings for Single Building HV Substation Drafting / Preparation | 1 | CHVAC | E000 | 00E1 | E000#GKpb00E1
1953 | 1953 | 1953 | 1953 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Complete HVAC System Design Calculation and drawings for Single Building HV Substation Submission | 2 | CHVAC | E000 | 00E2 | E000#GKpb00E2
1954 | 1954 | 1954 | 1954 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Complete HVAC System Design Calculation and drawings for Single Building HV Substation Review / Evaluation | 3 | CHVAC | E000 | 00E3 | E000#GKpb00E3
1955 | 1955 | 1955 | 1955 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Complete HVAC System Design Calculation and drawings for Single Building HV Substation Approval with Comments | 4 | CHVAC | E000 | 00E4 | E000#GKpb00E4
1956 | 1956 | 1956 | 1956 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Complete HVAC System Design Calculation and drawings for Single Building HV Substation FINAL Approval | 5 | CHVAC | E000 | 00E5 | E000#GKpb00E5
1957 | 1957 | 1957 | 1957 | SA24M005 | Plumbing System Design for Single Building HV Substation |  | 6 | -1 | 0 |  |  | X | E000#GKpb
1958 | 1958 | 1958 | 1958 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Plumbing System Design for Single Building HV Substation Drafting / Preparation | 1 | PHSB | E000 | 00E1 | E000PHSB00E1
1959 | 1959 | 1959 | 1959 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Plumbing System Design for Single Building HV Substation Submission | 2 | PHSB | E000 | 00E2 | E000PHSB00E2
1960 | 1960 | 1960 | 1960 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Plumbing System Design for Single Building HV Substation Review / Evaluation | 3 | PHSB | E000 | 00E3 | E000PHSB00E3
1961 | 1961 | 1961 | 1961 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Plumbing System Design for Single Building HV Substation Approval with Comments | 4 | PHSB | E000 | 00E4 | E000PHSB00E4
1962 | 1962 | 1962 | 1962 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Plumbing System Design for Single Building HV Substation FINAL Approval | 5 | PHSB | E000 | 00E5 | E000PHSB00E5
1963 | 1963 | 1963 | 1963 | SA24M005 | Fire Protection Design Calculation and Drawings for Single Building HV Substation |  | 6 | -1 | 0 |  |  | X
1964 | 1964 | 1964 | 1964 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Fire Protection Design Calculation and Drawings for Single Building HV Substation Drafting / Preparation | 1 | FPRDC | E000 | 00E1 | E000FPRDC00E1
1965 | 1965 | 1965 | 1965 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Fire Protection Design Calculation and Drawings for Single Building HV Substation Submission | 2 | FPRDC | E000 | 00E2 | E000FPRDC00E2
1966 | 1966 | 1966 | 1966 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Fire Protection Design Calculation and Drawings for Single Building HV Substation Review / Evaluation | 3 | FPRDC | E000 | 00E3 | E000FPRDC00E3
1967 | 1967 | 1967 | 1967 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Fire Protection Design Calculation and Drawings for Single Building HV Substation Approval with Comments | 4 | FPRDC | E000 | 00E4 | E000FPRDC00E4
1968 | 1968 | 1968 | 1968 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Fire Protection Design Calculation and Drawings for Single Building HV Substation FINAL Approval | 5 | FPRDC | E000 | 00E5 | E000FPRDC00E5
1969 | 1969 | 1969 | 1969 | SA24M005 | Tunnel Ventilation System Design Calculations & Drawings (Lot-1) |  | 6 | -1 | 0 |  |  | X
1970 | 1970 | 1970 | 1970 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Tunnel Ventilation System Design Calculations & Drawings (Lot-1) Drafting / Preparation | 1 | 0TVEN | E000 | 00E1 | E000#dZTw00E1
1971 | 1971 | 1971 | 1971 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Tunnel Ventilation System Design Calculations & Drawings (Lot-1) Submission | 2 | 0TVEN | E000 | 00E2 | E000#dZTw00E2
1972 | 1972 | 1972 | 1972 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Tunnel Ventilation System Design Calculations & Drawings (Lot-1) Review / Evaluation | 3 | 0TVEN | E000 | 00E3 | E000#dZTw00E3
1973 | 1973 | 1973 | 1973 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Tunnel Ventilation System Design Calculations & Drawings (Lot-1) Approval with Comments | 4 | 0TVEN | E000 | 00E4 | E000#dZTw00E4
1974 | 1974 | 1974 | 1974 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Tunnel Ventilation System Design Calculations & Drawings (Lot-1) FINAL Approval | 5 | 0TVEN | E000 | 00E5 | E000#dZTw00E5
1975 | 1975 | 1975 | 1975 | SA24M005 | Tunnel Drainage System Design Calculations & Drawings (Lot-1) |  | 6 | -1 | 0 |  |  | X | E000#dZTw
1976 | 1976 | 1976 | 1976 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Tunnel Drainage System Design Calculations & Drawings (Lot-1) Drafting / Preparation | 1 | MTUNL | E000 | 00E1 | E000#ReGy00E1
1977 | 1977 | 1977 | 1977 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Tunnel Drainage System Design Calculations & Drawings (Lot-1) Submission | 2 | MTUNL | E000 | 00E2 | E000#ReGy00E2
1978 | 1978 | 1978 | 1978 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Tunnel Drainage System Design Calculations & Drawings (Lot-1) Review / Evaluation | 3 | MTUNL | E000 | 00E3 | E000#ReGy00E3
1979 | 1979 | 1979 | 1979 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Tunnel Drainage System Design Calculations & Drawings (Lot-1) Approval with Comments | 4 | MTUNL | E000 | 00E4 | E000#ReGy00E4
1980 | 1980 | 1980 | 1980 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Tunnel Drainage System Design Calculations & Drawings (Lot-1) FINAL Approval | 5 | MTUNL | E000 | 00E5 | E000#ReGy00E5
1981 | 1981 | 1981 | 1981 | SA24M005 | Tunnel Fire Protection System Design Calculations & Drawings (Lot-1) |  | 6 | -1 | 0 |  |  | X | E000#ReGy
1982 | 1982 | 1982 | 1982 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Tunnel Fire Protection System Design Calculations & Drawings (Lot-1) Drafting / Preparation | 1 | MTFPS | E000 | 00E1 | E000#IQAd00E1
1983 | 1983 | 1983 | 1983 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Tunnel Fire Protection System Design Calculations & Drawings (Lot-1) Submission | 2 | MTFPS | E000 | 00E2 | E000#IQAd00E2
1984 | 1984 | 1984 | 1984 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Tunnel Fire Protection System Design Calculations & Drawings (Lot-1) Review / Evaluation | 3 | MTFPS | E000 | 00E3 | E000#IQAd00E3
1985 | 1985 | 1985 | 1985 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Tunnel Fire Protection System Design Calculations & Drawings (Lot-1) Approval with Comments | 4 | MTFPS | E000 | 00E4 | E000#IQAd00E4
1986 | 1986 | 1986 | 1986 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Tunnel Fire Protection System Design Calculations & Drawings (Lot-1) FINAL Approval | 5 | MTFPS | E000 | 00E5 | E000#IQAd00E5
1987 | 1987 | 1987 | 1987 | SA24M005 | Tunnel Ventilation System Design Calculations & Drawings (Lot-2) |  | 6 | -1 | 0 |  |  | X | E000#IQAd
1988 | 1988 | 1988 | 1988 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Tunnel Ventilation System Design Calculations & Drawings (Lot-2) Drafting / Preparation | 1 | 0TVEN | E000 | 00E1 | E000#GYBc00E1
1989 | 1989 | 1989 | 1989 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Tunnel Ventilation System Design Calculations & Drawings (Lot-2) Submission | 2 | 0TVEN | E000 | 00E2 | E000#GYBc00E2
1990 | 1990 | 1990 | 1990 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Tunnel Ventilation System Design Calculations & Drawings (Lot-2) Review / Evaluation | 3 | 0TVEN | E000 | 00E3 | E000#GYBc00E3
1991 | 1991 | 1991 | 1991 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Tunnel Ventilation System Design Calculations & Drawings (Lot-2) Approval with Comments | 4 | 0TVEN | E000 | 00E4 | E000#GYBc00E4
1992 | 1992 | 1992 | 1992 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Tunnel Ventilation System Design Calculations & Drawings (Lot-2) FINAL Approval | 5 | 0TVEN | E000 | 00E5 | E000#GYBc00E5
1993 | 1993 | 1993 | 1993 | SA24M005 | Tunnel Drainage System Design Calculations & Drawings (Lot-2) |  | 6 | -1 | 0 |  |  | X | E000#GYBc
1994 | 1994 | 1994 | 1994 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Tunnel Drainage System Design Calculations & Drawings (Lot-2) Drafting / Preparation | 1 | MTUNL | E000 | 00E1 | E000#vNKX00E1
1995 | 1995 | 1995 | 1995 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Tunnel Drainage System Design Calculations & Drawings (Lot-2) Submission | 2 | MTUNL | E000 | 00E2 | E000#vNKX00E2
1996 | 1996 | 1996 | 1996 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Tunnel Drainage System Design Calculations & Drawings (Lot-2) Review / Evaluation | 3 | MTUNL | E000 | 00E3 | E000#vNKX00E3
1997 | 1997 | 1997 | 1997 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Tunnel Drainage System Design Calculations & Drawings (Lot-2) Approval with Comments | 4 | MTUNL | E000 | 00E4 | E000#vNKX00E4
1998 | 1998 | 1998 | 1998 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Tunnel Drainage System Design Calculations & Drawings (Lot-2) FINAL Approval | 5 | MTUNL | E000 | 00E5 | E000#vNKX00E5
1999 | 1999 | 1999 | 1999 | SA24M005 | Tunnel Fire Protection System Design Calculations & Drawings (Lot-2) |  | 6 | -1 | 0 |  |  | X | E000#vNKX
2000 | 2000 | 2000 | 2000 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Tunnel Fire Protection System Design Calculations & Drawings (Lot-2) Drafting / Preparation | 1 | MTFPS | E000 | 00E1 | E000#MpQo00E1
2001 | 2001 | 2001 | 2001 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Tunnel Fire Protection System Design Calculations & Drawings (Lot-2) Submission | 2 | MTFPS | E000 | 00E2 | E000#MpQo00E2
2002 | 2002 | 2002 | 2002 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Tunnel Fire Protection System Design Calculations & Drawings (Lot-2) Review / Evaluation | 3 | MTFPS | E000 | 00E3 | E000#MpQo00E3
2003 | 2003 | 2003 | 2003 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Tunnel Fire Protection System Design Calculations & Drawings (Lot-2) Approval with Comments | 4 | MTFPS | E000 | 00E4 | E000#MpQo00E4
2004 | 2004 | 2004 | 2004 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical Tunnel Fire Protection System Design Calculations & Drawings (Lot-2) FINAL Approval | 5 | MTFPS | E000 | 00E5 | E000#MpQo00E5
2005 | 2005 | 2005 | 2005 | SA24M005 | HVAC Electrical Material Submittal |  | 6 | -1 | 0 |  |  | X | E000#MpQo
2006 | 2006 | 2006 | 2006 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical HVAC Electrical Material Submittal Drafting / Preparation | 1 | MHVAC | E000 | 00E1 | E000#LFRx00E1
2007 | 2007 | 2007 | 2007 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical HVAC Electrical Material Submittal Submission | 2 | MHVAC | E000 | 00E2 | E000#LFRx00E2
2008 | 2008 | 2008 | 2008 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical HVAC Electrical Material Submittal Review / Evaluation | 3 | MHVAC | E000 | 00E3 | E000#LFRx00E3
2009 | 2009 | 2009 | 2009 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical HVAC Electrical Material Submittal Approval with Comments | 4 | MHVAC | E000 | 00E4 | E000#LFRx00E4
2010 | 2010 | 2010 | 2010 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- V Mechanical HVAC Electrical Material Submittal FINAL Approval | 5 | MHVAC | E000 | 00E5 | E000#LFRx00E5
2011 | 2011 | 2011 | 2011 | SA24M005 | Phase- VI |  | 4 | -1 | 0 |  |  | X | E000#LFRx
2012 | 2012 | 2012 | 2012 | SA24M005 | Electrical |  | 5 | -1 | 0 |  |  | X | E000#LFRx
2013 | 2013 | 2013 | 2013 | SA24M005 | Guard House Electrical Layout & details |  | 6 | -1 | 0 |  |  | X | E000#LFRx
2014 | 2014 | 2014 | 2014 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Electrical Guard House Electrical Layout & details Drafting / Preparation | 1 | E0GH | E000 | 00E1 | E000E0GH00E1
2015 | 2015 | 2015 | 2015 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Electrical Guard House Electrical Layout & details Submission | 2 | E0GH | E000 | 00E2 | E000E0GH00E2
2016 | 2016 | 2016 | 2016 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Electrical Guard House Electrical Layout & details Review / Evaluation | 3 | E0GH | E000 | 00E3 | E000E0GH00E3
2017 | 2017 | 2017 | 2017 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Electrical Guard House Electrical Layout & details Approval with Comments | 4 | E0GH | E000 | 00E4 | E000E0GH00E4
2018 | 2018 | 2018 | 2018 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Electrical Guard House Electrical Layout & details FINAL Approval | 5 | E0GH | E000 | 00E5 | E000E0GH00E5
2019 | 2019 | 2019 | 2019 | SA24M005 | Pump House Electrical Layout & Details |  | 6 | -1 | 0 |  |  | X
2020 | 2020 | 2020 | 2020 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Electrical Pump House Electrical Layout & Details Drafting / Preparation | 1 | EPHPL | E000 | 00E1 | E000EPHPL00E1
2021 | 2021 | 2021 | 2021 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Electrical Pump House Electrical Layout & Details Submission | 2 | EPHPL | E000 | 00E2 | E000EPHPL00E2
2022 | 2022 | 2022 | 2022 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Electrical Pump House Electrical Layout & Details Review / Evaluation | 3 | EPHPL | E000 | 00E3 | E000EPHPL00E3
2023 | 2023 | 2023 | 2023 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Electrical Pump House Electrical Layout & Details Approval with Comments | 4 | EPHPL | E000 | 00E4 | E000EPHPL00E4
2024 | 2024 | 2024 | 2024 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Electrical Pump House Electrical Layout & Details FINAL Approval | 5 | EPHPL | E000 | 00E5 | E000EPHPL00E5
2025 | 2025 | 2025 | 2025 | SA24M005 | Civil |  | 5 | -1 | 0 |  |  | X
2026 | 2026 | 2026 | 2026 | SA24M005 | Guard House- Architectural Plan & Details |  | 6 | -1 | 0 |  |  | X
2027 | 2027 | 2027 | 2027 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Guard House- Architectural Plan & Details Drafting / Preparation | 1 | CGUAH | E000 | 00E1 | E000CGUAH00E1
2028 | 2028 | 2028 | 2028 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Guard House- Architectural Plan & Details Submission | 2 | CGUAH | E000 | 00E2 | E000CGUAH00E2
2029 | 2029 | 2029 | 2029 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Guard House- Architectural Plan & Details Review / Evaluation | 3 | CGUAH | E000 | 00E3 | E000CGUAH00E3
2030 | 2030 | 2030 | 2030 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Guard House- Architectural Plan & Details Approval with Comments | 4 | CGUAH | E000 | 00E4 | E000CGUAH00E4
2031 | 2031 | 2031 | 2031 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Guard House- Architectural Plan & Details FINAL Approval | 5 | CGUAH | E000 | 00E5 | E000CGUAH00E5
2032 | 2032 | 2032 | 2032 | SA24M005 | Guard House- Layout / Building Analysis/Foundation and Design Calculations / Column Reinforcement De |  | 6 | -1 | 0 |  |  | X
2033 | 2033 | 2033 | 2033 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Guard House- Layout / Building Analysis/Foundation and Design Calculations / Column Reinforcement De Drafting / Preparation | 1 | CGH | E000 | 00E1 | E000#pAfx00E1
2034 | 2034 | 2034 | 2034 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Guard House- Layout / Building Analysis/Foundation and Design Calculations / Column Reinforcement De Submission | 2 | CGH | E000 | 00E2 | E000#pAfx00E2
2035 | 2035 | 2035 | 2035 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Guard House- Layout / Building Analysis/Foundation and Design Calculations / Column Reinforcement De Review / Evaluation | 3 | CGH | E000 | 00E3 | E000#pAfx00E3
2036 | 2036 | 2036 | 2036 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Guard House- Layout / Building Analysis/Foundation and Design Calculations / Column Reinforcement De Approval with Comments | 4 | CGH | E000 | 00E4 | E000#pAfx00E4
2037 | 2037 | 2037 | 2037 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Guard House- Layout / Building Analysis/Foundation and Design Calculations / Column Reinforcement De FINAL Approval | 5 | CGH | E000 | 00E5 | E000#pAfx00E5
2038 | 2038 | 2038 | 2038 | SA24M005 | Guard House- Roof Level Reinforcement Details |  | 6 | -1 | 0 |  |  | X | E000#pAfx
2039 | 2039 | 2039 | 2039 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Guard House- Roof Level Reinforcement Details Drafting / Preparation | 1 | CGHRR | E000 | 00E1 | E000CGHRR00E1
2040 | 2040 | 2040 | 2040 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Guard House- Roof Level Reinforcement Details Submission | 2 | CGHRR | E000 | 00E2 | E000CGHRR00E2
2041 | 2041 | 2041 | 2041 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Guard House- Roof Level Reinforcement Details Review / Evaluation | 3 | CGHRR | E000 | 00E3 | E000CGHRR00E3
2042 | 2042 | 2042 | 2042 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Guard House- Roof Level Reinforcement Details Approval with Comments | 4 | CGHRR | E000 | 00E4 | E000CGHRR00E4
2043 | 2043 | 2043 | 2043 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Guard House- Roof Level Reinforcement Details FINAL Approval | 5 | CGHRR | E000 | 00E5 | E000CGHRR00E5
2044 | 2044 | 2044 | 2044 | SA24M005 | Guard House- Plans, Elevations, Sections & Structural Details for Guard House Toilet |  | 6 | -1 | 0 |  |  | X
2045 | 2045 | 2045 | 2045 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Guard House- Plans, Elevations, Sections & Structural Details for Guard House Toilet Drafting / Preparation | 1 | CGUHT | E000 | 00E1 | E000CGUHT00E1
2046 | 2046 | 2046 | 2046 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Guard House- Plans, Elevations, Sections & Structural Details for Guard House Toilet Submission | 2 | CGUHT | E000 | 00E2 | E000CGUHT00E2
2047 | 2047 | 2047 | 2047 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Guard House- Plans, Elevations, Sections & Structural Details for Guard House Toilet Review / Evaluation | 3 | CGUHT | E000 | 00E3 | E000CGUHT00E3
2048 | 2048 | 2048 | 2048 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Guard House- Plans, Elevations, Sections & Structural Details for Guard House Toilet Approval with Comments | 4 | CGUHT | E000 | 00E4 | E000CGUHT00E4
2049 | 2049 | 2049 | 2049 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Guard House- Plans, Elevations, Sections & Structural Details for Guard House Toilet FINAL Approval | 5 | CGUHT | E000 | 00E5 | E000CGUHT00E5
2050 | 2050 | 2050 | 2050 | SA24M005 | Guard House- Layout and Details of Septic Tank, Soak Pit for Guard House Toilet |  | 6 | -1 | 0 |  |  | X
2051 | 2051 | 2051 | 2051 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Guard House- Layout and Details of Septic Tank, Soak Pit for Guard House Toilet Drafting / Preparation | 1 | CGH | E000 | 00E1 | E000#YLao00E1
2052 | 2052 | 2052 | 2052 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Guard House- Layout and Details of Septic Tank, Soak Pit for Guard House Toilet Submission | 2 | CGH | E000 | 00E2 | E000#YLao00E2
2053 | 2053 | 2053 | 2053 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Guard House- Layout and Details of Septic Tank, Soak Pit for Guard House Toilet Review / Evaluation | 3 | CGH | E000 | 00E3 | E000#YLao00E3
2054 | 2054 | 2054 | 2054 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Guard House- Layout and Details of Septic Tank, Soak Pit for Guard House Toilet Approval with Comments | 4 | CGH | E000 | 00E4 | E000#YLao00E4
2055 | 2055 | 2055 | 2055 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Guard House- Layout and Details of Septic Tank, Soak Pit for Guard House Toilet FINAL Approval | 5 | CGH | E000 | 00E5 | E000#YLao00E5
2056 | 2056 | 2056 | 2056 | SA24M005 | External Telecom Shelter Fence Layout & Details |  | 6 | -1 | 0 |  |  | X | E000#YLao
2057 | 2057 | 2057 | 2057 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil External Telecom Shelter Fence Layout & Details Drafting / Preparation | 1 | E0TCS | E000 | 00E1 | E000E0TCS00E1
2058 | 2058 | 2058 | 2058 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil External Telecom Shelter Fence Layout & Details Submission | 2 | E0TCS | E000 | 00E2 | E000E0TCS00E2
2059 | 2059 | 2059 | 2059 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil External Telecom Shelter Fence Layout & Details Review / Evaluation | 3 | E0TCS | E000 | 00E3 | E000E0TCS00E3
2060 | 2060 | 2060 | 2060 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil External Telecom Shelter Fence Layout & Details Approval with Comments | 4 | E0TCS | E000 | 00E4 | E000E0TCS00E4
2061 | 2061 | 2061 | 2061 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil External Telecom Shelter Fence Layout & Details FINAL Approval | 5 | E0TCS | E000 | 00E5 | E000E0TCS00E5
2062 | 2062 | 2062 | 2062 | SA24M005 | Fire Pump House and Underground Water Tank- Architectural Plan & Detail drawings |  | 6 | -1 | 0 |  |  | X
2063 | 2063 | 2063 | 2063 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Fire Pump House and Underground Water Tank- Architectural Plan & Detail drawings Drafting / Preparation | 1 | CFPH | E000 | 00E1 | E000#zmUK00E1
2064 | 2064 | 2064 | 2064 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Fire Pump House and Underground Water Tank- Architectural Plan & Detail drawings Submission | 2 | CFPH | E000 | 00E2 | E000#zmUK00E2
2065 | 2065 | 2065 | 2065 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Fire Pump House and Underground Water Tank- Architectural Plan & Detail drawings Review / Evaluation | 3 | CFPH | E000 | 00E3 | E000#zmUK00E3
2066 | 2066 | 2066 | 2066 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Fire Pump House and Underground Water Tank- Architectural Plan & Detail drawings Approval with Comments | 4 | CFPH | E000 | 00E4 | E000#zmUK00E4
2067 | 2067 | 2067 | 2067 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Fire Pump House and Underground Water Tank- Architectural Plan & Detail drawings FINAL Approval | 5 | CFPH | E000 | 00E5 | E000#zmUK00E5
2068 | 2068 | 2068 | 2068 | SA24M005 | Fire Pump House and Underground Water Tank- Design Calculation, Layout & Details - Structural Drawin |  | 6 | -1 | 0 |  |  | X | E000#zmUK
2069 | 2069 | 2069 | 2069 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Fire Pump House and Underground Water Tank- Design Calculation, Layout & Details - Structural Drawin Drafting / Preparation | 1 | CFPH | E000 | 00E1 | E000#ghVg00E1
2070 | 2070 | 2070 | 2070 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Fire Pump House and Underground Water Tank- Design Calculation, Layout & Details - Structural Drawin Submission | 2 | CFPH | E000 | 00E2 | E000#ghVg00E2
2071 | 2071 | 2071 | 2071 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Fire Pump House and Underground Water Tank- Design Calculation, Layout & Details - Structural Drawin Review / Evaluation | 3 | CFPH | E000 | 00E3 | E000#ghVg00E3
2072 | 2072 | 2072 | 2072 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Fire Pump House and Underground Water Tank- Design Calculation, Layout & Details - Structural Drawin Approval with Comments | 4 | CFPH | E000 | 00E4 | E000#ghVg00E4
2073 | 2073 | 2073 | 2073 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Fire Pump House and Underground Water Tank- Design Calculation, Layout & Details - Structural Drawin FINAL Approval | 5 | CFPH | E000 | 00E5 | E000#ghVg00E5
2074 | 2074 | 2074 | 2074 | SA24M005 | Fire Pump House- Building Analysis/Foundation and Design Calculations / Column Reinforcement Details |  | 6 | -1 | 0 |  |  | X | E000#ghVg
2075 | 2075 | 2075 | 2075 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Fire Pump House- Building Analysis/Foundation and Design Calculations / Column Reinforcement Details Drafting / Preparation | 1 | CFPH | E000 | 00E1 | E000#HoWk00E1
2076 | 2076 | 2076 | 2076 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Fire Pump House- Building Analysis/Foundation and Design Calculations / Column Reinforcement Details Submission | 2 | CFPH | E000 | 00E2 | E000#HoWk00E2
2077 | 2077 | 2077 | 2077 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Fire Pump House- Building Analysis/Foundation and Design Calculations / Column Reinforcement Details Review / Evaluation | 3 | CFPH | E000 | 00E3 | E000#HoWk00E3
2078 | 2078 | 2078 | 2078 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Fire Pump House- Building Analysis/Foundation and Design Calculations / Column Reinforcement Details Approval with Comments | 4 | CFPH | E000 | 00E4 | E000#HoWk00E4
2079 | 2079 | 2079 | 2079 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Fire Pump House- Building Analysis/Foundation and Design Calculations / Column Reinforcement Details FINAL Approval | 5 | CFPH | E000 | 00E5 | E000#HoWk00E5
2080 | 2080 | 2080 | 2080 | SA24M005 | Fire Pump House- Roof Level Reinforcement Details |  | 6 | -1 | 0 |  |  | X | E000#HoWk
2081 | 2081 | 2081 | 2081 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Fire Pump House- Roof Level Reinforcement Details Drafting / Preparation | 1 | CFPHR | E000 | 00E1 | E000CFPHR00E1
2082 | 2082 | 2082 | 2082 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Fire Pump House- Roof Level Reinforcement Details Submission | 2 | CFPHR | E000 | 00E2 | E000CFPHR00E2
2083 | 2083 | 2083 | 2083 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Fire Pump House- Roof Level Reinforcement Details Review / Evaluation | 3 | CFPHR | E000 | 00E3 | E000CFPHR00E3
2084 | 2084 | 2084 | 2084 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Fire Pump House- Roof Level Reinforcement Details Approval with Comments | 4 | CFPHR | E000 | 00E4 | E000CFPHR00E4
2085 | 2085 | 2085 | 2085 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Fire Pump House- Roof Level Reinforcement Details FINAL Approval | 5 | CFPHR | E000 | 00E5 | E000CFPHR00E5
2086 | 2086 | 2086 | 2086 | SA24M005 | Fire Hydrant Foundation Layout and Details |  | 6 | -1 | 0 |  |  | X
2087 | 2087 | 2087 | 2087 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Fire Hydrant Foundation Layout and Details Drafting / Preparation | 1 | FHYF | E000 | 00E1 | E000FHYF00E1
2088 | 2088 | 2088 | 2088 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Fire Hydrant Foundation Layout and Details Submission | 2 | FHYF | E000 | 00E2 | E000FHYF00E2
2089 | 2089 | 2089 | 2089 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Fire Hydrant Foundation Layout and Details Review / Evaluation | 3 | FHYF | E000 | 00E3 | E000FHYF00E3
2090 | 2090 | 2090 | 2090 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Fire Hydrant Foundation Layout and Details Approval with Comments | 4 | FHYF | E000 | 00E4 | E000FHYF00E4
2091 | 2091 | 2091 | 2091 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Fire Hydrant Foundation Layout and Details FINAL Approval | 5 | FHYF | E000 | 00E5 | E000FHYF00E5
2092 | 2092 | 2092 | 2092 | SA24M005 | Fire Trench structural package |  | 6 | -1 | 0 |  |  | X
2093 | 2093 | 2093 | 2093 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Fire Trench structural package Drafting / Preparation | 1 | CFSTR | E000 | 00E1 | E000#CJNS00E1
2094 | 2094 | 2094 | 2094 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Fire Trench structural package Submission | 2 | CFSTR | E000 | 00E2 | E000#CJNS00E2
2095 | 2095 | 2095 | 2095 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Fire Trench structural package Review / Evaluation | 3 | CFSTR | E000 | 00E3 | E000#CJNS00E3
2096 | 2096 | 2096 | 2096 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Fire Trench structural package Approval with Comments | 4 | CFSTR | E000 | 00E4 | E000#CJNS00E4
2097 | 2097 | 2097 | 2097 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Fire Trench structural package FINAL Approval | 5 | CFSTR | E000 | 00E5 | E000#CJNS00E5
2098 | 2098 | 2098 | 2098 | SA24M005 | Substation Boundary Wall Pre-cast Panel Layout and Details |  | 6 | -1 | 0 |  |  | X | E000#CJNS
2099 | 2099 | 2099 | 2099 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Substation Boundary Wall Pre-cast Panel Layout and Details Drafting / Preparation | 1 | CSBW | E000 | 00E1 | E000CSBW00E1
2100 | 2100 | 2100 | 2100 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Substation Boundary Wall Pre-cast Panel Layout and Details Submission | 2 | CSBW | E000 | 00E2 | E000CSBW00E2
2101 | 2101 | 2101 | 2101 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Substation Boundary Wall Pre-cast Panel Layout and Details Review / Evaluation | 3 | CSBW | E000 | 00E3 | E000CSBW00E3
2102 | 2102 | 2102 | 2102 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Substation Boundary Wall Pre-cast Panel Layout and Details Approval with Comments | 4 | CSBW | E000 | 00E4 | E000CSBW00E4
2103 | 2103 | 2103 | 2103 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Substation Boundary Wall Pre-cast Panel Layout and Details FINAL Approval | 5 | CSBW | E000 | 00E5 | E000CSBW00E5
2104 | 2104 | 2104 | 2104 | SA24M005 | Substation Boundary Wall Foundation Design Calculations, Sections & details |  | 6 | -1 | 0 |  |  | X
2105 | 2105 | 2105 | 2105 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Substation Boundary Wall Foundation Design Calculations, Sections & details Drafting / Preparation | 1 | CSBWF | E000 | 00E1 | E000CSBWF00E1
2106 | 2106 | 2106 | 2106 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Substation Boundary Wall Foundation Design Calculations, Sections & details Submission | 2 | CSBWF | E000 | 00E2 | E000CSBWF00E2
2107 | 2107 | 2107 | 2107 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Substation Boundary Wall Foundation Design Calculations, Sections & details Review / Evaluation | 3 | CSBWF | E000 | 00E3 | E000CSBWF00E3
2108 | 2108 | 2108 | 2108 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Substation Boundary Wall Foundation Design Calculations, Sections & details Approval with Comments | 4 | CSBWF | E000 | 00E4 | E000CSBWF00E4
2109 | 2109 | 2109 | 2109 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Substation Boundary Wall Foundation Design Calculations, Sections & details FINAL Approval | 5 | CSBWF | E000 | 00E5 | E000CSBWF00E5
2110 | 2110 | 2110 | 2110 | SA24M005 | Sliding Gate and Personnel Gate Layout and Details |  | 6 | -1 | 0 |  |  | X
2111 | 2111 | 2111 | 2111 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Sliding Gate and Personnel Gate Layout and Details Drafting / Preparation | 1 | CSGP | E000 | 00E1 | E000CSGP00E1
2112 | 2112 | 2112 | 2112 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Sliding Gate and Personnel Gate Layout and Details Submission | 2 | CSGP | E000 | 00E2 | E000CSGP00E2
2113 | 2113 | 2113 | 2113 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Sliding Gate and Personnel Gate Layout and Details Review / Evaluation | 3 | CSGP | E000 | 00E3 | E000CSGP00E3
2114 | 2114 | 2114 | 2114 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Sliding Gate and Personnel Gate Layout and Details Approval with Comments | 4 | CSGP | E000 | 00E4 | E000CSGP00E4
2115 | 2115 | 2115 | 2115 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Sliding Gate and Personnel Gate Layout and Details FINAL Approval | 5 | CSGP | E000 | 00E5 | E000CSGP00E5
2116 | 2116 | 2116 | 2116 | SA24M005 | Chainlink Boundary Fence Details & Drawings |  | 6 | -1 | 0 |  |  | X
2117 | 2117 | 2117 | 2117 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Chainlink Boundary Fence Details & Drawings Drafting / Preparation | 1 | C0CBF | E000 | 00E1 | E000C0CBF00E1
2118 | 2118 | 2118 | 2118 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Chainlink Boundary Fence Details & Drawings Submission | 2 | C0CBF | E000 | 00E2 | E000C0CBF00E2
2119 | 2119 | 2119 | 2119 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Chainlink Boundary Fence Details & Drawings Review / Evaluation | 3 | C0CBF | E000 | 00E3 | E000C0CBF00E3
2120 | 2120 | 2120 | 2120 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Chainlink Boundary Fence Details & Drawings Approval with Comments | 4 | C0CBF | E000 | 00E4 | E000C0CBF00E4
2121 | 2121 | 2121 | 2121 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Civil Chainlink Boundary Fence Details & Drawings FINAL Approval | 5 | C0CBF | E000 | 00E5 | E000C0CBF00E5
2122 | 2122 | 2122 | 2122 | SA24M005 | Mechanical |  | 5 | -1 | 0 |  |  | X
2123 | 2123 | 2123 | 2123 | SA24M005 | Fire Signaling System Design for Substation |  | 6 | -1 | 0 |  |  | X
2124 | 2124 | 2124 | 2124 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Mechanical Fire Signaling System Design for Substation Drafting / Preparation | 1 | F0FSS | E000 | 00E1 | E000#UdSf00E1
2125 | 2125 | 2125 | 2125 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Mechanical Fire Signaling System Design for Substation Submission | 2 | F0FSS | E000 | 00E2 | E000#UdSf00E2
2126 | 2126 | 2126 | 2126 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Mechanical Fire Signaling System Design for Substation Review / Evaluation | 3 | F0FSS | E000 | 00E3 | E000#UdSf00E3
2127 | 2127 | 2127 | 2127 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Mechanical Fire Signaling System Design for Substation Approval with Comments | 4 | F0FSS | E000 | 00E4 | E000#UdSf00E4
2128 | 2128 | 2128 | 2128 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Mechanical Fire Signaling System Design for Substation FINAL Approval | 5 | F0FSS | E000 | 00E5 | E000#UdSf00E5
2129 | 2129 | 2129 | 2129 | SA24M005 | Design Submission for Fire Extinguishers |  | 6 | -1 | 0 |  |  | X | E000#UdSf
2130 | 2130 | 2130 | 2130 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Mechanical Design Submission for Fire Extinguishers Drafting / Preparation | 1 | FEXT | E000 | 00E1 | E000FEXT00E1
2131 | 2131 | 2131 | 2131 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Mechanical Design Submission for Fire Extinguishers Submission | 2 | FEXT | E000 | 00E2 | E000FEXT00E2
2132 | 2132 | 2132 | 2132 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Mechanical Design Submission for Fire Extinguishers Review / Evaluation | 3 | FEXT | E000 | 00E3 | E000FEXT00E3
2133 | 2133 | 2133 | 2133 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Mechanical Design Submission for Fire Extinguishers Approval with Comments | 4 | FEXT | E000 | 00E4 | E000FEXT00E4
2134 | 2134 | 2134 | 2134 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Mechanical Design Submission for Fire Extinguishers FINAL Approval | 5 | FEXT | E000 | 00E5 | E000FEXT00E5
2135 | 2135 | 2135 | 2135 | SA24M005 | HVAC Design Calculation and Drawings for Material Submittal for Security Building & toilet |  | 6 | -1 | 0 |  |  | X
2136 | 2136 | 2136 | 2136 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Mechanical HVAC Design Calculation and Drawings for Material Submittal for Security Building & toilet Drafting / Preparation | 1 | MHVAC | E000 | 00E1 | E000#aIVL00E1
2137 | 2137 | 2137 | 2137 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Mechanical HVAC Design Calculation and Drawings for Material Submittal for Security Building & toilet Submission | 2 | MHVAC | E000 | 00E2 | E000#aIVL00E2
2138 | 2138 | 2138 | 2138 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Mechanical HVAC Design Calculation and Drawings for Material Submittal for Security Building & toilet Review / Evaluation | 3 | MHVAC | E000 | 00E3 | E000#aIVL00E3
2139 | 2139 | 2139 | 2139 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Mechanical HVAC Design Calculation and Drawings for Material Submittal for Security Building & toilet Approval with Comments | 4 | MHVAC | E000 | 00E4 | E000#aIVL00E4
2140 | 2140 | 2140 | 2140 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Mechanical HVAC Design Calculation and Drawings for Material Submittal for Security Building & toilet FINAL Approval | 5 | MHVAC | E000 | 00E5 | E000#aIVL00E5
2141 | 2141 | 2141 | 2141 | SA24M005 | Pump House Ventilation System Design Calculation and Drawings |  | 6 | -1 | 0 |  |  | X | E000#aIVL
2142 | 2142 | 2142 | 2142 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Mechanical Pump House Ventilation System Design Calculation and Drawings Drafting / Preparation | 1 | PHV | E000 | 00E1 | E000PHV00E1
2143 | 2143 | 2143 | 2143 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Mechanical Pump House Ventilation System Design Calculation and Drawings Submission | 2 | PHV | E000 | 00E2 | E000PHV00E2
2144 | 2144 | 2144 | 2144 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Mechanical Pump House Ventilation System Design Calculation and Drawings Review / Evaluation | 3 | PHV | E000 | 00E3 | E000PHV00E3
2145 | 2145 | 2145 | 2145 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Mechanical Pump House Ventilation System Design Calculation and Drawings Approval with Comments | 4 | PHV | E000 | 00E4 | E000PHV00E4
2146 | 2146 | 2146 | 2146 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Mechanical Pump House Ventilation System Design Calculation and Drawings FINAL Approval | 5 | PHV | E000 | 00E5 | E000PHV00E5
2147 | 2147 | 2147 | 2147 | SA24M005 | Plumbing System Design Calculation and Drawings for Guard House Toilet |  | 6 | -1 | 0 |  |  | X
2148 | 2148 | 2148 | 2148 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Mechanical Plumbing System Design Calculation and Drawings for Guard House Toilet Drafting / Preparation | 1 | PLUMB | E000 | 00E1 | E000#YJLe00E1
2149 | 2149 | 2149 | 2149 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Mechanical Plumbing System Design Calculation and Drawings for Guard House Toilet Submission | 2 | PLUMB | E000 | 00E2 | E000#YJLe00E2
2150 | 2150 | 2150 | 2150 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Mechanical Plumbing System Design Calculation and Drawings for Guard House Toilet Review / Evaluation | 3 | PLUMB | E000 | 00E3 | E000#YJLe00E3
2151 | 2151 | 2151 | 2151 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Mechanical Plumbing System Design Calculation and Drawings for Guard House Toilet Approval with Comments | 4 | PLUMB | E000 | 00E4 | E000#YJLe00E4
2152 | 2152 | 2152 | 2152 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VI Mechanical Plumbing System Design Calculation and Drawings for Guard House Toilet FINAL Approval | 5 | PLUMB | E000 | 00E5 | E000#YJLe00E5
2153 | 2153 | 2153 | 2153 | SA24M005 | Phase- VII |  | 4 | -1 | 0 |  |  | X | E000#YJLe
2154 | 2154 | 2154 | 2154 | SA24M005 | Mechanical |  | 5 | -1 | 0 |  |  | X | E000#YJLe
2155 | 2155 | 2155 | 2155 | SA24M005 | ITP Submission for FACP |  | 6 | -1 | 0 |  |  | X | E000#YJLe
2156 | 2156 | 2156 | 2156 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Mechanical ITP Submission for FACP Drafting / Preparation | 1 | 0ITP | E000 | 00E1 | E0000ITP00E1
2157 | 2157 | 2157 | 2157 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Mechanical ITP Submission for FACP Submission | 2 | 0ITP | E000 | 00E2 | E0000ITP00E2
2158 | 2158 | 2158 | 2158 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Mechanical ITP Submission for FACP Review / Evaluation | 3 | 0ITP | E000 | 00E3 | E0000ITP00E3
2159 | 2159 | 2159 | 2159 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Mechanical ITP Submission for FACP Approval with Comments | 4 | 0ITP | E000 | 00E4 | E0000ITP00E4
2160 | 2160 | 2160 | 2160 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Mechanical ITP Submission for FACP FINAL Approval | 5 | 0ITP | E000 | 00E5 | E0000ITP00E5
2161 | 2161 | 2161 | 2161 | SA24M005 | Third Party Inspector submission for FACP FAT |  | 6 | -1 | 0 |  |  | X
2162 | 2162 | 2162 | 2162 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Mechanical Third Party Inspector submission for FACP FAT Drafting / Preparation | 1 | 0FACP | E000 | 00E1 | E0000FACP00E1
2163 | 2163 | 2163 | 2163 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Mechanical Third Party Inspector submission for FACP FAT Submission | 2 | 0FACP | E000 | 00E2 | E0000FACP00E2
2164 | 2164 | 2164 | 2164 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Mechanical Third Party Inspector submission for FACP FAT Review / Evaluation | 3 | 0FACP | E000 | 00E3 | E0000FACP00E3
2165 | 2165 | 2165 | 2165 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Mechanical Third Party Inspector submission for FACP FAT Approval with Comments | 4 | 0FACP | E000 | 00E4 | E0000FACP00E4
2166 | 2166 | 2166 | 2166 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Mechanical Third Party Inspector submission for FACP FAT FINAL Approval | 5 | 0FACP | E000 | 00E5 | E0000FACP00E5
2167 | 2167 | 2167 | 2167 | SA24M005 | FAT Reports for Fire Alarm Control Panel |  | 6 | -1 | 0 |  |  | X
2168 | 2168 | 2168 | 2168 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Mechanical FAT Reports for Fire Alarm Control Panel Drafting / Preparation | 1 | MFACP | E000 | 00E1 | E000MFACP00E1
2169 | 2169 | 2169 | 2169 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Mechanical FAT Reports for Fire Alarm Control Panel Submission | 2 | MFACP | E000 | 00E2 | E000MFACP00E2
2170 | 2170 | 2170 | 2170 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Mechanical FAT Reports for Fire Alarm Control Panel Review / Evaluation | 3 | MFACP | E000 | 00E3 | E000MFACP00E3
2171 | 2171 | 2171 | 2171 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Mechanical FAT Reports for Fire Alarm Control Panel Approval with Comments | 4 | MFACP | E000 | 00E4 | E000MFACP00E4
2172 | 2172 | 2172 | 2172 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Mechanical FAT Reports for Fire Alarm Control Panel FINAL Approval | 5 | MFACP | E000 | 00E5 | E000MFACP00E5
2173 | 2173 | 2173 | 2173 | SA24M005 | SAS |  | 5 | -1 | 0 |  |  | X
2174 | 2174 | 2174 | 2174 | SA24M005 | SAS FAT (NOMINEES & SCHEDULE ) |  | 6 | -1 | 0 |  |  | X
2175 | 2175 | 2175 | 2175 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII SAS SAS FAT (NOMINEES & SCHEDULE ) Drafting / Preparation | 1 | 0SASP | E000 | 00E1 | E000#yUai00E1
2176 | 2176 | 2176 | 2176 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII SAS SAS FAT (NOMINEES & SCHEDULE ) Submission | 2 | 0SASP | E000 | 00E2 | E000#yUai00E2
2177 | 2177 | 2177 | 2177 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII SAS SAS FAT (NOMINEES & SCHEDULE ) Review / Evaluation | 3 | 0SASP | E000 | 00E3 | E000#yUai00E3
2178 | 2178 | 2178 | 2178 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII SAS SAS FAT (NOMINEES & SCHEDULE ) Approval with Comments | 4 | 0SASP | E000 | 00E4 | E000#yUai00E4
2179 | 2179 | 2179 | 2179 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII SAS SAS FAT (NOMINEES & SCHEDULE ) FINAL Approval | 5 | 0SASP | E000 | 00E5 | E000#yUai00E5
2180 | 2180 | 2180 | 2180 | SA24M005 | SAS FAT REPORT |  | 6 | -1 | 0 |  |  | X | E000#yUai
2181 | 2181 | 2181 | 2181 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII SAS SAS FAT REPORT Drafting / Preparation | 1 | 0SASP | E000 | 00E1 | E000#HgEg00E1
2182 | 2182 | 2182 | 2182 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII SAS SAS FAT REPORT Submission | 2 | 0SASP | E000 | 00E2 | E000#HgEg00E2
2183 | 2183 | 2183 | 2183 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII SAS SAS FAT REPORT Review / Evaluation | 3 | 0SASP | E000 | 00E3 | E000#HgEg00E3
2184 | 2184 | 2184 | 2184 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII SAS SAS FAT REPORT Approval with Comments | 4 | 0SASP | E000 | 00E4 | E000#HgEg00E4
2185 | 2185 | 2185 | 2185 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII SAS SAS FAT REPORT FINAL Approval | 5 | 0SASP | E000 | 00E5 | E000#HgEg00E5
2186 | 2186 | 2186 | 2186 | SA24M005 | SCADA FAT REPORT |  | 6 | -1 | 0 |  |  | X | E000#HgEg
2187 | 2187 | 2187 | 2187 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII SAS SCADA FAT REPORT Drafting / Preparation | 1 | SCADA | E000 | 00E1 | E000#Vyzj00E1
2188 | 2188 | 2188 | 2188 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII SAS SCADA FAT REPORT Submission | 2 | SCADA | E000 | 00E2 | E000#Vyzj00E2
2189 | 2189 | 2189 | 2189 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII SAS SCADA FAT REPORT Review / Evaluation | 3 | SCADA | E000 | 00E3 | E000#Vyzj00E3
2190 | 2190 | 2190 | 2190 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII SAS SCADA FAT REPORT Approval with Comments | 4 | SCADA | E000 | 00E4 | E000#Vyzj00E4
2191 | 2191 | 2191 | 2191 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII SAS SCADA FAT REPORT FINAL Approval | 5 | SCADA | E000 | 00E5 | E000#Vyzj00E5
2192 | 2192 | 2192 | 2192 | SA24M005 | DSM FAT REPORT |  | 6 | -1 | 0 |  |  | X | E000#Vyzj
2193 | 2193 | 2193 | 2193 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII SAS DSM FAT REPORT Drafting / Preparation | 1 | DSASM | E000 | 00E1 | E000DSASM00E1
2194 | 2194 | 2194 | 2194 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII SAS DSM FAT REPORT Submission | 2 | DSASM | E000 | 00E2 | E000DSASM00E2
2195 | 2195 | 2195 | 2195 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII SAS DSM FAT REPORT Review / Evaluation | 3 | DSASM | E000 | 00E3 | E000DSASM00E3
2196 | 2196 | 2196 | 2196 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII SAS DSM FAT REPORT Approval with Comments | 4 | DSASM | E000 | 00E4 | E000DSASM00E4
2197 | 2197 | 2197 | 2197 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII SAS DSM FAT REPORT FINAL Approval | 5 | DSASM | E000 | 00E5 | E000DSASM00E5
2198 | 2198 | 2198 | 2198 | SA24M005 | Telecom |  | 5 | -1 | 0 |  |  | X
2199 | 2199 | 2199 | 2199 | SA24M005 | FOC- NMFOC |  | 6 | -1 | 0 |  |  | X
2200 | 2200 | 2200 | 2200 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom FOC- NMFOC Drafting / Preparation | 1 | #EHpG | E000 | 00E1 | E000#EHpG00E1
2201 | 2201 | 2201 | 2201 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom FOC- NMFOC Submission | 2 | #EHpG | E000 | 00E2 | E000#EHpG00E2
2202 | 2202 | 2202 | 2202 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom FOC- NMFOC Review / Evaluation | 3 | #EHpG | E000 | 00E3 | E000#EHpG00E3
2203 | 2203 | 2203 | 2203 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom FOC- NMFOC Approval with Comments | 4 | #EHpG | E000 | 00E4 | E000#EHpG00E4
2204 | 2204 | 2204 | 2204 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom FOC- NMFOC FINAL Approval | 5 | #EHpG | E000 | 00E5 | E000#EHpG00E5
2205 | 2205 | 2205 | 2205 | SA24M005 | FOC- OPGW |  | 6 | -1 | 0 |  |  | X
2206 | 2206 | 2206 | 2206 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom FOC- OPGW Drafting / Preparation | 1 | F0COPG | E000 | 00E1 | E000F0COPG00E1
2207 | 2207 | 2207 | 2207 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom FOC- OPGW Submission | 2 | F0COPG | E000 | 00E2 | E000F0COPG00E2
2208 | 2208 | 2208 | 2208 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom FOC- OPGW Review / Evaluation | 3 | F0COPG | E000 | 00E3 | E000F0COPG00E3
2209 | 2209 | 2209 | 2209 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom FOC- OPGW Approval with Comments | 4 | F0COPG | E000 | 00E4 | E000F0COPG00E4
2210 | 2210 | 2210 | 2210 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom FOC- OPGW FINAL Approval | 5 | F0COPG | E000 | 00E5 | E000F0COPG00E5
2211 | 2211 | 2211 | 2211 | SA24M005 | BATTERY CHARGER AND BATTERY BANK FOR COMMUNICATION |  | 6 | -1 | 0 |  |  | X
2212 | 2212 | 2212 | 2212 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom BATTERY CHARGER AND BATTERY BANK FOR COMMUNICATION Drafting / Preparation | 1 | TBATB | E000 | 00E1 | E000#kAii00E1
2213 | 2213 | 2213 | 2213 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom BATTERY CHARGER AND BATTERY BANK FOR COMMUNICATION Submission | 2 | TBATB | E000 | 00E2 | E000#kAii00E2
2214 | 2214 | 2214 | 2214 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom BATTERY CHARGER AND BATTERY BANK FOR COMMUNICATION Review / Evaluation | 3 | TBATB | E000 | 00E3 | E000#kAii00E3
2215 | 2215 | 2215 | 2215 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom BATTERY CHARGER AND BATTERY BANK FOR COMMUNICATION Approval with Comments | 4 | TBATB | E000 | 00E4 | E000#kAii00E4
2216 | 2216 | 2216 | 2216 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom BATTERY CHARGER AND BATTERY BANK FOR COMMUNICATION FINAL Approval | 5 | TBATB | E000 | 00E5 | E000#kAii00E5
2217 | 2217 | 2217 | 2217 | SA24M005 | DXC & DVM FIBER OPTIC COMMUNICATION SYSTEM EQUIPMENT |  | 6 | -1 | 0 |  |  | X | E000#kAii
2218 | 2218 | 2218 | 2218 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom DXC & DVM FIBER OPTIC COMMUNICATION SYSTEM EQUIPMENT Drafting / Preparation | 1 | TDXC | E000 | 00E1 | E000#VzQG00E1
2219 | 2219 | 2219 | 2219 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom DXC & DVM FIBER OPTIC COMMUNICATION SYSTEM EQUIPMENT Submission | 2 | TDXC | E000 | 00E2 | E000#VzQG00E2
2220 | 2220 | 2220 | 2220 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom DXC & DVM FIBER OPTIC COMMUNICATION SYSTEM EQUIPMENT Review / Evaluation | 3 | TDXC | E000 | 00E3 | E000#VzQG00E3
2221 | 2221 | 2221 | 2221 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom DXC & DVM FIBER OPTIC COMMUNICATION SYSTEM EQUIPMENT Approval with Comments | 4 | TDXC | E000 | 00E4 | E000#VzQG00E4
2222 | 2222 | 2222 | 2222 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom DXC & DVM FIBER OPTIC COMMUNICATION SYSTEM EQUIPMENT FINAL Approval | 5 | TDXC | E000 | 00E5 | E000#VzQG00E5
2223 | 2223 | 2223 | 2223 | SA24M005 | MPLS-TP SYSTEMS |  | 6 | -1 | 0 |  |  | X | E000#VzQG
2224 | 2224 | 2224 | 2224 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom MPLS-TP SYSTEMS Drafting / Preparation | 1 | MPLS-TP | E000 | 00E1 | E000#MpPA00E1
2225 | 2225 | 2225 | 2225 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom MPLS-TP SYSTEMS Submission | 2 | MPLS-TP | E000 | 00E2 | E000#MpPA00E2
2226 | 2226 | 2226 | 2226 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom MPLS-TP SYSTEMS Review / Evaluation | 3 | MPLS-TP | E000 | 00E3 | E000#MpPA00E3
2227 | 2227 | 2227 | 2227 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom MPLS-TP SYSTEMS Approval with Comments | 4 | MPLS-TP | E000 | 00E4 | E000#MpPA00E4
2228 | 2228 | 2228 | 2228 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom MPLS-TP SYSTEMS FINAL Approval | 5 | MPLS-TP | E000 | 00E5 | E000#MpPA00E5
2229 | 2229 | 2229 | 2229 | SA24M005 | BATTERY CHARGER & BATTERY BANK FOR COMMUNICATION |  | 6 | -1 | 0 |  |  | X | E000#MpPA
2230 | 2230 | 2230 | 2230 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom BATTERY CHARGER & BATTERY BANK FOR COMMUNICATION Drafting / Preparation | 1 | TBATB | E000 | 00E1 | E000#HTkW00E1
2231 | 2231 | 2231 | 2231 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom BATTERY CHARGER & BATTERY BANK FOR COMMUNICATION Submission | 2 | TBATB | E000 | 00E2 | E000#HTkW00E2
2232 | 2232 | 2232 | 2232 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom BATTERY CHARGER & BATTERY BANK FOR COMMUNICATION Review / Evaluation | 3 | TBATB | E000 | 00E3 | E000#HTkW00E3
2233 | 2233 | 2233 | 2233 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom BATTERY CHARGER & BATTERY BANK FOR COMMUNICATION Approval with Comments | 4 | TBATB | E000 | 00E4 | E000#HTkW00E4
2234 | 2234 | 2234 | 2234 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom BATTERY CHARGER & BATTERY BANK FOR COMMUNICATION FINAL Approval | 5 | TBATB | E000 | 00E5 | E000#HTkW00E5
2235 | 2235 | 2235 | 2235 | SA24M005 | PROTECTION SIGNALLING EQUIPMENT (PSE) |  | 6 | -1 | 0 |  |  | X | E000#HTkW
2236 | 2236 | 2236 | 2236 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom PROTECTION SIGNALLING EQUIPMENT (PSE) Drafting / Preparation | 1 | PTSE | E000 | 00E1 | E000#BCLU00E1
2237 | 2237 | 2237 | 2237 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom PROTECTION SIGNALLING EQUIPMENT (PSE) Submission | 2 | PTSE | E000 | 00E2 | E000#BCLU00E2
2238 | 2238 | 2238 | 2238 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom PROTECTION SIGNALLING EQUIPMENT (PSE) Review / Evaluation | 3 | PTSE | E000 | 00E3 | E000#BCLU00E3
2239 | 2239 | 2239 | 2239 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom PROTECTION SIGNALLING EQUIPMENT (PSE) Approval with Comments | 4 | PTSE | E000 | 00E4 | E000#BCLU00E4
2240 | 2240 | 2240 | 2240 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom PROTECTION SIGNALLING EQUIPMENT (PSE) FINAL Approval | 5 | PTSE | E000 | 00E5 | E000#BCLU00E5
2241 | 2241 | 2241 | 2241 | SA24M005 | AMI/AMR (COMMUNICATION PORTION ONLY) |  | 6 | -1 | 0 |  |  | X | E000#BCLU
2242 | 2242 | 2242 | 2242 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom AMI/AMR (COMMUNICATION PORTION ONLY) Drafting / Preparation | 1 | TAMI/A | E000 | 00E1 | E000TAMI/A00E1
2243 | 2243 | 2243 | 2243 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom AMI/AMR (COMMUNICATION PORTION ONLY) Submission | 2 | TAMI/A | E000 | 00E2 | E000TAMI/A00E2
2244 | 2244 | 2244 | 2244 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom AMI/AMR (COMMUNICATION PORTION ONLY) Review / Evaluation | 3 | TAMI/A | E000 | 00E3 | E000TAMI/A00E3
2245 | 2245 | 2245 | 2245 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom AMI/AMR (COMMUNICATION PORTION ONLY) Approval with Comments | 4 | TAMI/A | E000 | 00E4 | E000TAMI/A00E4
2246 | 2246 | 2246 | 2246 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom AMI/AMR (COMMUNICATION PORTION ONLY) FINAL Approval | 5 | TAMI/A | E000 | 00E5 | E000TAMI/A00E5
2247 | 2247 | 2247 | 2247 | SA24M005 | OPGW |  | 6 | -1 | 0 |  |  | X
2248 | 2248 | 2248 | 2248 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom OPGW Drafting / Preparation | 1 | 0OPGW | E000 | 00E1 | E0000OPGW00E1
2249 | 2249 | 2249 | 2249 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom OPGW Submission | 2 | 0OPGW | E000 | 00E2 | E0000OPGW00E2
2250 | 2250 | 2250 | 2250 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom OPGW Review / Evaluation | 3 | 0OPGW | E000 | 00E3 | E0000OPGW00E3
2251 | 2251 | 2251 | 2251 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom OPGW Approval with Comments | 4 | 0OPGW | E000 | 00E4 | E0000OPGW00E4
2252 | 2252 | 2252 | 2252 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom OPGW FINAL Approval | 5 | 0OPGW | E000 | 00E5 | E0000OPGW00E5
2253 | 2253 | 2253 | 2253 | SA24M005 | NMFOC |  | 6 | -1 | 0 |  |  | X
2254 | 2254 | 2254 | 2254 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom NMFOC Drafting / Preparation | 1 | TNMFOC | E000 | 00E1 | E000TNMFOC00E1
2255 | 2255 | 2255 | 2255 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom NMFOC Submission | 2 | TNMFOC | E000 | 00E2 | E000TNMFOC00E2
2256 | 2256 | 2256 | 2256 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom NMFOC Review / Evaluation | 3 | TNMFOC | E000 | 00E3 | E000TNMFOC00E3
2257 | 2257 | 2257 | 2257 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom NMFOC Approval with Comments | 4 | TNMFOC | E000 | 00E4 | E000TNMFOC00E4
2258 | 2258 | 2258 | 2258 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Design & Engineering Phase- VII Telecom NMFOC FINAL Approval | 5 | TNMFOC | E000 | 00E5 | E000TNMFOC00E5
2259 | 2259 | 2259 | 2259 | SA24M005 | Material Procurement |  | 3 | -1 | 0 |  |  | X
2260 | 2260 | 2260 | 2260 | SA24M005 | 380kV GIS |  | 4 | -1 | 0 |  |  | X
2261 | 2261 | 2261 | 2261 | SA24M005 | Purchase Request to SCM | P00000GIS00P1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 380kV GIS Purchase Request to SCM | 1 | 00GIS | P000 | 00P1 | P00000GIS00P1
2262 | 2262 | 2262 | 2262 | SA24M005 | Issue of RFQ | P00000GIS00P2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 380kV GIS Issue of RFQ | 2 | 00GIS | P000 | 00P2 | P00000GIS00P2
2263 | 2263 | 2263 | 2263 | SA24M005 | Receipt of Technical offer from Vendor | P00000GIS00P3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 380kV GIS Receipt of Technical offer from Vendor | 3 | 00GIS | P000 | 00P3 | P00000GIS00P3
2264 | 2264 | 2264 | 2264 | SA24M005 | Technical Evaluation by EDRC | P00000GIS00P4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 380kV GIS Technical Evaluation by EDRC | 4 | 00GIS | P000 | 00P4 | P00000GIS00P4
2265 | 2265 | 2265 | 2265 | SA24M005 | Final technical compliance from Vendor | P00000GIS00P5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 380kV GIS Final technical compliance from Vendor | 5 | 00GIS | P000 | 00P5 | P00000GIS00P5
2266 | 2266 | 2266 | 2266 | SA24M005 | Technical clearance by EDRC | P00000GIS00P6 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 380kV GIS Technical clearance by EDRC | 6 | 00GIS | P000 | 00P6 | P00000GIS00P6
2267 | 2267 | 2267 | 2267 | SA24M005 | Commercial Evaluation by SCM | P00000GIS00P7 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 380kV GIS Commercial Evaluation by SCM | 7 | 00GIS | P000 | 00P7 | P00000GIS00P7
2268 | 2268 | 2268 | 2268 | SA24M005 | Vendor negotiation & Finalization | P00000GIS00P8 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 380kV GIS Vendor negotiation & Finalization | 8 | 00GIS | P000 | 00P8 | P00000GIS00P8
2269 | 2269 | 2269 | 2269 | SA24M005 | HPC Approval / PO release to vendor | P00000GIS00P9 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 380kV GIS HPC Approval / PO release to vendor | 9 | 00GIS | P000 | 00P9 | P00000GIS00P9
2270 | 2270 | 2270 | 2270 | SA24M005 | 380kV HGIS |  | 4 | -1 | 0 |  |  | X
2271 | 2271 | 2271 | 2271 | SA24M005 | Purchase Request to SCM | P0000HGIS00P1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 380kV HGIS Purchase Request to SCM | 1 | 0HGIS | P000 | 00P1 | P0000HGIS00P1
2272 | 2272 | 2272 | 2272 | SA24M005 | Issue of RFQ | P0000HGIS00P2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 380kV HGIS Issue of RFQ | 2 | 0HGIS | P000 | 00P2 | P0000HGIS00P2
2273 | 2273 | 2273 | 2273 | SA24M005 | Receipt of Technical offer from Vendor | P0000HGIS00P3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 380kV HGIS Receipt of Technical offer from Vendor | 3 | 0HGIS | P000 | 00P3 | P0000HGIS00P3
2274 | 2274 | 2274 | 2274 | SA24M005 | Technical Evaluation by EDRC | P0000HGIS00P4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 380kV HGIS Technical Evaluation by EDRC | 4 | 0HGIS | P000 | 00P4 | P0000HGIS00P4
2275 | 2275 | 2275 | 2275 | SA24M005 | Final technical compliance from Vendor | P0000HGIS00P5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 380kV HGIS Final technical compliance from Vendor | 5 | 0HGIS | P000 | 00P5 | P0000HGIS00P5
2276 | 2276 | 2276 | 2276 | SA24M005 | Technical clearance by EDRC | P0000HGIS00P6 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 380kV HGIS Technical clearance by EDRC | 6 | 0HGIS | P000 | 00P6 | P0000HGIS00P6
2277 | 2277 | 2277 | 2277 | SA24M005 | Commercial Evaluation by SCM | P0000HGIS00P7 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 380kV HGIS Commercial Evaluation by SCM | 7 | 0HGIS | P000 | 00P7 | P0000HGIS00P7
2278 | 2278 | 2278 | 2278 | SA24M005 | Vendor negotiation & Finalization | P0000HGIS00P8 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 380kV HGIS Vendor negotiation & Finalization | 8 | 0HGIS | P000 | 00P8 | P0000HGIS00P8
2279 | 2279 | 2279 | 2279 | SA24M005 | HPC Approval / PO release to vendor | P0000HGIS00P9 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 380kV HGIS HPC Approval / PO release to vendor | 9 | 0HGIS | P000 | 00P9 | P0000HGIS00P9
2280 | 2280 | 2280 | 2280 | SA24M005 | 380kV GIB & Connectors |  | 4 | -1 | 0 |  |  | X
2281 | 2281 | 2281 | 2281 | SA24M005 | Purchase Request to SCM | P0000GIBC00P1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 380kV GIB & Connectors Purchase Request to SCM | 1 | 0GIBC | P000 | 00P1 | P0000GIBC00P1
2282 | 2282 | 2282 | 2282 | SA24M005 | Issue of RFQ | P0000GIBC00P2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 380kV GIB & Connectors Issue of RFQ | 2 | 0GIBC | P000 | 00P2 | P0000GIBC00P2
2283 | 2283 | 2283 | 2283 | SA24M005 | Receipt of Technical offer from Vendor | P0000GIBC00P3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 380kV GIB & Connectors Receipt of Technical offer from Vendor | 3 | 0GIBC | P000 | 00P3 | P0000GIBC00P3
2284 | 2284 | 2284 | 2284 | SA24M005 | Technical Evaluation by EDRC | P0000GIBC00P4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 380kV GIB & Connectors Technical Evaluation by EDRC | 4 | 0GIBC | P000 | 00P4 | P0000GIBC00P4
2285 | 2285 | 2285 | 2285 | SA24M005 | Final technical compliance from Vendor | P0000GIBC00P5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 380kV GIB & Connectors Final technical compliance from Vendor | 5 | 0GIBC | P000 | 00P5 | P0000GIBC00P5
2286 | 2286 | 2286 | 2286 | SA24M005 | Technical clearance by EDRC | P0000GIBC00P6 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 380kV GIB & Connectors Technical clearance by EDRC | 6 | 0GIBC | P000 | 00P6 | P0000GIBC00P6
2287 | 2287 | 2287 | 2287 | SA24M005 | Commercial Evaluation by SCM | P0000GIBC00P7 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 380kV GIB & Connectors Commercial Evaluation by SCM | 7 | 0GIBC | P000 | 00P7 | P0000GIBC00P7
2288 | 2288 | 2288 | 2288 | SA24M005 | Vendor negotiation & Finalization | P0000GIBC00P8 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 380kV GIB & Connectors Vendor negotiation & Finalization | 8 | 0GIBC | P000 | 00P8 | P0000GIBC00P8
2289 | 2289 | 2289 | 2289 | SA24M005 | HPC Approval / PO release to vendor | P0000GIBC00P9 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 380kV GIB & Connectors HPC Approval / PO release to vendor | 9 | 0GIBC | P000 | 00P9 | P0000GIBC00P9
2290 | 2290 | 2290 | 2290 | SA24M005 | 2500KVA Station Service Transformers |  | 4 | -1 | 0 |  |  | X
2291 | 2291 | 2291 | 2291 | SA24M005 | Purchase Request to SCM | P0000STRF00P1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 2500KVA Station Service Transformers Purchase Request to SCM | 1 | #lrtQ | P000 | 00P1 | P000#lrtQ00P1
2292 | 2292 | 2292 | 2292 | SA24M005 | Issue of RFQ | P0000STRF00P2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 2500KVA Station Service Transformers Issue of RFQ | 2 | #lrtQ | P000 | 00P2 | P000#lrtQ00P2
2293 | 2293 | 2293 | 2293 | SA24M005 | Receipt of Technical offer from Vendor | P0000STRF00P3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 2500KVA Station Service Transformers Receipt of Technical offer from Vendor | 3 | #lrtQ | P000 | 00P3 | P000#lrtQ00P3
2294 | 2294 | 2294 | 2294 | SA24M005 | Technical Evaluation by EDRC | P0000STRF00P4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 2500KVA Station Service Transformers Technical Evaluation by EDRC | 4 | #lrtQ | P000 | 00P4 | P000#lrtQ00P4
2295 | 2295 | 2295 | 2295 | SA24M005 | Final technical compliance from Vendor | P0000STRF00P5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 2500KVA Station Service Transformers Final technical compliance from Vendor | 5 | #lrtQ | P000 | 00P5 | P000#lrtQ00P5
2296 | 2296 | 2296 | 2296 | SA24M005 | Technical clearance by EDRC | P0000STRF00P6 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 2500KVA Station Service Transformers Technical clearance by EDRC | 6 | #lrtQ | P000 | 00P6 | P000#lrtQ00P6
2297 | 2297 | 2297 | 2297 | SA24M005 | Commercial Evaluation by SCM | P0000STRF00P7 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 2500KVA Station Service Transformers Commercial Evaluation by SCM | 7 | #lrtQ | P000 | 00P7 | P000#lrtQ00P7
2298 | 2298 | 2298 | 2298 | SA24M005 | Vendor negotiation & Finalization | P0000STRF00P8 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 2500KVA Station Service Transformers Vendor negotiation & Finalization | 8 | #lrtQ | P000 | 00P8 | P000#lrtQ00P8
2299 | 2299 | 2299 | 2299 | SA24M005 | HPC Approval / PO release to vendor | P0000STRF00P9 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 2500KVA Station Service Transformers HPC Approval / PO release to vendor | 9 | #lrtQ | P000 | 00P9 | P000#lrtQ00P9
2300 | 2300 | 2300 | 2300 | SA24M005 | 120MVAR Bus Shunt Reactor & Accessories |  | 4 | -1 | 0 |  |  | X
2301 | 2301 | 2301 | 2301 | SA24M005 | Purchase Request to SCM | P00000BSR00P1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 120MVAR Bus Shunt Reactor & Accessories Purchase Request to SCM | 1 | 00BSR | P000 | 00P1 | P00000BSR00P1
2302 | 2302 | 2302 | 2302 | SA24M005 | Issue of RFQ | P00000BSR00P2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 120MVAR Bus Shunt Reactor & Accessories Issue of RFQ | 2 | 00BSR | P000 | 00P2 | P00000BSR00P2
2303 | 2303 | 2303 | 2303 | SA24M005 | Receipt of Technical offer from Vendor | P00000BSR00P3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 120MVAR Bus Shunt Reactor & Accessories Receipt of Technical offer from Vendor | 3 | 00BSR | P000 | 00P3 | P00000BSR00P3
2304 | 2304 | 2304 | 2304 | SA24M005 | Technical Evaluation by EDRC | P00000BSR00P4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 120MVAR Bus Shunt Reactor & Accessories Technical Evaluation by EDRC | 4 | 00BSR | P000 | 00P4 | P00000BSR00P4
2305 | 2305 | 2305 | 2305 | SA24M005 | Final technical compliance from Vendor | P00000BSR00P5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 120MVAR Bus Shunt Reactor & Accessories Final technical compliance from Vendor | 5 | 00BSR | P000 | 00P5 | P00000BSR00P5
2306 | 2306 | 2306 | 2306 | SA24M005 | Technical clearance by EDRC | P00000BSR00P6 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 120MVAR Bus Shunt Reactor & Accessories Technical clearance by EDRC | 6 | 00BSR | P000 | 00P6 | P00000BSR00P6
2307 | 2307 | 2307 | 2307 | SA24M005 | Commercial Evaluation by SCM | P00000BSR00P7 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 120MVAR Bus Shunt Reactor & Accessories Commercial Evaluation by SCM | 7 | 00BSR | P000 | 00P7 | P00000BSR00P7
2308 | 2308 | 2308 | 2308 | SA24M005 | Vendor negotiation & Finalization | P00000BSR00P8 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 120MVAR Bus Shunt Reactor & Accessories Vendor negotiation & Finalization | 8 | 00BSR | P000 | 00P8 | P00000BSR00P8
2309 | 2309 | 2309 | 2309 | SA24M005 | HPC Approval / PO release to vendor | P00000BSR00P9 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 120MVAR Bus Shunt Reactor & Accessories HPC Approval / PO release to vendor | 9 | 00BSR | P000 | 00P9 | P00000BSR00P9
2310 | 2310 | 2310 | 2310 | SA24M005 | 150MVAR Line Shunt Reactor & Accessories |  | 4 | -1 | 0 |  |  | X
2311 | 2311 | 2311 | 2311 | SA24M005 | Purchase Request to SCM | P00000LSR00P1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 150MVAR Line Shunt Reactor & Accessories Purchase Request to SCM | 1 | 00LSR | P000 | 00P1 | P00000LSR00P1
2312 | 2312 | 2312 | 2312 | SA24M005 | Issue of RFQ | P00000LSR00P2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 150MVAR Line Shunt Reactor & Accessories Issue of RFQ | 2 | 00LSR | P000 | 00P2 | P00000LSR00P2
2313 | 2313 | 2313 | 2313 | SA24M005 | Receipt of Technical offer from Vendor | P00000LSR00P3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 150MVAR Line Shunt Reactor & Accessories Receipt of Technical offer from Vendor | 3 | 00LSR | P000 | 00P3 | P00000LSR00P3
2314 | 2314 | 2314 | 2314 | SA24M005 | Technical Evaluation by EDRC | P00000LSR00P4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 150MVAR Line Shunt Reactor & Accessories Technical Evaluation by EDRC | 4 | 00LSR | P000 | 00P4 | P00000LSR00P4
2315 | 2315 | 2315 | 2315 | SA24M005 | Final technical compliance from Vendor | P00000LSR00P5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 150MVAR Line Shunt Reactor & Accessories Final technical compliance from Vendor | 5 | 00LSR | P000 | 00P5 | P00000LSR00P5
2316 | 2316 | 2316 | 2316 | SA24M005 | Technical clearance by EDRC | P00000LSR00P6 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 150MVAR Line Shunt Reactor & Accessories Technical clearance by EDRC | 6 | 00LSR | P000 | 00P6 | P00000LSR00P6
2317 | 2317 | 2317 | 2317 | SA24M005 | Commercial Evaluation by SCM | P00000LSR00P7 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 150MVAR Line Shunt Reactor & Accessories Commercial Evaluation by SCM | 7 | 00LSR | P000 | 00P7 | P00000LSR00P7
2318 | 2318 | 2318 | 2318 | SA24M005 | Vendor negotiation & Finalization | P00000LSR00P8 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 150MVAR Line Shunt Reactor & Accessories Vendor negotiation & Finalization | 8 | 00LSR | P000 | 00P8 | P00000LSR00P8
2319 | 2319 | 2319 | 2319 | SA24M005 | HPC Approval / PO release to vendor | P00000LSR00P9 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 150MVAR Line Shunt Reactor & Accessories HPC Approval / PO release to vendor | 9 | 00LSR | P000 | 00P9 | P00000LSR00P9
2320 | 2320 | 2320 | 2320 | SA24M005 | Neutral Grounding Reactor (NGR) |  | 4 | -1 | 0 |  |  | X
2321 | 2321 | 2321 | 2321 | SA24M005 | Purchase Request to SCM | P00000NGR00P1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Neutral Grounding Reactor (NGR) Purchase Request to SCM | 1 | #BNPf | P000 | 00P1 | P000#BNPf00P1
2322 | 2322 | 2322 | 2322 | SA24M005 | Issue of RFQ | P00000NGR00P2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Neutral Grounding Reactor (NGR) Issue of RFQ | 2 | #BNPf | P000 | 00P2 | P000#BNPf00P2
2323 | 2323 | 2323 | 2323 | SA24M005 | Receipt of Technical offer from Vendor | P00000NGR00P3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Neutral Grounding Reactor (NGR) Receipt of Technical offer from Vendor | 3 | #BNPf | P000 | 00P3 | P000#BNPf00P3
2324 | 2324 | 2324 | 2324 | SA24M005 | Technical Evaluation by EDRC | P00000NGR00P4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Neutral Grounding Reactor (NGR) Technical Evaluation by EDRC | 4 | #BNPf | P000 | 00P4 | P000#BNPf00P4
2325 | 2325 | 2325 | 2325 | SA24M005 | Final technical compliance from Vendor | P00000NGR00P5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Neutral Grounding Reactor (NGR) Final technical compliance from Vendor | 5 | #BNPf | P000 | 00P5 | P000#BNPf00P5
2326 | 2326 | 2326 | 2326 | SA24M005 | Technical clearance by EDRC | P00000NGR00P6 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Neutral Grounding Reactor (NGR) Technical clearance by EDRC | 6 | #BNPf | P000 | 00P6 | P000#BNPf00P6
2327 | 2327 | 2327 | 2327 | SA24M005 | Commercial Evaluation by SCM | P00000NGR00P7 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Neutral Grounding Reactor (NGR) Commercial Evaluation by SCM | 7 | #BNPf | P000 | 00P7 | P000#BNPf00P7
2328 | 2328 | 2328 | 2328 | SA24M005 | Vendor negotiation & Finalization | P00000NGR00P8 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Neutral Grounding Reactor (NGR) Vendor negotiation & Finalization | 8 | #BNPf | P000 | 00P8 | P000#BNPf00P8
2329 | 2329 | 2329 | 2329 | SA24M005 | HPC Approval / PO release to vendor | P00000NGR00P9 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Neutral Grounding Reactor (NGR) HPC Approval / PO release to vendor | 9 | #BNPf | P000 | 00P9 | P000#BNPf00P9
2330 | 2330 | 2330 | 2330 | SA24M005 | 13.8kV Switchgear & Accessories |  | 4 | -1 | 0 |  |  | X
2331 | 2331 | 2331 | 2331 | SA24M005 | Purchase Request to SCM | P0000SWGR00P1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 13.8kV Switchgear & Accessories Purchase Request to SCM | 1 | 0SWGR | P000 | 00P1 | P0000SWGR00P1
2332 | 2332 | 2332 | 2332 | SA24M005 | Issue of RFQ | P0000SWGR00P2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 13.8kV Switchgear & Accessories Issue of RFQ | 2 | 0SWGR | P000 | 00P2 | P0000SWGR00P2
2333 | 2333 | 2333 | 2333 | SA24M005 | Receipt of Technical offer from Vendor | P0000SWGR00P3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 13.8kV Switchgear & Accessories Receipt of Technical offer from Vendor | 3 | 0SWGR | P000 | 00P3 | P0000SWGR00P3
2334 | 2334 | 2334 | 2334 | SA24M005 | Technical Evaluation by EDRC | P0000SWGR00P4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 13.8kV Switchgear & Accessories Technical Evaluation by EDRC | 4 | 0SWGR | P000 | 00P4 | P0000SWGR00P4
2335 | 2335 | 2335 | 2335 | SA24M005 | Final technical compliance from Vendor | P0000SWGR00P5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 13.8kV Switchgear & Accessories Final technical compliance from Vendor | 5 | 0SWGR | P000 | 00P5 | P0000SWGR00P5
2336 | 2336 | 2336 | 2336 | SA24M005 | Technical clearance by EDRC | P0000SWGR00P6 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 13.8kV Switchgear & Accessories Technical clearance by EDRC | 6 | 0SWGR | P000 | 00P6 | P0000SWGR00P6
2337 | 2337 | 2337 | 2337 | SA24M005 | Commercial Evaluation by SCM | P0000SWGR00P7 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 13.8kV Switchgear & Accessories Commercial Evaluation by SCM | 7 | 0SWGR | P000 | 00P7 | P0000SWGR00P7
2338 | 2338 | 2338 | 2338 | SA24M005 | Vendor negotiation & Finalization | P0000SWGR00P8 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 13.8kV Switchgear & Accessories Vendor negotiation & Finalization | 8 | 0SWGR | P000 | 00P8 | P0000SWGR00P8
2339 | 2339 | 2339 | 2339 | SA24M005 | HPC Approval / PO release to vendor | P0000SWGR00P9 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 13.8kV Switchgear & Accessories HPC Approval / PO release to vendor | 9 | 0SWGR | P000 | 00P9 | P0000SWGR00P9
2340 | 2340 | 2340 | 2340 | SA24M005 | 380kV Surge Arrestor |  | 4 | -1 | 0 |  |  | X
2341 | 2341 | 2341 | 2341 | SA24M005 | Purchase Request to SCM | P0000SRGA00P1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 380kV Surge Arrestor Purchase Request to SCM | 1 | SRGA | P000 | 00P1 | P000#GuyD00P1
2342 | 2342 | 2342 | 2342 | SA24M005 | Issue of RFQ | P0000SRGA00P2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 380kV Surge Arrestor Issue of RFQ | 2 | SRGA | P000 | 00P2 | P000#GuyD00P2
2343 | 2343 | 2343 | 2343 | SA24M005 | Receipt of Technical offer from Vendor | P0000SRGA00P3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 380kV Surge Arrestor Receipt of Technical offer from Vendor | 3 | SRGA | P000 | 00P3 | P000#GuyD00P3
2344 | 2344 | 2344 | 2344 | SA24M005 | Technical Evaluation by EDRC | P0000SRGA00P4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 380kV Surge Arrestor Technical Evaluation by EDRC | 4 | SRGA | P000 | 00P4 | P000#GuyD00P4
2345 | 2345 | 2345 | 2345 | SA24M005 | Final technical compliance from Vendor | P0000SRGA00P5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 380kV Surge Arrestor Final technical compliance from Vendor | 5 | SRGA | P000 | 00P5 | P000#GuyD00P5
2346 | 2346 | 2346 | 2346 | SA24M005 | Technical clearance by EDRC | P0000SRGA00P6 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 380kV Surge Arrestor Technical clearance by EDRC | 6 | SRGA | P000 | 00P6 | P000#GuyD00P6
2347 | 2347 | 2347 | 2347 | SA24M005 | Commercial Evaluation by SCM | P0000SRGA00P7 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 380kV Surge Arrestor Commercial Evaluation by SCM | 7 | SRGA | P000 | 00P7 | P000#GuyD00P7
2348 | 2348 | 2348 | 2348 | SA24M005 | Vendor negotiation & Finalization | P0000SRGA00P8 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 380kV Surge Arrestor Vendor negotiation & Finalization | 8 | SRGA | P000 | 00P8 | P000#GuyD00P8
2349 | 2349 | 2349 | 2349 | SA24M005 | HPC Approval / PO release to vendor | P0000SRGA00P9 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 380kV Surge Arrestor HPC Approval / PO release to vendor | 9 | SRGA | P000 | 00P9 | P000#GuyD00P9
2350 | 2350 | 2350 | 2350 | SA24M005 | Tubular / ACSR Conductors |  | 4 | -1 | 0 |  |  | X | P000#GuyD
2351 | 2351 | 2351 | 2351 | SA24M005 | Purchase Request to SCM | P0000COND00P1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Tubular / ACSR Conductors Purchase Request to SCM | 1 | COND | P000 | 00P1 | P000COND00P1
2352 | 2352 | 2352 | 2352 | SA24M005 | Issue of RFQ | P0000COND00P2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Tubular / ACSR Conductors Issue of RFQ | 2 | COND | P000 | 00P2 | P000COND00P2
2353 | 2353 | 2353 | 2353 | SA24M005 | Receipt of Technical offer from Vendor | P0000COND00P3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Tubular / ACSR Conductors Receipt of Technical offer from Vendor | 3 | COND | P000 | 00P3 | P000COND00P3
2354 | 2354 | 2354 | 2354 | SA24M005 | Technical Evaluation by EDRC | P0000COND00P4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Tubular / ACSR Conductors Technical Evaluation by EDRC | 4 | COND | P000 | 00P4 | P000COND00P4
2355 | 2355 | 2355 | 2355 | SA24M005 | Final technical compliance from Vendor | P0000COND00P5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Tubular / ACSR Conductors Final technical compliance from Vendor | 5 | COND | P000 | 00P5 | P000COND00P5
2356 | 2356 | 2356 | 2356 | SA24M005 | Technical clearance by EDRC | P0000COND00P6 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Tubular / ACSR Conductors Technical clearance by EDRC | 6 | COND | P000 | 00P6 | P000COND00P6
2357 | 2357 | 2357 | 2357 | SA24M005 | Commercial Evaluation by SCM | P0000COND00P7 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Tubular / ACSR Conductors Commercial Evaluation by SCM | 7 | COND | P000 | 00P7 | P000COND00P7
2358 | 2358 | 2358 | 2358 | SA24M005 | Vendor negotiation & Finalization | P0000COND00P8 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Tubular / ACSR Conductors Vendor negotiation & Finalization | 8 | COND | P000 | 00P8 | P000COND00P8
2359 | 2359 | 2359 | 2359 | SA24M005 | HPC Approval / PO release to vendor | P0000COND00P9 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Tubular / ACSR Conductors HPC Approval / PO release to vendor | 9 | COND | P000 | 00P9 | P000COND00P9
2360 | 2360 | 2360 | 2360 | SA24M005 | HV/MV Power Cables (Bonding & Grounding of cables) |  | 4 | -1 | 0 |  |  | X
2361 | 2361 | 2361 | 2361 | SA24M005 | Purchase Request to SCM | P0000POWC00P1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement HV/MV Power Cables (Bonding & Grounding of cables) Purchase Request to SCM | 1 | POWC | P000 | 00P1 | P000POWC00P1
2362 | 2362 | 2362 | 2362 | SA24M005 | Issue of RFQ | P0000POWC00P2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement HV/MV Power Cables (Bonding & Grounding of cables) Issue of RFQ | 2 | POWC | P000 | 00P2 | P000POWC00P2
2363 | 2363 | 2363 | 2363 | SA24M005 | Receipt of Technical offer from Vendor | P0000POWC00P3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement HV/MV Power Cables (Bonding & Grounding of cables) Receipt of Technical offer from Vendor | 3 | POWC | P000 | 00P3 | P000POWC00P3
2364 | 2364 | 2364 | 2364 | SA24M005 | Technical Evaluation by EDRC | P0000POWC00P4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement HV/MV Power Cables (Bonding & Grounding of cables) Technical Evaluation by EDRC | 4 | POWC | P000 | 00P4 | P000POWC00P4
2365 | 2365 | 2365 | 2365 | SA24M005 | Final technical compliance from Vendor | P0000POWC00P5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement HV/MV Power Cables (Bonding & Grounding of cables) Final technical compliance from Vendor | 5 | POWC | P000 | 00P5 | P000POWC00P5
2366 | 2366 | 2366 | 2366 | SA24M005 | Technical clearance by EDRC | P0000POWC00P6 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement HV/MV Power Cables (Bonding & Grounding of cables) Technical clearance by EDRC | 6 | POWC | P000 | 00P6 | P000POWC00P6
2367 | 2367 | 2367 | 2367 | SA24M005 | Commercial Evaluation by SCM | P0000POWC00P7 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement HV/MV Power Cables (Bonding & Grounding of cables) Commercial Evaluation by SCM | 7 | POWC | P000 | 00P7 | P000POWC00P7
2368 | 2368 | 2368 | 2368 | SA24M005 | Vendor negotiation & Finalization | P0000POWC00P8 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement HV/MV Power Cables (Bonding & Grounding of cables) Vendor negotiation & Finalization | 8 | POWC | P000 | 00P8 | P000POWC00P8
2369 | 2369 | 2369 | 2369 | SA24M005 | HPC Approval / PO release to vendor | P0000POWC00P9 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement HV/MV Power Cables (Bonding & Grounding of cables) HPC Approval / PO release to vendor | 9 | POWC | P000 | 00P9 | P000POWC00P9
2370 | 2370 | 2370 | 2370 | SA24M005 | Cable Termination Kit |  | 4 | -1 | 0 |  |  | X
2371 | 2371 | 2371 | 2371 | SA24M005 | Purchase Request to SCM | P0000CTRM00P1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Cable Termination Kit Purchase Request to SCM | 1 | CTRM | P000 | 00P1 | P000CTRM00P1
2372 | 2372 | 2372 | 2372 | SA24M005 | Issue of RFQ | P0000CTRM00P2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Cable Termination Kit Issue of RFQ | 2 | CTRM | P000 | 00P2 | P000CTRM00P2
2373 | 2373 | 2373 | 2373 | SA24M005 | Receipt of Technical offer from Vendor | P0000CTRM00P3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Cable Termination Kit Receipt of Technical offer from Vendor | 3 | CTRM | P000 | 00P3 | P000CTRM00P3
2374 | 2374 | 2374 | 2374 | SA24M005 | Technical Evaluation by EDRC | P0000CTRM00P4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Cable Termination Kit Technical Evaluation by EDRC | 4 | CTRM | P000 | 00P4 | P000CTRM00P4
2375 | 2375 | 2375 | 2375 | SA24M005 | Final technical compliance from Vendor | P0000CTRM00P5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Cable Termination Kit Final technical compliance from Vendor | 5 | CTRM | P000 | 00P5 | P000CTRM00P5
2376 | 2376 | 2376 | 2376 | SA24M005 | Technical clearance by EDRC | P0000CTRM00P6 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Cable Termination Kit Technical clearance by EDRC | 6 | CTRM | P000 | 00P6 | P000CTRM00P6
2377 | 2377 | 2377 | 2377 | SA24M005 | Commercial Evaluation by SCM | P0000CTRM00P7 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Cable Termination Kit Commercial Evaluation by SCM | 7 | CTRM | P000 | 00P7 | P000CTRM00P7
2378 | 2378 | 2378 | 2378 | SA24M005 | Vendor negotiation & Finalization | P0000CTRM00P8 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Cable Termination Kit Vendor negotiation & Finalization | 8 | CTRM | P000 | 00P8 | P000CTRM00P8
2379 | 2379 | 2379 | 2379 | SA24M005 | HPC Approval / PO release to vendor | P0000CTRM00P9 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Cable Termination Kit HPC Approval / PO release to vendor | 9 | CTRM | P000 | 00P9 | P000CTRM00P9
2380 | 2380 | 2380 | 2380 | SA24M005 | 125V Battery Bank |  | 4 | -1 | 0 |  |  | X
2381 | 2381 | 2381 | 2381 | SA24M005 | Purchase Request to SCM | P0000BATB00P1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 125V Battery Bank Purchase Request to SCM | 1 | BATB | P000 | 00P1 | P000BATB00P1
2382 | 2382 | 2382 | 2382 | SA24M005 | Issue of RFQ | P0000BATB00P2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 125V Battery Bank Issue of RFQ | 2 | BATB | P000 | 00P2 | P000BATB00P2
2383 | 2383 | 2383 | 2383 | SA24M005 | Receipt of Technical offer from Vendor | P0000BATB00P3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 125V Battery Bank Receipt of Technical offer from Vendor | 3 | BATB | P000 | 00P3 | P000BATB00P3
2384 | 2384 | 2384 | 2384 | SA24M005 | Technical Evaluation by EDRC | P0000BATB00P4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 125V Battery Bank Technical Evaluation by EDRC | 4 | BATB | P000 | 00P4 | P000BATB00P4
2385 | 2385 | 2385 | 2385 | SA24M005 | Final technical compliance from Vendor | P0000BATB00P5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 125V Battery Bank Final technical compliance from Vendor | 5 | BATB | P000 | 00P5 | P000BATB00P5
2386 | 2386 | 2386 | 2386 | SA24M005 | Technical clearance by EDRC | P0000BATB00P6 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 125V Battery Bank Technical clearance by EDRC | 6 | BATB | P000 | 00P6 | P000BATB00P6
2387 | 2387 | 2387 | 2387 | SA24M005 | Commercial Evaluation by SCM | P0000BATB00P7 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 125V Battery Bank Commercial Evaluation by SCM | 7 | BATB | P000 | 00P7 | P000BATB00P7
2388 | 2388 | 2388 | 2388 | SA24M005 | Vendor negotiation & Finalization | P0000BATB00P8 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 125V Battery Bank Vendor negotiation & Finalization | 8 | BATB | P000 | 00P8 | P000BATB00P8
2389 | 2389 | 2389 | 2389 | SA24M005 | HPC Approval / PO release to vendor | P0000BATB00P9 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 125V Battery Bank HPC Approval / PO release to vendor | 9 | BATB | P000 | 00P9 | P000BATB00P9
2390 | 2390 | 2390 | 2390 | SA24M005 | 125V Battery Chargers |  | 4 | -1 | 0 |  |  | X
2391 | 2391 | 2391 | 2391 | SA24M005 | Purchase Request to SCM | P0000BATC00P1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 125V Battery Chargers Purchase Request to SCM | 1 | BATC | P000 | 00P1 | P000BATC00P1
2392 | 2392 | 2392 | 2392 | SA24M005 | Issue of RFQ | P0000BATC00P2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 125V Battery Chargers Issue of RFQ | 2 | BATC | P000 | 00P2 | P000BATC00P2
2393 | 2393 | 2393 | 2393 | SA24M005 | Receipt of Technical offer from Vendor | P0000BATC00P3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 125V Battery Chargers Receipt of Technical offer from Vendor | 3 | BATC | P000 | 00P3 | P000BATC00P3
2394 | 2394 | 2394 | 2394 | SA24M005 | Technical Evaluation by EDRC | P0000BATC00P4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 125V Battery Chargers Technical Evaluation by EDRC | 4 | BATC | P000 | 00P4 | P000BATC00P4
2395 | 2395 | 2395 | 2395 | SA24M005 | Final technical compliance from Vendor | P0000BATC00P5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 125V Battery Chargers Final technical compliance from Vendor | 5 | BATC | P000 | 00P5 | P000BATC00P5
2396 | 2396 | 2396 | 2396 | SA24M005 | Technical clearance by EDRC | P0000BATC00P6 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 125V Battery Chargers Technical clearance by EDRC | 6 | BATC | P000 | 00P6 | P000BATC00P6
2397 | 2397 | 2397 | 2397 | SA24M005 | Commercial Evaluation by SCM | P0000BATC00P7 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 125V Battery Chargers Commercial Evaluation by SCM | 7 | BATC | P000 | 00P7 | P000BATC00P7
2398 | 2398 | 2398 | 2398 | SA24M005 | Vendor negotiation & Finalization | P0000BATC00P8 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 125V Battery Chargers Vendor negotiation & Finalization | 8 | BATC | P000 | 00P8 | P000BATC00P8
2399 | 2399 | 2399 | 2399 | SA24M005 | HPC Approval / PO release to vendor | P0000BATC00P9 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement 125V Battery Chargers HPC Approval / PO release to vendor | 9 | BATC | P000 | 00P9 | P000BATC00P9
2400 | 2400 | 2400 | 2400 | SA24M005 | ACDB Main & Sub-Panels |  | 4 | -1 | 0 |  |  | X
2401 | 2401 | 2401 | 2401 | SA24M005 | Purchase Request to SCM | P0000ACDB00P1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement ACDB Main & Sub-Panels Purchase Request to SCM | 1 | ACDB | P000 | 00P1 | P000ACDB00P1
2402 | 2402 | 2402 | 2402 | SA24M005 | Issue of RFQ | P0000ACDB00P2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement ACDB Main & Sub-Panels Issue of RFQ | 2 | ACDB | P000 | 00P2 | P000ACDB00P2
2403 | 2403 | 2403 | 2403 | SA24M005 | Receipt of Technical offer from Vendor | P0000ACDB00P3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement ACDB Main & Sub-Panels Receipt of Technical offer from Vendor | 3 | ACDB | P000 | 00P3 | P000ACDB00P3
2404 | 2404 | 2404 | 2404 | SA24M005 | Technical Evaluation by EDRC | P0000ACDB00P4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement ACDB Main & Sub-Panels Technical Evaluation by EDRC | 4 | ACDB | P000 | 00P4 | P000ACDB00P4
2405 | 2405 | 2405 | 2405 | SA24M005 | Final technical compliance from Vendor | P0000ACDB00P5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement ACDB Main & Sub-Panels Final technical compliance from Vendor | 5 | ACDB | P000 | 00P5 | P000ACDB00P5
2406 | 2406 | 2406 | 2406 | SA24M005 | Technical clearance by EDRC | P0000ACDB00P6 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement ACDB Main & Sub-Panels Technical clearance by EDRC | 6 | ACDB | P000 | 00P6 | P000ACDB00P6
2407 | 2407 | 2407 | 2407 | SA24M005 | Commercial Evaluation by SCM | P0000ACDB00P7 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement ACDB Main & Sub-Panels Commercial Evaluation by SCM | 7 | ACDB | P000 | 00P7 | P000ACDB00P7
2408 | 2408 | 2408 | 2408 | SA24M005 | Vendor negotiation & Finalization | P0000ACDB00P8 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement ACDB Main & Sub-Panels Vendor negotiation & Finalization | 8 | ACDB | P000 | 00P8 | P000ACDB00P8
2409 | 2409 | 2409 | 2409 | SA24M005 | HPC Approval / PO release to vendor | P0000ACDB00P9 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement ACDB Main & Sub-Panels HPC Approval / PO release to vendor | 9 | ACDB | P000 | 00P9 | P000ACDB00P9
2410 | 2410 | 2410 | 2410 | SA24M005 | DCDB Main & Sub-Panels |  | 4 | -1 | 0 |  |  | X
2411 | 2411 | 2411 | 2411 | SA24M005 | Purchase Request to SCM | P0000DCDB00P1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement DCDB Main & Sub-Panels Purchase Request to SCM | 1 | DCDB | P000 | 00P1 | P000DCDB00P1
2412 | 2412 | 2412 | 2412 | SA24M005 | Issue of RFQ | P0000DCDB00P2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement DCDB Main & Sub-Panels Issue of RFQ | 2 | DCDB | P000 | 00P2 | P000DCDB00P2
2413 | 2413 | 2413 | 2413 | SA24M005 | Receipt of Technical offer from Vendor | P0000DCDB00P3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement DCDB Main & Sub-Panels Receipt of Technical offer from Vendor | 3 | DCDB | P000 | 00P3 | P000DCDB00P3
2414 | 2414 | 2414 | 2414 | SA24M005 | Technical Evaluation by EDRC | P0000DCDB00P4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement DCDB Main & Sub-Panels Technical Evaluation by EDRC | 4 | DCDB | P000 | 00P4 | P000DCDB00P4
2415 | 2415 | 2415 | 2415 | SA24M005 | Final technical compliance from Vendor | P0000DCDB00P5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement DCDB Main & Sub-Panels Final technical compliance from Vendor | 5 | DCDB | P000 | 00P5 | P000DCDB00P5
2416 | 2416 | 2416 | 2416 | SA24M005 | Technical clearance by EDRC | P0000DCDB00P6 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement DCDB Main & Sub-Panels Technical clearance by EDRC | 6 | DCDB | P000 | 00P6 | P000DCDB00P6
2417 | 2417 | 2417 | 2417 | SA24M005 | Commercial Evaluation by SCM | P0000DCDB00P7 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement DCDB Main & Sub-Panels Commercial Evaluation by SCM | 7 | DCDB | P000 | 00P7 | P000DCDB00P7
2418 | 2418 | 2418 | 2418 | SA24M005 | Vendor negotiation & Finalization | P0000DCDB00P8 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement DCDB Main & Sub-Panels Vendor negotiation & Finalization | 8 | DCDB | P000 | 00P8 | P000DCDB00P8
2419 | 2419 | 2419 | 2419 | SA24M005 | HPC Approval / PO release to vendor | P0000DCDB00P9 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement DCDB Main & Sub-Panels HPC Approval / PO release to vendor | 9 | DCDB | P000 | 00P9 | P000DCDB00P9
2420 | 2420 | 2420 | 2420 | SA24M005 | LV Power & Control Cables |  | 4 | -1 | 0 |  |  | X
2421 | 2421 | 2421 | 2421 | SA24M005 | Purchase Request to SCM | P00000LVC00P1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement LV Power & Control Cables Purchase Request to SCM | 1 | 00LVC | P000 | 00P1 | P00000LVC00P1
2422 | 2422 | 2422 | 2422 | SA24M005 | Issue of RFQ | P00000LVC00P2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement LV Power & Control Cables Issue of RFQ | 2 | 00LVC | P000 | 00P2 | P00000LVC00P2
2423 | 2423 | 2423 | 2423 | SA24M005 | Receipt of Technical offer from Vendor | P00000LVC00P3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement LV Power & Control Cables Receipt of Technical offer from Vendor | 3 | 00LVC | P000 | 00P3 | P00000LVC00P3
2424 | 2424 | 2424 | 2424 | SA24M005 | Technical Evaluation by EDRC | P00000LVC00P4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement LV Power & Control Cables Technical Evaluation by EDRC | 4 | 00LVC | P000 | 00P4 | P00000LVC00P4
2425 | 2425 | 2425 | 2425 | SA24M005 | Final technical compliance from Vendor | P00000LVC00P5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement LV Power & Control Cables Final technical compliance from Vendor | 5 | 00LVC | P000 | 00P5 | P00000LVC00P5
2426 | 2426 | 2426 | 2426 | SA24M005 | Technical clearance by EDRC | P00000LVC00P6 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement LV Power & Control Cables Technical clearance by EDRC | 6 | 00LVC | P000 | 00P6 | P00000LVC00P6
2427 | 2427 | 2427 | 2427 | SA24M005 | Commercial Evaluation by SCM | P00000LVC00P7 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement LV Power & Control Cables Commercial Evaluation by SCM | 7 | 00LVC | P000 | 00P7 | P00000LVC00P7
2428 | 2428 | 2428 | 2428 | SA24M005 | Vendor negotiation & Finalization | P00000LVC00P8 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement LV Power & Control Cables Vendor negotiation & Finalization | 8 | 00LVC | P000 | 00P8 | P00000LVC00P8
2429 | 2429 | 2429 | 2429 | SA24M005 | HPC Approval / PO release to vendor | P00000LVC00P9 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement LV Power & Control Cables HPC Approval / PO release to vendor | 9 | 00LVC | P000 | 00P9 | P00000LVC00P9
2430 | 2430 | 2430 | 2430 | SA24M005 | Sheilded Instrumentation Cables |  | 4 | -1 | 0 |  |  | X
2431 | 2431 | 2431 | 2431 | SA24M005 | Purchase Request to SCM | P0000SHIC00P1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Sheilded Instrumentation Cables Purchase Request to SCM | 1 | SHIC | P000 | 00P1 | P000SHIC00P1
2432 | 2432 | 2432 | 2432 | SA24M005 | Issue of RFQ | P0000SHIC00P2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Sheilded Instrumentation Cables Issue of RFQ | 2 | SHIC | P000 | 00P2 | P000SHIC00P2
2433 | 2433 | 2433 | 2433 | SA24M005 | Receipt of Technical offer from Vendor | P0000SHIC00P3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Sheilded Instrumentation Cables Receipt of Technical offer from Vendor | 3 | SHIC | P000 | 00P3 | P000SHIC00P3
2434 | 2434 | 2434 | 2434 | SA24M005 | Technical Evaluation by EDRC | P0000SHIC00P4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Sheilded Instrumentation Cables Technical Evaluation by EDRC | 4 | SHIC | P000 | 00P4 | P000SHIC00P4
2435 | 2435 | 2435 | 2435 | SA24M005 | Final technical compliance from Vendor | P0000SHIC00P5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Sheilded Instrumentation Cables Final technical compliance from Vendor | 5 | SHIC | P000 | 00P5 | P000SHIC00P5
2436 | 2436 | 2436 | 2436 | SA24M005 | Technical clearance by EDRC | P0000SHIC00P6 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Sheilded Instrumentation Cables Technical clearance by EDRC | 6 | SHIC | P000 | 00P6 | P000SHIC00P6
2437 | 2437 | 2437 | 2437 | SA24M005 | Commercial Evaluation by SCM | P0000SHIC00P7 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Sheilded Instrumentation Cables Commercial Evaluation by SCM | 7 | SHIC | P000 | 00P7 | P000SHIC00P7
2438 | 2438 | 2438 | 2438 | SA24M005 | Vendor negotiation & Finalization | P0000SHIC00P8 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Sheilded Instrumentation Cables Vendor negotiation & Finalization | 8 | SHIC | P000 | 00P8 | P000SHIC00P8
2439 | 2439 | 2439 | 2439 | SA24M005 | HPC Approval / PO release to vendor | P0000SHIC00P9 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Sheilded Instrumentation Cables HPC Approval / PO release to vendor | 9 | SHIC | P000 | 00P9 | P000SHIC00P9
2440 | 2440 | 2440 | 2440 | SA24M005 | LV Cable Accessories |  | 4 | -1 | 0 |  |  | X
2441 | 2441 | 2441 | 2441 | SA24M005 | Purchase Request to SCM | P0000LVCA00P1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement LV Cable Accessories Purchase Request to SCM | 1 | LVCA | P000 | 00P1 | P000LVCA00P1
2442 | 2442 | 2442 | 2442 | SA24M005 | Issue of RFQ | P0000LVCA00P2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement LV Cable Accessories Issue of RFQ | 2 | LVCA | P000 | 00P2 | P000LVCA00P2
2443 | 2443 | 2443 | 2443 | SA24M005 | Receipt of Technical offer from Vendor | P0000LVCA00P3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement LV Cable Accessories Receipt of Technical offer from Vendor | 3 | LVCA | P000 | 00P3 | P000LVCA00P3
2444 | 2444 | 2444 | 2444 | SA24M005 | Technical Evaluation by EDRC | P0000LVCA00P4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement LV Cable Accessories Technical Evaluation by EDRC | 4 | LVCA | P000 | 00P4 | P000LVCA00P4
2445 | 2445 | 2445 | 2445 | SA24M005 | Final technical compliance from Vendor | P0000LVCA00P5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement LV Cable Accessories Final technical compliance from Vendor | 5 | LVCA | P000 | 00P5 | P000LVCA00P5
2446 | 2446 | 2446 | 2446 | SA24M005 | Technical clearance by EDRC | P0000LVCA00P6 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement LV Cable Accessories Technical clearance by EDRC | 6 | LVCA | P000 | 00P6 | P000LVCA00P6
2447 | 2447 | 2447 | 2447 | SA24M005 | Commercial Evaluation by SCM | P0000LVCA00P7 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement LV Cable Accessories Commercial Evaluation by SCM | 7 | LVCA | P000 | 00P7 | P000LVCA00P7
2448 | 2448 | 2448 | 2448 | SA24M005 | Vendor negotiation & Finalization | P0000LVCA00P8 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement LV Cable Accessories Vendor negotiation & Finalization | 8 | LVCA | P000 | 00P8 | P000LVCA00P8
2449 | 2449 | 2449 | 2449 | SA24M005 | HPC Approval / PO release to vendor | P0000LVCA00P9 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement LV Cable Accessories HPC Approval / PO release to vendor | 9 | LVCA | P000 | 00P9 | P000LVCA00P9
2450 | 2450 | 2450 | 2450 | SA24M005 | Cable Trays & Supports with Accessories |  | 4 | -1 | 0 |  |  | X
2451 | 2451 | 2451 | 2451 | SA24M005 | Purchase Request to SCM | P0000CBLT00P1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Cable Trays & Supports with Accessories Purchase Request to SCM | 1 | CBLT | P000 | 00P1 | P000CBLT00P1
2452 | 2452 | 2452 | 2452 | SA24M005 | Issue of RFQ | P0000CBLT00P2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Cable Trays & Supports with Accessories Issue of RFQ | 2 | CBLT | P000 | 00P2 | P000CBLT00P2
2453 | 2453 | 2453 | 2453 | SA24M005 | Receipt of Technical offer from Vendor | P0000CBLT00P3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Cable Trays & Supports with Accessories Receipt of Technical offer from Vendor | 3 | CBLT | P000 | 00P3 | P000CBLT00P3
2454 | 2454 | 2454 | 2454 | SA24M005 | Technical Evaluation by EDRC | P0000CBLT00P4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Cable Trays & Supports with Accessories Technical Evaluation by EDRC | 4 | CBLT | P000 | 00P4 | P000CBLT00P4
2455 | 2455 | 2455 | 2455 | SA24M005 | Final technical compliance from Vendor | P0000CBLT00P5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Cable Trays & Supports with Accessories Final technical compliance from Vendor | 5 | CBLT | P000 | 00P5 | P000CBLT00P5
2456 | 2456 | 2456 | 2456 | SA24M005 | Technical clearance by EDRC | P0000CBLT00P6 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Cable Trays & Supports with Accessories Technical clearance by EDRC | 6 | CBLT | P000 | 00P6 | P000CBLT00P6
2457 | 2457 | 2457 | 2457 | SA24M005 | Commercial Evaluation by SCM | P0000CBLT00P7 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Cable Trays & Supports with Accessories Commercial Evaluation by SCM | 7 | CBLT | P000 | 00P7 | P000CBLT00P7
2458 | 2458 | 2458 | 2458 | SA24M005 | Vendor negotiation & Finalization | P0000CBLT00P8 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Cable Trays & Supports with Accessories Vendor negotiation & Finalization | 8 | CBLT | P000 | 00P8 | P000CBLT00P8
2459 | 2459 | 2459 | 2459 | SA24M005 | HPC Approval / PO release to vendor | P0000CBLT00P9 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Cable Trays & Supports with Accessories HPC Approval / PO release to vendor | 9 | CBLT | P000 | 00P9 | P000CBLT00P9
2460 | 2460 | 2460 | 2460 | SA24M005 | Grounding Material with accessories |  | 4 | -1 | 0 |  |  | X
2461 | 2461 | 2461 | 2461 | SA24M005 | Purchase Request to SCM | P0000GRND00P1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Grounding Material with accessories Purchase Request to SCM | 1 | GRND | P000 | 00P1 | P000GRND00P1
2462 | 2462 | 2462 | 2462 | SA24M005 | Issue of RFQ | P0000GRND00P2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Grounding Material with accessories Issue of RFQ | 2 | GRND | P000 | 00P2 | P000GRND00P2
2463 | 2463 | 2463 | 2463 | SA24M005 | Receipt of Technical offer from Vendor | P0000GRND00P3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Grounding Material with accessories Receipt of Technical offer from Vendor | 3 | GRND | P000 | 00P3 | P000GRND00P3
2464 | 2464 | 2464 | 2464 | SA24M005 | Technical Evaluation by EDRC | P0000GRND00P4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Grounding Material with accessories Technical Evaluation by EDRC | 4 | GRND | P000 | 00P4 | P000GRND00P4
2465 | 2465 | 2465 | 2465 | SA24M005 | Final technical compliance from Vendor | P0000GRND00P5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Grounding Material with accessories Final technical compliance from Vendor | 5 | GRND | P000 | 00P5 | P000GRND00P5
2466 | 2466 | 2466 | 2466 | SA24M005 | Technical clearance by EDRC | P0000GRND00P6 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Grounding Material with accessories Technical clearance by EDRC | 6 | GRND | P000 | 00P6 | P000GRND00P6
2467 | 2467 | 2467 | 2467 | SA24M005 | Commercial Evaluation by SCM | P0000GRND00P7 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Grounding Material with accessories Commercial Evaluation by SCM | 7 | GRND | P000 | 00P7 | P000GRND00P7
2468 | 2468 | 2468 | 2468 | SA24M005 | Vendor negotiation & Finalization | P0000GRND00P8 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Grounding Material with accessories Vendor negotiation & Finalization | 8 | GRND | P000 | 00P8 | P000GRND00P8
2469 | 2469 | 2469 | 2469 | SA24M005 | HPC Approval / PO release to vendor | P0000GRND00P9 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Grounding Material with accessories HPC Approval / PO release to vendor | 9 | GRND | P000 | 00P9 | P000GRND00P9
2470 | 2470 | 2470 | 2470 | SA24M005 | Lighting Panels |  | 4 | -1 | 0 |  |  | X
2471 | 2471 | 2471 | 2471 | SA24M005 | Purchase Request to SCM | P0000LGPN00P1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Lighting Panels Purchase Request to SCM | 1 | LGPNL | P000 | 00P1 | P000LGPNL00P1
2472 | 2472 | 2472 | 2472 | SA24M005 | Issue of RFQ | P0000LGPN00P2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Lighting Panels Issue of RFQ | 2 | LGPNL | P000 | 00P2 | P000LGPNL00P2
2473 | 2473 | 2473 | 2473 | SA24M005 | Receipt of Technical offer from Vendor | P0000LGPN00P3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Lighting Panels Receipt of Technical offer from Vendor | 3 | LGPNL | P000 | 00P3 | P000LGPNL00P3
2474 | 2474 | 2474 | 2474 | SA24M005 | Technical Evaluation by EDRC | P0000LGPN00P4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Lighting Panels Technical Evaluation by EDRC | 4 | LGPNL | P000 | 00P4 | P000LGPNL00P4
2475 | 2475 | 2475 | 2475 | SA24M005 | Final technical compliance from Vendor | P0000LGPN00P5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Lighting Panels Final technical compliance from Vendor | 5 | LGPNL | P000 | 00P5 | P000LGPNL00P5
2476 | 2476 | 2476 | 2476 | SA24M005 | Technical clearance by EDRC | P0000LGPN00P6 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Lighting Panels Technical clearance by EDRC | 6 | LGPNL | P000 | 00P6 | P000LGPNL00P6
2477 | 2477 | 2477 | 2477 | SA24M005 | Commercial Evaluation by SCM | P0000LGPN00P7 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Lighting Panels Commercial Evaluation by SCM | 7 | LGPNL | P000 | 00P7 | P000LGPNL00P7
2478 | 2478 | 2478 | 2478 | SA24M005 | Vendor negotiation & Finalization | P0000LGPN00P8 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Lighting Panels Vendor negotiation & Finalization | 8 | LGPNL | P000 | 00P8 | P000LGPNL00P8
2479 | 2479 | 2479 | 2479 | SA24M005 | HPC Approval / PO release to vendor | P0000LGPN00P9 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Lighting Panels HPC Approval / PO release to vendor | 9 | LGPNL | P000 | 00P9 | P000LGPNL00P9
2480 | 2480 | 2480 | 2480 | SA24M005 | Outdoor Lighting Poles |  | 4 | -1 | 0 |  |  | X
2481 | 2481 | 2481 | 2481 | SA24M005 | Purchase Request to SCM | P0000LGPL00P1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Outdoor Lighting Poles Purchase Request to SCM | 1 | 0LGPL | P000 | 00P1 | P0000LGPL00P1
2482 | 2482 | 2482 | 2482 | SA24M005 | Issue of RFQ | P0000LGPL00P2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Outdoor Lighting Poles Issue of RFQ | 2 | 0LGPL | P000 | 00P2 | P0000LGPL00P2
2483 | 2483 | 2483 | 2483 | SA24M005 | Receipt of Technical offer from Vendor | P0000LGPL00P3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Outdoor Lighting Poles Receipt of Technical offer from Vendor | 3 | 0LGPL | P000 | 00P3 | P0000LGPL00P3
2484 | 2484 | 2484 | 2484 | SA24M005 | Technical Evaluation by EDRC | P0000LGPL00P4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Outdoor Lighting Poles Technical Evaluation by EDRC | 4 | 0LGPL | P000 | 00P4 | P0000LGPL00P4
2485 | 2485 | 2485 | 2485 | SA24M005 | Final technical compliance from Vendor | P0000LGPL00P5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Outdoor Lighting Poles Final technical compliance from Vendor | 5 | 0LGPL | P000 | 00P5 | P0000LGPL00P5
2486 | 2486 | 2486 | 2486 | SA24M005 | Technical clearance by EDRC | P0000LGPL00P6 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Outdoor Lighting Poles Technical clearance by EDRC | 6 | 0LGPL | P000 | 00P6 | P0000LGPL00P6
2487 | 2487 | 2487 | 2487 | SA24M005 | Commercial Evaluation by SCM | P0000LGPL00P7 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Outdoor Lighting Poles Commercial Evaluation by SCM | 7 | 0LGPL | P000 | 00P7 | P0000LGPL00P7
2488 | 2488 | 2488 | 2488 | SA24M005 | Vendor negotiation & Finalization | P0000LGPL00P8 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Outdoor Lighting Poles Vendor negotiation & Finalization | 8 | 0LGPL | P000 | 00P8 | P0000LGPL00P8
2489 | 2489 | 2489 | 2489 | SA24M005 | HPC Approval / PO release to vendor | P0000LGPL00P9 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Outdoor Lighting Poles HPC Approval / PO release to vendor | 9 | 0LGPL | P000 | 00P9 | P0000LGPL00P9
2490 | 2490 | 2490 | 2490 | SA24M005 | Light Fitting & Receptacles |  | 4 | -1 | 0 |  |  | X
2491 | 2491 | 2491 | 2491 | SA24M005 | Purchase Request to SCM | P0000LGFR00P1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Light Fitting & Receptacles Purchase Request to SCM | 1 | LGFR | P000 | 00P1 | P000LGFR00P1
2492 | 2492 | 2492 | 2492 | SA24M005 | Issue of RFQ | P0000LGFR00P2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Light Fitting & Receptacles Issue of RFQ | 2 | LGFR | P000 | 00P2 | P000LGFR00P2
2493 | 2493 | 2493 | 2493 | SA24M005 | Receipt of Technical offer from Vendor | P0000LGFR00P3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Light Fitting & Receptacles Receipt of Technical offer from Vendor | 3 | LGFR | P000 | 00P3 | P000LGFR00P3
2494 | 2494 | 2494 | 2494 | SA24M005 | Technical Evaluation by EDRC | P0000LGFR00P4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Light Fitting & Receptacles Technical Evaluation by EDRC | 4 | LGFR | P000 | 00P4 | P000LGFR00P4
2495 | 2495 | 2495 | 2495 | SA24M005 | Final technical compliance from Vendor | P0000LGFR00P5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Light Fitting & Receptacles Final technical compliance from Vendor | 5 | LGFR | P000 | 00P5 | P000LGFR00P5
2496 | 2496 | 2496 | 2496 | SA24M005 | Technical clearance by EDRC | P0000LGFR00P6 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Light Fitting & Receptacles Technical clearance by EDRC | 6 | LGFR | P000 | 00P6 | P000LGFR00P6
2497 | 2497 | 2497 | 2497 | SA24M005 | Commercial Evaluation by SCM | P0000LGFR00P7 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Light Fitting & Receptacles Commercial Evaluation by SCM | 7 | LGFR | P000 | 00P7 | P000LGFR00P7
2498 | 2498 | 2498 | 2498 | SA24M005 | Vendor negotiation & Finalization | P0000LGFR00P8 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Light Fitting & Receptacles Vendor negotiation & Finalization | 8 | LGFR | P000 | 00P8 | P000LGFR00P8
2499 | 2499 | 2499 | 2499 | SA24M005 | HPC Approval / PO release to vendor | P0000LGFR00P9 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Light Fitting & Receptacles HPC Approval / PO release to vendor | 9 | LGFR | P000 | 00P9 | P000LGFR00P9
2500 | 2500 | 2500 | 2500 | SA24M005 | Lighting Conduits, JB's & Accessories |  | 4 | -1 | 0 |  |  | X
2501 | 2501 | 2501 | 2501 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Lighting Conduits, JB's & Accessories Purchase Request to SCM | 1 | LGTCOND | P000 | 00P1 | P000LGTCOND00P1
2502 | 2502 | 2502 | 2502 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Lighting Conduits, JB's & Accessories Issue of RFQ | 2 | LGTCOND | P000 | 00P2 | P000LGTCOND00P2
2503 | 2503 | 2503 | 2503 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Lighting Conduits, JB's & Accessories Receipt of Technical offer from Vendor | 3 | LGTCOND | P000 | 00P3 | P000LGTCOND00P3
2504 | 2504 | 2504 | 2504 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Lighting Conduits, JB's & Accessories Technical Evaluation by EDRC | 4 | LGTCOND | P000 | 00P4 | P000LGTCOND00P4
2505 | 2505 | 2505 | 2505 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Lighting Conduits, JB's & Accessories Final technical compliance from Vendor | 5 | LGTCOND | P000 | 00P5 | P000LGTCOND00P5
2506 | 2506 | 2506 | 2506 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Lighting Conduits, JB's & Accessories Technical clearance by EDRC | 6 | LGTCOND | P000 | 00P6 | P000LGTCOND00P6
2507 | 2507 | 2507 | 2507 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Lighting Conduits, JB's & Accessories Commercial Evaluation by SCM | 7 | LGTCOND | P000 | 00P7 | P000LGTCOND00P7
2508 | 2508 | 2508 | 2508 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Lighting Conduits, JB's & Accessories Vendor negotiation & Finalization | 8 | LGTCOND | P000 | 00P8 | P000LGTCOND00P8
2509 | 2509 | 2509 | 2509 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Lighting Conduits, JB's & Accessories HPC Approval / PO release to vendor | 9 | LGTCOND | P000 | 00P9 | P000LGTCOND00P9
2510 | 2510 | 2510 | 2510 | SA24M005 | Lighting & Sheilding system |  | 4 | -1 | 0 |  |  | X
2511 | 2511 | 2511 | 2511 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Lighting & Sheilding system Purchase Request to SCM | 1 | LGSH | P000 | 00P1 | P000LGSH00P1
2512 | 2512 | 2512 | 2512 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Lighting & Sheilding system Issue of RFQ | 2 | LGSH | P000 | 00P2 | P000LGSH00P2
2513 | 2513 | 2513 | 2513 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Lighting & Sheilding system Receipt of Technical offer from Vendor | 3 | LGSH | P000 | 00P3 | P000LGSH00P3
2514 | 2514 | 2514 | 2514 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Lighting & Sheilding system Technical Evaluation by EDRC | 4 | LGSH | P000 | 00P4 | P000LGSH00P4
2515 | 2515 | 2515 | 2515 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Lighting & Sheilding system Final technical compliance from Vendor | 5 | LGSH | P000 | 00P5 | P000LGSH00P5
2516 | 2516 | 2516 | 2516 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Lighting & Sheilding system Technical clearance by EDRC | 6 | LGSH | P000 | 00P6 | P000LGSH00P6
2517 | 2517 | 2517 | 2517 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Lighting & Sheilding system Commercial Evaluation by SCM | 7 | LGSH | P000 | 00P7 | P000LGSH00P7
2518 | 2518 | 2518 | 2518 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Lighting & Sheilding system Vendor negotiation & Finalization | 8 | LGSH | P000 | 00P8 | P000LGSH00P8
2519 | 2519 | 2519 | 2519 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Lighting & Sheilding system HPC Approval / PO release to vendor | 9 | LGSH | P000 | 00P9 | P000LGSH00P9
2520 | 2520 | 2520 | 2520 | SA24M005 | Outdoor Equipment Steel Support Structure |  | 4 | -1 | 0 |  |  | X
2521 | 2521 | 2521 | 2521 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Outdoor Equipment Steel Support Structure Purchase Request to SCM | 1 | 0E0SR | P000 | 00P1 | P0000E0SR00P1
2522 | 2522 | 2522 | 2522 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Outdoor Equipment Steel Support Structure Issue of RFQ | 2 | 0E0SR | P000 | 00P2 | P0000E0SR00P2
2523 | 2523 | 2523 | 2523 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Outdoor Equipment Steel Support Structure Receipt of Technical offer from Vendor | 3 | 0E0SR | P000 | 00P3 | P0000E0SR00P3
2524 | 2524 | 2524 | 2524 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Outdoor Equipment Steel Support Structure Technical Evaluation by EDRC | 4 | 0E0SR | P000 | 00P4 | P0000E0SR00P4
2525 | 2525 | 2525 | 2525 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Outdoor Equipment Steel Support Structure Final technical compliance from Vendor | 5 | 0E0SR | P000 | 00P5 | P0000E0SR00P5
2526 | 2526 | 2526 | 2526 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Outdoor Equipment Steel Support Structure Technical clearance by EDRC | 6 | 0E0SR | P000 | 00P6 | P0000E0SR00P6
2527 | 2527 | 2527 | 2527 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Outdoor Equipment Steel Support Structure Commercial Evaluation by SCM | 7 | 0E0SR | P000 | 00P7 | P0000E0SR00P7
2528 | 2528 | 2528 | 2528 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Outdoor Equipment Steel Support Structure Vendor negotiation & Finalization | 8 | 0E0SR | P000 | 00P8 | P0000E0SR00P8
2529 | 2529 | 2529 | 2529 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Outdoor Equipment Steel Support Structure HPC Approval / PO release to vendor | 9 | 0E0SR | P000 | 00P9 | P0000E0SR00P9
2530 | 2530 | 2530 | 2530 | SA24M005 | Lattice Steel Gantry Structures |  | 4 | -1 | 0 |  |  | X
2531 | 2531 | 2531 | 2531 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Lattice Steel Gantry Structures Purchase Request to SCM | 1 | LGSTR | P000 | 00P1 | P000LGSTR00P1
2532 | 2532 | 2532 | 2532 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Lattice Steel Gantry Structures Issue of RFQ | 2 | LGSTR | P000 | 00P2 | P000LGSTR00P2
2533 | 2533 | 2533 | 2533 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Lattice Steel Gantry Structures Receipt of Technical offer from Vendor | 3 | LGSTR | P000 | 00P3 | P000LGSTR00P3
2534 | 2534 | 2534 | 2534 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Lattice Steel Gantry Structures Technical Evaluation by EDRC | 4 | LGSTR | P000 | 00P4 | P000LGSTR00P4
2535 | 2535 | 2535 | 2535 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Lattice Steel Gantry Structures Final technical compliance from Vendor | 5 | LGSTR | P000 | 00P5 | P000LGSTR00P5
2536 | 2536 | 2536 | 2536 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Lattice Steel Gantry Structures Technical clearance by EDRC | 6 | LGSTR | P000 | 00P6 | P000LGSTR00P6
2537 | 2537 | 2537 | 2537 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Lattice Steel Gantry Structures Commercial Evaluation by SCM | 7 | LGSTR | P000 | 00P7 | P000LGSTR00P7
2538 | 2538 | 2538 | 2538 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Lattice Steel Gantry Structures Vendor negotiation & Finalization | 8 | LGSTR | P000 | 00P8 | P000LGSTR00P8
2539 | 2539 | 2539 | 2539 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Lattice Steel Gantry Structures HPC Approval / PO release to vendor | 9 | LGSTR | P000 | 00P9 | P000LGSTR00P9
2540 | 2540 | 2540 | 2540 | SA24M005 | Protection & Metering System |  | 4 | -1 | 0 |  |  | X
2541 | 2541 | 2541 | 2541 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Protection & Metering System Purchase Request to SCM | 1 | PR0PMS | P000 | 00P1 | P000PR0PMS00P1
2542 | 2542 | 2542 | 2542 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Protection & Metering System Issue of RFQ | 2 | PR0PMS | P000 | 00P2 | P000PR0PMS00P2
2543 | 2543 | 2543 | 2543 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Protection & Metering System Receipt of Technical offer from Vendor | 3 | PR0PMS | P000 | 00P3 | P000PR0PMS00P3
2544 | 2544 | 2544 | 2544 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Protection & Metering System Technical Evaluation by EDRC | 4 | PR0PMS | P000 | 00P4 | P000PR0PMS00P4
2545 | 2545 | 2545 | 2545 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Protection & Metering System Final technical compliance from Vendor | 5 | PR0PMS | P000 | 00P5 | P000PR0PMS00P5
2546 | 2546 | 2546 | 2546 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Protection & Metering System Technical clearance by EDRC | 6 | PR0PMS | P000 | 00P6 | P000PR0PMS00P6
2547 | 2547 | 2547 | 2547 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Protection & Metering System Commercial Evaluation by SCM | 7 | PR0PMS | P000 | 00P7 | P000PR0PMS00P7
2548 | 2548 | 2548 | 2548 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Protection & Metering System Vendor negotiation & Finalization | 8 | PR0PMS | P000 | 00P8 | P000PR0PMS00P8
2549 | 2549 | 2549 | 2549 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Protection & Metering System HPC Approval / PO release to vendor | 9 | PR0PMS | P000 | 00P9 | P000PR0PMS00P9
2550 | 2550 | 2550 | 2550 | SA24M005 | Alarm and Annunciator System |  | 4 | -1 | 0 |  |  | X
2551 | 2551 | 2551 | 2551 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Alarm and Annunciator System Purchase Request to SCM | 1 | AALARM | P000 | 00P1 | P000AALARM00P1
2552 | 2552 | 2552 | 2552 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Alarm and Annunciator System Issue of RFQ | 2 | AALARM | P000 | 00P2 | P000AALARM00P2
2553 | 2553 | 2553 | 2553 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Alarm and Annunciator System Receipt of Technical offer from Vendor | 3 | AALARM | P000 | 00P3 | P000AALARM00P3
2554 | 2554 | 2554 | 2554 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Alarm and Annunciator System Technical Evaluation by EDRC | 4 | AALARM | P000 | 00P4 | P000AALARM00P4
2555 | 2555 | 2555 | 2555 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Alarm and Annunciator System Final technical compliance from Vendor | 5 | AALARM | P000 | 00P5 | P000AALARM00P5
2556 | 2556 | 2556 | 2556 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Alarm and Annunciator System Technical clearance by EDRC | 6 | AALARM | P000 | 00P6 | P000AALARM00P6
2557 | 2557 | 2557 | 2557 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Alarm and Annunciator System Commercial Evaluation by SCM | 7 | AALARM | P000 | 00P7 | P000AALARM00P7
2558 | 2558 | 2558 | 2558 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Alarm and Annunciator System Vendor negotiation & Finalization | 8 | AALARM | P000 | 00P8 | P000AALARM00P8
2559 | 2559 | 2559 | 2559 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Alarm and Annunciator System HPC Approval / PO release to vendor | 9 | AALARM | P000 | 00P9 | P000AALARM00P9
2560 | 2560 | 2560 | 2560 | SA24M005 | Communication system (48V Battery Bank) |  | 4 | -1 | 0 |  |  | X
2561 | 2561 | 2561 | 2561 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Communication system (48V Battery Bank) Purchase Request to SCM | 1 | 0BATB | P000 | 00P1 | P0000BATB00P1
2562 | 2562 | 2562 | 2562 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Communication system (48V Battery Bank) Issue of RFQ | 2 | 0BATB | P000 | 00P2 | P0000BATB00P2
2563 | 2563 | 2563 | 2563 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Communication system (48V Battery Bank) Receipt of Technical offer from Vendor | 3 | 0BATB | P000 | 00P3 | P0000BATB00P3
2564 | 2564 | 2564 | 2564 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Communication system (48V Battery Bank) Technical Evaluation by EDRC | 4 | 0BATB | P000 | 00P4 | P0000BATB00P4
2565 | 2565 | 2565 | 2565 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Communication system (48V Battery Bank) Final technical compliance from Vendor | 5 | 0BATB | P000 | 00P5 | P0000BATB00P5
2566 | 2566 | 2566 | 2566 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Communication system (48V Battery Bank) Technical clearance by EDRC | 6 | 0BATB | P000 | 00P6 | P0000BATB00P6
2567 | 2567 | 2567 | 2567 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Communication system (48V Battery Bank) Commercial Evaluation by SCM | 7 | 0BATB | P000 | 00P7 | P0000BATB00P7
2568 | 2568 | 2568 | 2568 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Communication system (48V Battery Bank) Vendor negotiation & Finalization | 8 | 0BATB | P000 | 00P8 | P0000BATB00P8
2569 | 2569 | 2569 | 2569 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Communication system (48V Battery Bank) HPC Approval / PO release to vendor | 9 | 0BATB | P000 | 00P9 | P0000BATB00P9
2570 | 2570 | 2570 | 2570 | SA24M005 | Communication system (48V Battery Chargers) |  | 4 | -1 | 0 |  |  | X
2571 | 2571 | 2571 | 2571 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Communication system (48V Battery Chargers) Purchase Request to SCM | 1 | 0BATC | P000 | 00P1 | P0000BATC00P1
2572 | 2572 | 2572 | 2572 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Communication system (48V Battery Chargers) Issue of RFQ | 2 | 0BATC | P000 | 00P2 | P0000BATC00P2
2573 | 2573 | 2573 | 2573 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Communication system (48V Battery Chargers) Receipt of Technical offer from Vendor | 3 | 0BATC | P000 | 00P3 | P0000BATC00P3
2574 | 2574 | 2574 | 2574 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Communication system (48V Battery Chargers) Technical Evaluation by EDRC | 4 | 0BATC | P000 | 00P4 | P0000BATC00P4
2575 | 2575 | 2575 | 2575 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Communication system (48V Battery Chargers) Final technical compliance from Vendor | 5 | 0BATC | P000 | 00P5 | P0000BATC00P5
2576 | 2576 | 2576 | 2576 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Communication system (48V Battery Chargers) Technical clearance by EDRC | 6 | 0BATC | P000 | 00P6 | P0000BATC00P6
2577 | 2577 | 2577 | 2577 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Communication system (48V Battery Chargers) Commercial Evaluation by SCM | 7 | 0BATC | P000 | 00P7 | P0000BATC00P7
2578 | 2578 | 2578 | 2578 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Communication system (48V Battery Chargers) Vendor negotiation & Finalization | 8 | 0BATC | P000 | 00P8 | P0000BATC00P8
2579 | 2579 | 2579 | 2579 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Communication system (48V Battery Chargers) HPC Approval / PO release to vendor | 9 | 0BATC | P000 | 00P9 | P0000BATC00P9
2580 | 2580 | 2580 | 2580 | SA24M005 | Communication system (Panels- DC/SDH/DVM/MDF) |  | 4 | -1 | 0 |  |  | X
2581 | 2581 | 2581 | 2581 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Communication system (Panels- DC/SDH/DVM/MDF) Purchase Request to SCM | 1 | COMM | P000 | 00P1 | P000#RswX00P1
2582 | 2582 | 2582 | 2582 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Communication system (Panels- DC/SDH/DVM/MDF) Issue of RFQ | 2 | COMM | P000 | 00P2 | P000#RswX00P2
2583 | 2583 | 2583 | 2583 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Communication system (Panels- DC/SDH/DVM/MDF) Receipt of Technical offer from Vendor | 3 | COMM | P000 | 00P3 | P000#RswX00P3
2584 | 2584 | 2584 | 2584 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Communication system (Panels- DC/SDH/DVM/MDF) Technical Evaluation by EDRC | 4 | COMM | P000 | 00P4 | P000#RswX00P4
2585 | 2585 | 2585 | 2585 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Communication system (Panels- DC/SDH/DVM/MDF) Final technical compliance from Vendor | 5 | COMM | P000 | 00P5 | P000#RswX00P5
2586 | 2586 | 2586 | 2586 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Communication system (Panels- DC/SDH/DVM/MDF) Technical clearance by EDRC | 6 | COMM | P000 | 00P6 | P000#RswX00P6
2587 | 2587 | 2587 | 2587 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Communication system (Panels- DC/SDH/DVM/MDF) Commercial Evaluation by SCM | 7 | COMM | P000 | 00P7 | P000#RswX00P7
2588 | 2588 | 2588 | 2588 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Communication system (Panels- DC/SDH/DVM/MDF) Vendor negotiation & Finalization | 8 | COMM | P000 | 00P8 | P000#RswX00P8
2589 | 2589 | 2589 | 2589 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Communication system (Panels- DC/SDH/DVM/MDF) HPC Approval / PO release to vendor | 9 | COMM | P000 | 00P9 | P000#RswX00P9
2590 | 2590 | 2590 | 2590 | SA24M005 | Communication system (Other Items) |  | 4 | -1 | 0 |  |  | X | P000#RswX
2591 | 2591 | 2591 | 2591 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Communication system (Other Items) Purchase Request to SCM | 1 | COMM | P000 | 00P1 | P000#Rvfg00P1
2592 | 2592 | 2592 | 2592 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Communication system (Other Items) Issue of RFQ | 2 | COMM | P000 | 00P2 | P000#Rvfg00P2
2593 | 2593 | 2593 | 2593 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Communication system (Other Items) Receipt of Technical offer from Vendor | 3 | COMM | P000 | 00P3 | P000#Rvfg00P3
2594 | 2594 | 2594 | 2594 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Communication system (Other Items) Technical Evaluation by EDRC | 4 | COMM | P000 | 00P4 | P000#Rvfg00P4
2595 | 2595 | 2595 | 2595 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Communication system (Other Items) Final technical compliance from Vendor | 5 | COMM | P000 | 00P5 | P000#Rvfg00P5
2596 | 2596 | 2596 | 2596 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Communication system (Other Items) Technical clearance by EDRC | 6 | COMM | P000 | 00P6 | P000#Rvfg00P6
2597 | 2597 | 2597 | 2597 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Communication system (Other Items) Commercial Evaluation by SCM | 7 | COMM | P000 | 00P7 | P000#Rvfg00P7
2598 | 2598 | 2598 | 2598 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Communication system (Other Items) Vendor negotiation & Finalization | 8 | COMM | P000 | 00P8 | P000#Rvfg00P8
2599 | 2599 | 2599 | 2599 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Communication system (Other Items) HPC Approval / PO release to vendor | 9 | COMM | P000 | 00P9 | P000#Rvfg00P9
2600 | 2600 | 2600 | 2600 | SA24M005 | SAS / SCADA System |  | 4 | -1 | 0 |  |  | X | P000#Rvfg
2601 | 2601 | 2601 | 2601 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement SAS / SCADA System Purchase Request to SCM | 1 | 0SCAD | P000 | 00P1 | P0000SCAD00P1
2602 | 2602 | 2602 | 2602 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement SAS / SCADA System Issue of RFQ | 2 | 0SCAD | P000 | 00P2 | P0000SCAD00P2
2603 | 2603 | 2603 | 2603 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement SAS / SCADA System Receipt of Technical offer from Vendor | 3 | 0SCAD | P000 | 00P3 | P0000SCAD00P3
2604 | 2604 | 2604 | 2604 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement SAS / SCADA System Technical Evaluation by EDRC | 4 | 0SCAD | P000 | 00P4 | P0000SCAD00P4
2605 | 2605 | 2605 | 2605 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement SAS / SCADA System Final technical compliance from Vendor | 5 | 0SCAD | P000 | 00P5 | P0000SCAD00P5
2606 | 2606 | 2606 | 2606 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement SAS / SCADA System Technical clearance by EDRC | 6 | 0SCAD | P000 | 00P6 | P0000SCAD00P6
2607 | 2607 | 2607 | 2607 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement SAS / SCADA System Commercial Evaluation by SCM | 7 | 0SCAD | P000 | 00P7 | P0000SCAD00P7
2608 | 2608 | 2608 | 2608 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement SAS / SCADA System Vendor negotiation & Finalization | 8 | 0SCAD | P000 | 00P8 | P0000SCAD00P8
2609 | 2609 | 2609 | 2609 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement SAS / SCADA System HPC Approval / PO release to vendor | 9 | 0SCAD | P000 | 00P9 | P0000SCAD00P9
2610 | 2610 | 2610 | 2610 | SA24M005 | HCIS System (CCTV etc.) |  | 4 | -1 | 0 |  |  | X
2611 | 2611 | 2611 | 2611 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement HCIS System (CCTV etc.) Purchase Request to SCM | 1 | HCIS | P000 | 00P1 | P000HCIS00P1
2612 | 2612 | 2612 | 2612 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement HCIS System (CCTV etc.) Issue of RFQ | 2 | HCIS | P000 | 00P2 | P000HCIS00P2
2613 | 2613 | 2613 | 2613 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement HCIS System (CCTV etc.) Receipt of Technical offer from Vendor | 3 | HCIS | P000 | 00P3 | P000HCIS00P3
2614 | 2614 | 2614 | 2614 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement HCIS System (CCTV etc.) Technical Evaluation by EDRC | 4 | HCIS | P000 | 00P4 | P000HCIS00P4
2615 | 2615 | 2615 | 2615 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement HCIS System (CCTV etc.) Final technical compliance from Vendor | 5 | HCIS | P000 | 00P5 | P000HCIS00P5
2616 | 2616 | 2616 | 2616 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement HCIS System (CCTV etc.) Technical clearance by EDRC | 6 | HCIS | P000 | 00P6 | P000HCIS00P6
2617 | 2617 | 2617 | 2617 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement HCIS System (CCTV etc.) Commercial Evaluation by SCM | 7 | HCIS | P000 | 00P7 | P000HCIS00P7
2618 | 2618 | 2618 | 2618 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement HCIS System (CCTV etc.) Vendor negotiation & Finalization | 8 | HCIS | P000 | 00P8 | P000HCIS00P8
2619 | 2619 | 2619 | 2619 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement HCIS System (CCTV etc.) HPC Approval / PO release to vendor | 9 | HCIS | P000 | 00P9 | P000HCIS00P9
2620 | 2620 | 2620 | 2620 | SA24M005 | Standalone Current Transformer ( 380kV) |  | 4 | -1 | 0 |  |  | X
2621 | 2621 | 2621 | 2621 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Standalone Current Transformer ( 380kV) Purchase Request to SCM | 1 | 0STRF | P000 | 00P1 | P0000STRF00P1
2622 | 2622 | 2622 | 2622 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Standalone Current Transformer ( 380kV) Issue of RFQ | 2 | 0STRF | P000 | 00P2 | P0000STRF00P2
2623 | 2623 | 2623 | 2623 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Standalone Current Transformer ( 380kV) Receipt of Technical offer from Vendor | 3 | 0STRF | P000 | 00P3 | P0000STRF00P3
2624 | 2624 | 2624 | 2624 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Standalone Current Transformer ( 380kV) Technical Evaluation by EDRC | 4 | 0STRF | P000 | 00P4 | P0000STRF00P4
2625 | 2625 | 2625 | 2625 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Standalone Current Transformer ( 380kV) Final technical compliance from Vendor | 5 | 0STRF | P000 | 00P5 | P0000STRF00P5
2626 | 2626 | 2626 | 2626 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Standalone Current Transformer ( 380kV) Technical clearance by EDRC | 6 | 0STRF | P000 | 00P6 | P0000STRF00P6
2627 | 2627 | 2627 | 2627 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Standalone Current Transformer ( 380kV) Commercial Evaluation by SCM | 7 | 0STRF | P000 | 00P7 | P0000STRF00P7
2628 | 2628 | 2628 | 2628 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Standalone Current Transformer ( 380kV) Vendor negotiation & Finalization | 8 | 0STRF | P000 | 00P8 | P0000STRF00P8
2629 | 2629 | 2629 | 2629 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Standalone Current Transformer ( 380kV) HPC Approval / PO release to vendor | 9 | 0STRF | P000 | 00P9 | P0000STRF00P9
2630 | 2630 | 2630 | 2630 | SA24M005 | Transient Fault Recorder |  | 4 | -1 | 0 |  |  | X
2631 | 2631 | 2631 | 2631 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Transient Fault Recorder Purchase Request to SCM | 1 | TFR | P000 | 00P1 | P000TFR00P1
2632 | 2632 | 2632 | 2632 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Transient Fault Recorder Issue of RFQ | 2 | TFR | P000 | 00P2 | P000TFR00P2
2633 | 2633 | 2633 | 2633 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Transient Fault Recorder Receipt of Technical offer from Vendor | 3 | TFR | P000 | 00P3 | P000TFR00P3
2634 | 2634 | 2634 | 2634 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Transient Fault Recorder Technical Evaluation by EDRC | 4 | TFR | P000 | 00P4 | P000TFR00P4
2635 | 2635 | 2635 | 2635 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Transient Fault Recorder Final technical compliance from Vendor | 5 | TFR | P000 | 00P5 | P000TFR00P5
2636 | 2636 | 2636 | 2636 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Transient Fault Recorder Technical clearance by EDRC | 6 | TFR | P000 | 00P6 | P000TFR00P6
2637 | 2637 | 2637 | 2637 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Transient Fault Recorder Commercial Evaluation by SCM | 7 | TFR | P000 | 00P7 | P000TFR00P7
2638 | 2638 | 2638 | 2638 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Transient Fault Recorder Vendor negotiation & Finalization | 8 | TFR | P000 | 00P8 | P000TFR00P8
2639 | 2639 | 2639 | 2639 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Transient Fault Recorder HPC Approval / PO release to vendor | 9 | TFR | P000 | 00P9 | P000TFR00P9
2640 | 2640 | 2640 | 2640 | SA24M005 | DSM Equipment |  | 4 | -1 | 0 |  |  | X
2641 | 2641 | 2641 | 2641 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement DSM Equipment Purchase Request to SCM | 1 | 0DSM | P000 | 00P1 | P0000DSM00P1
2642 | 2642 | 2642 | 2642 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement DSM Equipment Issue of RFQ | 2 | 0DSM | P000 | 00P2 | P0000DSM00P2
2643 | 2643 | 2643 | 2643 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement DSM Equipment Receipt of Technical offer from Vendor | 3 | 0DSM | P000 | 00P3 | P0000DSM00P3
2644 | 2644 | 2644 | 2644 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement DSM Equipment Technical Evaluation by EDRC | 4 | 0DSM | P000 | 00P4 | P0000DSM00P4
2645 | 2645 | 2645 | 2645 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement DSM Equipment Final technical compliance from Vendor | 5 | 0DSM | P000 | 00P5 | P0000DSM00P5
2646 | 2646 | 2646 | 2646 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement DSM Equipment Technical clearance by EDRC | 6 | 0DSM | P000 | 00P6 | P0000DSM00P6
2647 | 2647 | 2647 | 2647 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement DSM Equipment Commercial Evaluation by SCM | 7 | 0DSM | P000 | 00P7 | P0000DSM00P7
2648 | 2648 | 2648 | 2648 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement DSM Equipment Vendor negotiation & Finalization | 8 | 0DSM | P000 | 00P8 | P0000DSM00P8
2649 | 2649 | 2649 | 2649 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement DSM Equipment HPC Approval / PO release to vendor | 9 | 0DSM | P000 | 00P9 | P0000DSM00P9
2650 | 2650 | 2650 | 2650 | SA24M005 | CTPU with CTJB - BOX for 380kV |  | 4 | -1 | 0 |  |  | X
2651 | 2651 | 2651 | 2651 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement CTPU with CTJB - BOX for 380kV Purchase Request to SCM | 1 | CTPU | P000 | 00P1 | P000CTPU00P1
2652 | 2652 | 2652 | 2652 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement CTPU with CTJB - BOX for 380kV Issue of RFQ | 2 | CTPU | P000 | 00P2 | P000CTPU00P2
2653 | 2653 | 2653 | 2653 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement CTPU with CTJB - BOX for 380kV Receipt of Technical offer from Vendor | 3 | CTPU | P000 | 00P3 | P000CTPU00P3
2654 | 2654 | 2654 | 2654 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement CTPU with CTJB - BOX for 380kV Technical Evaluation by EDRC | 4 | CTPU | P000 | 00P4 | P000CTPU00P4
2655 | 2655 | 2655 | 2655 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement CTPU with CTJB - BOX for 380kV Final technical compliance from Vendor | 5 | CTPU | P000 | 00P5 | P000CTPU00P5
2656 | 2656 | 2656 | 2656 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement CTPU with CTJB - BOX for 380kV Technical clearance by EDRC | 6 | CTPU | P000 | 00P6 | P000CTPU00P6
2657 | 2657 | 2657 | 2657 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement CTPU with CTJB - BOX for 380kV Commercial Evaluation by SCM | 7 | CTPU | P000 | 00P7 | P000CTPU00P7
2658 | 2658 | 2658 | 2658 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement CTPU with CTJB - BOX for 380kV Vendor negotiation & Finalization | 8 | CTPU | P000 | 00P8 | P000CTPU00P8
2659 | 2659 | 2659 | 2659 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement CTPU with CTJB - BOX for 380kV HPC Approval / PO release to vendor | 9 | CTPU | P000 | 00P9 | P000CTPU00P9
2660 | 2660 | 2660 | 2660 | SA24M005 | PDMS System |  | 4 | -1 | 0 |  |  | X
2661 | 2661 | 2661 | 2661 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement PDMS System Purchase Request to SCM | 1 | PDMS | P000 | 00P1 | P000#HXio00P1
2662 | 2662 | 2662 | 2662 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement PDMS System Issue of RFQ | 2 | PDMS | P000 | 00P2 | P000#HXio00P2
2663 | 2663 | 2663 | 2663 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement PDMS System Receipt of Technical offer from Vendor | 3 | PDMS | P000 | 00P3 | P000#HXio00P3
2664 | 2664 | 2664 | 2664 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement PDMS System Technical Evaluation by EDRC | 4 | PDMS | P000 | 00P4 | P000#HXio00P4
2665 | 2665 | 2665 | 2665 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement PDMS System Final technical compliance from Vendor | 5 | PDMS | P000 | 00P5 | P000#HXio00P5
2666 | 2666 | 2666 | 2666 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement PDMS System Technical clearance by EDRC | 6 | PDMS | P000 | 00P6 | P000#HXio00P6
2667 | 2667 | 2667 | 2667 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement PDMS System Commercial Evaluation by SCM | 7 | PDMS | P000 | 00P7 | P000#HXio00P7
2668 | 2668 | 2668 | 2668 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement PDMS System Vendor negotiation & Finalization | 8 | PDMS | P000 | 00P8 | P000#HXio00P8
2669 | 2669 | 2669 | 2669 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement PDMS System HPC Approval / PO release to vendor | 9 | PDMS | P000 | 00P9 | P000#HXio00P9
2670 | 2670 | 2670 | 2670 | SA24M005 | Fault Locater (FL) System |  | 4 | -1 | 0 |  |  | X | P000#HXio
2671 | 2671 | 2671 | 2671 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Fault Locater (FL) System Purchase Request to SCM | 1 | FL | P000 | 00P1 | P000FL00P1
2672 | 2672 | 2672 | 2672 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Fault Locater (FL) System Issue of RFQ | 2 | FL | P000 | 00P2 | P000FL00P2
2673 | 2673 | 2673 | 2673 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Fault Locater (FL) System Receipt of Technical offer from Vendor | 3 | FL | P000 | 00P3 | P000FL00P3
2674 | 2674 | 2674 | 2674 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Fault Locater (FL) System Technical Evaluation by EDRC | 4 | FL | P000 | 00P4 | P000FL00P4
2675 | 2675 | 2675 | 2675 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Fault Locater (FL) System Final technical compliance from Vendor | 5 | FL | P000 | 00P5 | P000FL00P5
2676 | 2676 | 2676 | 2676 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Fault Locater (FL) System Technical clearance by EDRC | 6 | FL | P000 | 00P6 | P000FL00P6
2677 | 2677 | 2677 | 2677 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Fault Locater (FL) System Commercial Evaluation by SCM | 7 | FL | P000 | 00P7 | P000FL00P7
2678 | 2678 | 2678 | 2678 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Fault Locater (FL) System Vendor negotiation & Finalization | 8 | FL | P000 | 00P8 | P000FL00P8
2679 | 2679 | 2679 | 2679 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Fault Locater (FL) System HPC Approval / PO release to vendor | 9 | FL | P000 | 00P9 | P000FL00P9
2680 | 2680 | 2680 | 2680 | SA24M005 | Mechanical Materials |  | 4 | -1 | 0 |  |  | X
2681 | 2681 | 2681 | 2681 | SA24M005 | Electrical Overhead travelling (EOT) Crane |  | 5 | -1 | 0 |  |  | X
2682 | 2682 | 2682 | 2682 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Electrical Overhead travelling (EOT) Crane Purchase Request to SCM | 1 | E0EHC | P000 | 00P1 | P000E0EHC00P1
2683 | 2683 | 2683 | 2683 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Electrical Overhead travelling (EOT) Crane Issue of RFQ | 2 | E0EHC | P000 | 00P2 | P000E0EHC00P2
2684 | 2684 | 2684 | 2684 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Electrical Overhead travelling (EOT) Crane Receipt of Technical offer from Vendor | 3 | E0EHC | P000 | 00P3 | P000E0EHC00P3
2685 | 2685 | 2685 | 2685 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Electrical Overhead travelling (EOT) Crane Technical Evaluation by EDRC | 4 | E0EHC | P000 | 00P4 | P000E0EHC00P4
2686 | 2686 | 2686 | 2686 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Electrical Overhead travelling (EOT) Crane Final technical compliance from Vendor | 5 | E0EHC | P000 | 00P5 | P000E0EHC00P5
2687 | 2687 | 2687 | 2687 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Electrical Overhead travelling (EOT) Crane Technical clearance by EDRC | 6 | E0EHC | P000 | 00P6 | P000E0EHC00P6
2688 | 2688 | 2688 | 2688 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Electrical Overhead travelling (EOT) Crane Commercial Evaluation by SCM | 7 | E0EHC | P000 | 00P7 | P000E0EHC00P7
2689 | 2689 | 2689 | 2689 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Electrical Overhead travelling (EOT) Crane Vendor negotiation & Finalization | 8 | E0EHC | P000 | 00P8 | P000E0EHC00P8
2690 | 2690 | 2690 | 2690 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Electrical Overhead travelling (EOT) Crane HPC Approval / PO release to vendor | 9 | E0EHC | P000 | 00P9 | P000E0EHC00P9
2691 | 2691 | 2691 | 2691 | SA24M005 | HVAC System |  | 5 | -1 | 0 |  |  | X
2692 | 2692 | 2692 | 2692 | SA24M005 | PACU Units |  | 6 | -1 | 0 |  |  | X
2693 | 2693 | 2693 | 2693 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials HVAC System PACU Units Purchase Request to SCM | 1 | MHVAC | P000 | 00P1 | P000#LdMO00P1
2694 | 2694 | 2694 | 2694 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials HVAC System PACU Units Issue of RFQ | 2 | MHVAC | P000 | 00P2 | P000#LdMO00P2
2695 | 2695 | 2695 | 2695 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials HVAC System PACU Units Receipt of Technical offer from Vendor | 3 | MHVAC | P000 | 00P3 | P000#LdMO00P3
2696 | 2696 | 2696 | 2696 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials HVAC System PACU Units Technical Evaluation by EDRC | 4 | MHVAC | P000 | 00P4 | P000#LdMO00P4
2697 | 2697 | 2697 | 2697 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials HVAC System PACU Units Final technical compliance from Vendor | 5 | MHVAC | P000 | 00P5 | P000#LdMO00P5
2698 | 2698 | 2698 | 2698 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials HVAC System PACU Units Technical clearance by EDRC | 6 | MHVAC | P000 | 00P6 | P000#LdMO00P6
2699 | 2699 | 2699 | 2699 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials HVAC System PACU Units Commercial Evaluation by SCM | 7 | MHVAC | P000 | 00P7 | P000#LdMO00P7
2700 | 2700 | 2700 | 2700 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials HVAC System PACU Units Vendor negotiation & Finalization | 8 | MHVAC | P000 | 00P8 | P000#LdMO00P8
2701 | 2701 | 2701 | 2701 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials HVAC System PACU Units HPC Approval / PO release to vendor | 9 | MHVAC | P000 | 00P9 | P000#LdMO00P9
2702 | 2702 | 2702 | 2702 | SA24M005 | Ducts |  | 6 | -1 | 0 |  |  | X | P000#LdMO
2703 | 2703 | 2703 | 2703 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials HVAC System Ducts Purchase Request to SCM | 1 | MHVAC | P000 | 00P1 | P000#fOuD00P1
2704 | 2704 | 2704 | 2704 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials HVAC System Ducts Issue of RFQ | 2 | MHVAC | P000 | 00P2 | P000#fOuD00P2
2705 | 2705 | 2705 | 2705 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials HVAC System Ducts Receipt of Technical offer from Vendor | 3 | MHVAC | P000 | 00P3 | P000#fOuD00P3
2706 | 2706 | 2706 | 2706 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials HVAC System Ducts Technical Evaluation by EDRC | 4 | MHVAC | P000 | 00P4 | P000#fOuD00P4
2707 | 2707 | 2707 | 2707 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials HVAC System Ducts Final technical compliance from Vendor | 5 | MHVAC | P000 | 00P5 | P000#fOuD00P5
2708 | 2708 | 2708 | 2708 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials HVAC System Ducts Technical clearance by EDRC | 6 | MHVAC | P000 | 00P6 | P000#fOuD00P6
2709 | 2709 | 2709 | 2709 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials HVAC System Ducts Commercial Evaluation by SCM | 7 | MHVAC | P000 | 00P7 | P000#fOuD00P7
2710 | 2710 | 2710 | 2710 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials HVAC System Ducts Vendor negotiation & Finalization | 8 | MHVAC | P000 | 00P8 | P000#fOuD00P8
2711 | 2711 | 2711 | 2711 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials HVAC System Ducts HPC Approval / PO release to vendor | 9 | MHVAC | P000 | 00P9 | P000#fOuD00P9
2712 | 2712 | 2712 | 2712 | SA24M005 | Ventilation Fans |  | 6 | -1 | 0 |  |  | X | P000#fOuD
2713 | 2713 | 2713 | 2713 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials HVAC System Ventilation Fans Purchase Request to SCM | 1 | MHVAC | P000 | 00P1 | P000#HHeI00P1
2714 | 2714 | 2714 | 2714 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials HVAC System Ventilation Fans Issue of RFQ | 2 | MHVAC | P000 | 00P2 | P000#HHeI00P2
2715 | 2715 | 2715 | 2715 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials HVAC System Ventilation Fans Receipt of Technical offer from Vendor | 3 | MHVAC | P000 | 00P3 | P000#HHeI00P3
2716 | 2716 | 2716 | 2716 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials HVAC System Ventilation Fans Technical Evaluation by EDRC | 4 | MHVAC | P000 | 00P4 | P000#HHeI00P4
2717 | 2717 | 2717 | 2717 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials HVAC System Ventilation Fans Final technical compliance from Vendor | 5 | MHVAC | P000 | 00P5 | P000#HHeI00P5
2718 | 2718 | 2718 | 2718 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials HVAC System Ventilation Fans Technical clearance by EDRC | 6 | MHVAC | P000 | 00P6 | P000#HHeI00P6
2719 | 2719 | 2719 | 2719 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials HVAC System Ventilation Fans Commercial Evaluation by SCM | 7 | MHVAC | P000 | 00P7 | P000#HHeI00P7
2720 | 2720 | 2720 | 2720 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials HVAC System Ventilation Fans Vendor negotiation & Finalization | 8 | MHVAC | P000 | 00P8 | P000#HHeI00P8
2721 | 2721 | 2721 | 2721 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials HVAC System Ventilation Fans HPC Approval / PO release to vendor | 9 | MHVAC | P000 | 00P9 | P000#HHeI00P9
2722 | 2722 | 2722 | 2722 | SA24M005 | HVAC Control Panel & Accessories |  | 6 | -1 | 0 |  |  | X | P000#HHeI
2723 | 2723 | 2723 | 2723 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials HVAC System HVAC Control Panel & Accessories Purchase Request to SCM | 1 | MHVAC | P000 | 00P1 | P000#Sdpe00P1
2724 | 2724 | 2724 | 2724 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials HVAC System HVAC Control Panel & Accessories Issue of RFQ | 2 | MHVAC | P000 | 00P2 | P000#Sdpe00P2
2725 | 2725 | 2725 | 2725 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials HVAC System HVAC Control Panel & Accessories Receipt of Technical offer from Vendor | 3 | MHVAC | P000 | 00P3 | P000#Sdpe00P3
2726 | 2726 | 2726 | 2726 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials HVAC System HVAC Control Panel & Accessories Technical Evaluation by EDRC | 4 | MHVAC | P000 | 00P4 | P000#Sdpe00P4
2727 | 2727 | 2727 | 2727 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials HVAC System HVAC Control Panel & Accessories Final technical compliance from Vendor | 5 | MHVAC | P000 | 00P5 | P000#Sdpe00P5
2728 | 2728 | 2728 | 2728 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials HVAC System HVAC Control Panel & Accessories Technical clearance by EDRC | 6 | MHVAC | P000 | 00P6 | P000#Sdpe00P6
2729 | 2729 | 2729 | 2729 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials HVAC System HVAC Control Panel & Accessories Commercial Evaluation by SCM | 7 | MHVAC | P000 | 00P7 | P000#Sdpe00P7
2730 | 2730 | 2730 | 2730 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials HVAC System HVAC Control Panel & Accessories Vendor negotiation & Finalization | 8 | MHVAC | P000 | 00P8 | P000#Sdpe00P8
2731 | 2731 | 2731 | 2731 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials HVAC System HVAC Control Panel & Accessories HPC Approval / PO release to vendor | 9 | MHVAC | P000 | 00P9 | P000#Sdpe00P9
2732 | 2732 | 2732 | 2732 | SA24M005 | Split Type AC Units |  | 6 | -1 | 0 |  |  | X | P000#Sdpe
2733 | 2733 | 2733 | 2733 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials HVAC System Split Type AC Units Purchase Request to SCM | 1 | HVAC0ACU | P000 | 00P1 | P000HVAC0ACU00P1
2734 | 2734 | 2734 | 2734 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials HVAC System Split Type AC Units Issue of RFQ | 2 | HVAC0ACU | P000 | 00P2 | P000HVAC0ACU00P2
2735 | 2735 | 2735 | 2735 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials HVAC System Split Type AC Units Receipt of Technical offer from Vendor | 3 | HVAC0ACU | P000 | 00P3 | P000HVAC0ACU00P3
2736 | 2736 | 2736 | 2736 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials HVAC System Split Type AC Units Technical Evaluation by EDRC | 4 | HVAC0ACU | P000 | 00P4 | P000HVAC0ACU00P4
2737 | 2737 | 2737 | 2737 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials HVAC System Split Type AC Units Final technical compliance from Vendor | 5 | HVAC0ACU | P000 | 00P5 | P000HVAC0ACU00P5
2738 | 2738 | 2738 | 2738 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials HVAC System Split Type AC Units Technical clearance by EDRC | 6 | HVAC0ACU | P000 | 00P6 | P000HVAC0ACU00P6
2739 | 2739 | 2739 | 2739 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials HVAC System Split Type AC Units Commercial Evaluation by SCM | 7 | HVAC0ACU | P000 | 00P7 | P000HVAC0ACU00P7
2740 | 2740 | 2740 | 2740 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials HVAC System Split Type AC Units Vendor negotiation & Finalization | 8 | HVAC0ACU | P000 | 00P8 | P000HVAC0ACU00P8
2741 | 2741 | 2741 | 2741 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials HVAC System Split Type AC Units HPC Approval / PO release to vendor | 9 | HVAC0ACU | P000 | 00P9 | P000HVAC0ACU00P9
2742 | 2742 | 2742 | 2742 | SA24M005 | Fire Detection System |  | 5 | -1 | 0 |  |  | X
2743 | 2743 | 2743 | 2743 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Fire Detection System Purchase Request to SCM | 1 | FDSR | P000 | 00P1 | P000FDSR00P1
2744 | 2744 | 2744 | 2744 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Fire Detection System Issue of RFQ | 2 | FDSR | P000 | 00P2 | P000FDSR00P2
2745 | 2745 | 2745 | 2745 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Fire Detection System Receipt of Technical offer from Vendor | 3 | FDSR | P000 | 00P3 | P000FDSR00P3
2746 | 2746 | 2746 | 2746 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Fire Detection System Technical Evaluation by EDRC | 4 | FDSR | P000 | 00P4 | P000FDSR00P4
2747 | 2747 | 2747 | 2747 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Fire Detection System Final technical compliance from Vendor | 5 | FDSR | P000 | 00P5 | P000FDSR00P5
2748 | 2748 | 2748 | 2748 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Fire Detection System Technical clearance by EDRC | 6 | FDSR | P000 | 00P6 | P000FDSR00P6
2749 | 2749 | 2749 | 2749 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Fire Detection System Commercial Evaluation by SCM | 7 | FDSR | P000 | 00P7 | P000FDSR00P7
2750 | 2750 | 2750 | 2750 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Fire Detection System Vendor negotiation & Finalization | 8 | FDSR | P000 | 00P8 | P000FDSR00P8
2751 | 2751 | 2751 | 2751 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Fire Detection System HPC Approval / PO release to vendor | 9 | FDSR | P000 | 00P9 | P000FDSR00P9
2752 | 2752 | 2752 | 2752 | SA24M005 | Fire Alarm System |  | 5 | -1 | 0 |  |  | X
2753 | 2753 | 2753 | 2753 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Fire Alarm System Purchase Request to SCM | 1 | MFAS | P000 | 00P1 | P000MFAS00P1
2754 | 2754 | 2754 | 2754 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Fire Alarm System Issue of RFQ | 2 | MFAS | P000 | 00P2 | P000MFAS00P2
2755 | 2755 | 2755 | 2755 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Fire Alarm System Receipt of Technical offer from Vendor | 3 | MFAS | P000 | 00P3 | P000MFAS00P3
2756 | 2756 | 2756 | 2756 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Fire Alarm System Technical Evaluation by EDRC | 4 | MFAS | P000 | 00P4 | P000MFAS00P4
2757 | 2757 | 2757 | 2757 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Fire Alarm System Final technical compliance from Vendor | 5 | MFAS | P000 | 00P5 | P000MFAS00P5
2758 | 2758 | 2758 | 2758 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Fire Alarm System Technical clearance by EDRC | 6 | MFAS | P000 | 00P6 | P000MFAS00P6
2759 | 2759 | 2759 | 2759 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Fire Alarm System Commercial Evaluation by SCM | 7 | MFAS | P000 | 00P7 | P000MFAS00P7
2760 | 2760 | 2760 | 2760 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Fire Alarm System Vendor negotiation & Finalization | 8 | MFAS | P000 | 00P8 | P000MFAS00P8
2761 | 2761 | 2761 | 2761 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Fire Alarm System HPC Approval / PO release to vendor | 9 | MFAS | P000 | 00P9 | P000MFAS00P9
2762 | 2762 | 2762 | 2762 | SA24M005 | Fire Extinguisher System |  | 5 | -1 | 0 |  |  | X
2763 | 2763 | 2763 | 2763 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Fire Extinguisher System Purchase Request to SCM | 1 | FEXSY | P000 | 00P1 | P000FEXSY00P1
2764 | 2764 | 2764 | 2764 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Fire Extinguisher System Issue of RFQ | 2 | FEXSY | P000 | 00P2 | P000FEXSY00P2
2765 | 2765 | 2765 | 2765 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Fire Extinguisher System Receipt of Technical offer from Vendor | 3 | FEXSY | P000 | 00P3 | P000FEXSY00P3
2766 | 2766 | 2766 | 2766 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Fire Extinguisher System Technical Evaluation by EDRC | 4 | FEXSY | P000 | 00P4 | P000FEXSY00P4
2767 | 2767 | 2767 | 2767 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Fire Extinguisher System Final technical compliance from Vendor | 5 | FEXSY | P000 | 00P5 | P000FEXSY00P5
2768 | 2768 | 2768 | 2768 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Fire Extinguisher System Technical clearance by EDRC | 6 | FEXSY | P000 | 00P6 | P000FEXSY00P6
2769 | 2769 | 2769 | 2769 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Fire Extinguisher System Commercial Evaluation by SCM | 7 | FEXSY | P000 | 00P7 | P000FEXSY00P7
2770 | 2770 | 2770 | 2770 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Fire Extinguisher System Vendor negotiation & Finalization | 8 | FEXSY | P000 | 00P8 | P000FEXSY00P8
2771 | 2771 | 2771 | 2771 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Fire Extinguisher System HPC Approval / PO release to vendor | 9 | FEXSY | P000 | 00P9 | P000FEXSY00P9
2772 | 2772 | 2772 | 2772 | SA24M005 | Fire Hydrant System |  | 5 | -1 | 0 |  |  | X
2773 | 2773 | 2773 | 2773 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Fire Hydrant System Purchase Request to SCM | 1 | FHYD | P000 | 00P1 | P000FHYD00P1
2774 | 2774 | 2774 | 2774 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Fire Hydrant System Issue of RFQ | 2 | FHYD | P000 | 00P2 | P000FHYD00P2
2775 | 2775 | 2775 | 2775 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Fire Hydrant System Receipt of Technical offer from Vendor | 3 | FHYD | P000 | 00P3 | P000FHYD00P3
2776 | 2776 | 2776 | 2776 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Fire Hydrant System Technical Evaluation by EDRC | 4 | FHYD | P000 | 00P4 | P000FHYD00P4
2777 | 2777 | 2777 | 2777 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Fire Hydrant System Final technical compliance from Vendor | 5 | FHYD | P000 | 00P5 | P000FHYD00P5
2778 | 2778 | 2778 | 2778 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Fire Hydrant System Technical clearance by EDRC | 6 | FHYD | P000 | 00P6 | P000FHYD00P6
2779 | 2779 | 2779 | 2779 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Fire Hydrant System Commercial Evaluation by SCM | 7 | FHYD | P000 | 00P7 | P000FHYD00P7
2780 | 2780 | 2780 | 2780 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Fire Hydrant System Vendor negotiation & Finalization | 8 | FHYD | P000 | 00P8 | P000FHYD00P8
2781 | 2781 | 2781 | 2781 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Fire Hydrant System HPC Approval / PO release to vendor | 9 | FHYD | P000 | 00P9 | P000FHYD00P9
2782 | 2782 | 2782 | 2782 | SA24M005 | Wet Sprinkler System |  | 5 | -1 | 0 |  |  | X
2783 | 2783 | 2783 | 2783 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Wet Sprinkler System Purchase Request to SCM | 1 | MWSPR | P000 | 00P1 | P000MWSPR00P1
2784 | 2784 | 2784 | 2784 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Wet Sprinkler System Issue of RFQ | 2 | MWSPR | P000 | 00P2 | P000MWSPR00P2
2785 | 2785 | 2785 | 2785 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Wet Sprinkler System Receipt of Technical offer from Vendor | 3 | MWSPR | P000 | 00P3 | P000MWSPR00P3
2786 | 2786 | 2786 | 2786 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Wet Sprinkler System Technical Evaluation by EDRC | 4 | MWSPR | P000 | 00P4 | P000MWSPR00P4
2787 | 2787 | 2787 | 2787 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Wet Sprinkler System Final technical compliance from Vendor | 5 | MWSPR | P000 | 00P5 | P000MWSPR00P5
2788 | 2788 | 2788 | 2788 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Wet Sprinkler System Technical clearance by EDRC | 6 | MWSPR | P000 | 00P6 | P000MWSPR00P6
2789 | 2789 | 2789 | 2789 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Wet Sprinkler System Commercial Evaluation by SCM | 7 | MWSPR | P000 | 00P7 | P000MWSPR00P7
2790 | 2790 | 2790 | 2790 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Wet Sprinkler System Vendor negotiation & Finalization | 8 | MWSPR | P000 | 00P8 | P000MWSPR00P8
2791 | 2791 | 2791 | 2791 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Material Procurement Mechanical Materials Wet Sprinkler System HPC Approval / PO release to vendor | 9 | MWSPR | P000 | 00P9 | P000MWSPR00P9
2792 | 2792 | 2792 | 2792 | SA24M005 | Inspection & Delivery |  | 3 | -1 | 0 |  |  | X
2793 | 2793 | 2793 | 2793 | SA24M005 | 380kV GIS |  | 4 | -1 | 0 |  |  | X
2794 | 2794 | 2794 | 2794 | SA24M005 | MQP / ITP Submission | I00000GIS00I1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 380kV GIS MQP / ITP Submission | 1 | 00GIS | I000 | 00I1 | I00000GIS00I1
2795 | 2795 | 2795 | 2795 | SA24M005 | MQP / ITP Approval | I00000GIS00I2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 380kV GIS MQP / ITP Approval | 2 | 00GIS | I000 | 00I2 | I00000GIS00I2
2796 | 2796 | 2796 | 2796 | SA24M005 | Issuance of MFC | I00000GIS00I3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 380kV GIS Issuance of MFC | 3 | 00GIS | I000 | 00I3 | I00000GIS00I3
2797 | 2797 | 2797 | 2797 | SA24M005 | Lead Time For Manufacturing | I00000GIS00I4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 380kV GIS Lead Time For Manufacturing | 4 | 00GIS | I000 | 00I4 | I00000GIS00I4
2798 | 2798 | 2798 | 2798 | SA24M005 | Material readiness / Inspection call | I00000GIS00I5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 380kV GIS Material readiness / Inspection call | 5 | 00GIS | I000 | 00I5 | I00000GIS00I5
2799 | 2799 | 2799 | 2799 | SA24M005 | Inspection by client personal / Third party | I00000GIS00I6 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 380kV GIS Inspection by client personal / Third party | 6 | 00GIS | I000 | 00I6 | I00000GIS00I6
2800 | 2800 | 2800 | 2800 | SA24M005 | Submission of FAT Compliance by Vendor | I00000GIS00I7 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 380kV GIS Submission of FAT Compliance by Vendor | 7 | 00GIS | I000 | 00I7 | I00000GIS00I7
2801 | 2801 | 2801 | 2801 | SA24M005 | Dispatch Clearance to vendor | I00000GIS00I8 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 380kV GIS Dispatch Clearance to vendor | 8 | 00GIS | I000 | 00I8 | I00000GIS00I8
2802 | 2802 | 2802 | 2802 | SA24M005 | Transportation and Custom clearance | I00000GIS00I9 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 380kV GIS Transportation and Custom clearance | 9 | 00GIS | I000 | 00I9 | I00000GIS00I9
2803 | 2803 | 2803 | 2803 | SA24M005 | Receipt at site | I00000GIS0I10 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 380kV GIS Receipt at site | 10 | 00GIS | I000 | 0I10 | I00000GIS0I10
2804 | 2804 | 2804 | 2804 | SA24M005 | 380kV HGIS |  | 4 | -1 | 0 |  |  | X
2805 | 2805 | 2805 | 2805 | SA24M005 | MQP / ITP Submission | I0000HGIS00I1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 380kV HGIS MQP / ITP Submission | 1 | 0HGIS | I000 | 00I1 | I0000HGIS00I1
2806 | 2806 | 2806 | 2806 | SA24M005 | MQP / ITP Approval | I0000HGIS00I2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 380kV HGIS MQP / ITP Approval | 2 | 0HGIS | I000 | 00I2 | I0000HGIS00I2
2807 | 2807 | 2807 | 2807 | SA24M005 | Issuance of MFC | I0000HGIS00I3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 380kV HGIS Issuance of MFC | 3 | 0HGIS | I000 | 00I3 | I0000HGIS00I3
2808 | 2808 | 2808 | 2808 | SA24M005 | Lead Time For Manufacturing | I0000HGIS00I4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 380kV HGIS Lead Time For Manufacturing | 4 | 0HGIS | I000 | 00I4 | I0000HGIS00I4
2809 | 2809 | 2809 | 2809 | SA24M005 | Material readiness / Inspection call | I0000HGIS00I5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 380kV HGIS Material readiness / Inspection call | 5 | 0HGIS | I000 | 00I5 | I0000HGIS00I5
2810 | 2810 | 2810 | 2810 | SA24M005 | Inspection by client personal / Third Party | I0000HGIS00I6 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 380kV HGIS Inspection by client personal / Third Party | 6 | 0HGIS | I000 | 00I6 | I0000HGIS00I6
2811 | 2811 | 2811 | 2811 | SA24M005 | Submission of FAT Compliance by Vendor | I0000HGIS00I7 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 380kV HGIS Submission of FAT Compliance by Vendor | 7 | 0HGIS | I000 | 00I7 | I0000HGIS00I7
2812 | 2812 | 2812 | 2812 | SA24M005 | Dispatch Clearance to vendor | I0000HGIS00I8 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 380kV HGIS Dispatch Clearance to vendor | 8 | 0HGIS | I000 | 00I8 | I0000HGIS00I8
2813 | 2813 | 2813 | 2813 | SA24M005 | Transportation and Custom clearance | I0000HGIS00I9 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 380kV HGIS Transportation and Custom clearance | 9 | 0HGIS | I000 | 00I9 | I0000HGIS00I9
2814 | 2814 | 2814 | 2814 | SA24M005 | Receipt at site | I0000HGIS0I10 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 380kV HGIS Receipt at site | 10 | 0HGIS | I000 | 0I10 | I0000HGIS0I10
2815 | 2815 | 2815 | 2815 | SA24M005 | 380kV GIB & Connectors |  | 4 | -1 | 0 |  |  | X
2816 | 2816 | 2816 | 2816 | SA24M005 | MQP / ITP Submission | I0000GIBC00I1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 380kV GIB & Connectors MQP / ITP Submission | 1 | 0GIBC | I000 | 00I1 | I0000GIBC00I1
2817 | 2817 | 2817 | 2817 | SA24M005 | MQP / ITP Approval | I0000GIBC00I2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 380kV GIB & Connectors MQP / ITP Approval | 2 | 0GIBC | I000 | 00I2 | I0000GIBC00I2
2818 | 2818 | 2818 | 2818 | SA24M005 | Issuance of MFC | I0000GIBC00I3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 380kV GIB & Connectors Issuance of MFC | 3 | 0GIBC | I000 | 00I3 | I0000GIBC00I3
2819 | 2819 | 2819 | 2819 | SA24M005 | Lead Time For Manufacturing | I0000GIBC00I4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 380kV GIB & Connectors Lead Time For Manufacturing | 4 | 0GIBC | I000 | 00I4 | I0000GIBC00I4
2820 | 2820 | 2820 | 2820 | SA24M005 | Material readiness / Inspection call | I0000GIBC00I5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 380kV GIB & Connectors Material readiness / Inspection call | 5 | 0GIBC | I000 | 00I5 | I0000GIBC00I5
2821 | 2821 | 2821 | 2821 | SA24M005 | Inspection by client personal / Third Party | I0000GIBC00I6 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 380kV GIB & Connectors Inspection by client personal / Third Party | 6 | 0GIBC | I000 | 00I6 | I0000GIBC00I6
2822 | 2822 | 2822 | 2822 | SA24M005 | Submission of FAT Compliance by Vendor | I0000GIBC00I7 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 380kV GIB & Connectors Submission of FAT Compliance by Vendor | 7 | 0GIBC | I000 | 00I7 | I0000GIBC00I7
2823 | 2823 | 2823 | 2823 | SA24M005 | Dispatch Clearance to vendor | I0000GIBC00I8 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 380kV GIB & Connectors Dispatch Clearance to vendor | 8 | 0GIBC | I000 | 00I8 | I0000GIBC00I8
2824 | 2824 | 2824 | 2824 | SA24M005 | Transportation and Custom clearance | I0000GIBC00I9 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 380kV GIB & Connectors Transportation and Custom clearance | 9 | 0GIBC | I000 | 00I9 | I0000GIBC00I9
2825 | 2825 | 2825 | 2825 | SA24M005 | Receipt at site | I0000GIBC0I10 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 380kV GIB & Connectors Receipt at site | 10 | 0GIBC | I000 | 0I10 | I0000GIBC0I10
2826 | 2826 | 2826 | 2826 | SA24M005 | 2500KVA Station Service Transformers |  | 4 | -1 | 0 |  |  | X
2827 | 2827 | 2827 | 2827 | SA24M005 | MQP / ITP Submission | I0000STRF00I1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 2500KVA Station Service Transformers MQP / ITP Submission | 1 | #YOnA | I000 | 00I1 | I000#YOnA00I1
2828 | 2828 | 2828 | 2828 | SA24M005 | MQP / ITP Approval | I0000STRF00I2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 2500KVA Station Service Transformers MQP / ITP Approval | 2 | #YOnA | I000 | 00I2 | I000#YOnA00I2
2829 | 2829 | 2829 | 2829 | SA24M005 | Issuance of MFC | I0000STRF00I3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 2500KVA Station Service Transformers Issuance of MFC | 3 | #YOnA | I000 | 00I3 | I000#YOnA00I3
2830 | 2830 | 2830 | 2830 | SA24M005 | Lead Time For Manufacturing | I0000STRF00I4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 2500KVA Station Service Transformers Lead Time For Manufacturing | 4 | #YOnA | I000 | 00I4 | I000#YOnA00I4
2831 | 2831 | 2831 | 2831 | SA24M005 | Material readiness / Inspection call | I0000STRF00I5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 2500KVA Station Service Transformers Material readiness / Inspection call | 5 | #YOnA | I000 | 00I5 | I000#YOnA00I5
2832 | 2832 | 2832 | 2832 | SA24M005 | Inspection by client personal / Third Party | I0000STRF00I6 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 2500KVA Station Service Transformers Inspection by client personal / Third Party | 6 | #YOnA | I000 | 00I6 | I000#YOnA00I6
2833 | 2833 | 2833 | 2833 | SA24M005 | Submission of FAT Compliance by Vendor | I0000STRF00I7 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 2500KVA Station Service Transformers Submission of FAT Compliance by Vendor | 7 | #YOnA | I000 | 00I7 | I000#YOnA00I7
2834 | 2834 | 2834 | 2834 | SA24M005 | Dispatch Clearance to vendor | I0000STRF00I8 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 2500KVA Station Service Transformers Dispatch Clearance to vendor | 8 | #YOnA | I000 | 00I8 | I000#YOnA00I8
2835 | 2835 | 2835 | 2835 | SA24M005 | Transportation and Custom clearance | I0000STRF00I9 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 2500KVA Station Service Transformers Transportation and Custom clearance | 9 | #YOnA | I000 | 00I9 | I000#YOnA00I9
2836 | 2836 | 2836 | 2836 | SA24M005 | Receipt at site | I0000STRF0I10 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 2500KVA Station Service Transformers Receipt at site | 10 | #YOnA | I000 | 0I10 | I000#YOnA0I10
2837 | 2837 | 2837 | 2837 | SA24M005 | 120MVAR Bus Shunt Reactor & Accessories |  | 4 | -1 | 0 |  |  | X
2838 | 2838 | 2838 | 2838 | SA24M005 | MQP / ITP Submission | I00000BSR00I1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 120MVAR Bus Shunt Reactor & Accessories MQP / ITP Submission | 1 | 00BSR | I000 | 00I1 | I00000BSR00I1
2839 | 2839 | 2839 | 2839 | SA24M005 | MQP / ITP Approval | I00000BSR00I2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 120MVAR Bus Shunt Reactor & Accessories MQP / ITP Approval | 2 | 00BSR | I000 | 00I2 | I00000BSR00I2
2840 | 2840 | 2840 | 2840 | SA24M005 | Issuance of MFC | I00000BSR00I3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 120MVAR Bus Shunt Reactor & Accessories Issuance of MFC | 3 | 00BSR | I000 | 00I3 | I00000BSR00I3
2841 | 2841 | 2841 | 2841 | SA24M005 | Lead Time For Manufacturing | I00000BSR00I4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 120MVAR Bus Shunt Reactor & Accessories Lead Time For Manufacturing | 4 | 00BSR | I000 | 00I4 | I00000BSR00I4
2842 | 2842 | 2842 | 2842 | SA24M005 | Material readiness / Inspection call | I00000BSR00I5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 120MVAR Bus Shunt Reactor & Accessories Material readiness / Inspection call | 5 | 00BSR | I000 | 00I5 | I00000BSR00I5
2843 | 2843 | 2843 | 2843 | SA24M005 | Inspection by client personal / Third Party | I00000BSR00I6 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 120MVAR Bus Shunt Reactor & Accessories Inspection by client personal / Third Party | 6 | 00BSR | I000 | 00I6 | I00000BSR00I6
2844 | 2844 | 2844 | 2844 | SA24M005 | Submission of FAT Compliance by Vendor | I00000BSR00I7 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 120MVAR Bus Shunt Reactor & Accessories Submission of FAT Compliance by Vendor | 7 | 00BSR | I000 | 00I7 | I00000BSR00I7
2845 | 2845 | 2845 | 2845 | SA24M005 | Dispatch Clearance to vendor | I00000BSR00I8 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 120MVAR Bus Shunt Reactor & Accessories Dispatch Clearance to vendor | 8 | 00BSR | I000 | 00I8 | I00000BSR00I8
2846 | 2846 | 2846 | 2846 | SA24M005 | Transportation and Custom clearance | I00000BSR00I9 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 120MVAR Bus Shunt Reactor & Accessories Transportation and Custom clearance | 9 | 00BSR | I000 | 00I9 | I00000BSR00I9
2847 | 2847 | 2847 | 2847 | SA24M005 | Receipt at site | I00000BSR0I10 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 120MVAR Bus Shunt Reactor & Accessories Receipt at site | 10 | 00BSR | I000 | 0I10 | I00000BSR0I10
2848 | 2848 | 2848 | 2848 | SA24M005 | 150MVAR Line Shunt Reactor & Accessories |  | 4 | -1 | 0 |  |  | X
2849 | 2849 | 2849 | 2849 | SA24M005 | MQP / ITP Submission | I00000LSR00I1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 150MVAR Line Shunt Reactor & Accessories MQP / ITP Submission | 1 | 00LSR | I000 | 00I1 | I000#SXCE00I1
2850 | 2850 | 2850 | 2850 | SA24M005 | MQP / ITP Approval | I00000LSR00I2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 150MVAR Line Shunt Reactor & Accessories MQP / ITP Approval | 2 | 00LSR | I000 | 00I2 | I000#SXCE00I2
2851 | 2851 | 2851 | 2851 | SA24M005 | Issuance of MFC | I00000LSR00I3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 150MVAR Line Shunt Reactor & Accessories Issuance of MFC | 3 | 00LSR | I000 | 00I3 | I000#SXCE00I3
2852 | 2852 | 2852 | 2852 | SA24M005 | Lead Time For Manufacturing | I00000LSR00I4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 150MVAR Line Shunt Reactor & Accessories Lead Time For Manufacturing | 4 | 00LSR | I000 | 00I4 | I000#SXCE00I4
2853 | 2853 | 2853 | 2853 | SA24M005 | Material readiness / Inspection call | I00000LSR00I5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 150MVAR Line Shunt Reactor & Accessories Material readiness / Inspection call | 5 | 00LSR | I000 | 00I5 | I000#SXCE00I5
2854 | 2854 | 2854 | 2854 | SA24M005 | Inspection by client personal / Third Party | I00000LSR00I6 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 150MVAR Line Shunt Reactor & Accessories Inspection by client personal / Third Party | 6 | 00LSR | I000 | 00I6 | I000#SXCE00I6
2855 | 2855 | 2855 | 2855 | SA24M005 | Submission of FAT Compliance by Vendor | I00000LSR00I7 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 150MVAR Line Shunt Reactor & Accessories Submission of FAT Compliance by Vendor | 7 | 00LSR | I000 | 00I7 | I000#SXCE00I7
2856 | 2856 | 2856 | 2856 | SA24M005 | Dispatch Clearance to vendor | I00000LSR00I8 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 150MVAR Line Shunt Reactor & Accessories Dispatch Clearance to vendor | 8 | 00LSR | I000 | 00I8 | I000#SXCE00I8
2857 | 2857 | 2857 | 2857 | SA24M005 | Transportation and Custom clearance | I00000LSR00I9 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 150MVAR Line Shunt Reactor & Accessories Transportation and Custom clearance | 9 | 00LSR | I000 | 00I9 | I000#SXCE00I9
2858 | 2858 | 2858 | 2858 | SA24M005 | Receipt at site | I00000LSR0I10 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 150MVAR Line Shunt Reactor & Accessories Receipt at site | 10 | 00LSR | I000 | 0I10 | I000#SXCE0I10
2859 | 2859 | 2859 | 2859 | SA24M005 | Neutral Grounding Reactor (NGR) |  | 4 | -1 | 0 |  |  | X | I000#SXCE
2860 | 2860 | 2860 | 2860 | SA24M005 | MQP / ITP Submission | I00000NGR00I1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Neutral Grounding Reactor (NGR) MQP / ITP Submission | 1 | 00NGR | I000 | 00I1 | I00000NGR00I1
2861 | 2861 | 2861 | 2861 | SA24M005 | MQP / ITP Approval | I00000NGR00I2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Neutral Grounding Reactor (NGR) MQP / ITP Approval | 2 | 00NGR | I000 | 00I2 | I00000NGR00I2
2862 | 2862 | 2862 | 2862 | SA24M005 | Issuance of MFC | I00000NGR00I3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Neutral Grounding Reactor (NGR) Issuance of MFC | 3 | 00NGR | I000 | 00I3 | I00000NGR00I3
2863 | 2863 | 2863 | 2863 | SA24M005 | Lead Time For Manufacturing | I00000NGR00I4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Neutral Grounding Reactor (NGR) Lead Time For Manufacturing | 4 | 00NGR | I000 | 00I4 | I00000NGR00I4
2864 | 2864 | 2864 | 2864 | SA24M005 | Material readiness / Inspection call | I00000NGR00I5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Neutral Grounding Reactor (NGR) Material readiness / Inspection call | 5 | 00NGR | I000 | 00I5 | I00000NGR00I5
2865 | 2865 | 2865 | 2865 | SA24M005 | Inspection by client personal / Third Party | I00000NGR00I6 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Neutral Grounding Reactor (NGR) Inspection by client personal / Third Party | 6 | 00NGR | I000 | 00I6 | I00000NGR00I6
2866 | 2866 | 2866 | 2866 | SA24M005 | Submission of FAT Compliance by Vendor | I00000NGR00I7 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Neutral Grounding Reactor (NGR) Submission of FAT Compliance by Vendor | 7 | 00NGR | I000 | 00I7 | I00000NGR00I7
2867 | 2867 | 2867 | 2867 | SA24M005 | Dispatch Clearance to vendor | I00000NGR00I8 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Neutral Grounding Reactor (NGR) Dispatch Clearance to vendor | 8 | 00NGR | I000 | 00I8 | I00000NGR00I8
2868 | 2868 | 2868 | 2868 | SA24M005 | Transportation and Custom clearance | I00000NGR00I9 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Neutral Grounding Reactor (NGR) Transportation and Custom clearance | 9 | 00NGR | I000 | 00I9 | I00000NGR00I9
2869 | 2869 | 2869 | 2869 | SA24M005 | Receipt at site | I00000NGR0I10 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Neutral Grounding Reactor (NGR) Receipt at site | 10 | 00NGR | I000 | 0I10 | I00000NGR0I10
2870 | 2870 | 2870 | 2870 | SA24M005 | 13.8kV Switchgear & Accessories |  | 4 | -1 | 0 |  |  | X
2871 | 2871 | 2871 | 2871 | SA24M005 | MQP / ITP Submission | I0000SWGR00I1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 13.8kV Switchgear & Accessories MQP / ITP Submission | 1 | 0SWGR | I000 | 00I1 | I0000SWGR00I1
2872 | 2872 | 2872 | 2872 | SA24M005 | MQP / ITP Approval | I0000SWGR00I2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 13.8kV Switchgear & Accessories MQP / ITP Approval | 2 | 0SWGR | I000 | 00I2 | I0000SWGR00I2
2873 | 2873 | 2873 | 2873 | SA24M005 | Issuance of MFC | I0000SWGR00I3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 13.8kV Switchgear & Accessories Issuance of MFC | 3 | 0SWGR | I000 | 00I3 | I0000SWGR00I3
2874 | 2874 | 2874 | 2874 | SA24M005 | Lead Time For Manufacturing | I0000SWGR00I4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 13.8kV Switchgear & Accessories Lead Time For Manufacturing | 4 | 0SWGR | I000 | 00I4 | I0000SWGR00I4
2875 | 2875 | 2875 | 2875 | SA24M005 | Material readiness / Inspection call | I0000SWGR00I5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 13.8kV Switchgear & Accessories Material readiness / Inspection call | 5 | 0SWGR | I000 | 00I5 | I0000SWGR00I5
2876 | 2876 | 2876 | 2876 | SA24M005 | Inspection by client personal / Third Party | I0000SWGR00I6 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 13.8kV Switchgear & Accessories Inspection by client personal / Third Party | 6 | 0SWGR | I000 | 00I6 | I0000SWGR00I6
2877 | 2877 | 2877 | 2877 | SA24M005 | Submission of FAT Compliance by Vendor | I0000SWGR00I7 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 13.8kV Switchgear & Accessories Submission of FAT Compliance by Vendor | 7 | 0SWGR | I000 | 00I7 | I0000SWGR00I7
2878 | 2878 | 2878 | 2878 | SA24M005 | Dispatch Clearance to vendor | I0000SWGR00I8 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 13.8kV Switchgear & Accessories Dispatch Clearance to vendor | 8 | 0SWGR | I000 | 00I8 | I0000SWGR00I8
2879 | 2879 | 2879 | 2879 | SA24M005 | Transportation and Custom clearance | I0000SWGR00I9 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 13.8kV Switchgear & Accessories Transportation and Custom clearance | 9 | 0SWGR | I000 | 00I9 | I0000SWGR00I9
2880 | 2880 | 2880 | 2880 | SA24M005 | Receipt at site | I0000SWGR0I10 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 13.8kV Switchgear & Accessories Receipt at site | 10 | 0SWGR | I000 | 0I10 | I0000SWGR0I10
2881 | 2881 | 2881 | 2881 | SA24M005 | 380kV Surge Arrestor |  | 4 | -1 | 0 |  |  | X
2882 | 2882 | 2882 | 2882 | SA24M005 | MQP / ITP Submission | I0000SRGA00I1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 380kV Surge Arrestor MQP / ITP Submission | 1 | SRGA | I000 | 00I1 | I000#dhew00I1
2883 | 2883 | 2883 | 2883 | SA24M005 | MQP / ITP Approval | I0000SRGA00I2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 380kV Surge Arrestor MQP / ITP Approval | 2 | SRGA | I000 | 00I2 | I000#dhew00I2
2884 | 2884 | 2884 | 2884 | SA24M005 | Issuance of MFC | I0000SRGA00I3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 380kV Surge Arrestor Issuance of MFC | 3 | SRGA | I000 | 00I3 | I000#dhew00I3
2885 | 2885 | 2885 | 2885 | SA24M005 | Lead Time For Manufacturing | I0000SRGA00I4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 380kV Surge Arrestor Lead Time For Manufacturing | 4 | SRGA | I000 | 00I4 | I000#dhew00I4
2886 | 2886 | 2886 | 2886 | SA24M005 | Material readiness / Inspection call | I0000SRGA00I5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 380kV Surge Arrestor Material readiness / Inspection call | 5 | SRGA | I000 | 00I5 | I000#dhew00I5
2887 | 2887 | 2887 | 2887 | SA24M005 | Inspection by client personal / Third Party | I0000SRGA00I6 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 380kV Surge Arrestor Inspection by client personal / Third Party | 6 | SRGA | I000 | 00I6 | I000#dhew00I6
2888 | 2888 | 2888 | 2888 | SA24M005 | Submission of FAT Compliance by Vendor | I0000SRGA00I7 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 380kV Surge Arrestor Submission of FAT Compliance by Vendor | 7 | SRGA | I000 | 00I7 | I000#dhew00I7
2889 | 2889 | 2889 | 2889 | SA24M005 | Dispatch Clearance to vendor | I0000SRGA00I8 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 380kV Surge Arrestor Dispatch Clearance to vendor | 8 | SRGA | I000 | 00I8 | I000#dhew00I8
2890 | 2890 | 2890 | 2890 | SA24M005 | Transportation and Custom clearance | I0000SRGA00I9 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 380kV Surge Arrestor Transportation and Custom clearance | 9 | SRGA | I000 | 00I9 | I000#dhew00I9
2891 | 2891 | 2891 | 2891 | SA24M005 | Receipt at site | I0000SRGA0I10 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 380kV Surge Arrestor Receipt at site | 10 | SRGA | I000 | 0I10 | I000#dhew0I10
2892 | 2892 | 2892 | 2892 | SA24M005 | Tubular / ACSR Conductors |  | 4 | -1 | 0 |  |  | X | I000#dhew
2893 | 2893 | 2893 | 2893 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Tubular / ACSR Conductors MQP / ITP Submission | 1 | TUBC | I000 | 00I1 | I000TUBC00I1
2894 | 2894 | 2894 | 2894 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Tubular / ACSR Conductors MQP / ITP Approval | 2 | TUBC | I000 | 00I2 | I000TUBC00I2
2895 | 2895 | 2895 | 2895 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Tubular / ACSR Conductors Issuance of MFC | 3 | TUBC | I000 | 00I3 | I000TUBC00I3
2896 | 2896 | 2896 | 2896 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Tubular / ACSR Conductors Lead Time For Manufacturing | 4 | TUBC | I000 | 00I4 | I000TUBC00I4
2897 | 2897 | 2897 | 2897 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Tubular / ACSR Conductors Material readiness / Inspection call | 5 | TUBC | I000 | 00I5 | I000TUBC00I5
2898 | 2898 | 2898 | 2898 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Tubular / ACSR Conductors Inspection by client personal / Third Party | 6 | TUBC | I000 | 00I6 | I000TUBC00I6
2899 | 2899 | 2899 | 2899 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Tubular / ACSR Conductors Submission of FAT Compliance by Vendor | 7 | TUBC | I000 | 00I7 | I000TUBC00I7
2900 | 2900 | 2900 | 2900 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Tubular / ACSR Conductors Dispatch Clearance to vendor | 8 | TUBC | I000 | 00I8 | I000TUBC00I8
2901 | 2901 | 2901 | 2901 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Tubular / ACSR Conductors Transportation and Custom clearance | 9 | TUBC | I000 | 00I9 | I000TUBC00I9
2902 | 2902 | 2902 | 2902 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Tubular / ACSR Conductors Receipt at site | 10 | TUBC | I000 | 0I10 | I000TUBC0I10
2903 | 2903 | 2903 | 2903 | SA24M005 | HV/MV Power Cables (Bonding & Grounding of cables) |  | 4 | -1 | 0 |  |  | X
2904 | 2904 | 2904 | 2904 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery HV/MV Power Cables (Bonding & Grounding of cables) MQP / ITP Submission | 1 | 0POWC | I000 | 00I1 | I0000POWC00I1
2905 | 2905 | 2905 | 2905 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery HV/MV Power Cables (Bonding & Grounding of cables) MQP / ITP Approval | 2 | 0POWC | I000 | 00I2 | I0000POWC00I2
2906 | 2906 | 2906 | 2906 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery HV/MV Power Cables (Bonding & Grounding of cables) Issuance of MFC | 3 | 0POWC | I000 | 00I3 | I0000POWC00I3
2907 | 2907 | 2907 | 2907 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery HV/MV Power Cables (Bonding & Grounding of cables) Lead Time For Manufacturing | 4 | 0POWC | I000 | 00I4 | I0000POWC00I4
2908 | 2908 | 2908 | 2908 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery HV/MV Power Cables (Bonding & Grounding of cables) Material readiness / Inspection call | 5 | 0POWC | I000 | 00I5 | I0000POWC00I5
2909 | 2909 | 2909 | 2909 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery HV/MV Power Cables (Bonding & Grounding of cables) Inspection by client personal / Third Party | 6 | 0POWC | I000 | 00I6 | I0000POWC00I6
2910 | 2910 | 2910 | 2910 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery HV/MV Power Cables (Bonding & Grounding of cables) Submission of FAT Compliance by Vendor | 7 | 0POWC | I000 | 00I7 | I0000POWC00I7
2911 | 2911 | 2911 | 2911 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery HV/MV Power Cables (Bonding & Grounding of cables) Dispatch Clearance to vendor | 8 | 0POWC | I000 | 00I8 | I0000POWC00I8
2912 | 2912 | 2912 | 2912 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery HV/MV Power Cables (Bonding & Grounding of cables) Transportation and Custom clearance | 9 | 0POWC | I000 | 00I9 | I0000POWC00I9
2913 | 2913 | 2913 | 2913 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery HV/MV Power Cables (Bonding & Grounding of cables) Receipt at site | 10 | 0POWC | I000 | 0I10 | I0000POWC0I10
2914 | 2914 | 2914 | 2914 | SA24M005 | Cable Termination Kit |  | 4 | -1 | 0 |  |  | X
2915 | 2915 | 2915 | 2915 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Cable Termination Kit MQP / ITP Submission | 1 | CTRM | I000 | 00I1 | I000CTRM00I1
2916 | 2916 | 2916 | 2916 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Cable Termination Kit MQP / ITP Approval | 2 | CTRM | I000 | 00I2 | I000CTRM00I2
2917 | 2917 | 2917 | 2917 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Cable Termination Kit Issuance of MFC | 3 | CTRM | I000 | 00I3 | I000CTRM00I3
2918 | 2918 | 2918 | 2918 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Cable Termination Kit Lead Time For Manufacturing | 4 | CTRM | I000 | 00I4 | I000CTRM00I4
2919 | 2919 | 2919 | 2919 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Cable Termination Kit Material readiness / Inspection call | 5 | CTRM | I000 | 00I5 | I000CTRM00I5
2920 | 2920 | 2920 | 2920 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Cable Termination Kit Inspection by client personal / Third Party | 6 | CTRM | I000 | 00I6 | I000CTRM00I6
2921 | 2921 | 2921 | 2921 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Cable Termination Kit Submission of FAT Compliance by Vendor | 7 | CTRM | I000 | 00I7 | I000CTRM00I7
2922 | 2922 | 2922 | 2922 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Cable Termination Kit Dispatch Clearance to vendor | 8 | CTRM | I000 | 00I8 | I000CTRM00I8
2923 | 2923 | 2923 | 2923 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Cable Termination Kit Transportation and Custom clearance | 9 | CTRM | I000 | 00I9 | I000CTRM00I9
2924 | 2924 | 2924 | 2924 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Cable Termination Kit Receipt at site | 10 | CTRM | I000 | 0I10 | I000CTRM0I10
2925 | 2925 | 2925 | 2925 | SA24M005 | 125V Battery Bank |  | 4 | -1 | 0 |  |  | X
2926 | 2926 | 2926 | 2926 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 125V Battery Bank MQP / ITP Submission | 1 | BATB | I000 | 00I1 | I000BATB00I1
2927 | 2927 | 2927 | 2927 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 125V Battery Bank MQP / ITP Approval | 2 | BATB | I000 | 00I2 | I000BATB00I2
2928 | 2928 | 2928 | 2928 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 125V Battery Bank Issuance of MFC | 3 | BATB | I000 | 00I3 | I000BATB00I3
2929 | 2929 | 2929 | 2929 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 125V Battery Bank Lead Time For Manufacturing | 4 | BATB | I000 | 00I4 | I000BATB00I4
2930 | 2930 | 2930 | 2930 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 125V Battery Bank Material readiness / Inspection call | 5 | BATB | I000 | 00I5 | I000BATB00I5
2931 | 2931 | 2931 | 2931 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 125V Battery Bank Inspection by client personal / Third Party | 6 | BATB | I000 | 00I6 | I000BATB00I6
2932 | 2932 | 2932 | 2932 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 125V Battery Bank Submission of FAT Compliance by Vendor | 7 | BATB | I000 | 00I7 | I000BATB00I7
2933 | 2933 | 2933 | 2933 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 125V Battery Bank Dispatch Clearance to vendor | 8 | BATB | I000 | 00I8 | I000BATB00I8
2934 | 2934 | 2934 | 2934 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 125V Battery Bank Transportation and Custom clearance | 9 | BATB | I000 | 00I9 | I000BATB00I9
2935 | 2935 | 2935 | 2935 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 125V Battery Bank Receipt at site | 10 | BATB | I000 | 0I10 | I000BATB0I10
2936 | 2936 | 2936 | 2936 | SA24M005 | 125V Battery Chargers |  | 4 | -1 | 0 |  |  | X
2937 | 2937 | 2937 | 2937 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 125V Battery Chargers MQP / ITP Submission | 1 | BATC | I000 | 00I1 | I000BATC00I1
2938 | 2938 | 2938 | 2938 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 125V Battery Chargers MQP / ITP Approval | 2 | BATC | I000 | 00I2 | I000BATC00I2
2939 | 2939 | 2939 | 2939 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 125V Battery Chargers Issuance of MFC | 3 | BATC | I000 | 00I3 | I000BATC00I3
2940 | 2940 | 2940 | 2940 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 125V Battery Chargers Lead Time For Manufacturing | 4 | BATC | I000 | 00I4 | I000BATC00I4
2941 | 2941 | 2941 | 2941 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 125V Battery Chargers Material readiness / Inspection call | 5 | BATC | I000 | 00I5 | I000BATC00I5
2942 | 2942 | 2942 | 2942 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 125V Battery Chargers Inspection by client personal / Third Party | 6 | BATC | I000 | 00I6 | I000BATC00I6
2943 | 2943 | 2943 | 2943 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 125V Battery Chargers Submission of FAT Compliance by Vendor | 7 | BATC | I000 | 00I7 | I000BATC00I7
2944 | 2944 | 2944 | 2944 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 125V Battery Chargers Dispatch Clearance to vendor | 8 | BATC | I000 | 00I8 | I000BATC00I8
2945 | 2945 | 2945 | 2945 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 125V Battery Chargers Transportation and Custom clearance | 9 | BATC | I000 | 00I9 | I000BATC00I9
2946 | 2946 | 2946 | 2946 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery 125V Battery Chargers Receipt at site | 10 | BATC | I000 | 0I10 | I000BATC0I10
2947 | 2947 | 2947 | 2947 | SA24M005 | ACDB Main & Sub-Panels |  | 4 | -1 | 0 |  |  | X
2948 | 2948 | 2948 | 2948 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery ACDB Main & Sub-Panels MQP / ITP Submission | 1 | ACDB | I000 | 00I1 | I000ACDB00I1
2949 | 2949 | 2949 | 2949 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery ACDB Main & Sub-Panels MQP / ITP Approval | 2 | ACDB | I000 | 00I2 | I000ACDB00I2
2950 | 2950 | 2950 | 2950 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery ACDB Main & Sub-Panels Issuance of MFC | 3 | ACDB | I000 | 00I3 | I000ACDB00I3
2951 | 2951 | 2951 | 2951 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery ACDB Main & Sub-Panels Lead Time For Manufacturing | 4 | ACDB | I000 | 00I4 | I000ACDB00I4
2952 | 2952 | 2952 | 2952 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery ACDB Main & Sub-Panels Material readiness / Inspection call | 5 | ACDB | I000 | 00I5 | I000ACDB00I5
2953 | 2953 | 2953 | 2953 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery ACDB Main & Sub-Panels Inspection by client personal / Third Party | 6 | ACDB | I000 | 00I6 | I000ACDB00I6
2954 | 2954 | 2954 | 2954 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery ACDB Main & Sub-Panels Submission of FAT Compliance by Vendor | 7 | ACDB | I000 | 00I7 | I000ACDB00I7
2955 | 2955 | 2955 | 2955 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery ACDB Main & Sub-Panels Dispatch Clearance to vendor | 8 | ACDB | I000 | 00I8 | I000ACDB00I8
2956 | 2956 | 2956 | 2956 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery ACDB Main & Sub-Panels Transportation and Custom clearance | 9 | ACDB | I000 | 00I9 | I000ACDB00I9
2957 | 2957 | 2957 | 2957 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery ACDB Main & Sub-Panels Receipt at site | 10 | ACDB | I000 | 0I10 | I000ACDB0I10
2958 | 2958 | 2958 | 2958 | SA24M005 | DCDB Main & Sub-Panels |  | 4 | -1 | 0 |  |  | X
2959 | 2959 | 2959 | 2959 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery DCDB Main & Sub-Panels MQP / ITP Submission | 1 | DCDB | I000 | 00I1 | I000DCDB00I1
2960 | 2960 | 2960 | 2960 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery DCDB Main & Sub-Panels MQP / ITP Approval | 2 | DCDB | I000 | 00I2 | I000DCDB00I2
2961 | 2961 | 2961 | 2961 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery DCDB Main & Sub-Panels Issuance of MFC | 3 | DCDB | I000 | 00I3 | I000DCDB00I3
2962 | 2962 | 2962 | 2962 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery DCDB Main & Sub-Panels Lead Time For Manufacturing | 4 | DCDB | I000 | 00I4 | I000DCDB00I4
2963 | 2963 | 2963 | 2963 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery DCDB Main & Sub-Panels Material readiness / Inspection call | 5 | DCDB | I000 | 00I5 | I000DCDB00I5
2964 | 2964 | 2964 | 2964 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery DCDB Main & Sub-Panels Inspection by client personal / Third Party | 6 | DCDB | I000 | 00I6 | I000DCDB00I6
2965 | 2965 | 2965 | 2965 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery DCDB Main & Sub-Panels Submission of FAT Compliance by Vendor | 7 | DCDB | I000 | 00I7 | I000DCDB00I7
2966 | 2966 | 2966 | 2966 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery DCDB Main & Sub-Panels Dispatch Clearance to vendor | 8 | DCDB | I000 | 00I8 | I000DCDB00I8
2967 | 2967 | 2967 | 2967 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery DCDB Main & Sub-Panels Transportation and Custom clearance | 9 | DCDB | I000 | 00I9 | I000DCDB00I9
2968 | 2968 | 2968 | 2968 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery DCDB Main & Sub-Panels Receipt at site | 10 | DCDB | I000 | 0I10 | I000DCDB0I10
2969 | 2969 | 2969 | 2969 | SA24M005 | LV Power & Control Cables |  | 4 | -1 | 0 |  |  | X
2970 | 2970 | 2970 | 2970 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery LV Power & Control Cables MQP / ITP Submission | 1 | 00LVC | I000 | 00I1 | I00000LVC00I1
2971 | 2971 | 2971 | 2971 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery LV Power & Control Cables MQP / ITP Approval | 2 | 00LVC | I000 | 00I2 | I00000LVC00I2
2972 | 2972 | 2972 | 2972 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery LV Power & Control Cables Issuance of MFC | 3 | 00LVC | I000 | 00I3 | I00000LVC00I3
2973 | 2973 | 2973 | 2973 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery LV Power & Control Cables Lead Time For Manufacturing | 4 | 00LVC | I000 | 00I4 | I00000LVC00I4
2974 | 2974 | 2974 | 2974 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery LV Power & Control Cables Material readiness / Inspection call | 5 | 00LVC | I000 | 00I5 | I00000LVC00I5
2975 | 2975 | 2975 | 2975 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery LV Power & Control Cables Inspection by client personal / Third Party | 6 | 00LVC | I000 | 00I6 | I00000LVC00I6
2976 | 2976 | 2976 | 2976 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery LV Power & Control Cables Submission of FAT Compliance by Vendor | 7 | 00LVC | I000 | 00I7 | I00000LVC00I7
2977 | 2977 | 2977 | 2977 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery LV Power & Control Cables Dispatch Clearance to vendor | 8 | 00LVC | I000 | 00I8 | I00000LVC00I8
2978 | 2978 | 2978 | 2978 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery LV Power & Control Cables Transportation and Custom clearance | 9 | 00LVC | I000 | 00I9 | I00000LVC00I9
2979 | 2979 | 2979 | 2979 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery LV Power & Control Cables Receipt at site | 10 | 00LVC | I000 | 0I10 | I00000LVC0I10
2980 | 2980 | 2980 | 2980 | SA24M005 | Sheilded Instrumentation Cables |  | 4 | -1 | 0 |  |  | X
2981 | 2981 | 2981 | 2981 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Sheilded Instrumentation Cables MQP / ITP Submission | 1 | SHIC | I000 | 00I1 | I000SHIC00I1
2982 | 2982 | 2982 | 2982 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Sheilded Instrumentation Cables MQP / ITP Approval | 2 | SHIC | I000 | 00I2 | I000SHIC00I2
2983 | 2983 | 2983 | 2983 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Sheilded Instrumentation Cables Issuance of MFC | 3 | SHIC | I000 | 00I3 | I000SHIC00I3
2984 | 2984 | 2984 | 2984 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Sheilded Instrumentation Cables Lead Time For Manufacturing | 4 | SHIC | I000 | 00I4 | I000SHIC00I4
2985 | 2985 | 2985 | 2985 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Sheilded Instrumentation Cables Material readiness / Inspection call | 5 | SHIC | I000 | 00I5 | I000SHIC00I5
2986 | 2986 | 2986 | 2986 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Sheilded Instrumentation Cables Inspection by client personal / Third Party | 6 | SHIC | I000 | 00I6 | I000SHIC00I6
2987 | 2987 | 2987 | 2987 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Sheilded Instrumentation Cables Submission of FAT Compliance by Vendor | 7 | SHIC | I000 | 00I7 | I000SHIC00I7
2988 | 2988 | 2988 | 2988 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Sheilded Instrumentation Cables Dispatch Clearance to vendor | 8 | SHIC | I000 | 00I8 | I000SHIC00I8
2989 | 2989 | 2989 | 2989 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Sheilded Instrumentation Cables Transportation and Custom clearance | 9 | SHIC | I000 | 00I9 | I000SHIC00I9
2990 | 2990 | 2990 | 2990 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Sheilded Instrumentation Cables Receipt at site | 10 | SHIC | I000 | 0I10 | I000SHIC0I10
2991 | 2991 | 2991 | 2991 | SA24M005 | LV Cable Accessories |  | 4 | -1 | 0 |  |  | X
2992 | 2992 | 2992 | 2992 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery LV Cable Accessories MQP / ITP Submission | 1 | LVCA | I000 | 00I1 | I000LVCA00I1
2993 | 2993 | 2993 | 2993 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery LV Cable Accessories MQP / ITP Approval | 2 | LVCA | I000 | 00I2 | I000LVCA00I2
2994 | 2994 | 2994 | 2994 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery LV Cable Accessories Issuance of MFC | 3 | LVCA | I000 | 00I3 | I000LVCA00I3
2995 | 2995 | 2995 | 2995 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery LV Cable Accessories Lead Time For Manufacturing | 4 | LVCA | I000 | 00I4 | I000LVCA00I4
2996 | 2996 | 2996 | 2996 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery LV Cable Accessories Material readiness / Inspection call | 5 | LVCA | I000 | 00I5 | I000LVCA00I5
2997 | 2997 | 2997 | 2997 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery LV Cable Accessories Inspection by client personal / Third Party | 6 | LVCA | I000 | 00I6 | I000LVCA00I6
2998 | 2998 | 2998 | 2998 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery LV Cable Accessories Submission of FAT Compliance by Vendor | 7 | LVCA | I000 | 00I7 | I000LVCA00I7
2999 | 2999 | 2999 | 2999 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery LV Cable Accessories Dispatch Clearance to vendor | 8 | LVCA | I000 | 00I8 | I000LVCA00I8
3000 | 3000 | 3000 | 3000 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery LV Cable Accessories Transportation and Custom clearance | 9 | LVCA | I000 | 00I9 | I000LVCA00I9
3001 | 3001 | 3001 | 3001 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery LV Cable Accessories Receipt at site | 10 | LVCA | I000 | 0I10 | I000LVCA0I10
3002 | 3002 | 3002 | 3002 | SA24M005 | Cable Trays & Supports with Accessories |  | 4 | -1 | 0 |  |  | X
3003 | 3003 | 3003 | 3003 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Cable Trays & Supports with Accessories MQP / ITP Submission | 1 | 0CBLT | I000 | 00I1 | I0000CBLT00I1
3004 | 3004 | 3004 | 3004 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Cable Trays & Supports with Accessories MQP / ITP Approval | 2 | 0CBLT | I000 | 00I2 | I0000CBLT00I2
3005 | 3005 | 3005 | 3005 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Cable Trays & Supports with Accessories Issuance of MFC | 3 | 0CBLT | I000 | 00I3 | I0000CBLT00I3
3006 | 3006 | 3006 | 3006 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Cable Trays & Supports with Accessories Lead Time For Manufacturing | 4 | 0CBLT | I000 | 00I4 | I0000CBLT00I4
3007 | 3007 | 3007 | 3007 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Cable Trays & Supports with Accessories Material readiness / Inspection call | 5 | 0CBLT | I000 | 00I5 | I0000CBLT00I5
3008 | 3008 | 3008 | 3008 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Cable Trays & Supports with Accessories Inspection by client personal / Third Party | 6 | 0CBLT | I000 | 00I6 | I0000CBLT00I6
3009 | 3009 | 3009 | 3009 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Cable Trays & Supports with Accessories Submission of FAT Compliance by Vendor | 7 | 0CBLT | I000 | 00I7 | I0000CBLT00I7
3010 | 3010 | 3010 | 3010 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Cable Trays & Supports with Accessories Dispatch Clearance to vendor | 8 | 0CBLT | I000 | 00I8 | I0000CBLT00I8
3011 | 3011 | 3011 | 3011 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Cable Trays & Supports with Accessories Transportation and Custom clearance | 9 | 0CBLT | I000 | 00I9 | I0000CBLT00I9
3012 | 3012 | 3012 | 3012 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Cable Trays & Supports with Accessories Receipt at site | 10 | 0CBLT | I000 | 0I10 | I0000CBLT0I10
3013 | 3013 | 3013 | 3013 | SA24M005 | Grounding Material with accessories |  | 4 | -1 | 0 |  |  | X
3014 | 3014 | 3014 | 3014 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Grounding Material with accessories MQP / ITP Submission | 1 | GRND | I000 | 00I1 | I000#hodm00I1
3015 | 3015 | 3015 | 3015 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Grounding Material with accessories MQP / ITP Approval | 2 | GRND | I000 | 00I2 | I000#hodm00I2
3016 | 3016 | 3016 | 3016 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Grounding Material with accessories Issuance of MFC | 3 | GRND | I000 | 00I3 | I000#hodm00I3
3017 | 3017 | 3017 | 3017 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Grounding Material with accessories Lead Time For Manufacturing | 4 | GRND | I000 | 00I4 | I000#hodm00I4
3018 | 3018 | 3018 | 3018 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Grounding Material with accessories Material readiness / Inspection call | 5 | GRND | I000 | 00I5 | I000#hodm00I5
3019 | 3019 | 3019 | 3019 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Grounding Material with accessories Inspection by client personal / Third Party | 6 | GRND | I000 | 00I6 | I000#hodm00I6
3020 | 3020 | 3020 | 3020 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Grounding Material with accessories Submission of FAT Compliance by Vendor | 7 | GRND | I000 | 00I7 | I000#hodm00I7
3021 | 3021 | 3021 | 3021 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Grounding Material with accessories Dispatch Clearance to vendor | 8 | GRND | I000 | 00I8 | I000#hodm00I8
3022 | 3022 | 3022 | 3022 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Grounding Material with accessories Transportation and Custom clearance | 9 | GRND | I000 | 00I9 | I000#hodm00I9
3023 | 3023 | 3023 | 3023 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Grounding Material with accessories Receipt at site | 10 | GRND | I000 | 0I10 | I000#hodm0I10
3024 | 3024 | 3024 | 3024 | SA24M005 | Lighting Panels |  | 4 | -1 | 0 |  |  | X | I000#hodm
3025 | 3025 | 3025 | 3025 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Lighting Panels MQP / ITP Submission | 1 | LGPNL | I000 | 00I1 | I000LGPNL00I1
3026 | 3026 | 3026 | 3026 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Lighting Panels MQP / ITP Approval | 2 | LGPNL | I000 | 00I2 | I000LGPNL00I2
3027 | 3027 | 3027 | 3027 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Lighting Panels Issuance of MFC | 3 | LGPNL | I000 | 00I3 | I000LGPNL00I3
3028 | 3028 | 3028 | 3028 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Lighting Panels Lead Time For Manufacturing | 4 | LGPNL | I000 | 00I4 | I000LGPNL00I4
3029 | 3029 | 3029 | 3029 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Lighting Panels Material readiness / Inspection call | 5 | LGPNL | I000 | 00I5 | I000LGPNL00I5
3030 | 3030 | 3030 | 3030 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Lighting Panels Inspection by client personal / Third Party | 6 | LGPNL | I000 | 00I6 | I000LGPNL00I6
3031 | 3031 | 3031 | 3031 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Lighting Panels Submission of FAT Compliance by Vendor | 7 | LGPNL | I000 | 00I7 | I000LGPNL00I7
3032 | 3032 | 3032 | 3032 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Lighting Panels Dispatch Clearance to vendor | 8 | LGPNL | I000 | 00I8 | I000LGPNL00I8
3033 | 3033 | 3033 | 3033 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Lighting Panels Transportation and Custom clearance | 9 | LGPNL | I000 | 00I9 | I000LGPNL00I9
3034 | 3034 | 3034 | 3034 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Lighting Panels Receipt at site | 10 | LGPNL | I000 | 0I10 | I000LGPNL0I10
3035 | 3035 | 3035 | 3035 | SA24M005 | Outdoor Lighting Poles |  | 4 | -1 | 0 |  |  | X
3036 | 3036 | 3036 | 3036 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Outdoor Lighting Poles MQP / ITP Submission | 1 | 0LGPL | I000 | 00I1 | I0000LGPL00I1
3037 | 3037 | 3037 | 3037 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Outdoor Lighting Poles MQP / ITP Approval | 2 | 0LGPL | I000 | 00I2 | I0000LGPL00I2
3038 | 3038 | 3038 | 3038 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Outdoor Lighting Poles Issuance of MFC | 3 | 0LGPL | I000 | 00I3 | I0000LGPL00I3
3039 | 3039 | 3039 | 3039 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Outdoor Lighting Poles Lead Time For Manufacturing | 4 | 0LGPL | I000 | 00I4 | I0000LGPL00I4
3040 | 3040 | 3040 | 3040 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Outdoor Lighting Poles Material readiness / Inspection call | 5 | 0LGPL | I000 | 00I5 | I0000LGPL00I5
3041 | 3041 | 3041 | 3041 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Outdoor Lighting Poles Inspection by client personal / Third Party | 6 | 0LGPL | I000 | 00I6 | I0000LGPL00I6
3042 | 3042 | 3042 | 3042 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Outdoor Lighting Poles Submission of FAT Compliance by Vendor | 7 | 0LGPL | I000 | 00I7 | I0000LGPL00I7
3043 | 3043 | 3043 | 3043 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Outdoor Lighting Poles Dispatch Clearance to vendor | 8 | 0LGPL | I000 | 00I8 | I0000LGPL00I8
3044 | 3044 | 3044 | 3044 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Outdoor Lighting Poles Transportation and Custom clearance | 9 | 0LGPL | I000 | 00I9 | I0000LGPL00I9
3045 | 3045 | 3045 | 3045 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Outdoor Lighting Poles Receipt at site | 10 | 0LGPL | I000 | 0I10 | I0000LGPL0I10
3046 | 3046 | 3046 | 3046 | SA24M005 | Light Fitting & Receptacles |  | 4 | -1 | 0 |  |  | X
3047 | 3047 | 3047 | 3047 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Light Fitting & Receptacles MQP / ITP Submission | 1 | LGFR | I000 | 00I1 | I000LGFR00I1
3048 | 3048 | 3048 | 3048 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Light Fitting & Receptacles MQP / ITP Approval | 2 | LGFR | I000 | 00I2 | I000LGFR00I2
3049 | 3049 | 3049 | 3049 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Light Fitting & Receptacles Issuance of MFC | 3 | LGFR | I000 | 00I3 | I000LGFR00I3
3050 | 3050 | 3050 | 3050 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Light Fitting & Receptacles Lead Time For Manufacturing | 4 | LGFR | I000 | 00I4 | I000LGFR00I4
3051 | 3051 | 3051 | 3051 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Light Fitting & Receptacles Material readiness / Inspection call | 5 | LGFR | I000 | 00I5 | I000LGFR00I5
3052 | 3052 | 3052 | 3052 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Light Fitting & Receptacles Inspection by client personal / Third Party | 6 | LGFR | I000 | 00I6 | I000LGFR00I6
3053 | 3053 | 3053 | 3053 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Light Fitting & Receptacles Submission of FAT Compliance by Vendor | 7 | LGFR | I000 | 00I7 | I000LGFR00I7
3054 | 3054 | 3054 | 3054 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Light Fitting & Receptacles Dispatch Clearance to vendor | 8 | LGFR | I000 | 00I8 | I000LGFR00I8
3055 | 3055 | 3055 | 3055 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Light Fitting & Receptacles Transportation and Custom clearance | 9 | LGFR | I000 | 00I9 | I000LGFR00I9
3056 | 3056 | 3056 | 3056 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Light Fitting & Receptacles Receipt at site | 10 | LGFR | I000 | 0I10 | I000LGFR0I10
3057 | 3057 | 3057 | 3057 | SA24M005 | Lighting Conduits, JB's & Accessories |  | 4 | -1 | 0 |  |  | X
3058 | 3058 | 3058 | 3058 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Lighting Conduits, JB's & Accessories MQP / ITP Submission | 1 | LGJB | I000 | 00I1 | I000LGJB00I1
3059 | 3059 | 3059 | 3059 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Lighting Conduits, JB's & Accessories MQP / ITP Approval | 2 | LGJB | I000 | 00I2 | I000LGJB00I2
3060 | 3060 | 3060 | 3060 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Lighting Conduits, JB's & Accessories Issuance of MFC | 3 | LGJB | I000 | 00I3 | I000LGJB00I3
3061 | 3061 | 3061 | 3061 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Lighting Conduits, JB's & Accessories Lead Time For Manufacturing | 4 | LGJB | I000 | 00I4 | I000LGJB00I4
3062 | 3062 | 3062 | 3062 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Lighting Conduits, JB's & Accessories Material readiness / Inspection call | 5 | LGJB | I000 | 00I5 | I000LGJB00I5
3063 | 3063 | 3063 | 3063 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Lighting Conduits, JB's & Accessories Inspection by client personal / Third Party | 6 | LGJB | I000 | 00I6 | I000LGJB00I6
3064 | 3064 | 3064 | 3064 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Lighting Conduits, JB's & Accessories Submission of FAT Compliance by Vendor | 7 | LGJB | I000 | 00I7 | I000LGJB00I7
3065 | 3065 | 3065 | 3065 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Lighting Conduits, JB's & Accessories Dispatch Clearance to vendor | 8 | LGJB | I000 | 00I8 | I000LGJB00I8
3066 | 3066 | 3066 | 3066 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Lighting Conduits, JB's & Accessories Transportation and Custom clearance | 9 | LGJB | I000 | 00I9 | I000LGJB00I9
3067 | 3067 | 3067 | 3067 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Lighting Conduits, JB's & Accessories Receipt at site | 10 | LGJB | I000 | 0I10 | I000LGJB0I10
3068 | 3068 | 3068 | 3068 | SA24M005 | Lighting & Sheilding system |  | 4 | -1 | 0 |  |  | X
3069 | 3069 | 3069 | 3069 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Lighting & Sheilding system MQP / ITP Submission | 1 | LGSH | I000 | 00I1 | I000LGSH00I1
3070 | 3070 | 3070 | 3070 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Lighting & Sheilding system MQP / ITP Approval | 2 | LGSH | I000 | 00I2 | I000LGSH00I2
3071 | 3071 | 3071 | 3071 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Lighting & Sheilding system Issuance of MFC | 3 | LGSH | I000 | 00I3 | I000LGSH00I3
3072 | 3072 | 3072 | 3072 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Lighting & Sheilding system Lead Time For Manufacturing | 4 | LGSH | I000 | 00I4 | I000LGSH00I4
3073 | 3073 | 3073 | 3073 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Lighting & Sheilding system Material readiness / Inspection call | 5 | LGSH | I000 | 00I5 | I000LGSH00I5
3074 | 3074 | 3074 | 3074 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Lighting & Sheilding system Inspection by client personal / Third Party | 6 | LGSH | I000 | 00I6 | I000LGSH00I6
3075 | 3075 | 3075 | 3075 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Lighting & Sheilding system Submission of FAT Compliance by Vendor | 7 | LGSH | I000 | 00I7 | I000LGSH00I7
3076 | 3076 | 3076 | 3076 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Lighting & Sheilding system Dispatch Clearance to vendor | 8 | LGSH | I000 | 00I8 | I000LGSH00I8
3077 | 3077 | 3077 | 3077 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Lighting & Sheilding system Transportation and Custom clearance | 9 | LGSH | I000 | 00I9 | I000LGSH00I9
3078 | 3078 | 3078 | 3078 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Lighting & Sheilding system Receipt at site | 10 | LGSH | I000 | 0I10 | I000LGSH0I10
3079 | 3079 | 3079 | 3079 | SA24M005 | Outdoor Equipment Steel Support Structure |  | 4 | -1 | 0 |  |  | X
3080 | 3080 | 3080 | 3080 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Outdoor Equipment Steel Support Structure MQP / ITP Submission | 1 | OEQSR | I000 | 00I1 | I000OEQSR00I1
3081 | 3081 | 3081 | 3081 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Outdoor Equipment Steel Support Structure MQP / ITP Approval | 2 | OEQSR | I000 | 00I2 | I000OEQSR00I2
3082 | 3082 | 3082 | 3082 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Outdoor Equipment Steel Support Structure Issuance of MFC | 3 | OEQSR | I000 | 00I3 | I000OEQSR00I3
3083 | 3083 | 3083 | 3083 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Outdoor Equipment Steel Support Structure Lead Time For Manufacturing | 4 | OEQSR | I000 | 00I4 | I000OEQSR00I4
3084 | 3084 | 3084 | 3084 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Outdoor Equipment Steel Support Structure Material readiness / Inspection call | 5 | OEQSR | I000 | 00I5 | I000OEQSR00I5
3085 | 3085 | 3085 | 3085 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Outdoor Equipment Steel Support Structure Inspection by client personal / Third Party | 6 | OEQSR | I000 | 00I6 | I000OEQSR00I6
3086 | 3086 | 3086 | 3086 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Outdoor Equipment Steel Support Structure Submission of FAT Compliance by Vendor | 7 | OEQSR | I000 | 00I7 | I000OEQSR00I7
3087 | 3087 | 3087 | 3087 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Outdoor Equipment Steel Support Structure Dispatch Clearance to vendor | 8 | OEQSR | I000 | 00I8 | I000OEQSR00I8
3088 | 3088 | 3088 | 3088 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Outdoor Equipment Steel Support Structure Transportation and Custom clearance | 9 | OEQSR | I000 | 00I9 | I000OEQSR00I9
3089 | 3089 | 3089 | 3089 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Outdoor Equipment Steel Support Structure Receipt at site | 10 | OEQSR | I000 | 0I10 | I000OEQSR0I10
3090 | 3090 | 3090 | 3090 | SA24M005 | Lattice Steel Gantry Structures |  | 4 | -1 | 0 |  |  | X
3091 | 3091 | 3091 | 3091 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Lattice Steel Gantry Structures MQP / ITP Submission | 1 | LGSTR | I000 | 00I1 | I000LGSTR00I1
3092 | 3092 | 3092 | 3092 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Lattice Steel Gantry Structures MQP / ITP Approval | 2 | LGSTR | I000 | 00I2 | I000LGSTR00I2
3093 | 3093 | 3093 | 3093 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Lattice Steel Gantry Structures Issuance of MFC | 3 | LGSTR | I000 | 00I3 | I000LGSTR00I3
3094 | 3094 | 3094 | 3094 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Lattice Steel Gantry Structures Lead Time For Manufacturing | 4 | LGSTR | I000 | 00I4 | I000LGSTR00I4
3095 | 3095 | 3095 | 3095 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Lattice Steel Gantry Structures Material readiness / Inspection call | 5 | LGSTR | I000 | 00I5 | I000LGSTR00I5
3096 | 3096 | 3096 | 3096 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Lattice Steel Gantry Structures Inspection by client personal / Third Party | 6 | LGSTR | I000 | 00I6 | I000LGSTR00I6
3097 | 3097 | 3097 | 3097 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Lattice Steel Gantry Structures Submission of FAT Compliance by Vendor | 7 | LGSTR | I000 | 00I7 | I000LGSTR00I7
3098 | 3098 | 3098 | 3098 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Lattice Steel Gantry Structures Dispatch Clearance to vendor | 8 | LGSTR | I000 | 00I8 | I000LGSTR00I8
3099 | 3099 | 3099 | 3099 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Lattice Steel Gantry Structures Transportation and Custom clearance | 9 | LGSTR | I000 | 00I9 | I000LGSTR00I9
3100 | 3100 | 3100 | 3100 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Lattice Steel Gantry Structures Receipt at site | 10 | LGSTR | I000 | 0I10 | I000LGSTR0I10
3101 | 3101 | 3101 | 3101 | SA24M005 | Protection & Metering System |  | 4 | -1 | 0 |  |  | X
3102 | 3102 | 3102 | 3102 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Protection & Metering System MQP / ITP Submission | 1 | 0PRMS | I000 | 00I1 | I0000PRMS00I1
3103 | 3103 | 3103 | 3103 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Protection & Metering System MQP / ITP Approval | 2 | 0PRMS | I000 | 00I2 | I0000PRMS00I2
3104 | 3104 | 3104 | 3104 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Protection & Metering System Issuance of MFC | 3 | 0PRMS | I000 | 00I3 | I0000PRMS00I3
3105 | 3105 | 3105 | 3105 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Protection & Metering System Lead Time For Manufacturing | 4 | 0PRMS | I000 | 00I4 | I0000PRMS00I4
3106 | 3106 | 3106 | 3106 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Protection & Metering System Material readiness / Inspection call | 5 | 0PRMS | I000 | 00I5 | I0000PRMS00I5
3107 | 3107 | 3107 | 3107 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Protection & Metering System Inspection by client personal / Third Party | 6 | 0PRMS | I000 | 00I6 | I0000PRMS00I6
3108 | 3108 | 3108 | 3108 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Protection & Metering System Submission of FAT Compliance by Vendor | 7 | 0PRMS | I000 | 00I7 | I0000PRMS00I7
3109 | 3109 | 3109 | 3109 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Protection & Metering System Dispatch Clearance to vendor | 8 | 0PRMS | I000 | 00I8 | I0000PRMS00I8
3110 | 3110 | 3110 | 3110 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Protection & Metering System Transportation and Custom clearance | 9 | 0PRMS | I000 | 00I9 | I0000PRMS00I9
3111 | 3111 | 3111 | 3111 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Protection & Metering System Receipt at site | 10 | 0PRMS | I000 | 0I10 | I0000PRMS0I10
3112 | 3112 | 3112 | 3112 | SA24M005 | Alarm and Annunciator System |  | 4 | -1 | 0 |  |  | X
3113 | 3113 | 3113 | 3113 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Alarm and Annunciator System MQP / ITP Submission | 1 | AALARM | I000 | 00I1 | I000AALARM00I1
3114 | 3114 | 3114 | 3114 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Alarm and Annunciator System MQP / ITP Approval | 2 | AALARM | I000 | 00I2 | I000AALARM00I2
3115 | 3115 | 3115 | 3115 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Alarm and Annunciator System Issuance of MFC | 3 | AALARM | I000 | 00I3 | I000AALARM00I3
3116 | 3116 | 3116 | 3116 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Alarm and Annunciator System Lead Time For Manufacturing | 4 | AALARM | I000 | 00I4 | I000AALARM00I4
3117 | 3117 | 3117 | 3117 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Alarm and Annunciator System Material readiness / Inspection call | 5 | AALARM | I000 | 00I5 | I000AALARM00I5
3118 | 3118 | 3118 | 3118 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Alarm and Annunciator System Inspection by client personal / Third Party | 6 | AALARM | I000 | 00I6 | I000AALARM00I6
3119 | 3119 | 3119 | 3119 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Alarm and Annunciator System Submission of FAT Compliance by Vendor | 7 | AALARM | I000 | 00I7 | I000AALARM00I7
3120 | 3120 | 3120 | 3120 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Alarm and Annunciator System Dispatch Clearance to vendor | 8 | AALARM | I000 | 00I8 | I000AALARM00I8
3121 | 3121 | 3121 | 3121 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Alarm and Annunciator System Transportation and Custom clearance | 9 | AALARM | I000 | 00I9 | I000AALARM00I9
3122 | 3122 | 3122 | 3122 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Alarm and Annunciator System Receipt at site | 10 | AALARM | I000 | 0I10 | I000AALARM0I10
3123 | 3123 | 3123 | 3123 | SA24M005 | Communication system (48V Battery Bank) |  | 4 | -1 | 0 |  |  | X
3124 | 3124 | 3124 | 3124 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Communication system (48V Battery Bank) MQP / ITP Submission | 1 | 0COMM | I000 | 00I1 | I0000COMM00I1
3125 | 3125 | 3125 | 3125 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Communication system (48V Battery Bank) MQP / ITP Approval | 2 | 0COMM | I000 | 00I2 | I0000COMM00I2
3126 | 3126 | 3126 | 3126 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Communication system (48V Battery Bank) Issuance of MFC | 3 | 0COMM | I000 | 00I3 | I0000COMM00I3
3127 | 3127 | 3127 | 3127 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Communication system (48V Battery Bank) Lead Time For Manufacturing | 4 | 0COMM | I000 | 00I4 | I0000COMM00I4
3128 | 3128 | 3128 | 3128 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Communication system (48V Battery Bank) Material readiness / Inspection call | 5 | 0COMM | I000 | 00I5 | I0000COMM00I5
3129 | 3129 | 3129 | 3129 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Communication system (48V Battery Bank) Inspection by client personal / Third Party | 6 | 0COMM | I000 | 00I6 | I0000COMM00I6
3130 | 3130 | 3130 | 3130 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Communication system (48V Battery Bank) Submission of FAT Compliance by Vendor | 7 | 0COMM | I000 | 00I7 | I0000COMM00I7
3131 | 3131 | 3131 | 3131 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Communication system (48V Battery Bank) Dispatch Clearance to vendor | 8 | 0COMM | I000 | 00I8 | I0000COMM00I8
3132 | 3132 | 3132 | 3132 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Communication system (48V Battery Bank) Transportation and Custom clearance | 9 | 0COMM | I000 | 00I9 | I0000COMM00I9
3133 | 3133 | 3133 | 3133 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Communication system (48V Battery Bank) Receipt at site | 10 | 0COMM | I000 | 0I10 | I0000COMM0I10
3134 | 3134 | 3134 | 3134 | SA24M005 | Communication system (48V Battery Chargers) |  | 4 | -1 | 0 |  |  | X
3135 | 3135 | 3135 | 3135 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Communication system (48V Battery Chargers) MQP / ITP Submission | 1 | 0BATC | I000 | 00I1 | I0000BATC00I1
3136 | 3136 | 3136 | 3136 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Communication system (48V Battery Chargers) MQP / ITP Approval | 2 | 0BATC | I000 | 00I2 | I0000BATC00I2
3137 | 3137 | 3137 | 3137 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Communication system (48V Battery Chargers) Issuance of MFC | 3 | 0BATC | I000 | 00I3 | I0000BATC00I3
3138 | 3138 | 3138 | 3138 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Communication system (48V Battery Chargers) Lead Time For Manufacturing | 4 | 0BATC | I000 | 00I4 | I0000BATC00I4
3139 | 3139 | 3139 | 3139 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Communication system (48V Battery Chargers) Material readiness / Inspection call | 5 | 0BATC | I000 | 00I5 | I0000BATC00I5
3140 | 3140 | 3140 | 3140 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Communication system (48V Battery Chargers) Inspection by client personal / Third Party | 6 | 0BATC | I000 | 00I6 | I0000BATC00I6
3141 | 3141 | 3141 | 3141 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Communication system (48V Battery Chargers) Submission of FAT Compliance by Vendor | 7 | 0BATC | I000 | 00I7 | I0000BATC00I7
3142 | 3142 | 3142 | 3142 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Communication system (48V Battery Chargers) Dispatch Clearance to vendor | 8 | 0BATC | I000 | 00I8 | I0000BATC00I8
3143 | 3143 | 3143 | 3143 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Communication system (48V Battery Chargers) Transportation and Custom clearance | 9 | 0BATC | I000 | 00I9 | I0000BATC00I9
3144 | 3144 | 3144 | 3144 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Communication system (48V Battery Chargers) Receipt at site | 10 | 0BATC | I000 | 0I10 | I0000BATC0I10
3145 | 3145 | 3145 | 3145 | SA24M005 | Communication system (Panels- DC/SDH/DVM/MDF) |  | 4 | -1 | 0 |  |  | X
3146 | 3146 | 3146 | 3146 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Communication system (Panels- DC/SDH/DVM/MDF) MQP / ITP Submission | 1 | COMM | I000 | 00I1 | I000#lONA00I1
3147 | 3147 | 3147 | 3147 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Communication system (Panels- DC/SDH/DVM/MDF) MQP / ITP Approval | 2 | COMM | I000 | 00I2 | I000#lONA00I2
3148 | 3148 | 3148 | 3148 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Communication system (Panels- DC/SDH/DVM/MDF) Issuance of MFC | 3 | COMM | I000 | 00I3 | I000#lONA00I3
3149 | 3149 | 3149 | 3149 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Communication system (Panels- DC/SDH/DVM/MDF) Lead Time For Manufacturing | 4 | COMM | I000 | 00I4 | I000#lONA00I4
3150 | 3150 | 3150 | 3150 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Communication system (Panels- DC/SDH/DVM/MDF) Material readiness / Inspection call | 5 | COMM | I000 | 00I5 | I000#lONA00I5
3151 | 3151 | 3151 | 3151 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Communication system (Panels- DC/SDH/DVM/MDF) Inspection by client personal / Third Party | 6 | COMM | I000 | 00I6 | I000#lONA00I6
3152 | 3152 | 3152 | 3152 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Communication system (Panels- DC/SDH/DVM/MDF) Submission of FAT Compliance by Vendor | 7 | COMM | I000 | 00I7 | I000#lONA00I7
3153 | 3153 | 3153 | 3153 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Communication system (Panels- DC/SDH/DVM/MDF) Dispatch Clearance to vendor | 8 | COMM | I000 | 00I8 | I000#lONA00I8
3154 | 3154 | 3154 | 3154 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Communication system (Panels- DC/SDH/DVM/MDF) Transportation and Custom clearance | 9 | COMM | I000 | 00I9 | I000#lONA00I9
3155 | 3155 | 3155 | 3155 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Communication system (Panels- DC/SDH/DVM/MDF) Receipt at site | 10 | COMM | I000 | 0I10 | I000#lONA0I10
3156 | 3156 | 3156 | 3156 | SA24M005 | Communication system (Other Items) |  | 4 | -1 | 0 |  |  | X | I000#lONA
3157 | 3157 | 3157 | 3157 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Communication system (Other Items) MQP / ITP Submission | 1 | COMM | I000 | 00I1 | I000#iEqd00I1
3158 | 3158 | 3158 | 3158 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Communication system (Other Items) MQP / ITP Approval | 2 | COMM | I000 | 00I2 | I000#iEqd00I2
3159 | 3159 | 3159 | 3159 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Communication system (Other Items) Issuance of MFC | 3 | COMM | I000 | 00I3 | I000#iEqd00I3
3160 | 3160 | 3160 | 3160 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Communication system (Other Items) Lead Time For Manufacturing | 4 | COMM | I000 | 00I4 | I000#iEqd00I4
3161 | 3161 | 3161 | 3161 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Communication system (Other Items) Material readiness / Inspection call | 5 | COMM | I000 | 00I5 | I000#iEqd00I5
3162 | 3162 | 3162 | 3162 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Communication system (Other Items) Inspection by client personal / Third Party | 6 | COMM | I000 | 00I6 | I000#iEqd00I6
3163 | 3163 | 3163 | 3163 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Communication system (Other Items) Submission of FAT Compliance by Vendor | 7 | COMM | I000 | 00I7 | I000#iEqd00I7
3164 | 3164 | 3164 | 3164 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Communication system (Other Items) Dispatch Clearance to vendor | 8 | COMM | I000 | 00I8 | I000#iEqd00I8
3165 | 3165 | 3165 | 3165 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Communication system (Other Items) Transportation and Custom clearance | 9 | COMM | I000 | 00I9 | I000#iEqd00I9
3166 | 3166 | 3166 | 3166 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Communication system (Other Items) Receipt at site | 10 | COMM | I000 | 0I10 | I000#iEqd0I10
3167 | 3167 | 3167 | 3167 | SA24M005 | SAS / SCADA System |  | 4 | -1 | 0 |  |  | X | I000#iEqd
3168 | 3168 | 3168 | 3168 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery SAS / SCADA System MQP / ITP Submission | 1 | 0SCAD | I000 | 00I1 | I0000SCAD00I1
3169 | 3169 | 3169 | 3169 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery SAS / SCADA System MQP / ITP Approval | 2 | 0SCAD | I000 | 00I2 | I0000SCAD00I2
3170 | 3170 | 3170 | 3170 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery SAS / SCADA System Issuance of MFC | 3 | 0SCAD | I000 | 00I3 | I0000SCAD00I3
3171 | 3171 | 3171 | 3171 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery SAS / SCADA System Lead Time For Manufacturing | 4 | 0SCAD | I000 | 00I4 | I0000SCAD00I4
3172 | 3172 | 3172 | 3172 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery SAS / SCADA System Material readiness / Inspection call | 5 | 0SCAD | I000 | 00I5 | I0000SCAD00I5
3173 | 3173 | 3173 | 3173 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery SAS / SCADA System Inspection by client personal / Third Party | 6 | 0SCAD | I000 | 00I6 | I0000SCAD00I6
3174 | 3174 | 3174 | 3174 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery SAS / SCADA System Submission of FAT Compliance by Vendor | 7 | 0SCAD | I000 | 00I7 | I0000SCAD00I7
3175 | 3175 | 3175 | 3175 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery SAS / SCADA System Dispatch Clearance to vendor | 8 | 0SCAD | I000 | 00I8 | I0000SCAD00I8
3176 | 3176 | 3176 | 3176 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery SAS / SCADA System Transportation and Custom clearance | 9 | 0SCAD | I000 | 00I9 | I0000SCAD00I9
3177 | 3177 | 3177 | 3177 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery SAS / SCADA System Receipt at site | 10 | 0SCAD | I000 | 0I10 | I0000SCAD0I10
3178 | 3178 | 3178 | 3178 | SA24M005 | HCIS System (CCTV etc.) |  | 4 | -1 | 0 |  |  | X
3179 | 3179 | 3179 | 3179 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery HCIS System (CCTV etc.) MQP / ITP Submission | 1 | HCIS | I000 | 00I1 | I000HCIS00I1
3180 | 3180 | 3180 | 3180 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery HCIS System (CCTV etc.) MQP / ITP Approval | 2 | HCIS | I000 | 00I2 | I000HCIS00I2
3181 | 3181 | 3181 | 3181 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery HCIS System (CCTV etc.) Issuance of MFC | 3 | HCIS | I000 | 00I3 | I000HCIS00I3
3182 | 3182 | 3182 | 3182 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery HCIS System (CCTV etc.) Lead Time For Manufacturing | 4 | HCIS | I000 | 00I4 | I000HCIS00I4
3183 | 3183 | 3183 | 3183 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery HCIS System (CCTV etc.) Material readiness / Inspection call | 5 | HCIS | I000 | 00I5 | I000HCIS00I5
3184 | 3184 | 3184 | 3184 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery HCIS System (CCTV etc.) Inspection by client personal / Third Party | 6 | HCIS | I000 | 00I6 | I000HCIS00I6
3185 | 3185 | 3185 | 3185 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery HCIS System (CCTV etc.) Submission of FAT Compliance by Vendor | 7 | HCIS | I000 | 00I7 | I000HCIS00I7
3186 | 3186 | 3186 | 3186 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery HCIS System (CCTV etc.) Dispatch Clearance to vendor | 8 | HCIS | I000 | 00I8 | I000HCIS00I8
3187 | 3187 | 3187 | 3187 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery HCIS System (CCTV etc.) Transportation and Custom clearance | 9 | HCIS | I000 | 00I9 | I000HCIS00I9
3188 | 3188 | 3188 | 3188 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery HCIS System (CCTV etc.) Receipt at site | 10 | HCIS | I000 | 0I10 | I000HCIS0I10
3189 | 3189 | 3189 | 3189 | SA24M005 | Standalone Current Transformer ( 380kV) |  | 4 | -1 | 0 |  |  | X
3190 | 3190 | 3190 | 3190 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Standalone Current Transformer ( 380kV) MQP / ITP Submission | 1 | 0STRF | I000 | 00I1 | I0000STRF00I1
3191 | 3191 | 3191 | 3191 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Standalone Current Transformer ( 380kV) MQP / ITP Approval | 2 | 0STRF | I000 | 00I2 | I0000STRF00I2
3192 | 3192 | 3192 | 3192 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Standalone Current Transformer ( 380kV) Issuance of MFC | 3 | 0STRF | I000 | 00I3 | I0000STRF00I3
3193 | 3193 | 3193 | 3193 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Standalone Current Transformer ( 380kV) Lead Time For Manufacturing | 4 | 0STRF | I000 | 00I4 | I0000STRF00I4
3194 | 3194 | 3194 | 3194 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Standalone Current Transformer ( 380kV) Material readiness / Inspection call | 5 | 0STRF | I000 | 00I5 | I0000STRF00I5
3195 | 3195 | 3195 | 3195 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Standalone Current Transformer ( 380kV) Inspection by client personal / Third Party | 6 | 0STRF | I000 | 00I6 | I0000STRF00I6
3196 | 3196 | 3196 | 3196 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Standalone Current Transformer ( 380kV) Submission of FAT Compliance by Vendor | 7 | 0STRF | I000 | 00I7 | I0000STRF00I7
3197 | 3197 | 3197 | 3197 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Standalone Current Transformer ( 380kV) Dispatch Clearance to vendor | 8 | 0STRF | I000 | 00I8 | I0000STRF00I8
3198 | 3198 | 3198 | 3198 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Standalone Current Transformer ( 380kV) Transportation and Custom clearance | 9 | 0STRF | I000 | 00I9 | I0000STRF00I9
3199 | 3199 | 3199 | 3199 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Standalone Current Transformer ( 380kV) Receipt at site | 10 | 0STRF | I000 | 0I10 | I0000STRF0I10
3200 | 3200 | 3200 | 3200 | SA24M005 | Transient Fault Recorder |  | 4 | -1 | 0 |  |  | X
3201 | 3201 | 3201 | 3201 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Transient Fault Recorder MQP / ITP Submission | 1 | TFR | I000 | 00I1 | I000TFR00I1
3202 | 3202 | 3202 | 3202 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Transient Fault Recorder MQP / ITP Approval | 2 | TFR | I000 | 00I2 | I000TFR00I2
3203 | 3203 | 3203 | 3203 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Transient Fault Recorder Issuance of MFC | 3 | TFR | I000 | 00I3 | I000TFR00I3
3204 | 3204 | 3204 | 3204 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Transient Fault Recorder Lead Time For Manufacturing | 4 | TFR | I000 | 00I4 | I000TFR00I4
3205 | 3205 | 3205 | 3205 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Transient Fault Recorder Material readiness / Inspection call | 5 | TFR | I000 | 00I5 | I000TFR00I5
3206 | 3206 | 3206 | 3206 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Transient Fault Recorder Inspection by client personal / Third Party | 6 | TFR | I000 | 00I6 | I000TFR00I6
3207 | 3207 | 3207 | 3207 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Transient Fault Recorder Submission of FAT Compliance by Vendor | 7 | TFR | I000 | 00I7 | I000TFR00I7
3208 | 3208 | 3208 | 3208 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Transient Fault Recorder Dispatch Clearance to vendor | 8 | TFR | I000 | 00I8 | I000TFR00I8
3209 | 3209 | 3209 | 3209 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Transient Fault Recorder Transportation and Custom clearance | 9 | TFR | I000 | 00I9 | I000TFR00I9
3210 | 3210 | 3210 | 3210 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Transient Fault Recorder Receipt at site | 10 | TFR | I000 | 0I10 | I000TFR0I10
3211 | 3211 | 3211 | 3211 | SA24M005 | DSM Equipment |  | 4 | -1 | 0 |  |  | X
3212 | 3212 | 3212 | 3212 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery DSM Equipment MQP / ITP Submission | 1 | DSM0EQIP | I000 | 00I1 | I000DSM0EQIP00I1
3213 | 3213 | 3213 | 3213 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery DSM Equipment MQP / ITP Approval | 2 | DSM0EQIP | I000 | 00I2 | I000DSM0EQIP00I2
3214 | 3214 | 3214 | 3214 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery DSM Equipment Issuance of MFC | 3 | DSM0EQIP | I000 | 00I3 | I000DSM0EQIP00I3
3215 | 3215 | 3215 | 3215 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery DSM Equipment Lead Time For Manufacturing | 4 | DSM0EQIP | I000 | 00I4 | I000DSM0EQIP00I4
3216 | 3216 | 3216 | 3216 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery DSM Equipment Material readiness / Inspection call | 5 | DSM0EQIP | I000 | 00I5 | I000DSM0EQIP00I5
3217 | 3217 | 3217 | 3217 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery DSM Equipment Inspection by client personal / Third Party | 6 | DSM0EQIP | I000 | 00I6 | I000DSM0EQIP00I6
3218 | 3218 | 3218 | 3218 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery DSM Equipment Submission of FAT Compliance by Vendor | 7 | DSM0EQIP | I000 | 00I7 | I000DSM0EQIP00I7
3219 | 3219 | 3219 | 3219 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery DSM Equipment Dispatch Clearance to vendor | 8 | DSM0EQIP | I000 | 00I8 | I000DSM0EQIP00I8
3220 | 3220 | 3220 | 3220 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery DSM Equipment Transportation and Custom clearance | 9 | DSM0EQIP | I000 | 00I9 | I000DSM0EQIP00I9
3221 | 3221 | 3221 | 3221 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery DSM Equipment Receipt at site | 10 | DSM0EQIP | I000 | 0I10 | I000DSM0EQIP0I10
3222 | 3222 | 3222 | 3222 | SA24M005 | CTPU with CTJB - BOX for 380kV |  | 4 | -1 | 0 |  |  | X
3223 | 3223 | 3223 | 3223 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery CTPU with CTJB - BOX for 380kV MQP / ITP Submission | 1 | CTPU | I000 | 00I1 | I000CTPU00I1
3224 | 3224 | 3224 | 3224 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery CTPU with CTJB - BOX for 380kV MQP / ITP Approval | 2 | CTPU | I000 | 00I2 | I000CTPU00I2
3225 | 3225 | 3225 | 3225 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery CTPU with CTJB - BOX for 380kV Issuance of MFC | 3 | CTPU | I000 | 00I3 | I000CTPU00I3
3226 | 3226 | 3226 | 3226 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery CTPU with CTJB - BOX for 380kV Lead Time For Manufacturing | 4 | CTPU | I000 | 00I4 | I000CTPU00I4
3227 | 3227 | 3227 | 3227 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery CTPU with CTJB - BOX for 380kV Material readiness / Inspection call | 5 | CTPU | I000 | 00I5 | I000CTPU00I5
3228 | 3228 | 3228 | 3228 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery CTPU with CTJB - BOX for 380kV Inspection by client personal / Third Party | 6 | CTPU | I000 | 00I6 | I000CTPU00I6
3229 | 3229 | 3229 | 3229 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery CTPU with CTJB - BOX for 380kV Submission of FAT Compliance by Vendor | 7 | CTPU | I000 | 00I7 | I000CTPU00I7
3230 | 3230 | 3230 | 3230 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery CTPU with CTJB - BOX for 380kV Dispatch Clearance to vendor | 8 | CTPU | I000 | 00I8 | I000CTPU00I8
3231 | 3231 | 3231 | 3231 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery CTPU with CTJB - BOX for 380kV Transportation and Custom clearance | 9 | CTPU | I000 | 00I9 | I000CTPU00I9
3232 | 3232 | 3232 | 3232 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery CTPU with CTJB - BOX for 380kV Receipt at site | 10 | CTPU | I000 | 0I10 | I000CTPU0I10
3233 | 3233 | 3233 | 3233 | SA24M005 | PDMS System |  | 4 | -1 | 0 |  |  | X
3234 | 3234 | 3234 | 3234 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery PDMS System MQP / ITP Submission | 1 | PDMS | I000 | 00I1 | I000#NXQR00I1
3235 | 3235 | 3235 | 3235 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery PDMS System MQP / ITP Approval | 2 | PDMS | I000 | 00I2 | I000#NXQR00I2
3236 | 3236 | 3236 | 3236 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery PDMS System Issuance of MFC | 3 | PDMS | I000 | 00I3 | I000#NXQR00I3
3237 | 3237 | 3237 | 3237 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery PDMS System Lead Time For Manufacturing | 4 | PDMS | I000 | 00I4 | I000#NXQR00I4
3238 | 3238 | 3238 | 3238 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery PDMS System Material readiness / Inspection call | 5 | PDMS | I000 | 00I5 | I000#NXQR00I5
3239 | 3239 | 3239 | 3239 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery PDMS System Inspection by client personal / Third Party | 6 | PDMS | I000 | 00I6 | I000#NXQR00I6
3240 | 3240 | 3240 | 3240 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery PDMS System Submission of FAT Compliance by Vendor | 7 | PDMS | I000 | 00I7 | I000#NXQR00I7
3241 | 3241 | 3241 | 3241 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery PDMS System Dispatch Clearance to vendor | 8 | PDMS | I000 | 00I8 | I000#NXQR00I8
3242 | 3242 | 3242 | 3242 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery PDMS System Transportation and Custom clearance | 9 | PDMS | I000 | 00I9 | I000#NXQR00I9
3243 | 3243 | 3243 | 3243 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery PDMS System Receipt at site | 10 | PDMS | I000 | 0I10 | I000#NXQR0I10
3244 | 3244 | 3244 | 3244 | SA24M005 | Fault Locater (FL) System |  | 4 | -1 | 0 |  |  | X | I000#NXQR
3245 | 3245 | 3245 | 3245 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Fault Locater (FL) System MQP / ITP Submission | 1 | FL | I000 | 00I1 | I000FL00I1
3246 | 3246 | 3246 | 3246 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Fault Locater (FL) System MQP / ITP Approval | 2 | FL | I000 | 00I2 | I000FL00I2
3247 | 3247 | 3247 | 3247 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Fault Locater (FL) System Issuance of MFC | 3 | FL | I000 | 00I3 | I000FL00I3
3248 | 3248 | 3248 | 3248 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Fault Locater (FL) System Lead Time For Manufacturing | 4 | FL | I000 | 00I4 | I000FL00I4
3249 | 3249 | 3249 | 3249 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Fault Locater (FL) System Material readiness / Inspection call | 5 | FL | I000 | 00I5 | I000FL00I5
3250 | 3250 | 3250 | 3250 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Fault Locater (FL) System Inspection by client personal / Third Party | 6 | FL | I000 | 00I6 | I000FL00I6
3251 | 3251 | 3251 | 3251 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Fault Locater (FL) System Submission of FAT Compliance by Vendor | 7 | FL | I000 | 00I7 | I000FL00I7
3252 | 3252 | 3252 | 3252 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Fault Locater (FL) System Dispatch Clearance to vendor | 8 | FL | I000 | 00I8 | I000FL00I8
3253 | 3253 | 3253 | 3253 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Fault Locater (FL) System Transportation and Custom clearance | 9 | FL | I000 | 00I9 | I000FL00I9
3254 | 3254 | 3254 | 3254 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Fault Locater (FL) System Receipt at site | 10 | FL | I000 | 0I10 | I000FL0I10
3255 | 3255 | 3255 | 3255 | SA24M005 | Mechanical Materials |  | 4 | -1 | 0 |  |  | X
3256 | 3256 | 3256 | 3256 | SA24M005 | Electrical Overhead travelling (EOT) Crane |  | 5 | -1 | 0 |  |  | X
3257 | 3257 | 3257 | 3257 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Electrical Overhead travelling (EOT) Crane MQP / ITP Submission | 1 | E0EHC | I000 | 00I1 | I000E0EHC00I1
3258 | 3258 | 3258 | 3258 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Electrical Overhead travelling (EOT) Crane MQP / ITP Approval | 2 | E0EHC | I000 | 00I2 | I000E0EHC00I2
3259 | 3259 | 3259 | 3259 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Electrical Overhead travelling (EOT) Crane Issuance of MFC | 3 | E0EHC | I000 | 00I3 | I000E0EHC00I3
3260 | 3260 | 3260 | 3260 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Electrical Overhead travelling (EOT) Crane Lead Time For Manufacturing | 4 | E0EHC | I000 | 00I4 | I000E0EHC00I4
3261 | 3261 | 3261 | 3261 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Electrical Overhead travelling (EOT) Crane Material readiness / Inspection call | 5 | E0EHC | I000 | 00I5 | I000E0EHC00I5
3262 | 3262 | 3262 | 3262 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Electrical Overhead travelling (EOT) Crane Inspection by client personal / Third Party | 6 | E0EHC | I000 | 00I6 | I000E0EHC00I6
3263 | 3263 | 3263 | 3263 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Electrical Overhead travelling (EOT) Crane Submission of FAT Compliance by Vendor | 7 | E0EHC | I000 | 00I7 | I000E0EHC00I7
3264 | 3264 | 3264 | 3264 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Electrical Overhead travelling (EOT) Crane Dispatch Clearance to vendor | 8 | E0EHC | I000 | 00I8 | I000E0EHC00I8
3265 | 3265 | 3265 | 3265 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Electrical Overhead travelling (EOT) Crane Transportation and Custom clearance | 9 | E0EHC | I000 | 00I9 | I000E0EHC00I9
3266 | 3266 | 3266 | 3266 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Electrical Overhead travelling (EOT) Crane Receipt at site | 10 | E0EHC | I000 | 0I10 | I000E0EHC0I10
3267 | 3267 | 3267 | 3267 | SA24M005 | HVAC System |  | 5 | -1 | 0 |  |  | X
3268 | 3268 | 3268 | 3268 | SA24M005 | PACU Units |  | 6 | -1 | 0 |  |  | X
3269 | 3269 | 3269 | 3269 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System PACU Units MQP / ITP Submission | 1 | MHVAC | I000 | 00I1 | I000#sAzC00I1
3270 | 3270 | 3270 | 3270 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System PACU Units MQP / ITP Approval | 2 | MHVAC | I000 | 00I2 | I000#sAzC00I2
3271 | 3271 | 3271 | 3271 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System PACU Units Issuance of MFC | 3 | MHVAC | I000 | 00I3 | I000#sAzC00I3
3272 | 3272 | 3272 | 3272 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System PACU Units Lead Time For Manufacturing | 4 | MHVAC | I000 | 00I4 | I000#sAzC00I4
3273 | 3273 | 3273 | 3273 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System PACU Units Material readiness / Inspection call | 5 | MHVAC | I000 | 00I5 | I000#sAzC00I5
3274 | 3274 | 3274 | 3274 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System PACU Units Inspection by client personal / Third Party | 6 | MHVAC | I000 | 00I6 | I000#sAzC00I6
3275 | 3275 | 3275 | 3275 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System PACU Units Submission of FAT Compliance by Vendor | 7 | MHVAC | I000 | 00I7 | I000#sAzC00I7
3276 | 3276 | 3276 | 3276 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System PACU Units Dispatch Clearance to vendor | 8 | MHVAC | I000 | 00I8 | I000#sAzC00I8
3277 | 3277 | 3277 | 3277 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System PACU Units Transportation and Custom clearance | 9 | MHVAC | I000 | 00I9 | I000#sAzC00I9
3278 | 3278 | 3278 | 3278 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System PACU Units Receipt at site | 10 | MHVAC | I000 | 0I10 | I000#sAzC0I10
3279 | 3279 | 3279 | 3279 | SA24M005 | Ducts |  | 6 | -1 | 0 |  |  | X | I000#sAzC
3280 | 3280 | 3280 | 3280 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System Ducts MQP / ITP Submission | 1 | MHVAC | I000 | 00I1 | I000#eTSg00I1
3281 | 3281 | 3281 | 3281 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System Ducts MQP / ITP Approval | 2 | MHVAC | I000 | 00I2 | I000#eTSg00I2
3282 | 3282 | 3282 | 3282 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System Ducts Issuance of MFC | 3 | MHVAC | I000 | 00I3 | I000#eTSg00I3
3283 | 3283 | 3283 | 3283 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System Ducts Lead Time For Manufacturing | 4 | MHVAC | I000 | 00I4 | I000#eTSg00I4
3284 | 3284 | 3284 | 3284 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System Ducts Material readiness / Inspection call | 5 | MHVAC | I000 | 00I5 | I000#eTSg00I5
3285 | 3285 | 3285 | 3285 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System Ducts Inspection by client personal / Third Party | 6 | MHVAC | I000 | 00I6 | I000#eTSg00I6
3286 | 3286 | 3286 | 3286 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System Ducts Submission of FAT Compliance by Vendor | 7 | MHVAC | I000 | 00I7 | I000#eTSg00I7
3287 | 3287 | 3287 | 3287 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System Ducts Dispatch Clearance to vendor | 8 | MHVAC | I000 | 00I8 | I000#eTSg00I8
3288 | 3288 | 3288 | 3288 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System Ducts Transportation and Custom clearance | 9 | MHVAC | I000 | 00I9 | I000#eTSg00I9
3289 | 3289 | 3289 | 3289 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System Ducts Receipt at site | 10 | MHVAC | I000 | 0I10 | I000#eTSg0I10
3290 | 3290 | 3290 | 3290 | SA24M005 | Ventilation Fans |  | 6 | -1 | 0 |  |  | X | I000#eTSg
3291 | 3291 | 3291 | 3291 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System Ventilation Fans MQP / ITP Submission | 1 | MHVAC | I000 | 00I1 | I000#NIfl00I1
3292 | 3292 | 3292 | 3292 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System Ventilation Fans MQP / ITP Approval | 2 | MHVAC | I000 | 00I2 | I000#NIfl00I2
3293 | 3293 | 3293 | 3293 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System Ventilation Fans Issuance of MFC | 3 | MHVAC | I000 | 00I3 | I000#NIfl00I3
3294 | 3294 | 3294 | 3294 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System Ventilation Fans Lead Time For Manufacturing | 4 | MHVAC | I000 | 00I4 | I000#NIfl00I4
3295 | 3295 | 3295 | 3295 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System Ventilation Fans Material readiness / Inspection call | 5 | MHVAC | I000 | 00I5 | I000#NIfl00I5
3296 | 3296 | 3296 | 3296 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System Ventilation Fans Inspection by client personal / Third Party | 6 | MHVAC | I000 | 00I6 | I000#NIfl00I6
3297 | 3297 | 3297 | 3297 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System Ventilation Fans Submission of FAT Compliance by Vendor | 7 | MHVAC | I000 | 00I7 | I000#NIfl00I7
3298 | 3298 | 3298 | 3298 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System Ventilation Fans Dispatch Clearance to vendor | 8 | MHVAC | I000 | 00I8 | I000#NIfl00I8
3299 | 3299 | 3299 | 3299 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System Ventilation Fans Transportation and Custom clearance | 9 | MHVAC | I000 | 00I9 | I000#NIfl00I9
3300 | 3300 | 3300 | 3300 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System Ventilation Fans Receipt at site | 10 | MHVAC | I000 | 0I10 | I000#NIfl0I10
3301 | 3301 | 3301 | 3301 | SA24M005 | HVAC Control Panel & Accessories |  | 6 | -1 | 0 |  |  | X | I000#NIfl
3302 | 3302 | 3302 | 3302 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System HVAC Control Panel & Accessories MQP / ITP Submission | 1 | MHVAC | I000 | 00I1 | I000#oXdw00I1
3303 | 3303 | 3303 | 3303 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System HVAC Control Panel & Accessories MQP / ITP Approval | 2 | MHVAC | I000 | 00I2 | I000#oXdw00I2
3304 | 3304 | 3304 | 3304 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System HVAC Control Panel & Accessories Issuance of MFC | 3 | MHVAC | I000 | 00I3 | I000#oXdw00I3
3305 | 3305 | 3305 | 3305 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System HVAC Control Panel & Accessories Lead Time For Manufacturing | 4 | MHVAC | I000 | 00I4 | I000#oXdw00I4
3306 | 3306 | 3306 | 3306 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System HVAC Control Panel & Accessories Material readiness / Inspection call | 5 | MHVAC | I000 | 00I5 | I000#oXdw00I5
3307 | 3307 | 3307 | 3307 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System HVAC Control Panel & Accessories Inspection by client personal / Third Party | 6 | MHVAC | I000 | 00I6 | I000#oXdw00I6
3308 | 3308 | 3308 | 3308 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System HVAC Control Panel & Accessories Submission of FAT Compliance by Vendor | 7 | MHVAC | I000 | 00I7 | I000#oXdw00I7
3309 | 3309 | 3309 | 3309 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System HVAC Control Panel & Accessories Dispatch Clearance to vendor | 8 | MHVAC | I000 | 00I8 | I000#oXdw00I8
3310 | 3310 | 3310 | 3310 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System HVAC Control Panel & Accessories Transportation and Custom clearance | 9 | MHVAC | I000 | 00I9 | I000#oXdw00I9
3311 | 3311 | 3311 | 3311 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System HVAC Control Panel & Accessories Receipt at site | 10 | MHVAC | I000 | 0I10 | I000#oXdw0I10
3312 | 3312 | 3312 | 3312 | SA24M005 | Split Type AC Units |  | 6 | -1 | 0 |  |  | X | I000#oXdw
3313 | 3313 | 3313 | 3313 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System Split Type AC Units MQP / ITP Submission | 1 | MHVAC | I000 | 00I1 | I000#MdMg00I1
3314 | 3314 | 3314 | 3314 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System Split Type AC Units MQP / ITP Approval | 2 | MHVAC | I000 | 00I2 | I000#MdMg00I2
3315 | 3315 | 3315 | 3315 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System Split Type AC Units Issuance of MFC | 3 | MHVAC | I000 | 00I3 | I000#MdMg00I3
3316 | 3316 | 3316 | 3316 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System Split Type AC Units Lead Time For Manufacturing | 4 | MHVAC | I000 | 00I4 | I000#MdMg00I4
3317 | 3317 | 3317 | 3317 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System Split Type AC Units Material readiness / Inspection call | 5 | MHVAC | I000 | 00I5 | I000#MdMg00I5
3318 | 3318 | 3318 | 3318 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System Split Type AC Units Inspection by client personal / Third Party | 6 | MHVAC | I000 | 00I6 | I000#MdMg00I6
3319 | 3319 | 3319 | 3319 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System Split Type AC Units Submission of FAT Compliance by Vendor | 7 | MHVAC | I000 | 00I7 | I000#MdMg00I7
3320 | 3320 | 3320 | 3320 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System Split Type AC Units Dispatch Clearance to vendor | 8 | MHVAC | I000 | 00I8 | I000#MdMg00I8
3321 | 3321 | 3321 | 3321 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System Split Type AC Units Transportation and Custom clearance | 9 | MHVAC | I000 | 00I9 | I000#MdMg00I9
3322 | 3322 | 3322 | 3322 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials HVAC System Split Type AC Units Receipt at site | 10 | MHVAC | I000 | 0I10 | I000#MdMg0I10
3323 | 3323 | 3323 | 3323 | SA24M005 | Fire Detection System |  | 5 | -1 | 0 |  |  | X | I000#MdMg
3324 | 3324 | 3324 | 3324 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Fire Detection System MQP / ITP Submission | 1 | MFDS | I000 | 00I1 | I000MFDS00I1
3325 | 3325 | 3325 | 3325 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Fire Detection System MQP / ITP Approval | 2 | MFDS | I000 | 00I2 | I000MFDS00I2
3326 | 3326 | 3326 | 3326 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Fire Detection System Issuance of MFC | 3 | MFDS | I000 | 00I3 | I000MFDS00I3
3327 | 3327 | 3327 | 3327 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Fire Detection System Lead Time For Manufacturing | 4 | MFDS | I000 | 00I4 | I000MFDS00I4
3328 | 3328 | 3328 | 3328 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Fire Detection System Material readiness / Inspection call | 5 | MFDS | I000 | 00I5 | I000MFDS00I5
3329 | 3329 | 3329 | 3329 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Fire Detection System Inspection by client personal / Third Party | 6 | MFDS | I000 | 00I6 | I000MFDS00I6
3330 | 3330 | 3330 | 3330 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Fire Detection System Submission of FAT Compliance by Vendor | 7 | MFDS | I000 | 00I7 | I000MFDS00I7
3331 | 3331 | 3331 | 3331 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Fire Detection System Dispatch Clearance to vendor | 8 | MFDS | I000 | 00I8 | I000MFDS00I8
3332 | 3332 | 3332 | 3332 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Fire Detection System Transportation and Custom clearance | 9 | MFDS | I000 | 00I9 | I000MFDS00I9
3333 | 3333 | 3333 | 3333 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Fire Detection System Receipt at site | 10 | MFDS | I000 | 0I10 | I000MFDS0I10
3334 | 3334 | 3334 | 3334 | SA24M005 | Fire Alarm System |  | 5 | -1 | 0 |  |  | X
3335 | 3335 | 3335 | 3335 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Fire Alarm System MQP / ITP Submission | 1 | MFAS | I000 | 00I1 | I000MFAS00I1
3336 | 3336 | 3336 | 3336 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Fire Alarm System MQP / ITP Approval | 2 | MFAS | I000 | 00I2 | I000MFAS00I2
3337 | 3337 | 3337 | 3337 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Fire Alarm System Issuance of MFC | 3 | MFAS | I000 | 00I3 | I000MFAS00I3
3338 | 3338 | 3338 | 3338 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Fire Alarm System Lead Time For Manufacturing | 4 | MFAS | I000 | 00I4 | I000MFAS00I4
3339 | 3339 | 3339 | 3339 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Fire Alarm System Material readiness / Inspection call | 5 | MFAS | I000 | 00I5 | I000MFAS00I5
3340 | 3340 | 3340 | 3340 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Fire Alarm System Inspection by client personal / Third Party | 6 | MFAS | I000 | 00I6 | I000MFAS00I6
3341 | 3341 | 3341 | 3341 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Fire Alarm System Submission of FAT Compliance by Vendor | 7 | MFAS | I000 | 00I7 | I000MFAS00I7
3342 | 3342 | 3342 | 3342 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Fire Alarm System Dispatch Clearance to vendor | 8 | MFAS | I000 | 00I8 | I000MFAS00I8
3343 | 3343 | 3343 | 3343 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Fire Alarm System Transportation and Custom clearance | 9 | MFAS | I000 | 00I9 | I000MFAS00I9
3344 | 3344 | 3344 | 3344 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Fire Alarm System Receipt at site | 10 | MFAS | I000 | 0I10 | I000MFAS0I10
3345 | 3345 | 3345 | 3345 | SA24M005 | Fire Extinguisher System |  | 5 | -1 | 0 |  |  | X
3346 | 3346 | 3346 | 3346 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Fire Extinguisher System MQP / ITP Submission | 1 | FEXS | I000 | 00I1 | I000FEXS00I1
3347 | 3347 | 3347 | 3347 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Fire Extinguisher System MQP / ITP Approval | 2 | FEXS | I000 | 00I2 | I000FEXS00I2
3348 | 3348 | 3348 | 3348 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Fire Extinguisher System Issuance of MFC | 3 | FEXS | I000 | 00I3 | I000FEXS00I3
3349 | 3349 | 3349 | 3349 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Fire Extinguisher System Lead Time For Manufacturing | 4 | FEXS | I000 | 00I4 | I000FEXS00I4
3350 | 3350 | 3350 | 3350 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Fire Extinguisher System Material readiness / Inspection call | 5 | FEXS | I000 | 00I5 | I000FEXS00I5
3351 | 3351 | 3351 | 3351 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Fire Extinguisher System Inspection by client personal / Third Party | 6 | FEXS | I000 | 00I6 | I000FEXS00I6
3352 | 3352 | 3352 | 3352 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Fire Extinguisher System Submission of FAT Compliance by Vendor | 7 | FEXS | I000 | 00I7 | I000FEXS00I7
3353 | 3353 | 3353 | 3353 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Fire Extinguisher System Dispatch Clearance to vendor | 8 | FEXS | I000 | 00I8 | I000FEXS00I8
3354 | 3354 | 3354 | 3354 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Fire Extinguisher System Transportation and Custom clearance | 9 | FEXS | I000 | 00I9 | I000FEXS00I9
3355 | 3355 | 3355 | 3355 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Fire Extinguisher System Receipt at site | 10 | FEXS | I000 | 0I10 | I000FEXS0I10
3356 | 3356 | 3356 | 3356 | SA24M005 | Fire Hydrant System |  | 5 | -1 | 0 |  |  | X
3357 | 3357 | 3357 | 3357 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Fire Hydrant System MQP / ITP Submission | 1 | FHYD | I000 | 00I1 | I000FHYD00I1
3358 | 3358 | 3358 | 3358 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Fire Hydrant System MQP / ITP Approval | 2 | FHYD | I000 | 00I2 | I000FHYD00I2
3359 | 3359 | 3359 | 3359 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Fire Hydrant System Issuance of MFC | 3 | FHYD | I000 | 00I3 | I000FHYD00I3
3360 | 3360 | 3360 | 3360 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Fire Hydrant System Lead Time For Manufacturing | 4 | FHYD | I000 | 00I4 | I000FHYD00I4
3361 | 3361 | 3361 | 3361 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Fire Hydrant System Material readiness / Inspection call | 5 | FHYD | I000 | 00I5 | I000FHYD00I5
3362 | 3362 | 3362 | 3362 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Fire Hydrant System Inspection by client personal / Third Party | 6 | FHYD | I000 | 00I6 | I000FHYD00I6
3363 | 3363 | 3363 | 3363 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Fire Hydrant System Submission of FAT Compliance by Vendor | 7 | FHYD | I000 | 00I7 | I000FHYD00I7
3364 | 3364 | 3364 | 3364 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Fire Hydrant System Dispatch Clearance to vendor | 8 | FHYD | I000 | 00I8 | I000FHYD00I8
3365 | 3365 | 3365 | 3365 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Fire Hydrant System Transportation and Custom clearance | 9 | FHYD | I000 | 00I9 | I000FHYD00I9
3366 | 3366 | 3366 | 3366 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Fire Hydrant System Receipt at site | 10 | FHYD | I000 | 0I10 | I000FHYD0I10
3367 | 3367 | 3367 | 3367 | SA24M005 | Wet Sprinkler System |  | 5 | -1 | 0 |  |  | X
3368 | 3368 | 3368 | 3368 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Wet Sprinkler System MQP / ITP Submission | 1 | MWSPR | I000 | 00I1 | I000MWSPR00I1
3369 | 3369 | 3369 | 3369 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Wet Sprinkler System MQP / ITP Approval | 2 | MWSPR | I000 | 00I2 | I000MWSPR00I2
3370 | 3370 | 3370 | 3370 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Wet Sprinkler System Issuance of MFC | 3 | MWSPR | I000 | 00I3 | I000MWSPR00I3
3371 | 3371 | 3371 | 3371 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Wet Sprinkler System Lead Time For Manufacturing | 4 | MWSPR | I000 | 00I4 | I000MWSPR00I4
3372 | 3372 | 3372 | 3372 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Wet Sprinkler System Material readiness / Inspection call | 5 | MWSPR | I000 | 00I5 | I000MWSPR00I5
3373 | 3373 | 3373 | 3373 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Wet Sprinkler System Inspection by client personal / Third Party | 6 | MWSPR | I000 | 00I6 | I000MWSPR00I6
3374 | 3374 | 3374 | 3374 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Wet Sprinkler System Submission of FAT Compliance by Vendor | 7 | MWSPR | I000 | 00I7 | I000MWSPR00I7
3375 | 3375 | 3375 | 3375 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Wet Sprinkler System Dispatch Clearance to vendor | 8 | MWSPR | I000 | 00I8 | I000MWSPR00I8
3376 | 3376 | 3376 | 3376 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Wet Sprinkler System Transportation and Custom clearance | 9 | MWSPR | I000 | 00I9 | I000MWSPR00I9
3377 | 3377 | 3377 | 3377 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Inspection & Delivery Mechanical Materials Wet Sprinkler System Receipt at site | 10 | MWSPR | I000 | 0I10 | I000MWSPR0I10
3378 | 3378 | 3378 | 3378 | SA24M005 | Construction & Installation Works |  | 3 | -1 | 0 |  |  | X
3379 | 3379 | 3379 | 3379 | SA24M005 | General Works |  | 4 | -1 | 0 |  |  | X
3380 | 3380 | 3380 | 3380 | SA24M005 | Geotechnical Soil Investigation |  | 5 | -1 | 0 |  |  | X
3381 | 3381 | 3381 | 3381 | SA24M005 | Geo-technical Investigation at Site | C000G0GSI00C1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works General Works Geotechnical Soil Investigation Geo-technical Investigation at Site | 1 | G0GSI | C000 | 00C1 | C000G0GSI00C1
3382 | 3382 | 3382 | 3382 | SA24M005 | Geo-technical Report - Submission | C000G0GSI00C2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works General Works Geotechnical Soil Investigation Geo-technical Report - Submission | 2 | G0GSI | C000 | 00C2 | C000G0GSI00C2
3383 | 3383 | 3383 | 3383 | SA24M005 | Geo-technical Report - Approval | C000G0GSI00C3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works General Works Geotechnical Soil Investigation Geo-technical Report - Approval | 3 | G0GSI | C000 | 00C3 | C000G0GSI00C3
3384 | 3384 | 3384 | 3384 | SA24M005 | Access Road |  | 5 | -1 | 0 |  |  | X
3385 | 3385 | 3385 | 3385 | SA24M005 | Sub grade | C000G00AR00C1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works General Works Access Road Sub grade | 1 | G00AR | C000 | 00C1 | C000G00AR00C1
3386 | 3386 | 3386 | 3386 | SA24M005 | Sub base | C000G00AR00C2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works General Works Access Road Sub base | 2 | G00AR | C000 | 00C2 | C000G00AR00C2
3387 | 3387 | 3387 | 3387 | SA24M005 | Final Layer | C000G00AR00C3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works General Works Access Road Final Layer | 3 | G00AR | C000 | 00C3 | C000G00AR00C3
3388 | 3388 | 3388 | 3388 | SA24M005 | Site Developement |  | 5 | -1 | 0 |  |  | X
3389 | 3389 | 3389 | 3389 | SA24M005 | Topographic Survey - Submission | C000GSDEV00C1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works General Works Site Developement Topographic Survey - Submission | 1 | GSDEV | C000 | 00C1 | C000GSDEV00C1
3390 | 3390 | 3390 | 3390 | SA24M005 | Topographic Survey - Approval | C000GSDEV00C2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works General Works Site Developement Topographic Survey - Approval | 2 | GSDEV | C000 | 00C2 | C000GSDEV00C2
3391 | 3391 | 3391 | 3391 | SA24M005 | Site Leveling & Grading (Excavation/Cutting & Backfilling) | C000GSDEV00C3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works General Works Site Developement Site Leveling & Grading (Excavation/Cutting & Backfilling) | 3 | GSDEV | C000 | 00C3 | C000GSDEV00C3
3392 | 3392 | 3392 | 3392 | SA24M005 | Gravel Spreading | C000GSDEV00C4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works General Works Site Developement Gravel Spreading | 4 | GSDEV | C000 | 00C4 | C000GSDEV00C4
3393 | 3393 | 3393 | 3393 | SA24M005 | Civil Works |  | 4 | -1 | 0 |  |  | X
3394 | 3394 | 3394 | 3394 | SA24M005 | 380 kV GIS Building with Cable Tunnels |  | 5 | -1 | 0 |  |  | X
3395 | 3395 | 3395 | 3395 | SA24M005 | Sub Structure |  | 6 | -1 | 0 |  |  | X
3396 | 3396 | 3396 | 3396 | SA24M005 | Excavation | C000CGISB0SUB00C1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380 kV GIS Building with Cable Tunnels Sub Structure Excavation | 1 | CGISB0SUB | C000 | 00C1 | C000CGISB0SUB00C1
3397 | 3397 | 3397 | 3397 | SA24M005 | Backfilling & Compaction | C000CGISB0SUB00C2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380 kV GIS Building with Cable Tunnels Sub Structure Backfilling & Compaction | 2 | CGISB0SUB | C000 | 00C2 | C000CGISB0SUB00C2
3398 | 3398 | 3398 | 3398 | SA24M005 | Lean concrete works | C000CGISB0SUB00C3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380 kV GIS Building with Cable Tunnels Sub Structure Lean concrete works | 3 | CGISB0SUB | C000 | 00C3 | C000CGISB0SUB00C3
3399 | 3399 | 3399 | 3399 | SA24M005 | Waterproofing - Raft | C000CGISB0SUB00C4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380 kV GIS Building with Cable Tunnels Sub Structure Waterproofing - Raft | 4 | CGISB0SUB | C000 | 00C4 | C000CGISB0SUB00C4
3400 | 3400 | 3400 | 3400 | SA24M005 | Screed | C000CGISB0SUB00C5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380 kV GIS Building with Cable Tunnels Sub Structure Screed | 5 | CGISB0SUB | C000 | 00C5 | C000CGISB0SUB00C5
3401 | 3401 | 3401 | 3401 | SA24M005 | Raft | C000CGISB0SUB00C6 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380 kV GIS Building with Cable Tunnels Sub Structure Raft | 6 | CGISB0SUB | C000 | 00C6 | C000CGISB0SUB00C6
3402 | 3402 | 3402 | 3402 | SA24M005 | Tunnel Wall | C000CGISB0SUB00C7 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380 kV GIS Building with Cable Tunnels Sub Structure Tunnel Wall | 7 | CGISB0SUB | C000 | 00C7 | C000CGISB0SUB00C7
3403 | 3403 | 3403 | 3403 | SA24M005 | Lean concrete works | C000CGISB0SUB00C8 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380 kV GIS Building with Cable Tunnels Sub Structure Lean concrete works | 8 | CGISB0SUB | C000 | 00C8 | C000CGISB0SUB00C8
3404 | 3404 | 3404 | 3404 | SA24M005 | Tunnel Roof Slab ( 2 pour ) | C000CGISB0SUB00C9 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380 kV GIS Building with Cable Tunnels Sub Structure Tunnel Roof Slab ( 2 pour ) | 9 | CGISB0SUB | C000 | 00C9 | C000CGISB0SUB00C9
3405 | 3405 | 3405 | 3405 | SA24M005 | Isolated / Combined footings | C000CGISB0SUB0C10 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380 kV GIS Building with Cable Tunnels Sub Structure Isolated / Combined footings | 10 | CGISB0SUB | C000 | 0C10 | C000CGISB0SUB0C10
3406 | 3406 | 3406 | 3406 | SA24M005 | Columns upto beam bottom | C000CGISB0SUB0C11 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380 kV GIS Building with Cable Tunnels Sub Structure Columns upto beam bottom | 11 | CGISB0SUB | C000 | 0C11 | C000CGISB0SUB0C11
3407 | 3407 | 3407 | 3407 | SA24M005 | Wall waterproofing | C000CGISB0SUB0C12 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380 kV GIS Building with Cable Tunnels Sub Structure Wall waterproofing | 12 | CGISB0SUB | C000 | 0C12 | C000CGISB0SUB0C12
3408 | 3408 | 3408 | 3408 | SA24M005 | Backfilling & compaction outside | C000CGISB0SUB0C13 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380 kV GIS Building with Cable Tunnels Sub Structure Backfilling & compaction outside | 13 | CGISB0SUB | C000 | 0C13 | C000CGISB0SUB0C13
3409 | 3409 | 3409 | 3409 | SA24M005 | Coating works - Column | C000CGISB0SUB0C14 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380 kV GIS Building with Cable Tunnels Sub Structure Coating works - Column | 14 | CGISB0SUB | C000 | 0C14 | C000CGISB0SUB0C14
3410 | 3410 | 3410 | 3410 | SA24M005 | Backfilling upto SOG | C000CGISB0SUB0C15 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380 kV GIS Building with Cable Tunnels Sub Structure Backfilling upto SOG | 15 | CGISB0SUB | C000 | 0C15 | C000CGISB0SUB0C15
3411 | 3411 | 3411 | 3411 | SA24M005 | Beams, Slab with GIS Plate fixing & Grouting | C000CGISB0SUB0C16 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380 kV GIS Building with Cable Tunnels Sub Structure Beams, Slab with GIS Plate fixing & Grouting | 16 | CGISB0SUB | C000 | 0C16 | C000CGISB0SUB0C16
3412 | 3412 | 3412 | 3412 | SA24M005 | Super Structure |  | 6 | -1 | 0 |  |  | X
3413 | 3413 | 3413 | 3413 | SA24M005 | Precast works | C000CGISB0SUP00C1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380 kV GIS Building with Cable Tunnels Super Structure Precast works | 1 | CGISB0SUP | C000 | 00C1 | C000CGISB0SUP00C1
3414 | 3414 | 3414 | 3414 | SA24M005 | H beam installation for EOT | C000CGISB0SUP00C2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380 kV GIS Building with Cable Tunnels Super Structure H beam installation for EOT | 2 | CGISB0SUP | C000 | 00C2 | C000CGISB0SUP00C2
3415 | 3415 | 3415 | 3415 | SA24M005 | Screed works | C000CGISB0SUP00C3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380 kV GIS Building with Cable Tunnels Super Structure Screed works | 3 | CGISB0SUP | C000 | 00C3 | C000CGISB0SUP00C3
3416 | 3416 | 3416 | 3416 | SA24M005 | PACU foundations and other roof structures | C000CGISB0SUP00C4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380 kV GIS Building with Cable Tunnels Super Structure PACU foundations and other roof structures | 4 | CGISB0SUP | C000 | 00C4 | C000CGISB0SUP00C4
3417 | 3417 | 3417 | 3417 | SA24M005 | Roof waterproofing system | C000CGISB0SUP00C5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380 kV GIS Building with Cable Tunnels Super Structure Roof waterproofing system | 5 | CGISB0SUP | C000 | 00C5 | C000CGISB0SUP00C5
3418 | 3418 | 3418 | 3418 | SA24M005 | Finishing Works |  | 6 | -1 | 0 |  |  | X
3419 | 3419 | 3419 | 3419 | SA24M005 | Cable Tunnel |  | 7 | -1 | 0 |  |  | X
3420 | 3420 | 3420 | 3420 | SA24M005 | Ceiling painting | C000CGISB00FW00CT00C1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380 kV GIS Building with Cable Tunnels Finishing Works Cable Tunnel Ceiling painting | 1 | CGISB00FW00CT | C000 | 00C1 | C000CGISB00FW00CT00C1
3421 | 3421 | 3421 | 3421 | SA24M005 | Wall painting | C000CGISB00FW00CT00C2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380 kV GIS Building with Cable Tunnels Finishing Works Cable Tunnel Wall painting | 2 | CGISB00FW00CT | C000 | 00C2 | C000CGISB00FW00CT00C2
3422 | 3422 | 3422 | 3422 | SA24M005 | Floor epoxy | C000CGISB00FW00CT00C3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380 kV GIS Building with Cable Tunnels Finishing Works Cable Tunnel Floor epoxy | 3 | CGISB00FW00CT | C000 | 00C3 | C000CGISB00FW00CT00C3
3423 | 3423 | 3423 | 3423 | SA24M005 | 380kV GIS Building |  | 7 | -1 | 0 |  |  | X
3424 | 3424 | 3424 | 3424 | SA24M005 | EOT Installation | C000CGISB00FW0GIS00C1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380 kV GIS Building with Cable Tunnels Finishing Works 380kV GIS Building EOT Installation | 1 | CGISB00FW0GIS | C000 | 00C1 | C000CGISB00FW0GIS00C1
3425 | 3425 | 3425 | 3425 | SA24M005 | Ceiling painting | C000CGISB00FW0GIS00C2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380 kV GIS Building with Cable Tunnels Finishing Works 380kV GIS Building Ceiling painting | 2 | CGISB00FW0GIS | C000 | 00C2 | C000CGISB00FW0GIS00C2
3426 | 3426 | 3426 | 3426 | SA24M005 | Wall painting | C000CGISB00FW0GIS00C3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380 kV GIS Building with Cable Tunnels Finishing Works 380kV GIS Building Wall painting | 3 | CGISB00FW0GIS | C000 | 00C3 | C000CGISB00FW0GIS00C3
3427 | 3427 | 3427 | 3427 | SA24M005 | Door installation | C000CGISB00FW0GIS00C4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380 kV GIS Building with Cable Tunnels Finishing Works 380kV GIS Building Door installation | 4 | CGISB00FW0GIS | C000 | 00C4 | C000CGISB00FW0GIS00C4
3428 | 3428 | 3428 | 3428 | SA24M005 | Self levelling | C000CGISB00FW0GIS00C5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380 kV GIS Building with Cable Tunnels Finishing Works 380kV GIS Building Self levelling | 5 | CGISB00FW0GIS | C000 | 00C5 | C000CGISB00FW0GIS00C5
3429 | 3429 | 3429 | 3429 | SA24M005 | Equipment access | C000CGISB00FW0GIS00C6 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380 kV GIS Building with Cable Tunnels Finishing Works 380kV GIS Building Equipment access | 6 | CGISB00FW0GIS | C000 | 00C6 | C000CGISB00FW0GIS00C6
3430 | 3430 | 3430 | 3430 | SA24M005 | Installation of Access Ladder of Crane | C000CGISB00FW0GIS00C7 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380 kV GIS Building with Cable Tunnels Finishing Works 380kV GIS Building Installation of Access Ladder of Crane | 7 | CGISB00FW0GIS | C000 | 00C7 | C000CGISB00FW0GIS00C7
3431 | 3431 | 3431 | 3431 | SA24M005 | Staircase finishes | C000CGISB00FW0GIS00C8 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380 kV GIS Building with Cable Tunnels Finishing Works 380kV GIS Building Staircase finishes | 8 | CGISB00FW0GIS | C000 | 00C8 | C000CGISB00FW0GIS00C8
3432 | 3432 | 3432 | 3432 | SA24M005 | Control Room Building |  | 5 | -1 | 0 |  |  | X
3433 | 3433 | 3433 | 3433 | SA24M005 | Sub Structure |  | 6 | -1 | 0 |  |  | X
3434 | 3434 | 3434 | 3434 | SA24M005 | Excavation | C000C0CRB0SUB00C1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Control Room Building Sub Structure Excavation | 1 | C0CRB0SUB | C000 | 00C1 | C000C0CRB0SUB00C1
3435 | 3435 | 3435 | 3435 | SA24M005 | Backfilling & Compaction | C000C0CRB0SUB00C2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Control Room Building Sub Structure Backfilling & Compaction | 2 | C0CRB0SUB | C000 | 00C2 | C000C0CRB0SUB00C2
3436 | 3436 | 3436 | 3436 | SA24M005 | Lean concrete works (For Raft) | C000C0CRB0SUB00C3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Control Room Building Sub Structure Lean concrete works (For Raft) | 3 | C0CRB0SUB | C000 | 00C3 | C000C0CRB0SUB00C3
3437 | 3437 | 3437 | 3437 | SA24M005 | Waterproofing (For Raft) | C000C0CRB0SUB00C4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Control Room Building Sub Structure Waterproofing (For Raft) | 4 | C0CRB0SUB | C000 | 00C4 | C000C0CRB0SUB00C4
3438 | 3438 | 3438 | 3438 | SA24M005 | Screed (For Raft) | C000C0CRB0SUB00C5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Control Room Building Sub Structure Screed (For Raft) | 5 | C0CRB0SUB | C000 | 00C5 | C000C0CRB0SUB00C5
3439 | 3439 | 3439 | 3439 | SA24M005 | Raft | C000C0CRB0SUB00C6 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Control Room Building Sub Structure Raft | 6 | C0CRB0SUB | C000 | 00C6 | C000C0CRB0SUB00C6
3440 | 3440 | 3440 | 3440 | SA24M005 | Column upto beam bottom | C000C0CRB0SUB00C7 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Control Room Building Sub Structure Column upto beam bottom | 7 | C0CRB0SUB | C000 | 00C7 | C000C0CRB0SUB00C7
3441 | 3441 | 3441 | 3441 | SA24M005 | Basement wall | C000C0CRB0SUB00C8 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Control Room Building Sub Structure Basement wall | 8 | C0CRB0SUB | C000 | 00C8 | C000C0CRB0SUB00C8
3442 | 3442 | 3442 | 3442 | SA24M005 | Columns & Beam coating works | C000C0CRB0SUB00C9 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Control Room Building Sub Structure Columns & Beam coating works | 9 | C0CRB0SUB | C000 | 00C9 | C000C0CRB0SUB00C9
3443 | 3443 | 3443 | 3443 | SA24M005 | Lean concrete works (For Isolated Fdn) | C000C0CRB0SUB0C10 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Control Room Building Sub Structure Lean concrete works (For Isolated Fdn) | 10 | C0CRB0SUB | C000 | 0C10 | C000C0CRB0SUB0C10
3444 | 3444 | 3444 | 3444 | SA24M005 | Basement roof Slab | C000C0CRB0SUB0C11 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Control Room Building Sub Structure Basement roof Slab | 11 | C0CRB0SUB | C000 | 0C11 | C000C0CRB0SUB0C11
3445 | 3445 | 3445 | 3445 | SA24M005 | Backfilling & compaction upto SOG | C000C0CRB0SUB0C12 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Control Room Building Sub Structure Backfilling & compaction upto SOG | 12 | C0CRB0SUB | C000 | 0C12 | C000C0CRB0SUB0C12
3446 | 3446 | 3446 | 3446 | SA24M005 | Isolated /Combined footings | C000C0CRB0SUB0C13 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Control Room Building Sub Structure Isolated /Combined footings | 13 | C0CRB0SUB | C000 | 0C13 | C000C0CRB0SUB0C13
3447 | 3447 | 3447 | 3447 | SA24M005 | Slab on grade | C000C0CRB0SUB0C14 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Control Room Building Sub Structure Slab on grade | 14 | C0CRB0SUB | C000 | 0C14 | C000C0CRB0SUB0C14
3448 | 3448 | 3448 | 3448 | SA24M005 | Column upto beam bottom (For Isolated Fdn) | C000C0CRB0SUB0C15 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Control Room Building Sub Structure Column upto beam bottom (For Isolated Fdn) | 15 | C0CRB0SUB | C000 | 0C15 | C000C0CRB0SUB0C15
3449 | 3449 | 3449 | 3449 | SA24M005 | Wall waterproofing | C000C0CRB0SUB0C16 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Control Room Building Sub Structure Wall waterproofing | 16 | C0CRB0SUB | C000 | 0C16 | C000C0CRB0SUB0C16
3450 | 3450 | 3450 | 3450 | SA24M005 | Grade Beam | C000C0CRB0SUB0C17 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Control Room Building Sub Structure Grade Beam | 17 | C0CRB0SUB | C000 | 0C17 | C000C0CRB0SUB0C17
3451 | 3451 | 3451 | 3451 | SA24M005 | Backfilling & Compaction outside | C000C0CRB0SUB0C18 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Control Room Building Sub Structure Backfilling & Compaction outside | 18 | C0CRB0SUB | C000 | 0C18 | C000C0CRB0SUB0C18
3452 | 3452 | 3452 | 3452 | SA24M005 | Super Structure |  | 6 | -1 | 0 |  |  | X
3453 | 3453 | 3453 | 3453 | SA24M005 | Precast works | C000C0CRB0SUP00C1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Control Room Building Super Structure Precast works | 1 | C0CRB0SUP | C000 | 00C1 | C000C0CRB0SUP00C1
3454 | 3454 | 3454 | 3454 | SA24M005 | Roof Screed | C000C0CRB0SUP00C2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Control Room Building Super Structure Roof Screed | 2 | C0CRB0SUP | C000 | 00C2 | C000C0CRB0SUP00C2
3455 | 3455 | 3455 | 3455 | SA24M005 | PACU foundations and other roof structures | C000C0CRB0SUP00C3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Control Room Building Super Structure PACU foundations and other roof structures | 3 | C0CRB0SUP | C000 | 00C3 | C000C0CRB0SUP00C3
3456 | 3456 | 3456 | 3456 | SA24M005 | Roof waterproofing system | C000C0CRB0SUP00C4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Control Room Building Super Structure Roof waterproofing system | 4 | C0CRB0SUP | C000 | 00C4 | C000C0CRB0SUP00C4
3457 | 3457 | 3457 | 3457 | SA24M005 | Finishing Works |  | 6 | -1 | 0 |  |  | X
3458 | 3458 | 3458 | 3458 | SA24M005 | Basement |  | 7 | -1 | 0 |  |  | X
3459 | 3459 | 3459 | 3459 | SA24M005 | Ceiling painting | C000C0CRB00FW000B00C1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Control Room Building Finishing Works Basement Ceiling painting | 1 | C0CRB00FW000B | C000 | 00C1 | C000C0CRB00FW000B00C1
3460 | 3460 | 3460 | 3460 | SA24M005 | Wall painting | C000C0CRB00FW000B00C2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Control Room Building Finishing Works Basement Wall painting | 2 | C0CRB00FW000B | C000 | 00C2 | C000C0CRB00FW000B00C2
3461 | 3461 | 3461 | 3461 | SA24M005 | Floor epoxy | C000C0CRB00FW000B00C3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Control Room Building Finishing Works Basement Floor epoxy | 3 | C0CRB00FW000B | C000 | 00C3 | C000C0CRB00FW000B00C3
3462 | 3462 | 3462 | 3462 | SA24M005 | Ground Floor |  | 7 | -1 | 0 |  |  | X
3463 | 3463 | 3463 | 3463 | SA24M005 | Blockwork | C000C0CRB00FW00GF00C1 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Control Room Building Finishing Works Ground Floor Blockwork | 1 | C0CRB00FW00GF | C000 | 00C1 | C000C0CRB00FW00GF00C1
3464 | 3464 | 3464 | 3464 | SA24M005 | Plastering | C000C0CRB00FW00GF00C2 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Control Room Building Finishing Works Ground Floor Plastering | 2 | C0CRB00FW00GF | C000 | 00C2 | C000C0CRB00FW00GF00C2
3465 | 3465 | 3465 | 3465 | SA24M005 | Ceiling Painting | C000C0CRB00FW00GF00C3 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Control Room Building Finishing Works Ground Floor Ceiling Painting | 3 | C0CRB00FW00GF | C000 | 00C3 | C000C0CRB00FW00GF00C3
3466 | 3466 | 3466 | 3466 | SA24M005 | Wall Painting | C000C0CRB00FW00GF00C4 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Control Room Building Finishing Works Ground Floor Wall Painting | 4 | C0CRB00FW00GF | C000 | 00C4 | C000C0CRB00FW00GF00C4
3467 | 3467 | 3467 | 3467 | SA24M005 | MEP works above false ceiling | C000C0CRB00FW00GF00C5 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Control Room Building Finishing Works Ground Floor MEP works above false ceiling | 5 | C0CRB00FW00GF | C000 | 00C5 | C000C0CRB00FW00GF00C5
3468 | 3468 | 3468 | 3468 | SA24M005 | Door installation | C000C0CRB00FW00GF00C6 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Control Room Building Finishing Works Ground Floor Door installation | 6 | C0CRB00FW00GF | C000 | 00C6 | C000C0CRB00FW00GF00C6
3469 | 3469 | 3469 | 3469 | SA24M005 | Staircase finishes | C000C0CRB00FW00GF00C7 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Control Room Building Finishing Works Ground Floor Staircase finishes | 7 | C0CRB00FW00GF | C000 | 00C7 | C000C0CRB00FW00GF00C7
3470 | 3470 | 3470 | 3470 | SA24M005 | False ceiling | C000C0CRB00FW00GF00C8 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Control Room Building Finishing Works Ground Floor False ceiling | 8 | C0CRB00FW00GF | C000 | 00C8 | C000C0CRB00FW00GF00C8
3471 | 3471 | 3471 | 3471 | SA24M005 | Raised Floor (Communication Room) | C000C0CRB00FW00GF00C9 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Control Room Building Finishing Works Ground Floor Raised Floor (Communication Room) | 9 | C0CRB00FW00GF | C000 | 00C9 | C000C0CRB00FW00GF00C9
3472 | 3472 | 3472 | 3472 | SA24M005 | Self Levelling | C000C0CRB00FW00GF0C10 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Control Room Building Finishing Works Ground Floor Self Levelling | 10 | C0CRB00FW00GF | C000 | 0C10 | C000C0CRB00FW00GF0C10
3473 | 3473 | 3473 | 3473 | SA24M005 | Equipment access | C000C0CRB00FW00GF0C11 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Control Room Building Finishing Works Ground Floor Equipment access | 11 | C0CRB00FW00GF | C000 | 0C11 | C000C0CRB00FW00GF0C11
3474 | 3474 | 3474 | 3474 | SA24M005 | Tiling works Wall & Flooring at Battery room | C000C0CRB00FW00GF0C12 | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Control Room Building Finishing Works Ground Floor Tiling works Wall & Flooring at Battery room | 12 | C0CRB00FW00GF | C000 | 0C12 | C000C0CRB00FW00GF0C12
3475 | 3475 | 3475 | 3475 | SA24M005 | Fire Fighting Pump House |  | 5 | -1 | 0 |  |  | X
3476 | 3476 | 3476 | 3476 | SA24M005 | Sub Structure (U/G Water Tank) |  | 6 | -1 | 0 |  |  | X
3477 | 3477 | 3477 | 3477 | SA24M005 | Excavation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Fire Fighting Pump House Sub Structure (U/G Water Tank) Excavation | 1 | C0F0P | C000 | 00C1 | C000#MWCY00C1
3478 | 3478 | 3478 | 3478 | SA24M005 | Backfilling & Compaction |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Fire Fighting Pump House Sub Structure (U/G Water Tank) Backfilling & Compaction | 2 | C0F0P | C000 | 00C2 | C000#MWCY00C2
3479 | 3479 | 3479 | 3479 | SA24M005 | Lean concrete works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Fire Fighting Pump House Sub Structure (U/G Water Tank) Lean concrete works | 3 | C0F0P | C000 | 00C3 | C000#MWCY00C3
3480 | 3480 | 3480 | 3480 | SA24M005 | Waterproofing - Raft |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Fire Fighting Pump House Sub Structure (U/G Water Tank) Waterproofing - Raft | 4 | C0F0P | C000 | 00C4 | C000#MWCY00C4
3481 | 3481 | 3481 | 3481 | SA24M005 | Screed |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Fire Fighting Pump House Sub Structure (U/G Water Tank) Screed | 5 | C0F0P | C000 | 00C5 | C000#MWCY00C5
3482 | 3482 | 3482 | 3482 | SA24M005 | Raft/Footings/Pedestals |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Fire Fighting Pump House Sub Structure (U/G Water Tank) Raft/Footings/Pedestals | 6 | C0F0P | C000 | 00C6 | C000#MWCY00C6
3483 | 3483 | 3483 | 3483 | SA24M005 | walls & Columns |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Fire Fighting Pump House Sub Structure (U/G Water Tank) walls & Columns | 7 | C0F0P | C000 | 00C7 | C000#MWCY00C7
3484 | 3484 | 3484 | 3484 | SA24M005 | Beams, Slab |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Fire Fighting Pump House Sub Structure (U/G Water Tank) Beams, Slab | 8 | C0F0P | C000 | 00C8 | C000#MWCY00C8
3485 | 3485 | 3485 | 3485 | SA24M005 | Wall waterproofing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Fire Fighting Pump House Sub Structure (U/G Water Tank) Wall waterproofing | 9 | C0F0P | C000 | 00C9 | C000#MWCY00C9
3486 | 3486 | 3486 | 3486 | SA24M005 | Backfilling & compaction outside |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Fire Fighting Pump House Sub Structure (U/G Water Tank) Backfilling & compaction outside | 10 | C0F0P | C000 | 0C10 | C000#MWCY0C10
3487 | 3487 | 3487 | 3487 | SA24M005 | Super Structure (Pump Room) |  | 6 | -1 | 0 |  |  | X | C000#MWCY
3488 | 3488 | 3488 | 3488 | SA24M005 | Precast works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Fire Fighting Pump House Super Structure (Pump Room) Precast works | 1 | C0FPH0SUP | C000 | 00C1 | C000C0FPH0SUP00C1
3489 | 3489 | 3489 | 3489 | SA24M005 | Screed , foundations and other roof structures |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Fire Fighting Pump House Super Structure (Pump Room) Screed , foundations and other roof structures | 2 | C0FPH0SUP | C000 | 00C2 | C000C0FPH0SUP00C2
3490 | 3490 | 3490 | 3490 | SA24M005 | Roof waterproofing system |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Fire Fighting Pump House Super Structure (Pump Room) Roof waterproofing system | 3 | C0FPH0SUP | C000 | 00C3 | C000C0FPH0SUP00C3
3491 | 3491 | 3491 | 3491 | SA24M005 | Finishing Works (U/G Water Tank & Pump Room) |  | 6 | -1 | 0 |  |  | X
3492 | 3492 | 3492 | 3492 | SA24M005 | Ceiling painting |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Fire Fighting Pump House Finishing Works (U/G Water Tank & Pump Room) Ceiling painting | 1 | C0F0P | C000 | 00C1 | C000#fccw00C1
3493 | 3493 | 3493 | 3493 | SA24M005 | Wall painting |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Fire Fighting Pump House Finishing Works (U/G Water Tank & Pump Room) Wall painting | 2 | C0F0P | C000 | 00C2 | C000#fccw00C2
3494 | 3494 | 3494 | 3494 | SA24M005 | Floor epoxy |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Fire Fighting Pump House Finishing Works (U/G Water Tank & Pump Room) Floor epoxy | 3 | C0F0P | C000 | 00C3 | C000#fccw00C3
3495 | 3495 | 3495 | 3495 | SA24M005 | Door installation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Fire Fighting Pump House Finishing Works (U/G Water Tank & Pump Room) Door installation | 4 | C0F0P | C000 | 00C4 | C000#fccw00C4
3496 | 3496 | 3496 | 3496 | SA24M005 | Guard House |  | 5 | -1 | 0 |  |  | X | C000#fccw
3497 | 3497 | 3497 | 3497 | SA24M005 | Sub Structure |  | 6 | -1 | 0 |  |  | X | C000#fccw
3498 | 3498 | 3498 | 3498 | SA24M005 | Excavation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Guard House Sub Structure Excavation | 1 | CGU0SUB | C000 | 00C1 | C000CGU0SUB00C1
3499 | 3499 | 3499 | 3499 | SA24M005 | Backfilling & Compaction |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Guard House Sub Structure Backfilling & Compaction | 2 | CGU0SUB | C000 | 00C2 | C000CGU0SUB00C2
3500 | 3500 | 3500 | 3500 | SA24M005 | Lean concrete works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Guard House Sub Structure Lean concrete works | 3 | CGU0SUB | C000 | 00C3 | C000CGU0SUB00C3
3501 | 3501 | 3501 | 3501 | SA24M005 | Raft/Footings/Pedestals |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Guard House Sub Structure Raft/Footings/Pedestals | 4 | CGU0SUB | C000 | 00C4 | C000CGU0SUB00C4
3502 | 3502 | 3502 | 3502 | SA24M005 | Columns |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Guard House Sub Structure Columns | 5 | CGU0SUB | C000 | 00C5 | C000CGU0SUB00C5
3503 | 3503 | 3503 | 3503 | SA24M005 | Grade Slab |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Guard House Sub Structure Grade Slab | 6 | CGU0SUB | C000 | 00C6 | C000CGU0SUB00C6
3504 | 3504 | 3504 | 3504 | SA24M005 | Coal tar Epoxy |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Guard House Sub Structure Coal tar Epoxy | 7 | CGU0SUB | C000 | 00C7 | C000CGU0SUB00C7
3505 | 3505 | 3505 | 3505 | SA24M005 | Backfilling & compaction outside |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Guard House Sub Structure Backfilling & compaction outside | 8 | CGU0SUB | C000 | 00C8 | C000CGU0SUB00C8
3506 | 3506 | 3506 | 3506 | SA24M005 | Super Structure |  | 6 | -1 | 0 |  |  | X
3507 | 3507 | 3507 | 3507 | SA24M005 | Precast works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Guard House Super Structure Precast works | 1 | CGU0SUP | C000 | 00C1 | C000#wGHj00C1
3508 | 3508 | 3508 | 3508 | SA24M005 | Screed , foundations and other roof structures |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Guard House Super Structure Screed , foundations and other roof structures | 2 | CGU0SUP | C000 | 00C2 | C000#wGHj00C2
3509 | 3509 | 3509 | 3509 | SA24M005 | Roof waterproofing system |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Guard House Super Structure Roof waterproofing system | 3 | CGU0SUP | C000 | 00C3 | C000#wGHj00C3
3510 | 3510 | 3510 | 3510 | SA24M005 | Finishing Works |  | 6 | -1 | 0 |  |  | X | C000#wGHj
3511 | 3511 | 3511 | 3511 | SA24M005 | Ceiling painting |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Guard House Finishing Works Ceiling painting | 1 | CGU00FW00 | C000 | 00C1 | C000CGU00FW0000C1
3512 | 3512 | 3512 | 3512 | SA24M005 | Wall painting |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Guard House Finishing Works Wall painting | 2 | CGU00FW00 | C000 | 00C2 | C000CGU00FW0000C2
3513 | 3513 | 3513 | 3513 | SA24M005 | Door installation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Guard House Finishing Works Door installation | 3 | CGU00FW00 | C000 | 00C3 | C000CGU00FW0000C3
3514 | 3514 | 3514 | 3514 | SA24M005 | Floor epoxy |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Guard House Finishing Works Floor epoxy | 4 | CGU00FW00 | C000 | 00C4 | C000CGU00FW0000C4
3515 | 3515 | 3515 | 3515 | SA24M005 | Guard House Toilet |  | 5 | -1 | 0 |  |  | X
3516 | 3516 | 3516 | 3516 | SA24M005 | Sub Structure |  | 6 | -1 | 0 |  |  | X
3517 | 3517 | 3517 | 3517 | SA24M005 | Excavation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Guard House Toilet Sub Structure Excavation | 1 | CGHT0SUB | C000 | 00C1 | C000CGHT0SUB00C1
3518 | 3518 | 3518 | 3518 | SA24M005 | Backfilling & Compaction |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Guard House Toilet Sub Structure Backfilling & Compaction | 2 | CGHT0SUB | C000 | 00C2 | C000CGHT0SUB00C2
3519 | 3519 | 3519 | 3519 | SA24M005 | Lean concrete works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Guard House Toilet Sub Structure Lean concrete works | 3 | CGHT0SUB | C000 | 00C3 | C000CGHT0SUB00C3
3520 | 3520 | 3520 | 3520 | SA24M005 | Raft/Footings/Pedestals |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Guard House Toilet Sub Structure Raft/Footings/Pedestals | 4 | CGHT0SUB | C000 | 00C4 | C000CGHT0SUB00C4
3521 | 3521 | 3521 | 3521 | SA24M005 | Columns |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Guard House Toilet Sub Structure Columns | 5 | CGHT0SUB | C000 | 00C5 | C000CGHT0SUB00C5
3522 | 3522 | 3522 | 3522 | SA24M005 | Grade Slab |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Guard House Toilet Sub Structure Grade Slab | 6 | CGHT0SUB | C000 | 00C6 | C000CGHT0SUB00C6
3523 | 3523 | 3523 | 3523 | SA24M005 | Coal tar Epoxy |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Guard House Toilet Sub Structure Coal tar Epoxy | 7 | CGHT0SUB | C000 | 00C7 | C000CGHT0SUB00C7
3524 | 3524 | 3524 | 3524 | SA24M005 | Backfilling & compaction outside |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Guard House Toilet Sub Structure Backfilling & compaction outside | 8 | CGHT0SUB | C000 | 00C8 | C000CGHT0SUB00C8
3525 | 3525 | 3525 | 3525 | SA24M005 | Super Structure |  | 6 | -1 | 0 |  |  | X
3526 | 3526 | 3526 | 3526 | SA24M005 | Precast works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Guard House Toilet Super Structure Precast works | 1 | CGU0SUP | C000 | 00C1 | C000#kEJl00C1
3527 | 3527 | 3527 | 3527 | SA24M005 | Screed , foundations and other roof structures |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Guard House Toilet Super Structure Screed , foundations and other roof structures | 2 | CGU0SUP | C000 | 00C2 | C000#kEJl00C2
3528 | 3528 | 3528 | 3528 | SA24M005 | Roof waterproofing system |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Guard House Toilet Super Structure Roof waterproofing system | 3 | CGU0SUP | C000 | 00C3 | C000#kEJl00C3
3529 | 3529 | 3529 | 3529 | SA24M005 | Finishing Works |  | 6 | -1 | 0 |  |  | X | C000#kEJl
3530 | 3530 | 3530 | 3530 | SA24M005 | Falseceiling |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Guard House Toilet Finishing Works Falseceiling | 1 | CG00GT00FW | C000 | 00C1 | C000CG00GT00FW00C1
3531 | 3531 | 3531 | 3531 | SA24M005 | Wall painting |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Guard House Toilet Finishing Works Wall painting | 2 | CG00GT00FW | C000 | 00C2 | C000CG00GT00FW00C2
3532 | 3532 | 3532 | 3532 | SA24M005 | Door installation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Guard House Toilet Finishing Works Door installation | 3 | CG00GT00FW | C000 | 00C3 | C000CG00GT00FW00C3
3533 | 3533 | 3533 | 3533 | SA24M005 | Floor Tiles |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Guard House Toilet Finishing Works Floor Tiles | 4 | CG00GT00FW | C000 | 00C4 | C000CG00GT00FW00C4
3534 | 3534 | 3534 | 3534 | SA24M005 | Security Equipment Building |  | 5 | -1 | 0 |  |  | X
3535 | 3535 | 3535 | 3535 | SA24M005 | Sub Structure |  | 6 | -1 | 0 |  |  | X
3536 | 3536 | 3536 | 3536 | SA24M005 | Excavation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Security Equipment Building Sub Structure Excavation | 1 | C0SEB0SUB | C000 | 00C1 | C000C0SEB0SUB00C1
3537 | 3537 | 3537 | 3537 | SA24M005 | Backfilling & Compaction |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Security Equipment Building Sub Structure Backfilling & Compaction | 2 | C0SEB0SUB | C000 | 00C2 | C000C0SEB0SUB00C2
3538 | 3538 | 3538 | 3538 | SA24M005 | Lean concrete works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Security Equipment Building Sub Structure Lean concrete works | 3 | C0SEB0SUB | C000 | 00C3 | C000C0SEB0SUB00C3
3539 | 3539 | 3539 | 3539 | SA24M005 | Raft/Footings/Pedestals |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Security Equipment Building Sub Structure Raft/Footings/Pedestals | 4 | C0SEB0SUB | C000 | 00C4 | C000C0SEB0SUB00C4
3540 | 3540 | 3540 | 3540 | SA24M005 | Columns |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Security Equipment Building Sub Structure Columns | 5 | C0SEB0SUB | C000 | 00C5 | C000C0SEB0SUB00C5
3541 | 3541 | 3541 | 3541 | SA24M005 | Grade Slab |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Security Equipment Building Sub Structure Grade Slab | 6 | C0SEB0SUB | C000 | 00C6 | C000C0SEB0SUB00C6
3542 | 3542 | 3542 | 3542 | SA24M005 | Coal tar Epoxy |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Security Equipment Building Sub Structure Coal tar Epoxy | 7 | C0SEB0SUB | C000 | 00C7 | C000C0SEB0SUB00C7
3543 | 3543 | 3543 | 3543 | SA24M005 | Backfilling & compaction outside |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Security Equipment Building Sub Structure Backfilling & compaction outside | 8 | C0SEB0SUB | C000 | 00C8 | C000C0SEB0SUB00C8
3544 | 3544 | 3544 | 3544 | SA24M005 | Super Structure |  | 6 | -1 | 0 |  |  | X
3545 | 3545 | 3545 | 3545 | SA24M005 | Precast works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Security Equipment Building Super Structure Precast works | 1 | C0SEB0SUP | C000 | 00C1 | C000C0SEB0SUP00C1
3546 | 3546 | 3546 | 3546 | SA24M005 | Screed , foundations and other roof structures |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Security Equipment Building Super Structure Screed , foundations and other roof structures | 2 | C0SEB0SUP | C000 | 00C2 | C000C0SEB0SUP00C2
3547 | 3547 | 3547 | 3547 | SA24M005 | Roof waterproofing system |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Security Equipment Building Super Structure Roof waterproofing system | 3 | C0SEB0SUP | C000 | 00C3 | C000C0SEB0SUP00C3
3548 | 3548 | 3548 | 3548 | SA24M005 | Finishing Works |  | 6 | -1 | 0 |  |  | X
3549 | 3549 | 3549 | 3549 | SA24M005 | Falseceiling |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Security Equipment Building Finishing Works Falseceiling | 1 | C0SEB00FW | C000 | 00C1 | C000C0SEB00FW00C1
3550 | 3550 | 3550 | 3550 | SA24M005 | Wall painting |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Security Equipment Building Finishing Works Wall painting | 2 | C0SEB00FW | C000 | 00C2 | C000C0SEB00FW00C2
3551 | 3551 | 3551 | 3551 | SA24M005 | Door installation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Security Equipment Building Finishing Works Door installation | 3 | C0SEB00FW | C000 | 00C3 | C000C0SEB00FW00C3
3552 | 3552 | 3552 | 3552 | SA24M005 | Floor Tiles |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Security Equipment Building Finishing Works Floor Tiles | 4 | C0SEB00FW | C000 | 00C4 | C000C0SEB00FW00C4
3553 | 3553 | 3553 | 3553 | SA24M005 | Security Equipment Building Toilet |  | 5 | -1 | 0 |  |  | X
3554 | 3554 | 3554 | 3554 | SA24M005 | Sub Structure |  | 6 | -1 | 0 |  |  | X
3555 | 3555 | 3555 | 3555 | SA24M005 | Excavation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Security Equipment Building Toilet Sub Structure Excavation | 1 | CSEB0SUB | C000 | 00C1 | C000CSEB0SUB00C1
3556 | 3556 | 3556 | 3556 | SA24M005 | Backfilling & Compaction |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Security Equipment Building Toilet Sub Structure Backfilling & Compaction | 2 | CSEB0SUB | C000 | 00C2 | C000CSEB0SUB00C2
3557 | 3557 | 3557 | 3557 | SA24M005 | Lean concrete works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Security Equipment Building Toilet Sub Structure Lean concrete works | 3 | CSEB0SUB | C000 | 00C3 | C000CSEB0SUB00C3
3558 | 3558 | 3558 | 3558 | SA24M005 | Raft/Footings/Pedestals |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Security Equipment Building Toilet Sub Structure Raft/Footings/Pedestals | 4 | CSEB0SUB | C000 | 00C4 | C000CSEB0SUB00C4
3559 | 3559 | 3559 | 3559 | SA24M005 | Columns |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Security Equipment Building Toilet Sub Structure Columns | 5 | CSEB0SUB | C000 | 00C5 | C000CSEB0SUB00C5
3560 | 3560 | 3560 | 3560 | SA24M005 | Grade Slab |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Security Equipment Building Toilet Sub Structure Grade Slab | 6 | CSEB0SUB | C000 | 00C6 | C000CSEB0SUB00C6
3561 | 3561 | 3561 | 3561 | SA24M005 | Coal tar Epoxy |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Security Equipment Building Toilet Sub Structure Coal tar Epoxy | 7 | CSEB0SUB | C000 | 00C7 | C000CSEB0SUB00C7
3562 | 3562 | 3562 | 3562 | SA24M005 | Backfilling & compaction outside |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Security Equipment Building Toilet Sub Structure Backfilling & compaction outside | 8 | CSEB0SUB | C000 | 00C8 | C000CSEB0SUB00C8
3563 | 3563 | 3563 | 3563 | SA24M005 | Super Structure |  | 6 | -1 | 0 |  |  | X
3564 | 3564 | 3564 | 3564 | SA24M005 | Precast works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Security Equipment Building Toilet Super Structure Precast works | 1 | CSEB0SUP | C000 | 00C1 | C000CSEB0SUP00C1
3565 | 3565 | 3565 | 3565 | SA24M005 | Screed , foundations and other roof structures |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Security Equipment Building Toilet Super Structure Screed , foundations and other roof structures | 2 | CSEB0SUP | C000 | 00C2 | C000CSEB0SUP00C2
3566 | 3566 | 3566 | 3566 | SA24M005 | Roof waterproofing system |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Security Equipment Building Toilet Super Structure Roof waterproofing system | 3 | CSEB0SUP | C000 | 00C3 | C000CSEB0SUP00C3
3567 | 3567 | 3567 | 3567 | SA24M005 | Finishing Works |  | 6 | -1 | 0 |  |  | X
3568 | 3568 | 3568 | 3568 | SA24M005 | Ceiling painting |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Security Equipment Building Toilet Finishing Works Ceiling painting | 1 | C0SEB00FW00 | C000 | 00C1 | C000C0SEB00FW0000C1
3569 | 3569 | 3569 | 3569 | SA24M005 | Wall painting |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Security Equipment Building Toilet Finishing Works Wall painting | 2 | C0SEB00FW00 | C000 | 00C2 | C000C0SEB00FW0000C2
3570 | 3570 | 3570 | 3570 | SA24M005 | Door installation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Security Equipment Building Toilet Finishing Works Door installation | 3 | C0SEB00FW00 | C000 | 00C3 | C000C0SEB00FW0000C3
3571 | 3571 | 3571 | 3571 | SA24M005 | Floor epoxy |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Security Equipment Building Toilet Finishing Works Floor epoxy | 4 | C0SEB00FW00 | C000 | 00C4 | C000C0SEB00FW0000C4
3572 | 3572 | 3572 | 3572 | SA24M005 | IPP Building- 1 |  | 5 | -1 | 0 |  |  | X
3573 | 3573 | 3573 | 3573 | SA24M005 | Sub Structure |  | 6 | -1 | 0 |  |  | X
3574 | 3574 | 3574 | 3574 | SA24M005 | Excavation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works IPP Building- 1 Sub Structure Excavation | 1 | C0IPP0SUB | C000 | 00C1 | C000#JSyL00C1
3575 | 3575 | 3575 | 3575 | SA24M005 | Backfilling & Compaction |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works IPP Building- 1 Sub Structure Backfilling & Compaction | 2 | C0IPP0SUB | C000 | 00C2 | C000#JSyL00C2
3576 | 3576 | 3576 | 3576 | SA24M005 | Lean concrete works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works IPP Building- 1 Sub Structure Lean concrete works | 3 | C0IPP0SUB | C000 | 00C3 | C000#JSyL00C3
3577 | 3577 | 3577 | 3577 | SA24M005 | Raft/Footings/Pedestals |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works IPP Building- 1 Sub Structure Raft/Footings/Pedestals | 4 | C0IPP0SUB | C000 | 00C4 | C000#JSyL00C4
3578 | 3578 | 3578 | 3578 | SA24M005 | Columns |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works IPP Building- 1 Sub Structure Columns | 5 | C0IPP0SUB | C000 | 00C5 | C000#JSyL00C5
3579 | 3579 | 3579 | 3579 | SA24M005 | Grade Slab |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works IPP Building- 1 Sub Structure Grade Slab | 6 | C0IPP0SUB | C000 | 00C6 | C000#JSyL00C6
3580 | 3580 | 3580 | 3580 | SA24M005 | Coal tar Epoxy |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works IPP Building- 1 Sub Structure Coal tar Epoxy | 7 | C0IPP0SUB | C000 | 00C7 | C000#JSyL00C7
3581 | 3581 | 3581 | 3581 | SA24M005 | Backfilling & compaction outside |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works IPP Building- 1 Sub Structure Backfilling & compaction outside | 8 | C0IPP0SUB | C000 | 00C8 | C000#JSyL00C8
3582 | 3582 | 3582 | 3582 | SA24M005 | Super Structure |  | 6 | -1 | 0 |  |  | X | C000#JSyL
3583 | 3583 | 3583 | 3583 | SA24M005 | Precast works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works IPP Building- 1 Super Structure Precast works | 1 | C0IPP0SUP | C000 | 00C1 | C000#cfOk00C1
3584 | 3584 | 3584 | 3584 | SA24M005 | Screed , foundations and other roof structures |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works IPP Building- 1 Super Structure Screed , foundations and other roof structures | 2 | C0IPP0SUP | C000 | 00C2 | C000#cfOk00C2
3585 | 3585 | 3585 | 3585 | SA24M005 | Roof waterproofing system |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works IPP Building- 1 Super Structure Roof waterproofing system | 3 | C0IPP0SUP | C000 | 00C3 | C000#cfOk00C3
3586 | 3586 | 3586 | 3586 | SA24M005 | Finishing Works |  | 6 | -1 | 0 |  |  | X | C000#cfOk
3587 | 3587 | 3587 | 3587 | SA24M005 | Ceiling painting |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works IPP Building- 1 Finishing Works Ceiling painting | 1 | C0IPP00FW00 | C000 | 00C1 | C000#gyIR00C1
3588 | 3588 | 3588 | 3588 | SA24M005 | Wall painting |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works IPP Building- 1 Finishing Works Wall painting | 2 | C0IPP00FW00 | C000 | 00C2 | C000#gyIR00C2
3589 | 3589 | 3589 | 3589 | SA24M005 | Door installation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works IPP Building- 1 Finishing Works Door installation | 3 | C0IPP00FW00 | C000 | 00C3 | C000#gyIR00C3
3590 | 3590 | 3590 | 3590 | SA24M005 | Floor epoxy |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works IPP Building- 1 Finishing Works Floor epoxy | 4 | C0IPP00FW00 | C000 | 00C4 | C000#gyIR00C4
3591 | 3591 | 3591 | 3591 | SA24M005 | IPP Building- 2 |  | 5 | -1 | 0 |  |  | X | C000#gyIR
3592 | 3592 | 3592 | 3592 | SA24M005 | Sub Structure |  | 6 | -1 | 0 |  |  | X | C000#gyIR
3593 | 3593 | 3593 | 3593 | SA24M005 | Excavation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works IPP Building- 2 Sub Structure Excavation | 1 | C0IPP0SUB | C000 | 00C1 | C000#cYqE00C1
3594 | 3594 | 3594 | 3594 | SA24M005 | Backfilling & Compaction |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works IPP Building- 2 Sub Structure Backfilling & Compaction | 2 | C0IPP0SUB | C000 | 00C2 | C000#cYqE00C2
3595 | 3595 | 3595 | 3595 | SA24M005 | Lean concrete works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works IPP Building- 2 Sub Structure Lean concrete works | 3 | C0IPP0SUB | C000 | 00C3 | C000#cYqE00C3
3596 | 3596 | 3596 | 3596 | SA24M005 | Raft/Footings/Pedestals |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works IPP Building- 2 Sub Structure Raft/Footings/Pedestals | 4 | C0IPP0SUB | C000 | 00C4 | C000#cYqE00C4
3597 | 3597 | 3597 | 3597 | SA24M005 | Columns |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works IPP Building- 2 Sub Structure Columns | 5 | C0IPP0SUB | C000 | 00C5 | C000#cYqE00C5
3598 | 3598 | 3598 | 3598 | SA24M005 | Grade Slab |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works IPP Building- 2 Sub Structure Grade Slab | 6 | C0IPP0SUB | C000 | 00C6 | C000#cYqE00C6
3599 | 3599 | 3599 | 3599 | SA24M005 | Coal tar Epoxy |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works IPP Building- 2 Sub Structure Coal tar Epoxy | 7 | C0IPP0SUB | C000 | 00C7 | C000#cYqE00C7
3600 | 3600 | 3600 | 3600 | SA24M005 | Backfilling & compaction outside |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works IPP Building- 2 Sub Structure Backfilling & compaction outside | 8 | C0IPP0SUB | C000 | 00C8 | C000#cYqE00C8
3601 | 3601 | 3601 | 3601 | SA24M005 | Super Structure |  | 6 | -1 | 0 |  |  | X | C000#cYqE
3602 | 3602 | 3602 | 3602 | SA24M005 | Precast works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works IPP Building- 2 Super Structure Precast works | 1 | C0IPP0SUP | C000 | 00C1 | C000#akcg00C1
3603 | 3603 | 3603 | 3603 | SA24M005 | Screed , foundations and other roof structures |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works IPP Building- 2 Super Structure Screed , foundations and other roof structures | 2 | C0IPP0SUP | C000 | 00C2 | C000#akcg00C2
3604 | 3604 | 3604 | 3604 | SA24M005 | Roof waterproofing system |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works IPP Building- 2 Super Structure Roof waterproofing system | 3 | C0IPP0SUP | C000 | 00C3 | C000#akcg00C3
3605 | 3605 | 3605 | 3605 | SA24M005 | Finishing Works |  | 6 | -1 | 0 |  |  | X | C000#akcg
3606 | 3606 | 3606 | 3606 | SA24M005 | Ceiling painting |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works IPP Building- 2 Finishing Works Ceiling painting | 1 | C0IPP00FW00 | C000 | 00C1 | C000#kbTo00C1
3607 | 3607 | 3607 | 3607 | SA24M005 | Wall painting |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works IPP Building- 2 Finishing Works Wall painting | 2 | C0IPP00FW00 | C000 | 00C2 | C000#kbTo00C2
3608 | 3608 | 3608 | 3608 | SA24M005 | Door installation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works IPP Building- 2 Finishing Works Door installation | 3 | C0IPP00FW00 | C000 | 00C3 | C000#kbTo00C3
3609 | 3609 | 3609 | 3609 | SA24M005 | Floor epoxy |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works IPP Building- 2 Finishing Works Floor epoxy | 4 | C0IPP00FW00 | C000 | 00C4 | C000#kbTo00C4
3610 | 3610 | 3610 | 3610 | SA24M005 | 380kV Gantry |  | 5 | -1 | 0 |  |  | X | C000#kbTo
3611 | 3611 | 3611 | 3611 | SA24M005 | Foundation- 1 |  | 6 | -1 | 0 |  |  | X | C000#kbTo
3612 | 3612 | 3612 | 3612 | SA24M005 | Pile foundation works ( Auguring ) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 1 Pile foundation works ( Auguring ) | 1 | CGANF | C000 | 00C1 | C000#BszO00C1
3613 | 3613 | 3613 | 3613 | SA24M005 | Pile foundation works ( Rebar & Concrete ) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 1 Pile foundation works ( Rebar & Concrete ) | 2 | CGANF | C000 | 00C2 | C000#BszO00C2
3614 | 3614 | 3614 | 3614 | SA24M005 | Stub intallation & Shuttering |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 1 Stub intallation & Shuttering | 3 | CGANF | C000 | 00C3 | C000#BszO00C3
3615 | 3615 | 3615 | 3615 | SA24M005 | Pile ( Concrete ) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 1 Pile ( Concrete ) | 4 | CGANF | C000 | 00C4 | C000#BszO00C4
3616 | 3616 | 3616 | 3616 | SA24M005 | Coal tar epoxy |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 1 Coal tar epoxy | 5 | CGANF | C000 | 00C5 | C000#BszO00C5
3617 | 3617 | 3617 | 3617 | SA24M005 | PU Coating on exposed surfaces |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 1 PU Coating on exposed surfaces | 6 | CGANF | C000 | 00C6 | C000#BszO00C6
3618 | 3618 | 3618 | 3618 | SA24M005 | Foundation- 2 |  | 6 | -1 | 0 |  |  | X | C000#BszO
3619 | 3619 | 3619 | 3619 | SA24M005 | Pile foundation works ( Auguring ) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 2 Pile foundation works ( Auguring ) | 1 | CGANF | C000 | 00C1 | C000#TMvo00C1
3620 | 3620 | 3620 | 3620 | SA24M005 | Pile foundation works ( Rebar & Concrete ) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 2 Pile foundation works ( Rebar & Concrete ) | 2 | CGANF | C000 | 00C2 | C000#TMvo00C2
3621 | 3621 | 3621 | 3621 | SA24M005 | Stub intallation & Shuttering |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 2 Stub intallation & Shuttering | 3 | CGANF | C000 | 00C3 | C000#TMvo00C3
3622 | 3622 | 3622 | 3622 | SA24M005 | Pile ( Concrete ) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 2 Pile ( Concrete ) | 4 | CGANF | C000 | 00C4 | C000#TMvo00C4
3623 | 3623 | 3623 | 3623 | SA24M005 | Coal tar epoxy |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 2 Coal tar epoxy | 5 | CGANF | C000 | 00C5 | C000#TMvo00C5
3624 | 3624 | 3624 | 3624 | SA24M005 | PU Coating on exposed surfaces |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 2 PU Coating on exposed surfaces | 6 | CGANF | C000 | 00C6 | C000#TMvo00C6
3625 | 3625 | 3625 | 3625 | SA24M005 | Foundation- 3 |  | 6 | -1 | 0 |  |  | X | C000#TMvo
3626 | 3626 | 3626 | 3626 | SA24M005 | Pile foundation works ( Auguring ) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 3 Pile foundation works ( Auguring ) | 1 | CGANF | C000 | 00C1 | C000#mOzu00C1
3627 | 3627 | 3627 | 3627 | SA24M005 | Pile foundation works ( Rebar & Concrete ) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 3 Pile foundation works ( Rebar & Concrete ) | 2 | CGANF | C000 | 00C2 | C000#mOzu00C2
3628 | 3628 | 3628 | 3628 | SA24M005 | Stub intallation & Shuttering |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 3 Stub intallation & Shuttering | 3 | CGANF | C000 | 00C3 | C000#mOzu00C3
3629 | 3629 | 3629 | 3629 | SA24M005 | Pile ( Concrete ) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 3 Pile ( Concrete ) | 4 | CGANF | C000 | 00C4 | C000#mOzu00C4
3630 | 3630 | 3630 | 3630 | SA24M005 | Coal tar epoxy |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 3 Coal tar epoxy | 5 | CGANF | C000 | 00C5 | C000#mOzu00C5
3631 | 3631 | 3631 | 3631 | SA24M005 | PU Coating on exposed surfaces |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 3 PU Coating on exposed surfaces | 6 | CGANF | C000 | 00C6 | C000#mOzu00C6
3632 | 3632 | 3632 | 3632 | SA24M005 | Foundation- 4 |  | 6 | -1 | 0 |  |  | X | C000#mOzu
3633 | 3633 | 3633 | 3633 | SA24M005 | Pile foundation works ( Auguring ) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 4 Pile foundation works ( Auguring ) | 1 | CGANF | C000 | 00C1 | C000#ZJHP00C1
3634 | 3634 | 3634 | 3634 | SA24M005 | Pile foundation works ( Rebar & Concrete ) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 4 Pile foundation works ( Rebar & Concrete ) | 2 | CGANF | C000 | 00C2 | C000#ZJHP00C2
3635 | 3635 | 3635 | 3635 | SA24M005 | Stub intallation & Shuttering |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 4 Stub intallation & Shuttering | 3 | CGANF | C000 | 00C3 | C000#ZJHP00C3
3636 | 3636 | 3636 | 3636 | SA24M005 | Pile ( Concrete ) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 4 Pile ( Concrete ) | 4 | CGANF | C000 | 00C4 | C000#ZJHP00C4
3637 | 3637 | 3637 | 3637 | SA24M005 | Coal tar epoxy |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 4 Coal tar epoxy | 5 | CGANF | C000 | 00C5 | C000#ZJHP00C5
3638 | 3638 | 3638 | 3638 | SA24M005 | PU Coating on exposed surfaces |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 4 PU Coating on exposed surfaces | 6 | CGANF | C000 | 00C6 | C000#ZJHP00C6
3639 | 3639 | 3639 | 3639 | SA24M005 | Foundation- 5 |  | 6 | -1 | 0 |  |  | X | C000#ZJHP
3640 | 3640 | 3640 | 3640 | SA24M005 | Pile foundation works ( Auguring ) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 5 Pile foundation works ( Auguring ) | 1 | CGANF | C000 | 00C1 | C000#MGAB00C1
3641 | 3641 | 3641 | 3641 | SA24M005 | Pile foundation works ( Rebar & Concrete ) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 5 Pile foundation works ( Rebar & Concrete ) | 2 | CGANF | C000 | 00C2 | C000#MGAB00C2
3642 | 3642 | 3642 | 3642 | SA24M005 | Stub intallation & Shuttering |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 5 Stub intallation & Shuttering | 3 | CGANF | C000 | 00C3 | C000#MGAB00C3
3643 | 3643 | 3643 | 3643 | SA24M005 | Pile ( Concrete ) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 5 Pile ( Concrete ) | 4 | CGANF | C000 | 00C4 | C000#MGAB00C4
3644 | 3644 | 3644 | 3644 | SA24M005 | Coal tar epoxy |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 5 Coal tar epoxy | 5 | CGANF | C000 | 00C5 | C000#MGAB00C5
3645 | 3645 | 3645 | 3645 | SA24M005 | PU Coating on exposed surfaces |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 5 PU Coating on exposed surfaces | 6 | CGANF | C000 | 00C6 | C000#MGAB00C6
3646 | 3646 | 3646 | 3646 | SA24M005 | Foundation- 6 |  | 6 | -1 | 0 |  |  | X | C000#MGAB
3647 | 3647 | 3647 | 3647 | SA24M005 | Pile foundation works ( Auguring ) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 6 Pile foundation works ( Auguring ) | 1 | CGANF | C000 | 00C1 | C000#vJou00C1
3648 | 3648 | 3648 | 3648 | SA24M005 | Pile foundation works ( Rebar & Concrete ) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 6 Pile foundation works ( Rebar & Concrete ) | 2 | CGANF | C000 | 00C2 | C000#vJou00C2
3649 | 3649 | 3649 | 3649 | SA24M005 | Stub intallation & Shuttering |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 6 Stub intallation & Shuttering | 3 | CGANF | C000 | 00C3 | C000#vJou00C3
3650 | 3650 | 3650 | 3650 | SA24M005 | Pile ( Concrete ) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 6 Pile ( Concrete ) | 4 | CGANF | C000 | 00C4 | C000#vJou00C4
3651 | 3651 | 3651 | 3651 | SA24M005 | Coal tar epoxy |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 6 Coal tar epoxy | 5 | CGANF | C000 | 00C5 | C000#vJou00C5
3652 | 3652 | 3652 | 3652 | SA24M005 | PU Coating on exposed surfaces |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 6 PU Coating on exposed surfaces | 6 | CGANF | C000 | 00C6 | C000#vJou00C6
3653 | 3653 | 3653 | 3653 | SA24M005 | Foundation- 7 |  | 6 | -1 | 0 |  |  | X | C000#vJou
3654 | 3654 | 3654 | 3654 | SA24M005 | Pile foundation works ( Auguring ) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 7 Pile foundation works ( Auguring ) | 1 | CGANF | C000 | 00C1 | C000#aSkE00C1
3655 | 3655 | 3655 | 3655 | SA24M005 | Pile foundation works ( Rebar & Concrete ) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 7 Pile foundation works ( Rebar & Concrete ) | 2 | CGANF | C000 | 00C2 | C000#aSkE00C2
3656 | 3656 | 3656 | 3656 | SA24M005 | Stub intallation & Shuttering |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 7 Stub intallation & Shuttering | 3 | CGANF | C000 | 00C3 | C000#aSkE00C3
3657 | 3657 | 3657 | 3657 | SA24M005 | Pile ( Concrete ) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 7 Pile ( Concrete ) | 4 | CGANF | C000 | 00C4 | C000#aSkE00C4
3658 | 3658 | 3658 | 3658 | SA24M005 | Coal tar epoxy |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 7 Coal tar epoxy | 5 | CGANF | C000 | 00C5 | C000#aSkE00C5
3659 | 3659 | 3659 | 3659 | SA24M005 | PU Coating on exposed surfaces |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 7 PU Coating on exposed surfaces | 6 | CGANF | C000 | 00C6 | C000#aSkE00C6
3660 | 3660 | 3660 | 3660 | SA24M005 | Foundation- 8 |  | 6 | -1 | 0 |  |  | X | C000#aSkE
3661 | 3661 | 3661 | 3661 | SA24M005 | Pile foundation works ( Auguring ) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 8 Pile foundation works ( Auguring ) | 1 | CGANF | C000 | 00C1 | C000#Kuiu00C1
3662 | 3662 | 3662 | 3662 | SA24M005 | Pile foundation works ( Rebar & Concrete ) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 8 Pile foundation works ( Rebar & Concrete ) | 2 | CGANF | C000 | 00C2 | C000#Kuiu00C2
3663 | 3663 | 3663 | 3663 | SA24M005 | Stub intallation & Shuttering |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 8 Stub intallation & Shuttering | 3 | CGANF | C000 | 00C3 | C000#Kuiu00C3
3664 | 3664 | 3664 | 3664 | SA24M005 | Pile ( Concrete ) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 8 Pile ( Concrete ) | 4 | CGANF | C000 | 00C4 | C000#Kuiu00C4
3665 | 3665 | 3665 | 3665 | SA24M005 | Coal tar epoxy |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 8 Coal tar epoxy | 5 | CGANF | C000 | 00C5 | C000#Kuiu00C5
3666 | 3666 | 3666 | 3666 | SA24M005 | PU Coating on exposed surfaces |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 8 PU Coating on exposed surfaces | 6 | CGANF | C000 | 00C6 | C000#Kuiu00C6
3667 | 3667 | 3667 | 3667 | SA24M005 | Foundation- 9 |  | 6 | -1 | 0 |  |  | X | C000#Kuiu
3668 | 3668 | 3668 | 3668 | SA24M005 | Pile foundation works ( Auguring ) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 9 Pile foundation works ( Auguring ) | 1 | CGANF | C000 | 00C1 | C000#WVmi00C1
3669 | 3669 | 3669 | 3669 | SA24M005 | Pile foundation works ( Rebar & Concrete ) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 9 Pile foundation works ( Rebar & Concrete ) | 2 | CGANF | C000 | 00C2 | C000#WVmi00C2
3670 | 3670 | 3670 | 3670 | SA24M005 | Stub intallation & Shuttering |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 9 Stub intallation & Shuttering | 3 | CGANF | C000 | 00C3 | C000#WVmi00C3
3671 | 3671 | 3671 | 3671 | SA24M005 | Pile ( Concrete ) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 9 Pile ( Concrete ) | 4 | CGANF | C000 | 00C4 | C000#WVmi00C4
3672 | 3672 | 3672 | 3672 | SA24M005 | Coal tar epoxy |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 9 Coal tar epoxy | 5 | CGANF | C000 | 00C5 | C000#WVmi00C5
3673 | 3673 | 3673 | 3673 | SA24M005 | PU Coating on exposed surfaces |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 9 PU Coating on exposed surfaces | 6 | CGANF | C000 | 00C6 | C000#WVmi00C6
3674 | 3674 | 3674 | 3674 | SA24M005 | Foundation- 10 |  | 6 | -1 | 0 |  |  | X | C000#WVmi
3675 | 3675 | 3675 | 3675 | SA24M005 | Pile foundation works ( Auguring ) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 10 Pile foundation works ( Auguring ) | 1 | CGANF | C000 | 00C1 | C000#otxU00C1
3676 | 3676 | 3676 | 3676 | SA24M005 | Pile foundation works ( Rebar & Concrete ) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 10 Pile foundation works ( Rebar & Concrete ) | 2 | CGANF | C000 | 00C2 | C000#otxU00C2
3677 | 3677 | 3677 | 3677 | SA24M005 | Stub intallation & Shuttering |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 10 Stub intallation & Shuttering | 3 | CGANF | C000 | 00C3 | C000#otxU00C3
3678 | 3678 | 3678 | 3678 | SA24M005 | Pile ( Concrete ) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 10 Pile ( Concrete ) | 4 | CGANF | C000 | 00C4 | C000#otxU00C4
3679 | 3679 | 3679 | 3679 | SA24M005 | Coal tar epoxy |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 10 Coal tar epoxy | 5 | CGANF | C000 | 00C5 | C000#otxU00C5
3680 | 3680 | 3680 | 3680 | SA24M005 | PU Coating on exposed surfaces |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 10 PU Coating on exposed surfaces | 6 | CGANF | C000 | 00C6 | C000#otxU00C6
3681 | 3681 | 3681 | 3681 | SA24M005 | Foundation- 11 |  | 6 | -1 | 0 |  |  | X | C000#otxU
3682 | 3682 | 3682 | 3682 | SA24M005 | Pile foundation works ( Auguring ) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 11 Pile foundation works ( Auguring ) | 1 | CGANF | C000 | 00C1 | C000#WsAG00C1
3683 | 3683 | 3683 | 3683 | SA24M005 | Pile foundation works ( Rebar & Concrete ) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 11 Pile foundation works ( Rebar & Concrete ) | 2 | CGANF | C000 | 00C2 | C000#WsAG00C2
3684 | 3684 | 3684 | 3684 | SA24M005 | Stub intallation & Shuttering |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 11 Stub intallation & Shuttering | 3 | CGANF | C000 | 00C3 | C000#WsAG00C3
3685 | 3685 | 3685 | 3685 | SA24M005 | Pile ( Concrete ) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 11 Pile ( Concrete ) | 4 | CGANF | C000 | 00C4 | C000#WsAG00C4
3686 | 3686 | 3686 | 3686 | SA24M005 | Coal tar epoxy |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 11 Coal tar epoxy | 5 | CGANF | C000 | 00C5 | C000#WsAG00C5
3687 | 3687 | 3687 | 3687 | SA24M005 | PU Coating on exposed surfaces |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Gantry Foundation- 11 PU Coating on exposed surfaces | 6 | CGANF | C000 | 00C6 | C000#WsAG00C6
3688 | 3688 | 3688 | 3688 | SA24M005 | Outdoor structures Foundations |  | 5 | -1 | 0 |  |  | X | C000#WsAG
3689 | 3689 | 3689 | 3689 | SA24M005 | CT, SA, SF6 |  | 6 | -1 | 0 |  |  | X | C000#WsAG
3690 | 3690 | 3690 | 3690 | SA24M005 | Excavation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Outdoor structures Foundations CT, SA, SF6 Excavation | 1 | CT0SA0SF6 | C000 | 00C1 | C000CT0SA0SF600C1
3691 | 3691 | 3691 | 3691 | SA24M005 | Compaction |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Outdoor structures Foundations CT, SA, SF6 Compaction | 2 | CT0SA0SF6 | C000 | 00C2 | C000CT0SA0SF600C2
3692 | 3692 | 3692 | 3692 | SA24M005 | Lean Concrete under Foundation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Outdoor structures Foundations CT, SA, SF6 Lean Concrete under Foundation | 3 | CT0SA0SF6 | C000 | 00C3 | C000CT0SA0SF600C3
3693 | 3693 | 3693 | 3693 | SA24M005 | RC for Raft |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Outdoor structures Foundations CT, SA, SF6 RC for Raft | 4 | CT0SA0SF6 | C000 | 00C4 | C000CT0SA0SF600C4
3694 | 3694 | 3694 | 3694 | SA24M005 | RC for Pedestal |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Outdoor structures Foundations CT, SA, SF6 RC for Pedestal | 5 | CT0SA0SF6 | C000 | 00C5 | C000CT0SA0SF600C5
3695 | 3695 | 3695 | 3695 | SA24M005 | Coal tar epoxy |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Outdoor structures Foundations CT, SA, SF6 Coal tar epoxy | 6 | CT0SA0SF6 | C000 | 00C6 | C000CT0SA0SF600C6
3696 | 3696 | 3696 | 3696 | SA24M005 | Backfilling |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Outdoor structures Foundations CT, SA, SF6 Backfilling | 7 | CT0SA0SF6 | C000 | 00C7 | C000CT0SA0SF600C7
3697 | 3697 | 3697 | 3697 | SA24M005 | Lightning mast foundation, Light Poles |  | 6 | -1 | 0 |  |  | X
3698 | 3698 | 3698 | 3698 | SA24M005 | Excavation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Outdoor structures Foundations Lightning mast foundation, Light Poles Excavation | 1 | 0LGMA | C000 | 00C1 | C0000LGMA00C1
3699 | 3699 | 3699 | 3699 | SA24M005 | Compaction |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Outdoor structures Foundations Lightning mast foundation, Light Poles Compaction | 2 | 0LGMA | C000 | 00C2 | C0000LGMA00C2
3700 | 3700 | 3700 | 3700 | SA24M005 | Lean Concrete under Foundation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Outdoor structures Foundations Lightning mast foundation, Light Poles Lean Concrete under Foundation | 3 | 0LGMA | C000 | 00C3 | C0000LGMA00C3
3701 | 3701 | 3701 | 3701 | SA24M005 | RC for Raft |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Outdoor structures Foundations Lightning mast foundation, Light Poles RC for Raft | 4 | 0LGMA | C000 | 00C4 | C0000LGMA00C4
3702 | 3702 | 3702 | 3702 | SA24M005 | RC for Pedestal |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Outdoor structures Foundations Lightning mast foundation, Light Poles RC for Pedestal | 5 | 0LGMA | C000 | 00C5 | C0000LGMA00C5
3703 | 3703 | 3703 | 3703 | SA24M005 | Coal tar epoxy |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Outdoor structures Foundations Lightning mast foundation, Light Poles Coal tar epoxy | 6 | 0LGMA | C000 | 00C6 | C0000LGMA00C6
3704 | 3704 | 3704 | 3704 | SA24M005 | Backfilling |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Outdoor structures Foundations Lightning mast foundation, Light Poles Backfilling | 7 | 0LGMA | C000 | 00C7 | C0000LGMA00C7
3705 | 3705 | 3705 | 3705 | SA24M005 | Fire Walls |  | 5 | -1 | 0 |  |  | X
3706 | 3706 | 3706 | 3706 | SA24M005 | Excavation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Fire Walls Excavation | 1 | C0FW | C000 | 00C1 | C000C0FW00C1
3707 | 3707 | 3707 | 3707 | SA24M005 | Backfilling & Compaction |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Fire Walls Backfilling & Compaction | 2 | C0FW | C000 | 00C2 | C000C0FW00C2
3708 | 3708 | 3708 | 3708 | SA24M005 | Lean Concrete under Raft Foundation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Fire Walls Lean Concrete under Raft Foundation | 3 | C0FW | C000 | 00C3 | C000C0FW00C3
3709 | 3709 | 3709 | 3709 | SA24M005 | R.C for Raft Foundation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Fire Walls R.C for Raft Foundation | 4 | C0FW | C000 | 00C4 | C000C0FW00C4
3710 | 3710 | 3710 | 3710 | SA24M005 | R.C for Pedestal / Wall Foundation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Fire Walls R.C for Pedestal / Wall Foundation | 5 | C0FW | C000 | 00C5 | C000C0FW00C5
3711 | 3711 | 3711 | 3711 | SA24M005 | Backfilling Compaction up to Design Level |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Fire Walls Backfilling Compaction up to Design Level | 6 | C0FW | C000 | 00C6 | C000C0FW00C6
3712 | 3712 | 3712 | 3712 | SA24M005 | R.C for All Height of Walls with Form Work (Precast) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Fire Walls R.C for All Height of Walls with Form Work (Precast) | 7 | C0FW | C000 | 00C7 | C000C0FW00C7
3713 | 3713 | 3713 | 3713 | SA24M005 | Texture Painting |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Fire Walls Texture Painting | 8 | C0FW | C000 | 00C8 | C000C0FW00C8
3714 | 3714 | 3714 | 3714 | SA24M005 | Septic tank & Seepage Pits (CRB & SEB) |  | 5 | -1 | 0 |  |  | X
3715 | 3715 | 3715 | 3715 | SA24M005 | Excavation works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Septic tank & Seepage Pits (CRB & SEB) Excavation works | 1 | CRB&SEB | C000 | 00C1 | C000CRB&SEB00C1
3716 | 3716 | 3716 | 3716 | SA24M005 | Backfilling & Compaction |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Septic tank & Seepage Pits (CRB & SEB) Backfilling & Compaction | 2 | CRB&SEB | C000 | 00C2 | C000CRB&SEB00C2
3717 | 3717 | 3717 | 3717 | SA24M005 | Lean Concrete under Raft Foundation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Septic tank & Seepage Pits (CRB & SEB) Lean Concrete under Raft Foundation | 3 | CRB&SEB | C000 | 00C3 | C000CRB&SEB00C3
3718 | 3718 | 3718 | 3718 | SA24M005 | Horizontal Waterproofing for Raft Foundation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Septic tank & Seepage Pits (CRB & SEB) Horizontal Waterproofing for Raft Foundation | 4 | CRB&SEB | C000 | 00C4 | C000CRB&SEB00C4
3719 | 3719 | 3719 | 3719 | SA24M005 | Screed Layer Over Waterproofing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Septic tank & Seepage Pits (CRB & SEB) Screed Layer Over Waterproofing | 5 | CRB&SEB | C000 | 00C5 | C000CRB&SEB00C5
3720 | 3720 | 3720 | 3720 | SA24M005 | Raft foundation works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Septic tank & Seepage Pits (CRB & SEB) Raft foundation works | 6 | CRB&SEB | C000 | 00C6 | C000CRB&SEB00C6
3721 | 3721 | 3721 | 3721 | SA24M005 | Wall concreting works ( Incl Rebar, Shuttering & Concrete ) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Septic tank & Seepage Pits (CRB & SEB) Wall concreting works ( Incl Rebar, Shuttering & Concrete ) | 7 | CRB&SEB | C000 | 00C7 | C000CRB&SEB00C7
3722 | 3722 | 3722 | 3722 | SA24M005 | Slab works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Septic tank & Seepage Pits (CRB & SEB) Slab works | 8 | CRB&SEB | C000 | 00C8 | C000CRB&SEB00C8
3723 | 3723 | 3723 | 3723 | SA24M005 | Vertical Waterproofing & Protection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Septic tank & Seepage Pits (CRB & SEB) Vertical Waterproofing & Protection | 9 | CRB&SEB | C000 | 00C9 | C000CRB&SEB00C9
3724 | 3724 | 3724 | 3724 | SA24M005 | Back filling & Compaction works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Septic tank & Seepage Pits (CRB & SEB) Back filling & Compaction works | 10 | CRB&SEB | C000 | 0C10 | C000CRB&SEB0C10
3725 | 3725 | 3725 | 3725 | SA24M005 | Manual entry cover slab installation works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Septic tank & Seepage Pits (CRB & SEB) Manual entry cover slab installation works | 11 | CRB&SEB | C000 | 0C11 | C000CRB&SEB0C11
3726 | 3726 | 3726 | 3726 | SA24M005 | GIB Foundations |  | 5 | -1 | 0 |  |  | X
3727 | 3727 | 3727 | 3727 | SA24M005 | Excavation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works GIB Foundations Excavation | 1 | CG0FW | C000 | 00C1 | C000CG0FW00C1
3728 | 3728 | 3728 | 3728 | SA24M005 | Compaction |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works GIB Foundations Compaction | 2 | CG0FW | C000 | 00C2 | C000CG0FW00C2
3729 | 3729 | 3729 | 3729 | SA24M005 | Lean Concrete under Foundation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works GIB Foundations Lean Concrete under Foundation | 3 | CG0FW | C000 | 00C3 | C000CG0FW00C3
3730 | 3730 | 3730 | 3730 | SA24M005 | RC for Raft |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works GIB Foundations RC for Raft | 4 | CG0FW | C000 | 00C4 | C000CG0FW00C4
3731 | 3731 | 3731 | 3731 | SA24M005 | RC for Pedestal |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works GIB Foundations RC for Pedestal | 5 | CG0FW | C000 | 00C5 | C000CG0FW00C5
3732 | 3732 | 3732 | 3732 | SA24M005 | Coal tar epoxy |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works GIB Foundations Coal tar epoxy | 6 | CG0FW | C000 | 00C6 | C000CG0FW00C6
3733 | 3733 | 3733 | 3733 | SA24M005 | Backfilling |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works GIB Foundations Backfilling | 7 | CG0FW | C000 | 00C7 | C000CG0FW00C7
3734 | 3734 | 3734 | 3734 | SA24M005 | 380kV Hybrid GIS |  | 5 | -1 | 0 |  |  | X
3735 | 3735 | 3735 | 3735 | SA24M005 | Excavation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Hybrid GIS Excavation | 1 | CGISB | C000 | 00C1 | C000CGISB00C1
3736 | 3736 | 3736 | 3736 | SA24M005 | Compaction |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Hybrid GIS Compaction | 2 | CGISB | C000 | 00C2 | C000CGISB00C2
3737 | 3737 | 3737 | 3737 | SA24M005 | Lean Concrete under Raft Foundation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Hybrid GIS Lean Concrete under Raft Foundation | 3 | CGISB | C000 | 00C3 | C000CGISB00C3
3738 | 3738 | 3738 | 3738 | SA24M005 | R.C for Raft Foundation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Hybrid GIS R.C for Raft Foundation | 4 | CGISB | C000 | 00C4 | C000CGISB00C4
3739 | 3739 | 3739 | 3739 | SA24M005 | Cementious Coating & Painting |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Hybrid GIS Cementious Coating & Painting | 5 | CGISB | C000 | 00C5 | C000CGISB00C5
3740 | 3740 | 3740 | 3740 | SA24M005 | Backfilling Compaction up to Design Level |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Hybrid GIS Backfilling Compaction up to Design Level | 6 | CGISB | C000 | 00C6 | C000CGISB00C6
3741 | 3741 | 3741 | 3741 | SA24M005 | Readness for Installation of reactor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 380kV Hybrid GIS Readness for Installation of reactor | 7 | CGISB | C000 | 00C7 | C000CGISB00C7
3742 | 3742 | 3742 | 3742 | SA24M005 | Service Station Transformers |  | 5 | -1 | 0 |  |  | X
3743 | 3743 | 3743 | 3743 | SA24M005 | Excavation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Service Station Transformers Excavation | 1 | CSSTR | C000 | 00C1 | C000CSSTR00C1
3744 | 3744 | 3744 | 3744 | SA24M005 | Compaction |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Service Station Transformers Compaction | 2 | CSSTR | C000 | 00C2 | C000CSSTR00C2
3745 | 3745 | 3745 | 3745 | SA24M005 | Lean Concrete under Raft Foundation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Service Station Transformers Lean Concrete under Raft Foundation | 3 | CSSTR | C000 | 00C3 | C000CSSTR00C3
3746 | 3746 | 3746 | 3746 | SA24M005 | Horizontal Waterproofing for Raft Foundation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Service Station Transformers Horizontal Waterproofing for Raft Foundation | 4 | CSSTR | C000 | 00C4 | C000CSSTR00C4
3747 | 3747 | 3747 | 3747 | SA24M005 | Screed Layer Over Waterproofing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Service Station Transformers Screed Layer Over Waterproofing | 5 | CSSTR | C000 | 00C5 | C000CSSTR00C5
3748 | 3748 | 3748 | 3748 | SA24M005 | R.C for Raft Foundation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Service Station Transformers R.C for Raft Foundation | 6 | CSSTR | C000 | 00C6 | C000CSSTR00C6
3749 | 3749 | 3749 | 3749 | SA24M005 | R.C for Pedestal & Catch Basin Walls |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Service Station Transformers R.C for Pedestal & Catch Basin Walls | 7 | CSSTR | C000 | 00C7 | C000CSSTR00C7
3750 | 3750 | 3750 | 3750 | SA24M005 | Vertical Waterproofing & Protection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Service Station Transformers Vertical Waterproofing & Protection | 8 | CSSTR | C000 | 00C8 | C000CSSTR00C8
3751 | 3751 | 3751 | 3751 | SA24M005 | Cementious Coating & Painting |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Service Station Transformers Cementious Coating & Painting | 9 | CSSTR | C000 | 00C9 | C000CSSTR00C9
3752 | 3752 | 3752 | 3752 | SA24M005 | Backfilling Compaction up to Design Level |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Service Station Transformers Backfilling Compaction up to Design Level | 10 | CSSTR | C000 | 0C10 | C000CSSTR0C10
3753 | 3753 | 3753 | 3753 | SA24M005 | Installation of H-Beams and Gratings |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Service Station Transformers Installation of H-Beams and Gratings | 11 | CSSTR | C000 | 0C11 | C000CSSTR0C11
3754 | 3754 | 3754 | 3754 | SA24M005 | Readness for Installation Main Equipment of Transformer |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Service Station Transformers Readness for Installation Main Equipment of Transformer | 12 | CSSTR | C000 | 0C12 | C000CSSTR0C12
3755 | 3755 | 3755 | 3755 | SA24M005 | Gravel filling above grating |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Service Station Transformers Gravel filling above grating | 13 | CSSTR | C000 | 0C13 | C000CSSTR0C13
3756 | 3756 | 3756 | 3756 | SA24M005 | Crash Barier |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Service Station Transformers Crash Barier | 14 | CSSTR | C000 | 0C14 | C000CSSTR0C14
3757 | 3757 | 3757 | 3757 | SA24M005 | 150MVAR Line Shunt Reactor Foundation |  | 5 | -1 | 0 |  |  | X
3758 | 3758 | 3758 | 3758 | SA24M005 | Excavation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 150MVAR Line Shunt Reactor Foundation Excavation | 1 | CLSR | C000 | 00C1 | C000CLSR00C1
3759 | 3759 | 3759 | 3759 | SA24M005 | Compaction |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 150MVAR Line Shunt Reactor Foundation Compaction | 2 | CLSR | C000 | 00C2 | C000CLSR00C2
3760 | 3760 | 3760 | 3760 | SA24M005 | Lean Concrete under Raft Foundation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 150MVAR Line Shunt Reactor Foundation Lean Concrete under Raft Foundation | 3 | CLSR | C000 | 00C3 | C000CLSR00C3
3761 | 3761 | 3761 | 3761 | SA24M005 | Horizontal Waterproofing for Raft Foundation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 150MVAR Line Shunt Reactor Foundation Horizontal Waterproofing for Raft Foundation | 4 | CLSR | C000 | 00C4 | C000CLSR00C4
3762 | 3762 | 3762 | 3762 | SA24M005 | Screed Layer Over Waterproofing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 150MVAR Line Shunt Reactor Foundation Screed Layer Over Waterproofing | 5 | CLSR | C000 | 00C5 | C000CLSR00C5
3763 | 3763 | 3763 | 3763 | SA24M005 | R.C for Raft Foundation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 150MVAR Line Shunt Reactor Foundation R.C for Raft Foundation | 6 | CLSR | C000 | 00C6 | C000CLSR00C6
3764 | 3764 | 3764 | 3764 | SA24M005 | R.C for Pedestal & Catch Basin Walls |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 150MVAR Line Shunt Reactor Foundation R.C for Pedestal & Catch Basin Walls | 7 | CLSR | C000 | 00C7 | C000CLSR00C7
3765 | 3765 | 3765 | 3765 | SA24M005 | Installation of Rail Tracks |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 150MVAR Line Shunt Reactor Foundation Installation of Rail Tracks | 8 | CLSR | C000 | 00C8 | C000CLSR00C8
3766 | 3766 | 3766 | 3766 | SA24M005 | Vertical Waterproofing & Protection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 150MVAR Line Shunt Reactor Foundation Vertical Waterproofing & Protection | 9 | CLSR | C000 | 00C9 | C000CLSR00C9
3767 | 3767 | 3767 | 3767 | SA24M005 | Cementious Coating & Painting |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 150MVAR Line Shunt Reactor Foundation Cementious Coating & Painting | 10 | CLSR | C000 | 0C10 | C000CLSR0C10
3768 | 3768 | 3768 | 3768 | SA24M005 | Installation of H-Beams and Gratings |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 150MVAR Line Shunt Reactor Foundation Installation of H-Beams and Gratings | 11 | CLSR | C000 | 0C11 | C000CLSR0C11
3769 | 3769 | 3769 | 3769 | SA24M005 | Backfilling Compaction up to Design Level |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 150MVAR Line Shunt Reactor Foundation Backfilling Compaction up to Design Level | 12 | CLSR | C000 | 0C12 | C000CLSR0C12
3770 | 3770 | 3770 | 3770 | SA24M005 | Readyness for Installation of Transformer |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 150MVAR Line Shunt Reactor Foundation Readyness for Installation of Transformer | 13 | CLSR | C000 | 0C13 | C000CLSR0C13
3771 | 3771 | 3771 | 3771 | SA24M005 | Gravel filling above grating |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 150MVAR Line Shunt Reactor Foundation Gravel filling above grating | 14 | CLSR | C000 | 0C14 | C000CLSR0C14
3772 | 3772 | 3772 | 3772 | SA24M005 | Crash Barier |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 150MVAR Line Shunt Reactor Foundation Crash Barier | 15 | CLSR | C000 | 0C15 | C000CLSR0C15
3773 | 3773 | 3773 | 3773 | SA24M005 | 120MVAR Bus Shunt Reactor Foundation |  | 5 | -1 | 0 |  |  | X
3774 | 3774 | 3774 | 3774 | SA24M005 | Excavation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 120MVAR Bus Shunt Reactor Foundation Excavation | 1 | 00BSR | C000 | 00C1 | C00000BSR00C1
3775 | 3775 | 3775 | 3775 | SA24M005 | Compaction |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 120MVAR Bus Shunt Reactor Foundation Compaction | 2 | 00BSR | C000 | 00C2 | C00000BSR00C2
3776 | 3776 | 3776 | 3776 | SA24M005 | Lean Concrete under Raft Foundation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 120MVAR Bus Shunt Reactor Foundation Lean Concrete under Raft Foundation | 3 | 00BSR | C000 | 00C3 | C00000BSR00C3
3777 | 3777 | 3777 | 3777 | SA24M005 | Horizontal Waterproofing for Raft Foundation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 120MVAR Bus Shunt Reactor Foundation Horizontal Waterproofing for Raft Foundation | 4 | 00BSR | C000 | 00C4 | C00000BSR00C4
3778 | 3778 | 3778 | 3778 | SA24M005 | Screed Layer Over Waterproofing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 120MVAR Bus Shunt Reactor Foundation Screed Layer Over Waterproofing | 5 | 00BSR | C000 | 00C5 | C00000BSR00C5
3779 | 3779 | 3779 | 3779 | SA24M005 | R.C for Raft Foundation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 120MVAR Bus Shunt Reactor Foundation R.C for Raft Foundation | 6 | 00BSR | C000 | 00C6 | C00000BSR00C6
3780 | 3780 | 3780 | 3780 | SA24M005 | R.C for Pedestal & Catch Basin Walls |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 120MVAR Bus Shunt Reactor Foundation R.C for Pedestal & Catch Basin Walls | 7 | 00BSR | C000 | 00C7 | C00000BSR00C7
3781 | 3781 | 3781 | 3781 | SA24M005 | Vertical Waterproofing & Protection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 120MVAR Bus Shunt Reactor Foundation Vertical Waterproofing & Protection | 8 | 00BSR | C000 | 00C8 | C00000BSR00C8
3782 | 3782 | 3782 | 3782 | SA24M005 | Installation of Rail Tracks |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 120MVAR Bus Shunt Reactor Foundation Installation of Rail Tracks | 9 | 00BSR | C000 | 00C9 | C00000BSR00C9
3783 | 3783 | 3783 | 3783 | SA24M005 | Cementious Coating & Painting |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 120MVAR Bus Shunt Reactor Foundation Cementious Coating & Painting | 10 | 00BSR | C000 | 0C10 | C00000BSR0C10
3784 | 3784 | 3784 | 3784 | SA24M005 | Installation of H-Beams and Gratings |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 120MVAR Bus Shunt Reactor Foundation Installation of H-Beams and Gratings | 11 | 00BSR | C000 | 0C11 | C00000BSR0C11
3785 | 3785 | 3785 | 3785 | SA24M005 | Readyness for Installation of Transformer |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 120MVAR Bus Shunt Reactor Foundation Readyness for Installation of Transformer | 12 | 00BSR | C000 | 0C12 | C00000BSR0C12
3786 | 3786 | 3786 | 3786 | SA24M005 | Gravel filling above grating |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 120MVAR Bus Shunt Reactor Foundation Gravel filling above grating | 13 | 00BSR | C000 | 0C13 | C00000BSR0C13
3787 | 3787 | 3787 | 3787 | SA24M005 | Backfilling Compaction up to Design Level |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 120MVAR Bus Shunt Reactor Foundation Backfilling Compaction up to Design Level | 14 | 00BSR | C000 | 0C14 | C00000BSR0C14
3788 | 3788 | 3788 | 3788 | SA24M005 | Crash Barier |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works 120MVAR Bus Shunt Reactor Foundation Crash Barier | 15 | 00BSR | C000 | 0C15 | C00000BSR0C15
3789 | 3789 | 3789 | 3789 | SA24M005 | Tunnel & Duct Bank |  | 5 | -1 | 0 |  |  | X
3790 | 3790 | 3790 | 3790 | SA24M005 | Control Cable tunnel from Control building to 380kV GIS building |  | 6 | -1 | 0 |  |  | X
3791 | 3791 | 3791 | 3791 | SA24M005 | Excavation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Tunnel & Duct Bank Control Cable tunnel from Control building to 380kV GIS building Excavation | 1 | CTDB00CG | C000 | 00C1 | C000#OBSv00C1
3792 | 3792 | 3792 | 3792 | SA24M005 | Backfilling & Compaction |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Tunnel & Duct Bank Control Cable tunnel from Control building to 380kV GIS building Backfilling & Compaction | 2 | CTDB00CG | C000 | 00C2 | C000#OBSv00C2
3793 | 3793 | 3793 | 3793 | SA24M005 | Lean Concrete under Raft Foundation of Tunnel |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Tunnel & Duct Bank Control Cable tunnel from Control building to 380kV GIS building Lean Concrete under Raft Foundation of Tunnel | 3 | CTDB00CG | C000 | 00C3 | C000#OBSv00C3
3794 | 3794 | 3794 | 3794 | SA24M005 | Horizontal Waterproofing for Raft Foundation Tunnel |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Tunnel & Duct Bank Control Cable tunnel from Control building to 380kV GIS building Horizontal Waterproofing for Raft Foundation Tunnel | 4 | CTDB00CG | C000 | 00C4 | C000#OBSv00C4
3795 | 3795 | 3795 | 3795 | SA24M005 | Screed Layer Over Waterproofing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Tunnel & Duct Bank Control Cable tunnel from Control building to 380kV GIS building Screed Layer Over Waterproofing | 5 | CTDB00CG | C000 | 00C5 | C000#OBSv00C5
3796 | 3796 | 3796 | 3796 | SA24M005 | R.C for Raft Foundation of Tunnel |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Tunnel & Duct Bank Control Cable tunnel from Control building to 380kV GIS building R.C for Raft Foundation of Tunnel | 6 | CTDB00CG | C000 | 00C6 | C000#OBSv00C6
3797 | 3797 | 3797 | 3797 | SA24M005 | R.C for Walls of Tunnel |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Tunnel & Duct Bank Control Cable tunnel from Control building to 380kV GIS building R.C for Walls of Tunnel | 7 | CTDB00CG | C000 | 00C7 | C000#OBSv00C7
3798 | 3798 | 3798 | 3798 | SA24M005 | R.C for Slab of Tunnel |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Tunnel & Duct Bank Control Cable tunnel from Control building to 380kV GIS building R.C for Slab of Tunnel | 8 | CTDB00CG | C000 | 00C8 | C000#OBSv00C8
3799 | 3799 | 3799 | 3799 | SA24M005 | Verticall Waterproofing for Walls of Tunnel |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Tunnel & Duct Bank Control Cable tunnel from Control building to 380kV GIS building Verticall Waterproofing for Walls of Tunnel | 9 | CTDB00CG | C000 | 00C9 | C000#OBSv00C9
3800 | 3800 | 3800 | 3800 | SA24M005 | Waterproofing for Slab |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Tunnel & Duct Bank Control Cable tunnel from Control building to 380kV GIS building Waterproofing for Slab | 10 | CTDB00CG | C000 | 0C10 | C000#OBSv0C10
3801 | 3801 | 3801 | 3801 | SA24M005 | Out Side Backfilling & Compaction up to Design Level |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Tunnel & Duct Bank Control Cable tunnel from Control building to 380kV GIS building Out Side Backfilling & Compaction up to Design Level | 11 | CTDB00CG | C000 | 0C11 | C000#OBSv0C11
3802 | 3802 | 3802 | 3802 | SA24M005 | Finishing/Painting/Cementacious |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Tunnel & Duct Bank Control Cable tunnel from Control building to 380kV GIS building Finishing/Painting/Cementacious | 12 | CTDB00CG | C000 | 0C12 | C000#OBSv0C12
3803 | 3803 | 3803 | 3803 | SA24M005 | Floor Epoxy |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Tunnel & Duct Bank Control Cable tunnel from Control building to 380kV GIS building Floor Epoxy | 13 | CTDB00CG | C000 | 0C13 | C000#OBSv0C13
3804 | 3804 | 3804 | 3804 | SA24M005 | 380kV Cable tunnel from Outside Fence to 380kV GIS |  | 6 | -1 | 0 |  |  | X | C000#OBSv
3805 | 3805 | 3805 | 3805 | SA24M005 | Excavation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Tunnel & Duct Bank 380kV Cable tunnel from Outside Fence to 380kV GIS Excavation | 1 | CTDB00CG | C000 | 00C1 | C000#wolt00C1
3806 | 3806 | 3806 | 3806 | SA24M005 | Backfilling & Compaction |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Tunnel & Duct Bank 380kV Cable tunnel from Outside Fence to 380kV GIS Backfilling & Compaction | 2 | CTDB00CG | C000 | 00C2 | C000#wolt00C2
3807 | 3807 | 3807 | 3807 | SA24M005 | Lean Concrete under Raft Foundation of Tunnel |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Tunnel & Duct Bank 380kV Cable tunnel from Outside Fence to 380kV GIS Lean Concrete under Raft Foundation of Tunnel | 3 | CTDB00CG | C000 | 00C3 | C000#wolt00C3
3808 | 3808 | 3808 | 3808 | SA24M005 | Horizontal Waterproofing for Raft Foundation Tunnel |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Tunnel & Duct Bank 380kV Cable tunnel from Outside Fence to 380kV GIS Horizontal Waterproofing for Raft Foundation Tunnel | 4 | CTDB00CG | C000 | 00C4 | C000#wolt00C4
3809 | 3809 | 3809 | 3809 | SA24M005 | Screed Layer Over Waterproofing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Tunnel & Duct Bank 380kV Cable tunnel from Outside Fence to 380kV GIS Screed Layer Over Waterproofing | 5 | CTDB00CG | C000 | 00C5 | C000#wolt00C5
3810 | 3810 | 3810 | 3810 | SA24M005 | R.C for Raft Foundation of Tunnel |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Tunnel & Duct Bank 380kV Cable tunnel from Outside Fence to 380kV GIS R.C for Raft Foundation of Tunnel | 6 | CTDB00CG | C000 | 00C6 | C000#wolt00C6
3811 | 3811 | 3811 | 3811 | SA24M005 | R.C for Walls of Tunnel |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Tunnel & Duct Bank 380kV Cable tunnel from Outside Fence to 380kV GIS R.C for Walls of Tunnel | 7 | CTDB00CG | C000 | 00C7 | C000#wolt00C7
3812 | 3812 | 3812 | 3812 | SA24M005 | Waterproofing for Slab |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Tunnel & Duct Bank 380kV Cable tunnel from Outside Fence to 380kV GIS Waterproofing for Slab | 8 | CTDB00CG | C000 | 00C8 | C000#wolt00C8
3813 | 3813 | 3813 | 3813 | SA24M005 | R.C for Slab of Tunnel |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Tunnel & Duct Bank 380kV Cable tunnel from Outside Fence to 380kV GIS R.C for Slab of Tunnel | 9 | CTDB00CG | C000 | 00C9 | C000#wolt00C9
3814 | 3814 | 3814 | 3814 | SA24M005 | R.C for Fire Exit Stairs of Tunnel |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Tunnel & Duct Bank 380kV Cable tunnel from Outside Fence to 380kV GIS R.C for Fire Exit Stairs of Tunnel | 10 | CTDB00CG | C000 | 0C10 | C000#wolt0C10
3815 | 3815 | 3815 | 3815 | SA24M005 | Verticall Waterproofing for Walls of Tunnel |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Tunnel & Duct Bank 380kV Cable tunnel from Outside Fence to 380kV GIS Verticall Waterproofing for Walls of Tunnel | 11 | CTDB00CG | C000 | 0C11 | C000#wolt0C11
3816 | 3816 | 3816 | 3816 | SA24M005 | Out Side Backfilling & Compaction up to Design Level |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Tunnel & Duct Bank 380kV Cable tunnel from Outside Fence to 380kV GIS Out Side Backfilling & Compaction up to Design Level | 12 | CTDB00CG | C000 | 0C12 | C000#wolt0C12
3817 | 3817 | 3817 | 3817 | SA24M005 | Finishing/Painting/Cementacious |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Tunnel & Duct Bank 380kV Cable tunnel from Outside Fence to 380kV GIS Finishing/Painting/Cementacious | 13 | CTDB00CG | C000 | 0C13 | C000#wolt0C13
3818 | 3818 | 3818 | 3818 | SA24M005 | Floor Epoxy |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Tunnel & Duct Bank 380kV Cable tunnel from Outside Fence to 380kV GIS Floor Epoxy | 14 | CTDB00CG | C000 | 0C14 | C000#wolt0C14
3819 | 3819 | 3819 | 3819 | SA24M005 | Cable Duct bank |  | 6 | -1 | 0 |  |  | X | C000#wolt
3820 | 3820 | 3820 | 3820 | SA24M005 | Cable Duct bank incl. man holes & hand holes |  | 7 | -1 | 0 |  |  | X | C000#wolt
3821 | 3821 | 3821 | 3821 | SA24M005 | Excavation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Tunnel & Duct Bank Cable Duct bank Cable Duct bank incl. man holes & hand holes Excavation | 1 | CTDB00CD | C000 | 00C1 | C000CTDB00CD00C1
3822 | 3822 | 3822 | 3822 | SA24M005 | Construction of Man holes |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Tunnel & Duct Bank Cable Duct bank Cable Duct bank incl. man holes & hand holes Construction of Man holes | 2 | CTDB00CD | C000 | 00C2 | C000CTDB00CD00C2
3823 | 3823 | 3823 | 3823 | SA24M005 | Construction of Hand holes |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Tunnel & Duct Bank Cable Duct bank Cable Duct bank incl. man holes & hand holes Construction of Hand holes | 3 | CTDB00CD | C000 | 00C3 | C000CTDB00CD00C3
3824 | 3824 | 3824 | 3824 | SA24M005 | Compaction |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Tunnel & Duct Bank Cable Duct bank Cable Duct bank incl. man holes & hand holes Compaction | 4 | CTDB00CD | C000 | 00C4 | C000CTDB00CD00C4
3825 | 3825 | 3825 | 3825 | SA24M005 | Fixing of conduits and spacers |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Tunnel & Duct Bank Cable Duct bank Cable Duct bank incl. man holes & hand holes Fixing of conduits and spacers | 5 | CTDB00CD | C000 | 00C5 | C000CTDB00CD00C5
3826 | 3826 | 3826 | 3826 | SA24M005 | Concrete Inc steel and shuttering |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Tunnel & Duct Bank Cable Duct bank Cable Duct bank incl. man holes & hand holes Concrete Inc steel and shuttering | 6 | CTDB00CD | C000 | 00C6 | C000CTDB00CD00C6
3827 | 3827 | 3827 | 3827 | SA24M005 | Finishing/Painting/Cementacious |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Tunnel & Duct Bank Cable Duct bank Cable Duct bank incl. man holes & hand holes Finishing/Painting/Cementacious | 7 | CTDB00CD | C000 | 00C7 | C000CTDB00CD00C7
3828 | 3828 | 3828 | 3828 | SA24M005 | Out Side Backfilling & Compaction |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Tunnel & Duct Bank Cable Duct bank Cable Duct bank incl. man holes & hand holes Out Side Backfilling & Compaction | 8 | CTDB00CD | C000 | 00C8 | C000CTDB00CD00C8
3829 | 3829 | 3829 | 3829 | SA24M005 | Duct banks and Man holes, hand holes (Communication) |  | 5 | -1 | 0 |  |  | X
3830 | 3830 | 3830 | 3830 | SA24M005 | Excavation works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Duct banks and Man holes, hand holes (Communication) Excavation works | 1 | C0DBM | C000 | 00C1 | C000C0DBM00C1
3831 | 3831 | 3831 | 3831 | SA24M005 | Man holes works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Duct banks and Man holes, hand holes (Communication) Man holes works | 2 | C0DBM | C000 | 00C2 | C000C0DBM00C2
3832 | 3832 | 3832 | 3832 | SA24M005 | Hand hole works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Duct banks and Man holes, hand holes (Communication) Hand hole works | 3 | C0DBM | C000 | 00C3 | C000C0DBM00C3
3833 | 3833 | 3833 | 3833 | SA24M005 | Duct bank works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Duct banks and Man holes, hand holes (Communication) Duct bank works | 4 | C0DBM | C000 | 00C4 | C000C0DBM00C4
3834 | 3834 | 3834 | 3834 | SA24M005 | Back filling & Compaction works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Duct banks and Man holes, hand holes (Communication) Back filling & Compaction works | 5 | C0DBM | C000 | 00C5 | C000C0DBM00C5
3835 | 3835 | 3835 | 3835 | SA24M005 | Fire trench works |  | 5 | -1 | 0 |  |  | X
3836 | 3836 | 3836 | 3836 | SA24M005 | Earth work excavation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Fire trench works Earth work excavation | 1 | CW0FRT | C000 | 00C1 | C000CW0FRT00C1
3837 | 3837 | 3837 | 3837 | SA24M005 | Supply and laying of Lean concrete -75 mm thick |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Fire trench works Supply and laying of Lean concrete -75 mm thick | 2 | CW0FRT | C000 | 00C2 | C000CW0FRT00C2
3838 | 3838 | 3838 | 3838 | SA24M005 | Concreting work |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Fire trench works Concreting work | 3 | CW0FRT | C000 | 00C3 | C000CW0FRT00C3
3839 | 3839 | 3839 | 3839 | SA24M005 | Supply, Bending, placing, and binding of Rebar works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Fire trench works Supply, Bending, placing, and binding of Rebar works | 4 | CW0FRT | C000 | 00C4 | C000CW0FRT00C4
3840 | 3840 | 3840 | 3840 | SA24M005 | Shuttering works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Fire trench works Shuttering works | 5 | CW0FRT | C000 | 00C5 | C000CW0FRT00C5
3841 | 3841 | 3841 | 3841 | SA24M005 | Laying of 2 layers of 150-micron polyethylene vapor barrier sheet |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Fire trench works Laying of 2 layers of 150-micron polyethylene vapor barrier sheet | 6 | CW0FRT | C000 | 00C6 | C000CW0FRT00C6
3842 | 3842 | 3842 | 3842 | SA24M005 | PVC water stopper at Trench wall |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Fire trench works PVC water stopper at Trench wall | 7 | CW0FRT | C000 | 00C7 | C000CW0FRT00C7
3843 | 3843 | 3843 | 3843 | SA24M005 | Application of 2 coats of coal tar epoxy |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Fire trench works Application of 2 coats of coal tar epoxy | 8 | CW0FRT | C000 | 00C8 | C000CW0FRT00C8
3844 | 3844 | 3844 | 3844 | SA24M005 | Elastomeric Paint ( floor ) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Fire trench works Elastomeric Paint ( floor ) | 9 | CW0FRT | C000 | 00C9 | C000CW0FRT00C9
3845 | 3845 | 3845 | 3845 | SA24M005 | 2 Coats of cementitious paint (internal wall & ceiling) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Fire trench works 2 Coats of cementitious paint (internal wall & ceiling) | 10 | CW0FRT | C000 | 0C10 | C000CW0FRT0C10
3846 | 3846 | 3846 | 3846 | SA24M005 | Precast Slab Cover |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Fire trench works Precast Slab Cover | 11 | CW0FRT | C000 | 0C11 | C000CW0FRT0C11
3847 | 3847 | 3847 | 3847 | SA24M005 | Edge angle support |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Fire trench works Edge angle support | 12 | CW0FRT | C000 | 0C12 | C000CW0FRT0C12
3848 | 3848 | 3848 | 3848 | SA24M005 | Boundary Retaining Walls |  | 5 | -1 | 0 |  |  | X
3849 | 3849 | 3849 | 3849 | SA24M005 | Earth work excavation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Boundary Retaining Walls Earth work excavation | 1 | CBW00RE | C000 | 00C1 | C000CBW00RE00C1
3850 | 3850 | 3850 | 3850 | SA24M005 | Backfilling with selected fill |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Boundary Retaining Walls Backfilling with selected fill | 2 | CBW00RE | C000 | 00C2 | C000CBW00RE00C2
3851 | 3851 | 3851 | 3851 | SA24M005 | Laying of 2 layers of 150 Micron Polyethylene vapor barrier sheet below lean concrete |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Boundary Retaining Walls Laying of 2 layers of 150 Micron Polyethylene vapor barrier sheet below lean concrete | 3 | CBW00RE | C000 | 00C3 | C000CBW00RE00C3
3852 | 3852 | 3852 | 3852 | SA24M005 | Supply and laying of Lean Concrete 75mm thick |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Boundary Retaining Walls Supply and laying of Lean Concrete 75mm thick | 4 | CBW00RE | C000 | 00C4 | C000CBW00RE00C4
3853 | 3853 | 3853 | 3853 | SA24M005 | Concreting work |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Boundary Retaining Walls Concreting work | 5 | CBW00RE | C000 | 00C5 | C000CBW00RE00C5
3854 | 3854 | 3854 | 3854 | SA24M005 | Supply, Bending, placing, and binding of Rebar works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Boundary Retaining Walls Supply, Bending, placing, and binding of Rebar works | 6 | CBW00RE | C000 | 00C6 | C000CBW00RE00C6
3855 | 3855 | 3855 | 3855 | SA24M005 | Shuttering works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Boundary Retaining Walls Shuttering works | 7 | CBW00RE | C000 | 00C7 | C000CBW00RE00C7
3856 | 3856 | 3856 | 3856 | SA24M005 | Supply and Application of 2 coats of coal tar epoxy over foundation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Boundary Retaining Walls Supply and Application of 2 coats of coal tar epoxy over foundation | 8 | CBW00RE | C000 | 00C8 | C000CBW00RE00C8
3857 | 3857 | 3857 | 3857 | SA24M005 | 12mm thick Isolation Joint |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Boundary Retaining Walls 12mm thick Isolation Joint | 9 | CBW00RE | C000 | 00C9 | C000CBW00RE00C9
3858 | 3858 | 3858 | 3858 | SA24M005 | Precast wall panel 120 thk. Of size (3mx3m) with 400 x 400 x 2.9m precast column |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Boundary Retaining Walls Precast wall panel 120 thk. Of size (3mx3m) with 400 x 400 x 2.9m precast column | 10 | CBW00RE | C000 | 0C10 | C000CBW00RE0C10
3859 | 3859 | 3859 | 3859 | SA24M005 | Application of Textured Emulsion Paint |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Boundary Retaining Walls Application of Textured Emulsion Paint | 11 | CBW00RE | C000 | 0C11 | C000CBW00RE0C11
3860 | 3860 | 3860 | 3860 | SA24M005 | 110 dia. PVC weep holes |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Boundary Retaining Walls 110 dia. PVC weep holes | 12 | CBW00RE | C000 | 0C12 | C000CBW00RE0C12
3861 | 3861 | 3861 | 3861 | SA24M005 | Granular fill |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Boundary Retaining Walls Granular fill | 13 | CBW00RE | C000 | 0C13 | C000CBW00RE0C13
3862 | 3862 | 3862 | 3862 | SA24M005 | Drain Works |  | 5 | -1 | 0 |  |  | X
3863 | 3863 | 3863 | 3863 | SA24M005 | Excavation works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Drain Works Excavation works | 1 | C0DRA | C000 | 00C1 | C000C0DRA00C1
3864 | 3864 | 3864 | 3864 | SA24M005 | Backfilling & Compaction |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Drain Works Backfilling & Compaction | 2 | C0DRA | C000 | 00C2 | C000C0DRA00C2
3865 | 3865 | 3865 | 3865 | SA24M005 | Laying of 2 layers of 150 micron polyethylene vapor barrier sheet |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Drain Works Laying of 2 layers of 150 micron polyethylene vapor barrier sheet | 3 | C0DRA | C000 | 00C3 | C000C0DRA00C3
3866 | 3866 | 3866 | 3866 | SA24M005 | Lean Concrete- 75mm Think |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Drain Works Lean Concrete- 75mm Think | 4 | C0DRA | C000 | 00C4 | C000C0DRA00C4
3867 | 3867 | 3867 | 3867 | SA24M005 | Reinforcement works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Drain Works Reinforcement works | 5 | C0DRA | C000 | 00C5 | C000C0DRA00C5
3868 | 3868 | 3868 | 3868 | SA24M005 | Shuttering Works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Drain Works Shuttering Works | 6 | C0DRA | C000 | 00C6 | C000C0DRA00C6
3869 | 3869 | 3869 | 3869 | SA24M005 | RCC Concrete works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Drain Works RCC Concrete works | 7 | C0DRA | C000 | 00C7 | C000C0DRA00C7
3870 | 3870 | 3870 | 3870 | SA24M005 | Waterproofing- Application of 2 coats of coal tar epoxy |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Drain Works Waterproofing- Application of 2 coats of coal tar epoxy | 8 | C0DRA | C000 | 00C8 | C000C0DRA00C8
3871 | 3871 | 3871 | 3871 | SA24M005 | PVC Water stopper |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Drain Works PVC Water stopper | 9 | C0DRA | C000 | 00C9 | C000C0DRA00C9
3872 | 3872 | 3872 | 3872 | SA24M005 | Application of Cementitious paint |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Drain Works Application of Cementitious paint | 10 | C0DRA | C000 | 0C10 | C000C0DRA0C10
3873 | 3873 | 3873 | 3873 | SA24M005 | Steel garting cover |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Drain Works Steel garting cover | 11 | C0DRA | C000 | 0C11 | C000C0DRA0C11
3874 | 3874 | 3874 | 3874 | SA24M005 | Security Fence & Gate |  | 5 | -1 | 0 |  |  | X
3875 | 3875 | 3875 | 3875 | SA24M005 | TYPE IV Fence |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Security Fence & Gate TYPE IV Fence | 1 | CSFCG | C000 | 00C1 | C000CSFCG00C1
3876 | 3876 | 3876 | 3876 | SA24M005 | Perimeter Fence (Class-I) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Security Fence & Gate Perimeter Fence (Class-I) | 2 | CSFCG | C000 | 00C2 | C000CSFCG00C2
3877 | 3877 | 3877 | 3877 | SA24M005 | Anti-Vehicle Barrier around as per HCIS - Class I |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Security Fence & Gate Anti-Vehicle Barrier around as per HCIS - Class I | 3 | CSFCG | C000 | 00C3 | C000CSFCG00C3
3878 | 3878 | 3878 | 3878 | SA24M005 | Providing Gates as per requirement |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Security Fence & Gate Providing Gates as per requirement | 4 | CSFCG | C000 | 00C4 | C000CSFCG00C4
3879 | 3879 | 3879 | 3879 | SA24M005 | Common Civil Works |  | 5 | -1 | 0 |  |  | X
3880 | 3880 | 3880 | 3880 | SA24M005 | Walkway and ramp works / Landing Platforms |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Common Civil Works Walkway and ramp works / Landing Platforms | 1 | C0CWW | C000 | 00C1 | C000C0CWW00C1
3881 | 3881 | 3881 | 3881 | SA24M005 | Asphalting works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Common Civil Works Asphalting works | 2 | C0CWW | C000 | 00C2 | C000C0CWW00C2
3882 | 3882 | 3882 | 3882 | SA24M005 | Base course works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Common Civil Works Base course works | 3 | C0CWW | C000 | 00C3 | C000C0CWW00C3
3883 | 3883 | 3883 | 3883 | SA24M005 | Precast curb stone works - along the road side |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Common Civil Works Precast curb stone works - along the road side | 4 | C0CWW | C000 | 00C4 | C000C0CWW00C4
3884 | 3884 | 3884 | 3884 | SA24M005 | Car Parking - shelter works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Common Civil Works Car Parking - shelter works | 5 | C0CWW | C000 | 00C5 | C000C0CWW00C5
3885 | 3885 | 3885 | 3885 | SA24M005 | Sign board installation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Common Civil Works Sign board installation | 6 | C0CWW | C000 | 00C6 | C000C0CWW00C6
3886 | 3886 | 3886 | 3886 | SA24M005 | Civil Punchlist |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Civil Works Common Civil Works Civil Punchlist | 7 | C0CWW | C000 | 00C7 | C000C0CWW00C7
3887 | 3887 | 3887 | 3887 | SA24M005 | Electrical Works |  | 4 | -1 | 0 |  |  | X
3888 | 3888 | 3888 | 3888 | SA24M005 | 380KV GIS |  | 5 | -1 | 0 |  |  | X
3889 | 3889 | 3889 | 3889 | SA24M005 | Clean Room Access |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380KV GIS Clean Room Access | 1 | E0GIS | C000 | 00C1 | C000E0GIS00C1
3890 | 3890 | 3890 | 3890 | SA24M005 | OEM Engineer Availability |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380KV GIS OEM Engineer Availability | 2 | E0GIS | C000 | 00C2 | C000E0GIS00C2
3891 | 3891 | 3891 | 3891 | SA24M005 | Installation of supporting structures |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380KV GIS Installation of supporting structures | 3 | E0GIS | C000 | 00C3 | C000E0GIS00C3
3892 | 3892 | 3892 | 3892 | SA24M005 | Installation of CB Modules |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380KV GIS Installation of CB Modules | 4 | E0GIS | C000 | 00C4 | C000E0GIS00C4
3893 | 3893 | 3893 | 3893 | SA24M005 | Installation of Disconnector Switch Modules |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380KV GIS Installation of Disconnector Switch Modules | 5 | E0GIS | C000 | 00C5 | C000E0GIS00C5
3894 | 3894 | 3894 | 3894 | SA24M005 | Installation of Grounding Switch Modules |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380KV GIS Installation of Grounding Switch Modules | 6 | E0GIS | C000 | 00C6 | C000E0GIS00C6
3895 | 3895 | 3895 | 3895 | SA24M005 | Installation of High Speed Granding Switch Modules |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380KV GIS Installation of High Speed Granding Switch Modules | 7 | E0GIS | C000 | 00C7 | C000E0GIS00C7
3896 | 3896 | 3896 | 3896 | SA24M005 | Installation of Voltage Transformer Modules |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380KV GIS Installation of Voltage Transformer Modules | 8 | E0GIS | C000 | 00C8 | C000E0GIS00C8
3897 | 3897 | 3897 | 3897 | SA24M005 | Installation of Current Transformer Modules |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380KV GIS Installation of Current Transformer Modules | 9 | E0GIS | C000 | 00C9 | C000E0GIS00C9
3898 | 3898 | 3898 | 3898 | SA24M005 | Installation of GIS Surge Arrestor Modules |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380KV GIS Installation of GIS Surge Arrestor Modules | 10 | E0GIS | C000 | 0C10 | C000E0GIS0C10
3899 | 3899 | 3899 | 3899 | SA24M005 | Installing of erection accessories |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380KV GIS Installing of erection accessories | 11 | E0GIS | C000 | 0C11 | C000E0GIS0C11
3900 | 3900 | 3900 | 3900 | SA24M005 | Installation of Gas Density Monitors |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380KV GIS Installation of Gas Density Monitors | 12 | E0GIS | C000 | 0C12 | C000E0GIS0C12
3901 | 3901 | 3901 | 3901 | SA24M005 | GIS-Earthing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380KV GIS GIS-Earthing | 13 | E0GIS | C000 | 0C13 | C000E0GIS0C13
3902 | 3902 | 3902 | 3902 | SA24M005 | GIS Gas Filling |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380KV GIS GIS Gas Filling | 14 | E0GIS | C000 | 0C14 | C000E0GIS0C14
3903 | 3903 | 3903 | 3903 | SA24M005 | Installation of LCC Panel |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380KV GIS Installation of LCC Panel | 15 | E0GIS | C000 | 0C15 | C000E0GIS0C15
3904 | 3904 | 3904 | 3904 | SA24M005 | Installation of PDMS Panels & Accessories |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380KV GIS Installation of PDMS Panels & Accessories | 16 | E0GIS | C000 | 0C16 | C000E0GIS0C16
3905 | 3905 | 3905 | 3905 | SA24M005 | Earthing of LCC & PDMS Panels |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380KV GIS Earthing of LCC & PDMS Panels | 17 | E0GIS | C000 | 0C17 | C000E0GIS0C17
3906 | 3906 | 3906 | 3906 | SA24M005 | GIS to LCC Cable Laying & Termination |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380KV GIS GIS to LCC Cable Laying & Termination | 18 | E0GIS | C000 | 0C18 | C000E0GIS0C18
3907 | 3907 | 3907 | 3907 | SA24M005 | LCC to LCC Cable Laying & Termination |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380KV GIS LCC to LCC Cable Laying & Termination | 19 | E0GIS | C000 | 0C19 | C000E0GIS0C19
3908 | 3908 | 3908 | 3908 | SA24M005 | AC Supply Availability for LCC Panel |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380KV GIS AC Supply Availability for LCC Panel | 20 | E0GIS | C000 | 0C20 | C000E0GIS0C20
3909 | 3909 | 3909 | 3909 | SA24M005 | DC Supply availability of LCC Panel |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380KV GIS DC Supply availability of LCC Panel | 21 | E0GIS | C000 | 0C21 | C000E0GIS0C21
3910 | 3910 | 3910 | 3910 | SA24M005 | Intial Local Operation by OEM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380KV GIS Intial Local Operation by OEM | 22 | E0GIS | C000 | 0C22 | C000E0GIS0C22
3911 | 3911 | 3911 | 3911 | SA24M005 | Initial Electrical Operation by OEM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380KV GIS Initial Electrical Operation by OEM | 23 | E0GIS | C000 | 0C23 | C000E0GIS0C23
3912 | 3912 | 3912 | 3912 | SA24M005 | 380KV HGIS |  | 5 | -1 | 0 |  |  | X
3913 | 3913 | 3913 | 3913 | SA24M005 | Access availability |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380KV HGIS Access availability | 1 | EHGIS | C000 | 00C1 | C000EHGIS00C1
3914 | 3914 | 3914 | 3914 | SA24M005 | OEM Engineer Availability |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380KV HGIS OEM Engineer Availability | 2 | EHGIS | C000 | 00C2 | C000EHGIS00C2
3915 | 3915 | 3915 | 3915 | SA24M005 | Installation of supporting structures |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380KV HGIS Installation of supporting structures | 3 | EHGIS | C000 | 00C3 | C000EHGIS00C3
3916 | 3916 | 3916 | 3916 | SA24M005 | Installation of CB Modules |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380KV HGIS Installation of CB Modules | 4 | EHGIS | C000 | 00C4 | C000EHGIS00C4
3917 | 3917 | 3917 | 3917 | SA24M005 | Installation of Disconnector Switch Modules |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380KV HGIS Installation of Disconnector Switch Modules | 5 | EHGIS | C000 | 00C5 | C000EHGIS00C5
3918 | 3918 | 3918 | 3918 | SA24M005 | Installation of Grounding Switch Modules |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380KV HGIS Installation of Grounding Switch Modules | 6 | EHGIS | C000 | 00C6 | C000EHGIS00C6
3919 | 3919 | 3919 | 3919 | SA24M005 | Installation of Current Transformer Modules |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380KV HGIS Installation of Current Transformer Modules | 7 | EHGIS | C000 | 00C7 | C000EHGIS00C7
3920 | 3920 | 3920 | 3920 | SA24M005 | Installation of Surge Arrestor Modules |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380KV HGIS Installation of Surge Arrestor Modules | 8 | EHGIS | C000 | 00C8 | C000EHGIS00C8
3921 | 3921 | 3921 | 3921 | SA24M005 | Installing of erection accessories |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380KV HGIS Installing of erection accessories | 9 | EHGIS | C000 | 00C9 | C000EHGIS00C9
3922 | 3922 | 3922 | 3922 | SA24M005 | Installation of Gas Density Monitors |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380KV HGIS Installation of Gas Density Monitors | 10 | EHGIS | C000 | 0C10 | C000EHGIS0C10
3923 | 3923 | 3923 | 3923 | SA24M005 | GIS-Earthing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380KV HGIS GIS-Earthing | 11 | EHGIS | C000 | 0C11 | C000EHGIS0C11
3924 | 3924 | 3924 | 3924 | SA24M005 | GIS Gas Filling |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380KV HGIS GIS Gas Filling | 12 | EHGIS | C000 | 0C12 | C000EHGIS0C12
3925 | 3925 | 3925 | 3925 | SA24M005 | Installation of LCC Panel |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380KV HGIS Installation of LCC Panel | 13 | EHGIS | C000 | 0C13 | C000EHGIS0C13
3926 | 3926 | 3926 | 3926 | SA24M005 | Installation of PDMS Panels & Accessories |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380KV HGIS Installation of PDMS Panels & Accessories | 14 | EHGIS | C000 | 0C14 | C000EHGIS0C14
3927 | 3927 | 3927 | 3927 | SA24M005 | Earthing of LCC & PDMS Panels |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380KV HGIS Earthing of LCC & PDMS Panels | 15 | EHGIS | C000 | 0C15 | C000EHGIS0C15
3928 | 3928 | 3928 | 3928 | SA24M005 | GIS to LCC Cable Laying & Termination |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380KV HGIS GIS to LCC Cable Laying & Termination | 16 | EHGIS | C000 | 0C16 | C000EHGIS0C16
3929 | 3929 | 3929 | 3929 | SA24M005 | LCC to LCC Cable Laying & Termination |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380KV HGIS LCC to LCC Cable Laying & Termination | 17 | EHGIS | C000 | 0C17 | C000EHGIS0C17
3930 | 3930 | 3930 | 3930 | SA24M005 | AC Supply Availability for LCC Panel |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380KV HGIS AC Supply Availability for LCC Panel | 18 | EHGIS | C000 | 0C18 | C000EHGIS0C18
3931 | 3931 | 3931 | 3931 | SA24M005 | DC Supply availability of LCC Panel |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380KV HGIS DC Supply availability of LCC Panel | 19 | EHGIS | C000 | 0C19 | C000EHGIS0C19
3932 | 3932 | 3932 | 3932 | SA24M005 | Intial Local Operation by OEM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380KV HGIS Intial Local Operation by OEM | 20 | EHGIS | C000 | 0C20 | C000EHGIS0C20
3933 | 3933 | 3933 | 3933 | SA24M005 | Initial Electrical Operation by OEM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380KV HGIS Initial Electrical Operation by OEM | 21 | EHGIS | C000 | 0C21 | C000EHGIS0C21
3934 | 3934 | 3934 | 3934 | SA24M005 | GIB & Connectors |  | 5 | -1 | 0 |  |  | X
3935 | 3935 | 3935 | 3935 | SA24M005 | Erection of supporting structures |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works GIB & Connectors Erection of supporting structures | 1 | E0GIB | C000 | 00C1 | C000E0GIB00C1
3936 | 3936 | 3936 | 3936 | SA24M005 | Erection of electrical equipment |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works GIB & Connectors Erection of electrical equipment | 2 | E0GIB | C000 | 00C2 | C000E0GIB00C2
3937 | 3937 | 3937 | 3937 | SA24M005 | Installtion of GIB with Gas density & Pressure monitoring devices |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works GIB & Connectors Installtion of GIB with Gas density & Pressure monitoring devices | 3 | E0GIB | C000 | 00C3 | C000E0GIB00C3
3938 | 3938 | 3938 | 3938 | SA24M005 | Installing of erection accessories |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works GIB & Connectors Installing of erection accessories | 4 | E0GIB | C000 | 00C4 | C000E0GIB00C4
3939 | 3939 | 3939 | 3939 | SA24M005 | Earthing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works GIB & Connectors Earthing | 5 | E0GIB | C000 | 00C5 | C000E0GIB00C5
3940 | 3940 | 3940 | 3940 | SA24M005 | HV/PD Test kit Availability |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works GIB & Connectors HV/PD Test kit Availability | 6 | E0GIB | C000 | 00C6 | C000E0GIB00C6
3941 | 3941 | 3941 | 3941 | SA24M005 | Test Bushing Installation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works GIB & Connectors Test Bushing Installation | 7 | E0GIB | C000 | 00C7 | C000E0GIB00C7
3942 | 3942 | 3942 | 3942 | SA24M005 | Station Service Transformers |  | 5 | -1 | 0 |  |  | X
3943 | 3943 | 3943 | 3943 | SA24M005 | Erection of Transformer |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Station Service Transformers Erection of Transformer | 1 | E0STRF | C000 | 00C1 | C000E0STRF00C1
3944 | 3944 | 3944 | 3944 | SA24M005 | Erection of accessories |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Station Service Transformers Erection of accessories | 2 | E0STRF | C000 | 00C2 | C000E0STRF00C2
3945 | 3945 | 3945 | 3945 | SA24M005 | Earthing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Station Service Transformers Earthing | 3 | E0STRF | C000 | 00C3 | C000E0STRF00C3
3946 | 3946 | 3946 | 3946 | SA24M005 | Checking of tightness and leaks |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Station Service Transformers Checking of tightness and leaks | 4 | E0STRF | C000 | 00C4 | C000E0STRF00C4
3947 | 3947 | 3947 | 3947 | SA24M005 | Oil Filtration of Transformer |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Station Service Transformers Oil Filtration of Transformer | 5 | E0STRF | C000 | 00C5 | C000E0STRF00C5
3948 | 3948 | 3948 | 3948 | SA24M005 | Oil Test Report of Transformer |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Station Service Transformers Oil Test Report of Transformer | 6 | E0STRF | C000 | 00C6 | C000E0STRF00C6
3949 | 3949 | 3949 | 3949 | SA24M005 | Power/Control cable laying to Transformer MB box |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Station Service Transformers Power/Control cable laying to Transformer MB box | 7 | E0STRF | C000 | 00C7 | C000E0STRF00C7
3950 | 3950 | 3950 | 3950 | SA24M005 | Power/Control cable termination to Transformer MB box |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Station Service Transformers Power/Control cable termination to Transformer MB box | 8 | E0STRF | C000 | 00C8 | C000E0STRF00C8
3951 | 3951 | 3951 | 3951 | SA24M005 | IPS tube / Conductor connection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Station Service Transformers IPS tube / Conductor connection | 9 | E0STRF | C000 | 00C9 | C000E0STRF00C9
3952 | 3952 | 3952 | 3952 | SA24M005 | Cabling & Termination |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Station Service Transformers Cabling & Termination | 10 | E0STRF | C000 | 0C10 | C000E0STRF0C10
3953 | 3953 | 3953 | 3953 | SA24M005 | 120 MVAR Shunt Reactor |  | 5 | -1 | 0 |  |  | X
3954 | 3954 | 3954 | 3954 | SA24M005 | Erection of Reactor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 120 MVAR Shunt Reactor Erection of Reactor | 1 | E0SR | C000 | 00C1 | C000E0SR00C1
3955 | 3955 | 3955 | 3955 | SA24M005 | Erection of accessories |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 120 MVAR Shunt Reactor Erection of accessories | 2 | E0SR | C000 | 00C2 | C000E0SR00C2
3956 | 3956 | 3956 | 3956 | SA24M005 | Earthing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 120 MVAR Shunt Reactor Earthing | 3 | E0SR | C000 | 00C3 | C000E0SR00C3
3957 | 3957 | 3957 | 3957 | SA24M005 | Checking of tightness and leaks |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 120 MVAR Shunt Reactor Checking of tightness and leaks | 4 | E0SR | C000 | 00C4 | C000E0SR00C4
3958 | 3958 | 3958 | 3958 | SA24M005 | Vacuuming |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 120 MVAR Shunt Reactor Vacuuming | 5 | E0SR | C000 | 00C5 | C000E0SR00C5
3959 | 3959 | 3959 | 3959 | SA24M005 | Oil Filtration of Reactor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 120 MVAR Shunt Reactor Oil Filtration of Reactor | 6 | E0SR | C000 | 00C6 | C000E0SR00C6
3960 | 3960 | 3960 | 3960 | SA24M005 | Oil Test Report of Reactor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 120 MVAR Shunt Reactor Oil Test Report of Reactor | 7 | E0SR | C000 | 00C7 | C000E0SR00C7
3961 | 3961 | 3961 | 3961 | SA24M005 | Power/Control cable laying to Reactor MB box |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 120 MVAR Shunt Reactor Power/Control cable laying to Reactor MB box | 8 | E0SR | C000 | 00C8 | C000E0SR00C8
3962 | 3962 | 3962 | 3962 | SA24M005 | Power/Control cable termination to Reactor MB box |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 120 MVAR Shunt Reactor Power/Control cable termination to Reactor MB box | 9 | E0SR | C000 | 00C9 | C000E0SR00C9
3963 | 3963 | 3963 | 3963 | SA24M005 | IPS tube / Conductor connection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 120 MVAR Shunt Reactor IPS tube / Conductor connection | 10 | E0SR | C000 | 0C10 | C000E0SR0C10
3964 | 3964 | 3964 | 3964 | SA24M005 | Cabling & Termination |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 120 MVAR Shunt Reactor Cabling & Termination | 11 | E0SR | C000 | 0C11 | C000E0SR0C11
3965 | 3965 | 3965 | 3965 | SA24M005 | 150 MVAR Line Reactor |  | 5 | -1 | 0 |  |  | X
3966 | 3966 | 3966 | 3966 | SA24M005 | Erection of Reactor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 150 MVAR Line Reactor Erection of Reactor | 1 | E0LR | C000 | 00C1 | C000E0LR00C1
3967 | 3967 | 3967 | 3967 | SA24M005 | Erection of accessories |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 150 MVAR Line Reactor Erection of accessories | 2 | E0LR | C000 | 00C2 | C000E0LR00C2
3968 | 3968 | 3968 | 3968 | SA24M005 | Earthing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 150 MVAR Line Reactor Earthing | 3 | E0LR | C000 | 00C3 | C000E0LR00C3
3969 | 3969 | 3969 | 3969 | SA24M005 | Checking of tightness and leaks |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 150 MVAR Line Reactor Checking of tightness and leaks | 4 | E0LR | C000 | 00C4 | C000E0LR00C4
3970 | 3970 | 3970 | 3970 | SA24M005 | Vacuuming |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 150 MVAR Line Reactor Vacuuming | 5 | E0LR | C000 | 00C5 | C000E0LR00C5
3971 | 3971 | 3971 | 3971 | SA24M005 | Oil Filtration of Reactor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 150 MVAR Line Reactor Oil Filtration of Reactor | 6 | E0LR | C000 | 00C6 | C000E0LR00C6
3972 | 3972 | 3972 | 3972 | SA24M005 | Oil Test Report of Reactor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 150 MVAR Line Reactor Oil Test Report of Reactor | 7 | E0LR | C000 | 00C7 | C000E0LR00C7
3973 | 3973 | 3973 | 3973 | SA24M005 | Power/Control cable laying to Reactor MB box |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 150 MVAR Line Reactor Power/Control cable laying to Reactor MB box | 8 | E0LR | C000 | 00C8 | C000E0LR00C8
3974 | 3974 | 3974 | 3974 | SA24M005 | Power/Control cable termination to Reactor MB box |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 150 MVAR Line Reactor Power/Control cable termination to Reactor MB box | 9 | E0LR | C000 | 00C9 | C000E0LR00C9
3975 | 3975 | 3975 | 3975 | SA24M005 | IPS tube / Conductor connection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 150 MVAR Line Reactor IPS tube / Conductor connection | 10 | E0LR | C000 | 0C10 | C000E0LR0C10
3976 | 3976 | 3976 | 3976 | SA24M005 | Cabling & Termination |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 150 MVAR Line Reactor Cabling & Termination | 11 | E0LR | C000 | 0C11 | C000E0LR0C11
3977 | 3977 | 3977 | 3977 | SA24M005 | Neutral Grounding Reactor |  | 5 | -1 | 0 |  |  | X
3978 | 3978 | 3978 | 3978 | SA24M005 | Erection of NGR |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Neutral Grounding Reactor Erection of NGR | 1 | E0NGR | C000 | 00C1 | C000E0NGR00C1
3979 | 3979 | 3979 | 3979 | SA24M005 | Erection of accessories |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Neutral Grounding Reactor Erection of accessories | 2 | E0NGR | C000 | 00C2 | C000E0NGR00C2
3980 | 3980 | 3980 | 3980 | SA24M005 | Earthing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Neutral Grounding Reactor Earthing | 3 | E0NGR | C000 | 00C3 | C000E0NGR00C3
3981 | 3981 | 3981 | 3981 | SA24M005 | Power/Control cable laying to Reactor MB box |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Neutral Grounding Reactor Power/Control cable laying to Reactor MB box | 4 | E0NGR | C000 | 00C4 | C000E0NGR00C4
3982 | 3982 | 3982 | 3982 | SA24M005 | Power/Control cable termination to Reactor MB box |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Neutral Grounding Reactor Power/Control cable termination to Reactor MB box | 5 | E0NGR | C000 | 00C5 | C000E0NGR00C5
3983 | 3983 | 3983 | 3983 | SA24M005 | IPS tube / Conductor connection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Neutral Grounding Reactor IPS tube / Conductor connection | 6 | E0NGR | C000 | 00C6 | C000E0NGR00C6
3984 | 3984 | 3984 | 3984 | SA24M005 | Cabling & Termination |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Neutral Grounding Reactor Cabling & Termination | 7 | E0NGR | C000 | 00C7 | C000E0NGR00C7
3985 | 3985 | 3985 | 3985 | SA24M005 | 13.8kV Switchgear |  | 5 | -1 | 0 |  |  | X
3986 | 3986 | 3986 | 3986 | SA24M005 | Marking of Panels |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 13.8kV Switchgear Marking of Panels | 1 | E0SWGR | C000 | 00C1 | C000E0SWGR00C1
3987 | 3987 | 3987 | 3987 | SA24M005 | Erection of electrical equipment |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 13.8kV Switchgear Erection of electrical equipment | 2 | E0SWGR | C000 | 00C2 | C000E0SWGR00C2
3988 | 3988 | 3988 | 3988 | SA24M005 | Busbar coupling |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 13.8kV Switchgear Busbar coupling | 3 | E0SWGR | C000 | 00C3 | C000E0SWGR00C3
3989 | 3989 | 3989 | 3989 | SA24M005 | Earthing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 13.8kV Switchgear Earthing | 4 | E0SWGR | C000 | 00C4 | C000E0SWGR00C4
3990 | 3990 | 3990 | 3990 | SA24M005 | Inter-Panel wiring |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 13.8kV Switchgear Inter-Panel wiring | 5 | E0SWGR | C000 | 00C5 | C000E0SWGR00C5
3991 | 3991 | 3991 | 3991 | SA24M005 | AC & DC supply availability |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 13.8kV Switchgear AC & DC supply availability | 6 | E0SWGR | C000 | 00C6 | C000E0SWGR00C6
3992 | 3992 | 3992 | 3992 | SA24M005 | P&C Cable laying & Termination |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 13.8kV Switchgear P&C Cable laying & Termination | 7 | E0SWGR | C000 | 00C7 | C000E0SWGR00C7
3993 | 3993 | 3993 | 3993 | SA24M005 | Outdoor Surge Arrestor |  | 5 | -1 | 0 |  |  | X
3994 | 3994 | 3994 | 3994 | SA24M005 | Erection of supporting structure |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Outdoor Surge Arrestor Erection of supporting structure | 1 | E0SRG | C000 | 00C1 | C000E0SRG00C1
3995 | 3995 | 3995 | 3995 | SA24M005 | Erection of electrical equipment |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Outdoor Surge Arrestor Erection of electrical equipment | 2 | E0SRG | C000 | 00C2 | C000E0SRG00C2
3996 | 3996 | 3996 | 3996 | SA24M005 | Installing of erection accessories (Clamps/Connectors/Hardware Fitting etc) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Outdoor Surge Arrestor Installing of erection accessories (Clamps/Connectors/Hardware Fitting etc) | 3 | E0SRG | C000 | 00C3 | C000E0SRG00C3
3997 | 3997 | 3997 | 3997 | SA24M005 | Earthing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Outdoor Surge Arrestor Earthing | 4 | E0SRG | C000 | 00C4 | C000E0SRG00C4
3998 | 3998 | 3998 | 3998 | SA24M005 | IPS tube / Conductor connection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Outdoor Surge Arrestor IPS tube / Conductor connection | 5 | E0SRG | C000 | 00C5 | C000E0SRG00C5
3999 | 3999 | 3999 | 3999 | SA24M005 | HV / MV Powe Cables |  | 5 | -1 | 0 |  |  | X
4000 | 4000 | 4000 | 4000 | SA24M005 | Installation of cable trays |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works HV / MV Powe Cables Installation of cable trays | 1 | E0POWC | C000 | 00C1 | C000E0POWC00C1
4001 | 4001 | 4001 | 4001 | SA24M005 | Cable laying |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works HV / MV Powe Cables Cable laying | 2 | E0POWC | C000 | 00C2 | C000E0POWC00C2
4002 | 4002 | 4002 | 4002 | SA24M005 | Cable Termination |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works HV / MV Powe Cables Cable Termination | 3 | E0POWC | C000 | 00C3 | C000E0POWC00C3
4003 | 4003 | 4003 | 4003 | SA24M005 | Earthing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works HV / MV Powe Cables Earthing | 4 | E0POWC | C000 | 00C4 | C000E0POWC00C4
4004 | 4004 | 4004 | 4004 | SA24M005 | 125V Battery Bank & Battery Charger |  | 5 | -1 | 0 |  |  | X
4005 | 4005 | 4005 | 4005 | SA24M005 | Erection of base frame |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 125V Battery Bank & Battery Charger Erection of base frame | 1 | EBBCB | C000 | 00C1 | C000EBBCB00C1
4006 | 4006 | 4006 | 4006 | SA24M005 | Erection of Battery bank on the baseframe |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 125V Battery Bank & Battery Charger Erection of Battery bank on the baseframe | 2 | EBBCB | C000 | 00C2 | C000EBBCB00C2
4007 | 4007 | 4007 | 4007 | SA24M005 | Battery coupling / Alignment |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 125V Battery Bank & Battery Charger Battery coupling / Alignment | 3 | EBBCB | C000 | 00C3 | C000EBBCB00C3
4008 | 4008 | 4008 | 4008 | SA24M005 | Installation of fuse box |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 125V Battery Bank & Battery Charger Installation of fuse box | 4 | EBBCB | C000 | 00C4 | C000EBBCB00C4
4009 | 4009 | 4009 | 4009 | SA24M005 | Installation of battery Charger |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 125V Battery Bank & Battery Charger Installation of battery Charger | 5 | EBBCB | C000 | 00C5 | C000EBBCB00C5
4010 | 4010 | 4010 | 4010 | SA24M005 | Associated cabling between charger, fuse box and panel |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 125V Battery Bank & Battery Charger Associated cabling between charger, fuse box and panel | 6 | EBBCB | C000 | 00C6 | C000EBBCB00C6
4011 | 4011 | 4011 | 4011 | SA24M005 | OEM Engineer availability |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 125V Battery Bank & Battery Charger OEM Engineer availability | 7 | EBBCB | C000 | 00C7 | C000EBBCB00C7
4012 | 4012 | 4012 | 4012 | SA24M005 | AC supply availability |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 125V Battery Bank & Battery Charger AC supply availability | 8 | EBBCB | C000 | 00C8 | C000EBBCB00C8
4013 | 4013 | 4013 | 4013 | SA24M005 | Battery charging |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 125V Battery Bank & Battery Charger Battery charging | 9 | EBBCB | C000 | 00C9 | C000EBBCB00C9
4014 | 4014 | 4014 | 4014 | SA24M005 | Load Test / Discharging |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 125V Battery Bank & Battery Charger Load Test / Discharging | 10 | EBBCB | C000 | 0C10 | C000EBBCB0C10
4015 | 4015 | 4015 | 4015 | SA24M005 | Control cable laying & termination in battery charger |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 125V Battery Bank & Battery Charger Control cable laying & termination in battery charger | 11 | EBBCB | C000 | 0C11 | C000EBBCB0C11
4016 | 4016 | 4016 | 4016 | SA24M005 | Earthing Works |  | 5 | -1 | 0 |  |  | X
4017 | 4017 | 4017 | 4017 | SA24M005 | Laying of Main grid & Earth mat |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Earthing Works Laying of Main grid & Earth mat | 1 | E0EAW | C000 | 00C1 | C000E0EAW00C1
4018 | 4018 | 4018 | 4018 | SA24M005 | ACDB Main & Sub-Panels |  | 5 | -1 | 0 |  |  | X | C000E0EAW
4019 | 4019 | 4019 | 4019 | SA24M005 | Marking of Panels |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works ACDB Main & Sub-Panels Marking of Panels | 1 | E0ACDB | C000 | 00C1 | C000E0ACDB00C1
4020 | 4020 | 4020 | 4020 | SA24M005 | Erection of supporting structures |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works ACDB Main & Sub-Panels Erection of supporting structures | 2 | E0ACDB | C000 | 00C2 | C000E0ACDB00C2
4021 | 4021 | 4021 | 4021 | SA24M005 | Installtion of Panels |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works ACDB Main & Sub-Panels Installtion of Panels | 3 | E0ACDB | C000 | 00C3 | C000E0ACDB00C3
4022 | 4022 | 4022 | 4022 | SA24M005 | Busbar coupling |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works ACDB Main & Sub-Panels Busbar coupling | 4 | E0ACDB | C000 | 00C4 | C000E0ACDB00C4
4023 | 4023 | 4023 | 4023 | SA24M005 | Earthing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works ACDB Main & Sub-Panels Earthing | 5 | E0ACDB | C000 | 00C5 | C000E0ACDB00C5
4024 | 4024 | 4024 | 4024 | SA24M005 | Panel Wiring and Connections |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works ACDB Main & Sub-Panels Panel Wiring and Connections | 6 | E0ACDB | C000 | 00C6 | C000E0ACDB00C6
4025 | 4025 | 4025 | 4025 | SA24M005 | Electrical components (CB, Fuses, Contactors, Relays, Meters) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works ACDB Main & Sub-Panels Electrical components (CB, Fuses, Contactors, Relays, Meters) | 7 | E0ACDB | C000 | 00C7 | C000E0ACDB00C7
4026 | 4026 | 4026 | 4026 | SA24M005 | AC Supply availability |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works ACDB Main & Sub-Panels AC Supply availability | 8 | E0ACDB | C000 | 00C8 | C000E0ACDB00C8
4027 | 4027 | 4027 | 4027 | SA24M005 | Final Cabling & Terminations |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works ACDB Main & Sub-Panels Final Cabling & Terminations | 9 | E0ACDB | C000 | 00C9 | C000E0ACDB00C9
4028 | 4028 | 4028 | 4028 | SA24M005 | DCDB Main & Sub-Panels |  | 5 | -1 | 0 |  |  | X
4029 | 4029 | 4029 | 4029 | SA24M005 | Marking of Panels |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works DCDB Main & Sub-Panels Marking of Panels | 1 | E0DCDB | C000 | 00C1 | C000E0DCDB00C1
4030 | 4030 | 4030 | 4030 | SA24M005 | Erection of supporting structures |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works DCDB Main & Sub-Panels Erection of supporting structures | 2 | E0DCDB | C000 | 00C2 | C000E0DCDB00C2
4031 | 4031 | 4031 | 4031 | SA24M005 | Installtion of Panels |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works DCDB Main & Sub-Panels Installtion of Panels | 3 | E0DCDB | C000 | 00C3 | C000E0DCDB00C3
4032 | 4032 | 4032 | 4032 | SA24M005 | Busbar coupling |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works DCDB Main & Sub-Panels Busbar coupling | 4 | E0DCDB | C000 | 00C4 | C000E0DCDB00C4
4033 | 4033 | 4033 | 4033 | SA24M005 | Earthing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works DCDB Main & Sub-Panels Earthing | 5 | E0DCDB | C000 | 00C5 | C000E0DCDB00C5
4034 | 4034 | 4034 | 4034 | SA24M005 | Panel Wiring and Connections |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works DCDB Main & Sub-Panels Panel Wiring and Connections | 6 | E0DCDB | C000 | 00C6 | C000E0DCDB00C6
4035 | 4035 | 4035 | 4035 | SA24M005 | Electrical components (CB, Fuses, Contactors, Relays, Meters) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works DCDB Main & Sub-Panels Electrical components (CB, Fuses, Contactors, Relays, Meters) | 7 | E0DCDB | C000 | 00C7 | C000E0DCDB00C7
4036 | 4036 | 4036 | 4036 | SA24M005 | DC Supply availability |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works DCDB Main & Sub-Panels DC Supply availability | 8 | E0DCDB | C000 | 00C8 | C000E0DCDB00C8
4037 | 4037 | 4037 | 4037 | SA24M005 | Final Cabling & Terminations |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works DCDB Main & Sub-Panels Final Cabling & Terminations | 9 | E0DCDB | C000 | 00C9 | C000E0DCDB00C9
4038 | 4038 | 4038 | 4038 | SA24M005 | LV Power Cables |  | 5 | -1 | 0 |  |  | X
4039 | 4039 | 4039 | 4039 | SA24M005 | Installation of cable trays |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works LV Power Cables Installation of cable trays | 1 | E0LVC | C000 | 00C1 | C000#kdfi00C1
4040 | 4040 | 4040 | 4040 | SA24M005 | Cable laying |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works LV Power Cables Cable laying | 2 | E0LVC | C000 | 00C2 | C000#kdfi00C2
4041 | 4041 | 4041 | 4041 | SA24M005 | Cable Termination |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works LV Power Cables Cable Termination | 3 | E0LVC | C000 | 00C3 | C000#kdfi00C3
4042 | 4042 | 4042 | 4042 | SA24M005 | Earthing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works LV Power Cables Earthing | 4 | E0LVC | C000 | 00C4 | C000#kdfi00C4
4043 | 4043 | 4043 | 4043 | SA24M005 | LV Control Cables |  | 5 | -1 | 0 |  |  | X | C000#kdfi
4044 | 4044 | 4044 | 4044 | SA24M005 | Installation of cable trays |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works LV Control Cables Installation of cable trays | 1 | E0LVC | C000 | 00C1 | C000#tPoJ00C1
4045 | 4045 | 4045 | 4045 | SA24M005 | Cable laying |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works LV Control Cables Cable laying | 2 | E0LVC | C000 | 00C2 | C000#tPoJ00C2
4046 | 4046 | 4046 | 4046 | SA24M005 | Cable Termination |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works LV Control Cables Cable Termination | 3 | E0LVC | C000 | 00C3 | C000#tPoJ00C3
4047 | 4047 | 4047 | 4047 | SA24M005 | Earthing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works LV Control Cables Earthing | 4 | E0LVC | C000 | 00C4 | C000#tPoJ00C4
4048 | 4048 | 4048 | 4048 | SA24M005 | Sheilded Instrumentation Cables |  | 5 | -1 | 0 |  |  | X | C000#tPoJ
4049 | 4049 | 4049 | 4049 | SA24M005 | Installation of cable trays |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Sheilded Instrumentation Cables Installation of cable trays | 1 | E0SHI | C000 | 00C1 | C000E0SHI00C1
4050 | 4050 | 4050 | 4050 | SA24M005 | Cable laying |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Sheilded Instrumentation Cables Cable laying | 2 | E0SHI | C000 | 00C2 | C000E0SHI00C2
4051 | 4051 | 4051 | 4051 | SA24M005 | Cable Termination |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Sheilded Instrumentation Cables Cable Termination | 3 | E0SHI | C000 | 00C3 | C000E0SHI00C3
4052 | 4052 | 4052 | 4052 | SA24M005 | Earthing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Sheilded Instrumentation Cables Earthing | 4 | E0SHI | C000 | 00C4 | C000E0SHI00C4
4053 | 4053 | 4053 | 4053 | SA24M005 | LV Cable Accessories |  | 5 | -1 | 0 |  |  | X
4054 | 4054 | 4054 | 4054 | SA24M005 | Cable cleats, Joints and Terminations |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works LV Cable Accessories Cable cleats, Joints and Terminations | 1 | LVCA | C000 | 00C1 | C000LVCA00C1
4055 | 4055 | 4055 | 4055 | SA24M005 | Cable Markers and Identification |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works LV Cable Accessories Cable Markers and Identification | 2 | LVCA | C000 | 00C2 | C000LVCA00C2
4056 | 4056 | 4056 | 4056 | SA24M005 | Cable Protection Systems |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works LV Cable Accessories Cable Protection Systems | 3 | LVCA | C000 | 00C3 | C000LVCA00C3
4057 | 4057 | 4057 | 4057 | SA24M005 | Cable Dressing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works LV Cable Accessories Cable Dressing | 4 | LVCA | C000 | 00C4 | C000LVCA00C4
4058 | 4058 | 4058 | 4058 | SA24M005 | Lighting System |  | 5 | -1 | 0 |  |  | X
4059 | 4059 | 4059 | 4059 | SA24M005 | Installation of Lighting Panels |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Lighting System Installation of Lighting Panels | 1 | E0LGP | C000 | 00C1 | C000E0LGP00C1
4060 | 4060 | 4060 | 4060 | SA24M005 | Installation of Outdoor Lighting Poles |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Lighting System Installation of Outdoor Lighting Poles | 2 | E0LGP | C000 | 00C2 | C000E0LGP00C2
4061 | 4061 | 4061 | 4061 | SA24M005 | Installation of Light Fittings |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Lighting System Installation of Light Fittings | 3 | E0LGP | C000 | 00C3 | C000E0LGP00C3
4062 | 4062 | 4062 | 4062 | SA24M005 | Installation of Receptacles |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Lighting System Installation of Receptacles | 4 | E0LGP | C000 | 00C4 | C000E0LGP00C4
4063 | 4063 | 4063 | 4063 | SA24M005 | Lighting conduits, Junction Boxes & Accessories |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Lighting System Lighting conduits, Junction Boxes & Accessories | 5 | E0LGP | C000 | 00C5 | C000E0LGP00C5
4064 | 4064 | 4064 | 4064 | SA24M005 | Lighting & Sheilding system |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Lighting System Lighting & Sheilding system | 6 | E0LGP | C000 | 00C6 | C000E0LGP00C6
4065 | 4065 | 4065 | 4065 | SA24M005 | Outdoor Equipments |  | 5 | -1 | 0 |  |  | X
4066 | 4066 | 4066 | 4066 | SA24M005 | Installation of grounding grid & Testing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Outdoor Equipments Installation of grounding grid & Testing | 1 | E0GRD | C000 | 00C1 | C000E0GRD00C1
4067 | 4067 | 4067 | 4067 | SA24M005 | EHV & MV Cable laying |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Outdoor Equipments EHV & MV Cable laying | 2 | E0GRD | C000 | 00C2 | C000E0GRD00C2
4068 | 4068 | 4068 | 4068 | SA24M005 | Termination of cable both sides |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Outdoor Equipments Termination of cable both sides | 3 | E0GRD | C000 | 00C3 | C000E0GRD00C3
4069 | 4069 | 4069 | 4069 | SA24M005 | LV/Control/Instrument Cable Pulling |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Outdoor Equipments LV/Control/Instrument Cable Pulling | 4 | E0GRD | C000 | 00C4 | C000E0GRD00C4
4070 | 4070 | 4070 | 4070 | SA24M005 | 380kV Gantry Towers |  | 5 | -1 | 0 |  |  | X
4071 | 4071 | 4071 | 4071 | SA24M005 | Tower- 1 |  | 6 | -1 | 0 |  |  | X
4072 | 4072 | 4072 | 4072 | SA24M005 | Erection of structure |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 1 Erection of structure | 1 | E0GWT0001 | C000 | 00C1 | C000E0GWT000100C1
4073 | 4073 | 4073 | 4073 | SA24M005 | Conductor stringing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 1 Conductor stringing | 2 | E0GWT0001 | C000 | 00C2 | C000E0GWT000100C2
4074 | 4074 | 4074 | 4074 | SA24M005 | Installing of erection accessories |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 1 Installing of erection accessories | 3 | E0GWT0001 | C000 | 00C3 | C000E0GWT000100C3
4075 | 4075 | 4075 | 4075 | SA24M005 | Tack Welding / Tower Tightning & Pal nut Fixing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 1 Tack Welding / Tower Tightning & Pal nut Fixing | 4 | E0GWT0001 | C000 | 00C4 | C000E0GWT000100C4
4076 | 4076 | 4076 | 4076 | SA24M005 | Earthing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 1 Earthing | 5 | E0GWT0001 | C000 | 00C5 | C000E0GWT000100C5
4077 | 4077 | 4077 | 4077 | SA24M005 | Tower- 2 |  | 6 | -1 | 0 |  |  | X
4078 | 4078 | 4078 | 4078 | SA24M005 | Erection of structure |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 2 Erection of structure | 1 | E0GNT | C000 | 00C1 | C000#qEDi00C1
4079 | 4079 | 4079 | 4079 | SA24M005 | Conductor stringing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 2 Conductor stringing | 2 | E0GNT | C000 | 00C2 | C000#qEDi00C2
4080 | 4080 | 4080 | 4080 | SA24M005 | Installing of erection accessories |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 2 Installing of erection accessories | 3 | E0GNT | C000 | 00C3 | C000#qEDi00C3
4081 | 4081 | 4081 | 4081 | SA24M005 | Tack Welding / Tower Tightning & Pal nut Fixing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 2 Tack Welding / Tower Tightning & Pal nut Fixing | 4 | E0GNT | C000 | 00C4 | C000#qEDi00C4
4082 | 4082 | 4082 | 4082 | SA24M005 | Earthing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 2 Earthing | 5 | E0GNT | C000 | 00C5 | C000#qEDi00C5
4083 | 4083 | 4083 | 4083 | SA24M005 | Tower- 3 |  | 6 | -1 | 0 |  |  | X | C000#qEDi
4084 | 4084 | 4084 | 4084 | SA24M005 | Erection of structure |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 3 Erection of structure | 1 | E0GNT | C000 | 00C1 | C000#VXUp00C1
4085 | 4085 | 4085 | 4085 | SA24M005 | Conductor stringing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 3 Conductor stringing | 2 | E0GNT | C000 | 00C2 | C000#VXUp00C2
4086 | 4086 | 4086 | 4086 | SA24M005 | Installing of erection accessories |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 3 Installing of erection accessories | 3 | E0GNT | C000 | 00C3 | C000#VXUp00C3
4087 | 4087 | 4087 | 4087 | SA24M005 | Tack Welding / Tower Tightning & Pal nut Fixing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 3 Tack Welding / Tower Tightning & Pal nut Fixing | 4 | E0GNT | C000 | 00C4 | C000#VXUp00C4
4088 | 4088 | 4088 | 4088 | SA24M005 | Earthing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 3 Earthing | 5 | E0GNT | C000 | 00C5 | C000#VXUp00C5
4089 | 4089 | 4089 | 4089 | SA24M005 | Tower- 4 |  | 6 | -1 | 0 |  |  | X | C000#VXUp
4090 | 4090 | 4090 | 4090 | SA24M005 | Erection of structure |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 4 Erection of structure | 1 | E0GWT04 | C000 | 00C1 | C000E0GWT0400C1
4091 | 4091 | 4091 | 4091 | SA24M005 | Conductor stringing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 4 Conductor stringing | 2 | E0GWT04 | C000 | 00C2 | C000E0GWT0400C2
4092 | 4092 | 4092 | 4092 | SA24M005 | Installing of erection accessories |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 4 Installing of erection accessories | 3 | E0GWT04 | C000 | 00C3 | C000E0GWT0400C3
4093 | 4093 | 4093 | 4093 | SA24M005 | Tack Welding / Tower Tightning & Pal nut Fixing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 4 Tack Welding / Tower Tightning & Pal nut Fixing | 4 | E0GWT04 | C000 | 00C4 | C000E0GWT0400C4
4094 | 4094 | 4094 | 4094 | SA24M005 | Earthing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 4 Earthing | 5 | E0GWT04 | C000 | 00C5 | C000E0GWT0400C5
4095 | 4095 | 4095 | 4095 | SA24M005 | Tower- 5 |  | 6 | -1 | 0 |  |  | X
4096 | 4096 | 4096 | 4096 | SA24M005 | Erection of structure |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 5 Erection of structure | 1 | E0GNT05 | C000 | 00C1 | C000E0GNT0500C1
4097 | 4097 | 4097 | 4097 | SA24M005 | Conductor stringing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 5 Conductor stringing | 2 | E0GNT05 | C000 | 00C2 | C000E0GNT0500C2
4098 | 4098 | 4098 | 4098 | SA24M005 | Installing of erection accessories |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 5 Installing of erection accessories | 3 | E0GNT05 | C000 | 00C3 | C000E0GNT0500C3
4099 | 4099 | 4099 | 4099 | SA24M005 | Tack Welding / Tower Tightning & Pal nut Fixing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 5 Tack Welding / Tower Tightning & Pal nut Fixing | 4 | E0GNT05 | C000 | 00C4 | C000E0GNT0500C4
4100 | 4100 | 4100 | 4100 | SA24M005 | Earthing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 5 Earthing | 5 | E0GNT05 | C000 | 00C5 | C000E0GNT0500C5
4101 | 4101 | 4101 | 4101 | SA24M005 | Tower- 6 |  | 6 | -1 | 0 |  |  | X
4102 | 4102 | 4102 | 4102 | SA24M005 | Erection of structure |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 6 Erection of structure | 1 | E0GNT06 | C000 | 00C1 | C000E0GNT0600C1
4103 | 4103 | 4103 | 4103 | SA24M005 | Conductor stringing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 6 Conductor stringing | 2 | E0GNT06 | C000 | 00C2 | C000E0GNT0600C2
4104 | 4104 | 4104 | 4104 | SA24M005 | Installing of erection accessories |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 6 Installing of erection accessories | 3 | E0GNT06 | C000 | 00C3 | C000E0GNT0600C3
4105 | 4105 | 4105 | 4105 | SA24M005 | Tack Welding / Tower Tightning & Pal nut Fixing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 6 Tack Welding / Tower Tightning & Pal nut Fixing | 4 | E0GNT06 | C000 | 00C4 | C000E0GNT0600C4
4106 | 4106 | 4106 | 4106 | SA24M005 | Earthing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 6 Earthing | 5 | E0GNT06 | C000 | 00C5 | C000E0GNT0600C5
4107 | 4107 | 4107 | 4107 | SA24M005 | Tower- 7 |  | 6 | -1 | 0 |  |  | X
4108 | 4108 | 4108 | 4108 | SA24M005 | Erection of structure |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 7 Erection of structure | 1 | E0GWT07 | C000 | 00C1 | C000E0GWT0700C1
4109 | 4109 | 4109 | 4109 | SA24M005 | Conductor stringing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 7 Conductor stringing | 2 | E0GWT07 | C000 | 00C2 | C000E0GWT0700C2
4110 | 4110 | 4110 | 4110 | SA24M005 | Installing of erection accessories |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 7 Installing of erection accessories | 3 | E0GWT07 | C000 | 00C3 | C000E0GWT0700C3
4111 | 4111 | 4111 | 4111 | SA24M005 | Tack Welding / Tower Tightning & Pal nut Fixing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 7 Tack Welding / Tower Tightning & Pal nut Fixing | 4 | E0GWT07 | C000 | 00C4 | C000E0GWT0700C4
4112 | 4112 | 4112 | 4112 | SA24M005 | Earthing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 7 Earthing | 5 | E0GWT07 | C000 | 00C5 | C000E0GWT0700C5
4113 | 4113 | 4113 | 4113 | SA24M005 | Tower- 8 |  | 6 | -1 | 0 |  |  | X
4114 | 4114 | 4114 | 4114 | SA24M005 | Erection of structure |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 8 Erection of structure | 1 | E0GNT | C000 | 00C1 | C000#tVeu00C1
4115 | 4115 | 4115 | 4115 | SA24M005 | Conductor stringing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 8 Conductor stringing | 2 | E0GNT | C000 | 00C2 | C000#tVeu00C2
4116 | 4116 | 4116 | 4116 | SA24M005 | Installing of erection accessories |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 8 Installing of erection accessories | 3 | E0GNT | C000 | 00C3 | C000#tVeu00C3
4117 | 4117 | 4117 | 4117 | SA24M005 | Tack Welding / Tower Tightning & Pal nut Fixing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 8 Tack Welding / Tower Tightning & Pal nut Fixing | 4 | E0GNT | C000 | 00C4 | C000#tVeu00C4
4118 | 4118 | 4118 | 4118 | SA24M005 | Earthing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 8 Earthing | 5 | E0GNT | C000 | 00C5 | C000#tVeu00C5
4119 | 4119 | 4119 | 4119 | SA24M005 | Tower- 9 |  | 6 | -1 | 0 |  |  | X | C000#tVeu
4120 | 4120 | 4120 | 4120 | SA24M005 | Erection of structure |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 9 Erection of structure | 1 | E0GNT | C000 | 00C1 | C000#kwlT00C1
4121 | 4121 | 4121 | 4121 | SA24M005 | Conductor stringing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 9 Conductor stringing | 2 | E0GNT | C000 | 00C2 | C000#kwlT00C2
4122 | 4122 | 4122 | 4122 | SA24M005 | Installing of erection accessories |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 9 Installing of erection accessories | 3 | E0GNT | C000 | 00C3 | C000#kwlT00C3
4123 | 4123 | 4123 | 4123 | SA24M005 | Tack Welding / Tower Tightning & Pal nut Fixing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 9 Tack Welding / Tower Tightning & Pal nut Fixing | 4 | E0GNT | C000 | 00C4 | C000#kwlT00C4
4124 | 4124 | 4124 | 4124 | SA24M005 | Earthing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 9 Earthing | 5 | E0GNT | C000 | 00C5 | C000#kwlT00C5
4125 | 4125 | 4125 | 4125 | SA24M005 | Tower- 10 |  | 6 | -1 | 0 |  |  | X | C000#kwlT
4126 | 4126 | 4126 | 4126 | SA24M005 | Erection of structure |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 10 Erection of structure | 1 | E0GNT | C000 | 00C1 | C000#lMMA00C1
4127 | 4127 | 4127 | 4127 | SA24M005 | Conductor stringing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 10 Conductor stringing | 2 | E0GNT | C000 | 00C2 | C000#lMMA00C2
4128 | 4128 | 4128 | 4128 | SA24M005 | Installing of erection accessories |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 10 Installing of erection accessories | 3 | E0GNT | C000 | 00C3 | C000#lMMA00C3
4129 | 4129 | 4129 | 4129 | SA24M005 | Tack Welding / Tower Tightning & Pal nut Fixing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 10 Tack Welding / Tower Tightning & Pal nut Fixing | 4 | E0GNT | C000 | 00C4 | C000#lMMA00C4
4130 | 4130 | 4130 | 4130 | SA24M005 | Earthing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 10 Earthing | 5 | E0GNT | C000 | 00C5 | C000#lMMA00C5
4131 | 4131 | 4131 | 4131 | SA24M005 | Tower- 11 |  | 6 | -1 | 0 |  |  | X | C000#lMMA
4132 | 4132 | 4132 | 4132 | SA24M005 | Erection of structure |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 11 Erection of structure | 1 | E0GNT | C000 | 00C1 | C000#Atsu00C1
4133 | 4133 | 4133 | 4133 | SA24M005 | Conductor stringing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 11 Conductor stringing | 2 | E0GNT | C000 | 00C2 | C000#Atsu00C2
4134 | 4134 | 4134 | 4134 | SA24M005 | Installing of erection accessories |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 11 Installing of erection accessories | 3 | E0GNT | C000 | 00C3 | C000#Atsu00C3
4135 | 4135 | 4135 | 4135 | SA24M005 | Tack Welding / Tower Tightning & Pal nut Fixing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 11 Tack Welding / Tower Tightning & Pal nut Fixing | 4 | E0GNT | C000 | 00C4 | C000#Atsu00C4
4136 | 4136 | 4136 | 4136 | SA24M005 | Earthing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works 380kV Gantry Towers Tower- 11 Earthing | 5 | E0GNT | C000 | 00C5 | C000#Atsu00C5
4137 | 4137 | 4137 | 4137 | SA24M005 | Protection & Metering / Annunciation System |  | 5 | -1 | 0 |  |  | X | C000#Atsu
4138 | 4138 | 4138 | 4138 | SA24M005 | 380-230kV OHTL Feeder Protection Without Shunt Reactor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Protection & Metering / Annunciation System 380-230kV OHTL Feeder Protection Without Shunt Reactor | 1 | E0PRM | C000 | 00C1 | C000E0PRM00C1
4139 | 4139 | 4139 | 4139 | SA24M005 | 380-230kV OHTL Feeder Protection With Shunt Reactor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Protection & Metering / Annunciation System 380-230kV OHTL Feeder Protection With Shunt Reactor | 2 | E0PRM | C000 | 00C2 | C000E0PRM00C2
4140 | 4140 | 4140 | 4140 | SA24M005 | 380kV Generating Bays for SUGT Connection Protection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Protection & Metering / Annunciation System 380kV Generating Bays for SUGT Connection Protection | 3 | E0PRM | C000 | 00C3 | C000E0PRM00C3
4141 | 4141 | 4141 | 4141 | SA24M005 | 380-230kV Bus Shunt Reactor Protection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Protection & Metering / Annunciation System 380-230kV Bus Shunt Reactor Protection | 4 | E0PRM | C000 | 00C4 | C000E0PRM00C4
4142 | 4142 | 4142 | 4142 | SA24M005 | 380kV Bus Bar Protection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Protection & Metering / Annunciation System 380kV Bus Bar Protection | 5 | E0PRM | C000 | 00C5 | C000E0PRM00C5
4143 | 4143 | 4143 | 4143 | SA24M005 | 380kV Circuit Breaker Fail Protection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Protection & Metering / Annunciation System 380kV Circuit Breaker Fail Protection | 6 | E0PRM | C000 | 00C6 | C000E0PRM00C6
4144 | 4144 | 4144 | 4144 | SA24M005 | 13.8kV Feeder Protection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Protection & Metering / Annunciation System 13.8kV Feeder Protection | 7 | E0PRM | C000 | 00C7 | C000E0PRM00C7
4145 | 4145 | 4145 | 4145 | SA24M005 | AR & I/T and U/O Voltage Protection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Protection & Metering / Annunciation System AR & I/T and U/O Voltage Protection | 8 | E0PRM | C000 | 00C8 | C000E0PRM00C8
4146 | 4146 | 4146 | 4146 | SA24M005 | PD Protection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Protection & Metering / Annunciation System PD Protection | 9 | E0PRM | C000 | 00C9 | C000E0PRM00C9
4147 | 4147 | 4147 | 4147 | SA24M005 | ABTS & ACCS |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Protection & Metering / Annunciation System ABTS & ACCS | 10 | E0PRM | C000 | 0C10 | C000E0PRM0C10
4148 | 4148 | 4148 | 4148 | SA24M005 | Transient Fault Recorder Panel (TFR) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Protection & Metering / Annunciation System Transient Fault Recorder Panel (TFR) | 11 | E0PRM | C000 | 0C11 | C000E0PRM0C11
4149 | 4149 | 4149 | 4149 | SA24M005 | RTCC Panels- Automatic Voltage Regulator (AVR) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Protection & Metering / Annunciation System RTCC Panels- Automatic Voltage Regulator (AVR) | 12 | E0PRM | C000 | 0C12 | C000E0PRM0C12
4150 | 4150 | 4150 | 4150 | SA24M005 | Synchro check Relay Panel |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Protection & Metering / Annunciation System Synchro check Relay Panel | 13 | E0PRM | C000 | 0C13 | C000E0PRM0C13
4151 | 4151 | 4151 | 4151 | SA24M005 | SST Protection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Protection & Metering / Annunciation System SST Protection | 14 | E0PRM | C000 | 0C14 | C000E0PRM0C14
4152 | 4152 | 4152 | 4152 | SA24M005 | Energy Metering System |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Protection & Metering / Annunciation System Energy Metering System | 15 | E0PRM | C000 | 0C15 | C000E0PRM0C15
4153 | 4153 | 4153 | 4153 | SA24M005 | AMI |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Protection & Metering / Annunciation System AMI | 16 | E0PRM | C000 | 0C16 | C000E0PRM0C16
4154 | 4154 | 4154 | 4154 | SA24M005 | Alarm & Annunciator System |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Protection & Metering / Annunciation System Alarm & Annunciator System | 17 | E0PRM | C000 | 0C17 | C000E0PRM0C17
4155 | 4155 | 4155 | 4155 | SA24M005 | Communication System |  | 5 | -1 | 0 |  |  | X
4156 | 4156 | 4156 | 4156 | SA24M005 | Installation of 48V Battery Bank |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Communication System Installation of 48V Battery Bank | 1 | ECOMM | C000 | 00C1 | C000ECOMM00C1
4157 | 4157 | 4157 | 4157 | SA24M005 | Installation of 40V Battery Chargers |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Communication System Installation of 40V Battery Chargers | 2 | ECOMM | C000 | 00C2 | C000ECOMM00C2
4158 | 4158 | 4158 | 4158 | SA24M005 | Installation of DC Panel |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Communication System Installation of DC Panel | 3 | ECOMM | C000 | 00C3 | C000ECOMM00C3
4159 | 4159 | 4159 | 4159 | SA24M005 | Installation of SDH Panels |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Communication System Installation of SDH Panels | 4 | ECOMM | C000 | 00C4 | C000ECOMM00C4
4160 | 4160 | 4160 | 4160 | SA24M005 | Installation of DVM Panels |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Communication System Installation of DVM Panels | 5 | ECOMM | C000 | 00C5 | C000ECOMM00C5
4161 | 4161 | 4161 | 4161 | SA24M005 | Installtion of MDF Panels |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Communication System Installtion of MDF Panels | 6 | ECOMM | C000 | 00C6 | C000ECOMM00C6
4162 | 4162 | 4162 | 4162 | SA24M005 | Communication Grade DC Power System |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Communication System Communication Grade DC Power System | 7 | ECOMM | C000 | 00C7 | C000ECOMM00C7
4163 | 4163 | 4163 | 4163 | SA24M005 | P Telephony System Requirements |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Communication System P Telephony System Requirements | 8 | ECOMM | C000 | 00C8 | C000ECOMM00C8
4164 | 4164 | 4164 | 4164 | SA24M005 | PDS/PABX Premises Distribution system |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Communication System PDS/PABX Premises Distribution system | 9 | ECOMM | C000 | 00C9 | C000ECOMM00C9
4165 | 4165 | 4165 | 4165 | SA24M005 | Duct Bank System |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Communication System Duct Bank System | 10 | ECOMM | C000 | 0C10 | C000ECOMM0C10
4166 | 4166 | 4166 | 4166 | SA24M005 | OFMR |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Communication System OFMR | 11 | ECOMM | C000 | 0C11 | C000ECOMM0C11
4167 | 4167 | 4167 | 4167 | SA24M005 | Medium Density FOTE for HV S/S |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Communication System Medium Density FOTE for HV S/S | 12 | ECOMM | C000 | 0C12 | C000ECOMM0C12
4168 | 4168 | 4168 | 4168 | SA24M005 | MPLS- TP |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Communication System MPLS- TP | 13 | ECOMM | C000 | 0C13 | C000ECOMM0C13
4169 | 4169 | 4169 | 4169 | SA24M005 | PSE Module |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Communication System PSE Module | 14 | ECOMM | C000 | 0C14 | C000ECOMM0C14
4170 | 4170 | 4170 | 4170 | SA24M005 | SAS / SCADA System |  | 5 | -1 | 0 |  |  | X
4171 | 4171 | 4171 | 4171 | SA24M005 | Erection of SAS Panels |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works SAS / SCADA System Erection of SAS Panels | 1 | ESAS | C000 | 00C1 | C000ESAS00C1
4172 | 4172 | 4172 | 4172 | SA24M005 | Erection of SAS Fiber Patch Panels |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works SAS / SCADA System Erection of SAS Fiber Patch Panels | 2 | ESAS | C000 | 00C2 | C000ESAS00C2
4173 | 4173 | 4173 | 4173 | SA24M005 | Erection of SAS IFC Panels |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works SAS / SCADA System Erection of SAS IFC Panels | 3 | ESAS | C000 | 00C3 | C000ESAS00C3
4174 | 4174 | 4174 | 4174 | SA24M005 | Erection of SAS Fiber Cables |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works SAS / SCADA System Erection of SAS Fiber Cables | 4 | ESAS | C000 | 00C4 | C000ESAS00C4
4175 | 4175 | 4175 | 4175 | SA24M005 | Installation SAS Accessories |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works SAS / SCADA System Installation SAS Accessories | 5 | ESAS | C000 | 00C5 | C000ESAS00C5
4176 | 4176 | 4176 | 4176 | SA24M005 | LED Display Monitors, Associate KVM accessories |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works SAS / SCADA System LED Display Monitors, Associate KVM accessories | 6 | ESAS | C000 | 00C6 | C000ESAS00C6
4177 | 4177 | 4177 | 4177 | SA24M005 | Installation of DSM Panel |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works SAS / SCADA System Installation of DSM Panel | 7 | ESAS | C000 | 00C7 | C000ESAS00C7
4178 | 4178 | 4178 | 4178 | SA24M005 | Earthing Works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works SAS / SCADA System Earthing Works | 8 | ESAS | C000 | 00C8 | C000ESAS00C8
4179 | 4179 | 4179 | 4179 | SA24M005 | Interpanel Wiring of SAS Panels |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works SAS / SCADA System Interpanel Wiring of SAS Panels | 9 | ESAS | C000 | 00C9 | C000ESAS00C9
4180 | 4180 | 4180 | 4180 | SA24M005 | Control Desk installation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works SAS / SCADA System Control Desk installation | 10 | ESAS | C000 | 0C10 | C000ESAS0C10
4181 | 4181 | 4181 | 4181 | SA24M005 | GPS & Antenna fixing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works SAS / SCADA System GPS & Antenna fixing | 11 | ESAS | C000 | 0C11 | C000ESAS0C11
4182 | 4182 | 4182 | 4182 | SA24M005 | AC/DC cable laying & termination |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works SAS / SCADA System AC/DC cable laying & termination | 12 | ESAS | C000 | 0C12 | C000ESAS0C12
4183 | 4183 | 4183 | 4183 | SA24M005 | Inverter Commissioning |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works SAS / SCADA System Inverter Commissioning | 13 | ESAS | C000 | 0C13 | C000ESAS0C13
4184 | 4184 | 4184 | 4184 | SA24M005 | FO & Patch card Laying & Splicing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works SAS / SCADA System FO & Patch card Laying & Splicing | 14 | ESAS | C000 | 0C14 | C000ESAS0C14
4185 | 4185 | 4185 | 4185 | SA24M005 | OEM Engineer Availability |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works SAS / SCADA System OEM Engineer Availability | 15 | ESAS | C000 | 0C15 | C000ESAS0C15
4186 | 4186 | 4186 | 4186 | SA24M005 | Control cable laying & termination |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works SAS / SCADA System Control cable laying & termination | 16 | ESAS | C000 | 0C16 | C000ESAS0C16
4187 | 4187 | 4187 | 4187 | SA24M005 | LDC Communication |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works SAS / SCADA System LDC Communication | 17 | ESAS | C000 | 0C17 | C000ESAS0C17
4188 | 4188 | 4188 | 4188 | SA24M005 | HVAC System |  | 5 | -1 | 0 |  |  | X
4189 | 4189 | 4189 | 4189 | SA24M005 | Installation of PACU Units |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works HVAC System Installation of PACU Units | 1 | EHVAC | C000 | 00C1 | C000EHVAC00C1
4190 | 4190 | 4190 | 4190 | SA24M005 | Installation of Ducts |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works HVAC System Installation of Ducts | 2 | EHVAC | C000 | 00C2 | C000EHVAC00C2
4191 | 4191 | 4191 | 4191 | SA24M005 | Installation of Ventilation Fans |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works HVAC System Installation of Ventilation Fans | 3 | EHVAC | C000 | 00C3 | C000EHVAC00C3
4192 | 4192 | 4192 | 4192 | SA24M005 | Installation of HVAC Control Panels |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works HVAC System Installation of HVAC Control Panels | 4 | EHVAC | C000 | 00C4 | C000EHVAC00C4
4193 | 4193 | 4193 | 4193 | SA24M005 | Installation of HVAC Accessories |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works HVAC System Installation of HVAC Accessories | 5 | EHVAC | C000 | 00C5 | C000EHVAC00C5
4194 | 4194 | 4194 | 4194 | SA24M005 | Installation of Split type Air Conditioning Units |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works HVAC System Installation of Split type Air Conditioning Units | 6 | EHVAC | C000 | 00C6 | C000EHVAC00C6
4195 | 4195 | 4195 | 4195 | SA24M005 | Fire Fighting System |  | 5 | -1 | 0 |  |  | X
4196 | 4196 | 4196 | 4196 | SA24M005 | Installation of Fire Detection System |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Fire Fighting System Installation of Fire Detection System | 1 | EFRFS | C000 | 00C1 | C000EFRFS00C1
4197 | 4197 | 4197 | 4197 | SA24M005 | Installation of Fire Alarm System |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Fire Fighting System Installation of Fire Alarm System | 2 | EFRFS | C000 | 00C2 | C000EFRFS00C2
4198 | 4198 | 4198 | 4198 | SA24M005 | Installation of Fire Extinguisher System |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Fire Fighting System Installation of Fire Extinguisher System | 3 | EFRFS | C000 | 00C3 | C000EFRFS00C3
4199 | 4199 | 4199 | 4199 | SA24M005 | Installation of Fire Hydrant System |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Fire Fighting System Installation of Fire Hydrant System | 4 | EFRFS | C000 | 00C4 | C000EFRFS00C4
4200 | 4200 | 4200 | 4200 | SA24M005 | Installation of Wet Sprinkler System |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Fire Fighting System Installation of Wet Sprinkler System | 5 | EFRFS | C000 | 00C5 | C000EFRFS00C5
4201 | 4201 | 4201 | 4201 | SA24M005 | Installation of Clean Agent Fire Extinguishing System |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Fire Fighting System Installation of Clean Agent Fire Extinguishing System | 6 | EFRFS | C000 | 00C6 | C000EFRFS00C6
4202 | 4202 | 4202 | 4202 | SA24M005 | HCIS System |  | 5 | -1 | 0 |  |  | X
4203 | 4203 | 4203 | 4203 | SA24M005 | Installation of CCTV with Security Camera |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works HCIS System Installation of CCTV with Security Camera | 1 | EHCIS | C000 | 00C1 | C000EHCIS00C1
4204 | 4204 | 4204 | 4204 | SA24M005 | Inter Connection Cabling works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works HCIS System Inter Connection Cabling works | 2 | EHCIS | C000 | 00C2 | C000EHCIS00C2
4205 | 4205 | 4205 | 4205 | SA24M005 | Earthing Works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works HCIS System Earthing Works | 3 | EHCIS | C000 | 00C3 | C000EHCIS00C3
4206 | 4206 | 4206 | 4206 | SA24M005 | Other HCIS Works (Complete in all respect) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works HCIS System Other HCIS Works (Complete in all respect) | 4 | EHCIS | C000 | 00C4 | C000EHCIS00C4
4207 | 4207 | 4207 | 4207 | SA24M005 | Misc. / Other works |  | 5 | -1 | 0 |  |  | X
4208 | 4208 | 4208 | 4208 | SA24M005 | Misc. Other works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Electrical Works Misc. / Other works Misc. Other works | 1 | E0MISC | C000 | 00C1 | C000E0MISC00C1
4209 | 4209 | 4209 | 4209 | SA24M005 | Mechanical Works |  | 4 | -1 | 0 |  |  | X | C000E0MISC
4210 | 4210 | 4210 | 4210 | SA24M005 | 380KV GIS Building |  | 5 | -1 | 0 |  |  | X | C000E0MISC
4211 | 4211 | 4211 | 4211 | SA24M005 | Installation of EOT Crane with load test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Mechanical Works 380KV GIS Building Installation of EOT Crane with load test | 1 | 0E0CR | C000 | 00C1 | C0000E0CR00C1
4212 | 4212 | 4212 | 4212 | SA24M005 | Installation of HVAC Double skin Duct Indoor with all accessories |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Mechanical Works 380KV GIS Building Installation of HVAC Double skin Duct Indoor with all accessories | 2 | 0E0CR | C000 | 00C2 | C0000E0CR00C2
4213 | 4213 | 4213 | 4213 | SA24M005 | Installation of conduits , cable pulling and Detectors of Fire Alarm & Fire Fighting System |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Mechanical Works 380KV GIS Building Installation of conduits , cable pulling and Detectors of Fire Alarm & Fire Fighting System | 3 | 0E0CR | C000 | 00C3 | C0000E0CR00C3
4214 | 4214 | 4214 | 4214 | SA24M005 | Installation of Fire Alarm FACP / DDC panels |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Mechanical Works 380KV GIS Building Installation of Fire Alarm FACP / DDC panels | 4 | 0E0CR | C000 | 00C4 | C0000E0CR00C4
4215 | 4215 | 4215 | 4215 | SA24M005 | Installation of HVAC Double skin Duct with outdoor with all accessories |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Mechanical Works 380KV GIS Building Installation of HVAC Double skin Duct with outdoor with all accessories | 5 | 0E0CR | C000 | 00C5 | C0000E0CR00C5
4216 | 4216 | 4216 | 4216 | SA24M005 | Installation of Smoke purging / Exhaust Fans |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Mechanical Works 380KV GIS Building Installation of Smoke purging / Exhaust Fans | 6 | 0E0CR | C000 | 00C6 | C0000E0CR00C6
4217 | 4217 | 4217 | 4217 | SA24M005 | Opening Closing with Fire Stop Material |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Mechanical Works 380KV GIS Building Opening Closing with Fire Stop Material | 7 | 0E0CR | C000 | 00C7 | C0000E0CR00C7
4218 | 4218 | 4218 | 4218 | SA24M005 | Control Room Building |  | 5 | -1 | 0 |  |  | X
4219 | 4219 | 4219 | 4219 | SA24M005 | Installation of HVAC Double skin Duct Indoor with all accessories |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Mechanical Works Control Room Building Installation of HVAC Double skin Duct Indoor with all accessories | 1 | C0CRB0HVAC | C000 | 00C1 | C000C0CRB0HVAC00C1
4220 | 4220 | 4220 | 4220 | SA24M005 | Installation of conduits , cable pulling and Detectors of Fire Alarm & Fire Fighting System |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Mechanical Works Control Room Building Installation of conduits , cable pulling and Detectors of Fire Alarm & Fire Fighting System | 2 | C0CRB0HVAC | C000 | 00C2 | C000C0CRB0HVAC00C2
4221 | 4221 | 4221 | 4221 | SA24M005 | Installation of Fire Alarm FACP/DDC panels |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Mechanical Works Control Room Building Installation of Fire Alarm FACP/DDC panels | 3 | C0CRB0HVAC | C000 | 00C3 | C000C0CRB0HVAC00C3
4222 | 4222 | 4222 | 4222 | SA24M005 | Plumbing Work for Water Supply & Sewage of Toilet |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Mechanical Works Control Room Building Plumbing Work for Water Supply & Sewage of Toilet | 4 | C0CRB0HVAC | C000 | 00C4 | C000C0CRB0HVAC00C4
4223 | 4223 | 4223 | 4223 | SA24M005 | Plumping Work for Water Supply & Sewage of Battery Room |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Mechanical Works Control Room Building Plumping Work for Water Supply & Sewage of Battery Room | 5 | C0CRB0HVAC | C000 | 00C5 | C000C0CRB0HVAC00C5
4224 | 4224 | 4224 | 4224 | SA24M005 | Installation of Eyes Wash in Battery Room |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Mechanical Works Control Room Building Installation of Eyes Wash in Battery Room | 6 | C0CRB0HVAC | C000 | 00C6 | C000C0CRB0HVAC00C6
4225 | 4225 | 4225 | 4225 | SA24M005 | Installation of Sanitary Devices in Toilet |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Mechanical Works Control Room Building Installation of Sanitary Devices in Toilet | 7 | C0CRB0HVAC | C000 | 00C7 | C000C0CRB0HVAC00C7
4226 | 4226 | 4226 | 4226 | SA24M005 | Installation of NOVEC CYLINDERS for Building |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Mechanical Works Control Room Building Installation of NOVEC CYLINDERS for Building | 8 | C0CRB0HVAC | C000 | 00C8 | C000C0CRB0HVAC00C8
4227 | 4227 | 4227 | 4227 | SA24M005 | Installation of Sump Pump With Pipe and Fittings |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Mechanical Works Control Room Building Installation of Sump Pump With Pipe and Fittings | 9 | C0CRB0HVAC | C000 | 00C9 | C000C0CRB0HVAC00C9
4228 | 4228 | 4228 | 4228 | SA24M005 | Installation of HVAC Double skin Duct with outdoor with all accessories |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Mechanical Works Control Room Building Installation of HVAC Double skin Duct with outdoor with all accessories | 10 | C0CRB0HVAC | C000 | 0C10 | C000C0CRB0HVAC0C10
4229 | 4229 | 4229 | 4229 | SA24M005 | Installation of Smoke purging / Exhaust Fans |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Mechanical Works Control Room Building Installation of Smoke purging / Exhaust Fans | 11 | C0CRB0HVAC | C000 | 0C11 | C000C0CRB0HVAC0C11
4230 | 4230 | 4230 | 4230 | SA24M005 | Installation of Water Tank and Pump at Roof |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Mechanical Works Control Room Building Installation of Water Tank and Pump at Roof | 12 | C0CRB0HVAC | C000 | 0C12 | C000C0CRB0HVAC0C12
4231 | 4231 | 4231 | 4231 | SA24M005 | Installation of Fire Fighting nozzles |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Mechanical Works Control Room Building Installation of Fire Fighting nozzles | 13 | C0CRB0HVAC | C000 | 0C13 | C000C0CRB0HVAC0C13
4232 | 4232 | 4232 | 4232 | SA24M005 | Installation of Fire Stop Material |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Mechanical Works Control Room Building Installation of Fire Stop Material | 14 | C0CRB0HVAC | C000 | 0C14 | C000C0CRB0HVAC0C14
4233 | 4233 | 4233 | 4233 | SA24M005 | Outdoor Equipments |  | 5 | -1 | 0 |  |  | X
4234 | 4234 | 4234 | 4234 | SA24M005 | Installation of HVAC PACU for 380 kV GIS Building |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Mechanical Works Outdoor Equipments Installation of HVAC PACU for 380 kV GIS Building | 1 | 0HVAC | C000 | 00C1 | C0000HVAC00C1
4235 | 4235 | 4235 | 4235 | SA24M005 | Installation of Transfer and Boster Pump With Pipe and Fittings |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Mechanical Works Outdoor Equipments Installation of Transfer and Boster Pump With Pipe and Fittings | 2 | 0HVAC | C000 | 00C2 | C0000HVAC00C2
4236 | 4236 | 4236 | 4236 | SA24M005 | Installation of HVAC PACU for Control Building |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Mechanical Works Outdoor Equipments Installation of HVAC PACU for Control Building | 3 | 0HVAC | C000 | 00C3 | C0000HVAC00C3
4237 | 4237 | 4237 | 4237 | SA24M005 | Fire Pump Installation |  | 5 | -1 | 0 |  |  | X
4238 | 4238 | 4238 | 4238 | SA24M005 | Fire Pump Installation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Mechanical Works Fire Pump Installation Fire Pump Installation | 1 | F0FPI | C000 | 00C1 | C000F0FPI00C1
4239 | 4239 | 4239 | 4239 | SA24M005 | HCIS System |  | 5 | -1 | 0 |  |  | X | C000F0FPI
4240 | 4240 | 4240 | 4240 | SA24M005 | Installation of HCIS System ( Security system ) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Construction & Installation Works Mechanical Works HCIS System Installation of HCIS System ( Security system ) | 1 | HCIS | C000 | 00C1 | C000HCIS00C1
4241 | 4241 | 4241 | 4241 | SA24M005 | Testing, Commissioning & Energization |  | 3 | -1 | 0 |  |  | X | C000HCIS
4242 | 4242 | 4242 | 4242 | SA24M005 | Prechecks |  | 4 | -1 | 0 |  |  | X | C000HCIS
4243 | 4243 | 4243 | 4243 | SA24M005 | Substation Battery Bank |  | 5 | -1 | 0 |  |  | X | C000HCIS
4244 | 4244 | 4244 | 4244 | SA24M005 | Substation Battery Bank |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Substation Battery Bank Substation Battery Bank | 1 | SUBSBAT | E000 | 00E1 | E000#sibW00E1
4245 | 4245 | 4245 | 4245 | SA24M005 | Substation Battery Charger |  | 5 | -1 | 0 |  |  | X | E000#sibW
4246 | 4246 | 4246 | 4246 | SA24M005 | Substation Battery Charger |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Substation Battery Charger Substation Battery Charger | 1 | SUBSBAT | E000 | 00E1 | E000#oKxZ00E1
4247 | 4247 | 4247 | 4247 | SA24M005 | Battery Monitoring |  | 5 | -1 | 0 |  |  | X | E000#oKxZ
4248 | 4248 | 4248 | 4248 | SA24M005 | Battery Monitoring Panel |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Battery Monitoring Battery Monitoring Panel | 1 | BATMP | E000 | 00E1 | E000BATMP00E1
4249 | 4249 | 4249 | 4249 | SA24M005 | Communication Battery Bank |  | 5 | -1 | 0 |  |  | X | E000BATMP
4250 | 4250 | 4250 | 4250 | SA24M005 | Communication Battery Bank |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Communication Battery Bank Communication Battery Bank | 1 | 0CBBC | E000 | 00E1 | E0000CBBC00E1
4251 | 4251 | 4251 | 4251 | SA24M005 | Communication Battery Charger |  | 5 | -1 | 0 |  |  | X | E0000CBBC
4252 | 4252 | 4252 | 4252 | SA24M005 | Communication Battery Charger |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Communication Battery Charger Communication Battery Charger | 1 | 0CBCH | E000 | 00E1 | E0000CBCH00E1
4253 | 4253 | 4253 | 4253 | SA24M005 | DCDB |  | 5 | -1 | 0 |  |  | X | E0000CBCH
4254 | 4254 | 4254 | 4254 | SA24M005 | Contact Resistance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks DCDB Contact Resistance | 1 | DCDB | E000 | 00E1 | E000DCDB00E1
4255 | 4255 | 4255 | 4255 | SA24M005 | Components |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks DCDB Components | 2 | DCDB | E000 | 00E2 | E000DCDB00E2
4256 | 4256 | 4256 | 4256 | SA24M005 | Scheme Check |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks DCDB Scheme Check | 3 | DCDB | E000 | 00E3 | E000DCDB00E3
4257 | 4257 | 4257 | 4257 | SA24M005 | ACDB |  | 5 | -1 | 0 |  |  | X
4258 | 4258 | 4258 | 4258 | SA24M005 | Component |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks ACDB Component | 1 | ACDB | E000 | 00E1 | E000ACDB00E1
4259 | 4259 | 4259 | 4259 | SA24M005 | Contact Resistance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks ACDB Contact Resistance | 2 | ACDB | E000 | 00E2 | E000ACDB00E2
4260 | 4260 | 4260 | 4260 | SA24M005 | Protection Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks ACDB Protection Relay Acceptance Test | 3 | ACDB | E000 | 00E3 | E000ACDB00E3
4261 | 4261 | 4261 | 4261 | SA24M005 | Protection Relay Final Setting Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks ACDB Protection Relay Final Setting Test | 4 | ACDB | E000 | 00E4 | E000ACDB00E4
4262 | 4262 | 4262 | 4262 | SA24M005 | Scheme Check |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks ACDB Scheme Check | 5 | ACDB | E000 | 00E5 | E000ACDB00E5
4263 | 4263 | 4263 | 4263 | SA24M005 | High Voltage |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks ACDB High Voltage | 6 | ACDB | E000 | 00E6 | E000ACDB00E6
4264 | 4264 | 4264 | 4264 | SA24M005 | Extra High Voltage Switchgear(380kV GIS) |  | 5 | -1 | 0 |  |  | X
4265 | 4265 | 4265 | 4265 | SA24M005 | Auxiliary Relay Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Extra High Voltage Switchgear(380kV GIS) Auxiliary Relay Test | 1 | E0SWGR | E000 | 00E1 | E000#pzvP00E1
4266 | 4266 | 4266 | 4266 | SA24M005 | MCB And MCCB Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Extra High Voltage Switchgear(380kV GIS) MCB And MCCB Test | 2 | E0SWGR | E000 | 00E2 | E000#pzvP00E2
4267 | 4267 | 4267 | 4267 | SA24M005 | Meter Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Extra High Voltage Switchgear(380kV GIS) Meter Test | 3 | E0SWGR | E000 | 00E3 | E000#pzvP00E3
4268 | 4268 | 4268 | 4268 | SA24M005 | Annunciator |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Extra High Voltage Switchgear(380kV GIS) Annunciator | 4 | E0SWGR | E000 | 00E4 | E000#pzvP00E4
4269 | 4269 | 4269 | 4269 | SA24M005 | Calibration of SF6 Density Gauge and its Pressure Switch |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Extra High Voltage Switchgear(380kV GIS) Calibration of SF6 Density Gauge and its Pressure Switch | 5 | E0SWGR | E000 | 00E5 | E000#pzvP00E5
4270 | 4270 | 4270 | 4270 | SA24M005 | SF6 Gas Purity and Dew Point |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Extra High Voltage Switchgear(380kV GIS) SF6 Gas Purity and Dew Point | 6 | E0SWGR | E000 | 00E6 | E000#pzvP00E6
4271 | 4271 | 4271 | 4271 | SA24M005 | SF6 Gas Leakage Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Extra High Voltage Switchgear(380kV GIS) SF6 Gas Leakage Test | 7 | E0SWGR | E000 | 00E7 | E000#pzvP00E7
4272 | 4272 | 4272 | 4272 | SA24M005 | Contact Resistance test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Extra High Voltage Switchgear(380kV GIS) Contact Resistance test | 8 | E0SWGR | E000 | 00E8 | E000#pzvP00E8
4273 | 4273 | 4273 | 4273 | SA24M005 | CB Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Extra High Voltage Switchgear(380kV GIS) CB Test | 9 | E0SWGR | E000 | 00E9 | E000#pzvP00E9
4274 | 4274 | 4274 | 4274 | SA24M005 | ES & DS Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Extra High Voltage Switchgear(380kV GIS) ES & DS Test | 10 | E0SWGR | E000 | 0E10 | E000#pzvP0E10
4275 | 4275 | 4275 | 4275 | SA24M005 | ES 10KV TEST |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Extra High Voltage Switchgear(380kV GIS) ES 10KV TEST | 11 | E0SWGR | E000 | 0E11 | E000#pzvP0E11
4276 | 4276 | 4276 | 4276 | SA24M005 | CT Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Extra High Voltage Switchgear(380kV GIS) CT Test | 12 | E0SWGR | E000 | 0E12 | E000#pzvP0E12
4277 | 4277 | 4277 | 4277 | SA24M005 | CT Secondary Circuit Injection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Extra High Voltage Switchgear(380kV GIS) CT Secondary Circuit Injection | 13 | E0SWGR | E000 | 0E13 | E000#pzvP0E13
4278 | 4278 | 4278 | 4278 | SA24M005 | CT Loop Resistance and Single Earth Point |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Extra High Voltage Switchgear(380kV GIS) CT Loop Resistance and Single Earth Point | 14 | E0SWGR | E000 | 0E14 | E000#pzvP0E14
4279 | 4279 | 4279 | 4279 | SA24M005 | VT Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Extra High Voltage Switchgear(380kV GIS) VT Test | 15 | E0SWGR | E000 | 0E15 | E000#pzvP0E15
4280 | 4280 | 4280 | 4280 | SA24M005 | VT Secondary Circuit Injection & Loop Resistance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Extra High Voltage Switchgear(380kV GIS) VT Secondary Circuit Injection & Loop Resistance | 16 | E0SWGR | E000 | 0E16 | E000#pzvP0E16
4281 | 4281 | 4281 | 4281 | SA24M005 | Calibration of Partial Discharge Sensor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Extra High Voltage Switchgear(380kV GIS) Calibration of Partial Discharge Sensor | 17 | E0SWGR | E000 | 0E17 | E000#pzvP0E17
4282 | 4282 | 4282 | 4282 | SA24M005 | Metrosil |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Extra High Voltage Switchgear(380kV GIS) Metrosil | 18 | E0SWGR | E000 | 0E18 | E000#pzvP0E18
4283 | 4283 | 4283 | 4283 | SA24M005 | EHV Synchronizing Scheme Check |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Extra High Voltage Switchgear(380kV GIS) EHV Synchronizing Scheme Check | 19 | E0SWGR | E000 | 0E19 | E000#pzvP0E19
4284 | 4284 | 4284 | 4284 | SA24M005 | LCC Scheme Check |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Extra High Voltage Switchgear(380kV GIS) LCC Scheme Check | 20 | E0SWGR | E000 | 0E20 | E000#pzvP0E20
4285 | 4285 | 4285 | 4285 | SA24M005 | Extra High Voltage Switchgear(380kV Hybird GIS) |  | 5 | -1 | 0 |  |  | X | E000#pzvP
4286 | 4286 | 4286 | 4286 | SA24M005 | Auxiliary Relay Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Extra High Voltage Switchgear(380kV Hybird GIS) Auxiliary Relay Test | 1 | E0SWGR | E000 | 00E1 | E000#eHHA00E1
4287 | 4287 | 4287 | 4287 | SA24M005 | MCB And MCCB Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Extra High Voltage Switchgear(380kV Hybird GIS) MCB And MCCB Test | 2 | E0SWGR | E000 | 00E2 | E000#eHHA00E2
4288 | 4288 | 4288 | 4288 | SA24M005 | Meter Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Extra High Voltage Switchgear(380kV Hybird GIS) Meter Test | 3 | E0SWGR | E000 | 00E3 | E000#eHHA00E3
4289 | 4289 | 4289 | 4289 | SA24M005 | Annunciator |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Extra High Voltage Switchgear(380kV Hybird GIS) Annunciator | 4 | E0SWGR | E000 | 00E4 | E000#eHHA00E4
4290 | 4290 | 4290 | 4290 | SA24M005 | Calibration of SF6 Density Gauge and its Pressure Switch |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Extra High Voltage Switchgear(380kV Hybird GIS) Calibration of SF6 Density Gauge and its Pressure Switch | 5 | E0SWGR | E000 | 00E5 | E000#eHHA00E5
4291 | 4291 | 4291 | 4291 | SA24M005 | SF6 Gas Purity and Dew Point |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Extra High Voltage Switchgear(380kV Hybird GIS) SF6 Gas Purity and Dew Point | 6 | E0SWGR | E000 | 00E6 | E000#eHHA00E6
4292 | 4292 | 4292 | 4292 | SA24M005 | SF6 Gas Leakage Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Extra High Voltage Switchgear(380kV Hybird GIS) SF6 Gas Leakage Test | 7 | E0SWGR | E000 | 00E7 | E000#eHHA00E7
4293 | 4293 | 4293 | 4293 | SA24M005 | Contact Resistance test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Extra High Voltage Switchgear(380kV Hybird GIS) Contact Resistance test | 8 | E0SWGR | E000 | 00E8 | E000#eHHA00E8
4294 | 4294 | 4294 | 4294 | SA24M005 | CB Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Extra High Voltage Switchgear(380kV Hybird GIS) CB Test | 9 | E0SWGR | E000 | 00E9 | E000#eHHA00E9
4295 | 4295 | 4295 | 4295 | SA24M005 | ES & DS Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Extra High Voltage Switchgear(380kV Hybird GIS) ES & DS Test | 10 | E0SWGR | E000 | 0E10 | E000#eHHA0E10
4296 | 4296 | 4296 | 4296 | SA24M005 | ES 10KV TEST |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Extra High Voltage Switchgear(380kV Hybird GIS) ES 10KV TEST | 11 | E0SWGR | E000 | 0E11 | E000#eHHA0E11
4297 | 4297 | 4297 | 4297 | SA24M005 | CT Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Extra High Voltage Switchgear(380kV Hybird GIS) CT Test | 12 | E0SWGR | E000 | 0E12 | E000#eHHA0E12
4298 | 4298 | 4298 | 4298 | SA24M005 | CT Secondary Circuit Injection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Extra High Voltage Switchgear(380kV Hybird GIS) CT Secondary Circuit Injection | 13 | E0SWGR | E000 | 0E13 | E000#eHHA0E13
4299 | 4299 | 4299 | 4299 | SA24M005 | CT Loop Resistance and Single Earth Point |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Extra High Voltage Switchgear(380kV Hybird GIS) CT Loop Resistance and Single Earth Point | 14 | E0SWGR | E000 | 0E14 | E000#eHHA0E14
4300 | 4300 | 4300 | 4300 | SA24M005 | Calibration of Partial Discharge Sensor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Extra High Voltage Switchgear(380kV Hybird GIS) Calibration of Partial Discharge Sensor | 15 | E0SWGR | E000 | 0E15 | E000#eHHA0E15
4301 | 4301 | 4301 | 4301 | SA24M005 | Metrosil |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Extra High Voltage Switchgear(380kV Hybird GIS) Metrosil | 16 | E0SWGR | E000 | 0E16 | E000#eHHA0E16
4302 | 4302 | 4302 | 4302 | SA24M005 | On-Line Partial Discharge Monitoring System |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Extra High Voltage Switchgear(380kV Hybird GIS) On-Line Partial Discharge Monitoring System | 17 | E0SWGR | E000 | 0E17 | E000#eHHA0E17
4303 | 4303 | 4303 | 4303 | SA24M005 | EHV Synchronizing Scheme Check |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Extra High Voltage Switchgear(380kV Hybird GIS) EHV Synchronizing Scheme Check | 18 | E0SWGR | E000 | 0E18 | E000#eHHA0E18
4304 | 4304 | 4304 | 4304 | SA24M005 | LCC Scheme Check |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Extra High Voltage Switchgear(380kV Hybird GIS) LCC Scheme Check | 19 | E0SWGR | E000 | 0E19 | E000#eHHA0E19
4305 | 4305 | 4305 | 4305 | SA24M005 | 13.8 kV Switchgear |  | 5 | -1 | 0 |  |  | X | E000#eHHA
4306 | 4306 | 4306 | 4306 | SA24M005 | MCB And MCCB Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks 13.8 kV Switchgear MCB And MCCB Test | 1 | 0SWGR | E000 | 00E1 | E0000SWGR00E1
4307 | 4307 | 4307 | 4307 | SA24M005 | Auxiliary Relay Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks 13.8 kV Switchgear Auxiliary Relay Test | 2 | 0SWGR | E000 | 00E2 | E0000SWGR00E2
4308 | 4308 | 4308 | 4308 | SA24M005 | Meter Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks 13.8 kV Switchgear Meter Test | 3 | 0SWGR | E000 | 00E3 | E0000SWGR00E3
4309 | 4309 | 4309 | 4309 | SA24M005 | CT Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks 13.8 kV Switchgear CT Test | 4 | 0SWGR | E000 | 00E4 | E0000SWGR00E4
4310 | 4310 | 4310 | 4310 | SA24M005 | CT Loop Resistance and Single Earth Point |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks 13.8 kV Switchgear CT Loop Resistance and Single Earth Point | 5 | 0SWGR | E000 | 00E5 | E0000SWGR00E5
4311 | 4311 | 4311 | 4311 | SA24M005 | CT Circuit Secondary Injection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks 13.8 kV Switchgear CT Circuit Secondary Injection | 6 | 0SWGR | E000 | 00E6 | E0000SWGR00E6
4312 | 4312 | 4312 | 4312 | SA24M005 | VT Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks 13.8 kV Switchgear VT Test | 7 | 0SWGR | E000 | 00E7 | E0000SWGR00E7
4313 | 4313 | 4313 | 4313 | SA24M005 | VT Secondary Circuit Injection & Loop Resistance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks 13.8 kV Switchgear VT Secondary Circuit Injection & Loop Resistance | 8 | 0SWGR | E000 | 00E8 | E0000SWGR00E8
4314 | 4314 | 4314 | 4314 | SA24M005 | CB Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks 13.8 kV Switchgear CB Test | 9 | 0SWGR | E000 | 00E9 | E0000SWGR00E9
4315 | 4315 | 4315 | 4315 | SA24M005 | BB Contact Resistance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks 13.8 kV Switchgear BB Contact Resistance Test | 10 | 0SWGR | E000 | 0E10 | E0000SWGR0E10
4316 | 4316 | 4316 | 4316 | SA24M005 | ES Contact Resistance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks 13.8 kV Switchgear ES Contact Resistance Test | 11 | 0SWGR | E000 | 0E11 | E0000SWGR0E11
4317 | 4317 | 4317 | 4317 | SA24M005 | Cooling Fans System |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks 13.8 kV Switchgear Cooling Fans System | 12 | 0SWGR | E000 | 0E12 | E0000SWGR0E12
4318 | 4318 | 4318 | 4318 | SA24M005 | Scheme Check |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks 13.8 kV Switchgear Scheme Check | 13 | 0SWGR | E000 | 0E13 | E0000SWGR0E13
4319 | 4319 | 4319 | 4319 | SA24M005 | Stand Alone Surge Arrester |  | 5 | -1 | 0 |  |  | X
4320 | 4320 | 4320 | 4320 | SA24M005 | EHV Stand Alone Surge Arrester |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Stand Alone Surge Arrester EHV Stand Alone Surge Arrester | 1 | ESURG | E000 | 00E1 | E000#mxXb00E1
4321 | 4321 | 4321 | 4321 | SA24M005 | Stand Alone Current Transformer |  | 5 | -1 | 0 |  |  | X | E000#mxXb
4322 | 4322 | 4322 | 4322 | SA24M005 | EHV Stand Alone CT |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Stand Alone Current Transformer EHV Stand Alone CT | 1 | 0STRF | E000 | 00E1 | E0000STRF00E1
4323 | 4323 | 4323 | 4323 | SA24M005 | EHV Stand Alone CT Secondary Circuit Injection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Stand Alone Current Transformer EHV Stand Alone CT Secondary Circuit Injection | 2 | 0STRF | E000 | 00E2 | E0000STRF00E2
4324 | 4324 | 4324 | 4324 | SA24M005 | EHV Stand Alone CT Loop Resistance and Single Earth Point |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Stand Alone Current Transformer EHV Stand Alone CT Loop Resistance and Single Earth Point | 3 | 0STRF | E000 | 00E3 | E0000STRF00E3
4325 | 4325 | 4325 | 4325 | SA24M005 | Low Voltage Cable |  | 5 | -1 | 0 |  |  | X
4326 | 4326 | 4326 | 4326 | SA24M005 | LV Cable Insulation Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Low Voltage Cable LV Cable Insulation Test | 1 | LVCLI | E000 | 00E1 | E000LVCLI00E1
4327 | 4327 | 4327 | 4327 | SA24M005 | LV Cable Phasing and Continuity Check |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Low Voltage Cable LV Cable Phasing and Continuity Check | 2 | LVCLI | E000 | 00E2 | E000LVCLI00E2
4328 | 4328 | 4328 | 4328 | SA24M005 | Auxiliary/Trip Relay In Control And Protection Panels |  | 5 | -1 | 0 |  |  | X
4329 | 4329 | 4329 | 4329 | SA24M005 | Auxiliary Relays Test In Control Room Panels |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Auxiliary/Trip Relay In Control And Protection Panels Auxiliary Relays Test In Control Room Panels | 1 | AUXRLY | E000 | 00E1 | E000AUXRLY00E1
4330 | 4330 | 4330 | 4330 | SA24M005 | Trip Relays Test In Control Room Panels |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Auxiliary/Trip Relay In Control And Protection Panels Trip Relays Test In Control Room Panels | 2 | AUXRLY | E000 | 00E2 | E000AUXRLY00E2
4331 | 4331 | 4331 | 4331 | SA24M005 | MCB In Control And Protection Panels |  | 5 | -1 | 0 |  |  | X
4332 | 4332 | 4332 | 4332 | SA24M005 | MCB Test In Control And Protection Panels |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks MCB In Control And Protection Panels MCB Test In Control And Protection Panels | 1 | 0MCB | E000 | 00E1 | E000#bcMt00E1
4333 | 4333 | 4333 | 4333 | SA24M005 | Scheme Check for Protection Panels |  | 5 | -1 | 0 |  |  | X | E000#bcMt
4334 | 4334 | 4334 | 4334 | SA24M005 | EHV Line Protection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Scheme Check for Protection Panels EHV Line Protection | 1 | 0E0PLP | E000 | 00E1 | E0000E0PLP00E1
4335 | 4335 | 4335 | 4335 | SA24M005 | EHV Auto Recloser Panel |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Scheme Check for Protection Panels EHV Auto Recloser Panel | 2 | 0E0PLP | E000 | 00E2 | E0000E0PLP00E2
4336 | 4336 | 4336 | 4336 | SA24M005 | EHV Shunt Reactor Protection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Scheme Check for Protection Panels EHV Shunt Reactor Protection | 3 | 0E0PLP | E000 | 00E3 | E0000E0PLP00E3
4337 | 4337 | 4337 | 4337 | SA24M005 | EHV Tee Protection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Scheme Check for Protection Panels EHV Tee Protection | 4 | 0E0PLP | E000 | 00E4 | E0000E0PLP00E4
4338 | 4338 | 4338 | 4338 | SA24M005 | EHV BBP |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Scheme Check for Protection Panels EHV BBP | 5 | 0E0PLP | E000 | 00E5 | E0000E0PLP00E5
4339 | 4339 | 4339 | 4339 | SA24M005 | EHV CBF |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Scheme Check for Protection Panels EHV CBF | 6 | 0E0PLP | E000 | 00E6 | E0000E0PLP00E6
4340 | 4340 | 4340 | 4340 | SA24M005 | EHV Pole Discrepancy |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Scheme Check for Protection Panels EHV Pole Discrepancy | 7 | 0E0PLP | E000 | 00E7 | E0000E0PLP00E7
4341 | 4341 | 4341 | 4341 | SA24M005 | EHV Trip Circuit Supervision |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Scheme Check for Protection Panels EHV Trip Circuit Supervision | 8 | 0E0PLP | E000 | 00E8 | E0000E0PLP00E8
4342 | 4342 | 4342 | 4342 | SA24M005 | Transient Fault Recorder TFR Panel |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Scheme Check for Protection Panels Transient Fault Recorder TFR Panel | 9 | 0E0PLP | E000 | 00E9 | E0000E0PLP00E9
4343 | 4343 | 4343 | 4343 | SA24M005 | DSM PANEL TESTING |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Scheme Check for Protection Panels DSM PANEL TESTING | 10 | 0E0PLP | E000 | 0E10 | E0000E0PLP0E10
4344 | 4344 | 4344 | 4344 | SA24M005 | Energy Meter Panel Scheme Check |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Scheme Check for Protection Panels Energy Meter Panel Scheme Check | 11 | 0E0PLP | E000 | 0E11 | E0000E0PLP0E11
4345 | 4345 | 4345 | 4345 | SA24M005 | EHV Line Protection (380kV Lines) |  | 5 | -1 | 0 |  |  | X
4346 | 4346 | 4346 | 4346 | SA24M005 | Main 1 Multifunction Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks EHV Line Protection (380kV Lines) Main 1 Multifunction Relay Acceptance Test | 1 | E0EHW | E000 | 00E1 | E000#brrL00E1
4347 | 4347 | 4347 | 4347 | SA24M005 | Main 2 Multifunction Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks EHV Line Protection (380kV Lines) Main 2 Multifunction Relay Acceptance Test | 2 | E0EHW | E000 | 00E2 | E000#brrL00E2
4348 | 4348 | 4348 | 4348 | SA24M005 | Undervoltage and Overvoltage Relay Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks EHV Line Protection (380kV Lines) Undervoltage and Overvoltage Relay Test | 3 | E0EHW | E000 | 00E3 | E000#brrL00E3
4349 | 4349 | 4349 | 4349 | SA24M005 | Automatic Recloser |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks EHV Line Protection (380kV Lines) Automatic Recloser | 4 | E0EHW | E000 | 00E4 | E000#brrL00E4
4350 | 4350 | 4350 | 4350 | SA24M005 | EHV Shunt Reactor Protection & Line Reactor |  | 5 | -1 | 0 |  |  | X | E000#brrL
4351 | 4351 | 4351 | 4351 | SA24M005 | Set 1 Differential Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks EHV Shunt Reactor Protection & Line Reactor Set 1 Differential Relay Acceptance Test | 1 | E0SHR | E000 | 00E1 | E000#YWXV00E1
4352 | 4352 | 4352 | 4352 | SA24M005 | Set 2 Differential Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks EHV Shunt Reactor Protection & Line Reactor Set 2 Differential Relay Acceptance Test | 2 | E0SHR | E000 | 00E2 | E000#YWXV00E2
4353 | 4353 | 4353 | 4353 | SA24M005 | Overcurrent And Earth Fault Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks EHV Shunt Reactor Protection & Line Reactor Overcurrent And Earth Fault Relay Acceptance Test | 3 | E0SHR | E000 | 00E3 | E000#YWXV00E3
4354 | 4354 | 4354 | 4354 | SA24M005 | Overcurrent And Earth Fault Relay Final Setting Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks EHV Shunt Reactor Protection & Line Reactor Overcurrent And Earth Fault Relay Final Setting Test | 4 | E0SHR | E000 | 00E4 | E000#YWXV00E4
4355 | 4355 | 4355 | 4355 | SA24M005 | Under voltage and Over voltage relay |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks EHV Shunt Reactor Protection & Line Reactor Under voltage and Over voltage relay | 5 | E0SHR | E000 | 00E5 | E000#YWXV00E5
4356 | 4356 | 4356 | 4356 | SA24M005 | Set 1 CT Supervision Relay Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks EHV Shunt Reactor Protection & Line Reactor Set 1 CT Supervision Relay Test | 6 | E0SHR | E000 | 00E6 | E000#YWXV00E6
4357 | 4357 | 4357 | 4357 | SA24M005 | Set 2 CT Supervision Relay Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks EHV Shunt Reactor Protection & Line Reactor Set 2 CT Supervision Relay Test | 7 | E0SHR | E000 | 00E7 | E000#YWXV00E7
4358 | 4358 | 4358 | 4358 | SA24M005 | EHV TEE Protection |  | 5 | -1 | 0 |  |  | X | E000#YWXV
4359 | 4359 | 4359 | 4359 | SA24M005 | Set 1 Differential Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks EHV TEE Protection Set 1 Differential Relay Acceptance Test | 1 | E0EHW | E000 | 00E1 | E000#IPrv00E1
4360 | 4360 | 4360 | 4360 | SA24M005 | Set 2 Differential Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks EHV TEE Protection Set 2 Differential Relay Acceptance Test | 2 | E0EHW | E000 | 00E2 | E000#IPrv00E2
4361 | 4361 | 4361 | 4361 | SA24M005 | Set 1 CT Supervision Relay |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks EHV TEE Protection Set 1 CT Supervision Relay | 3 | E0EHW | E000 | 00E3 | E000#IPrv00E3
4362 | 4362 | 4362 | 4362 | SA24M005 | Set 2 CT Supervision Relay |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks EHV TEE Protection Set 2 CT Supervision Relay | 4 | E0EHW | E000 | 00E4 | E000#IPrv00E4
4363 | 4363 | 4363 | 4363 | SA24M005 | EHV STUB Protection |  | 5 | -1 | 0 |  |  | X | E000#IPrv
4364 | 4364 | 4364 | 4364 | SA24M005 | Set 1 Stub Protection Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks EHV STUB Protection Set 1 Stub Protection Relay Acceptance Test | 1 | E0STR | E000 | 00E1 | E000#DLtC00E1
4365 | 4365 | 4365 | 4365 | SA24M005 | Set 1 Stub Protection Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks EHV STUB Protection Set 1 Stub Protection Relay Acceptance Test | 2 | E0STR | E000 | 00E2 | E000#DLtC00E2
4366 | 4366 | 4366 | 4366 | SA24M005 | EHV Bus Bar Protection |  | 5 | -1 | 0 |  |  | X | E000#DLtC
4367 | 4367 | 4367 | 4367 | SA24M005 | Set 1 High Impedance BBP |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks EHV Bus Bar Protection Set 1 High Impedance BBP | 1 | E0BBP | E000 | 00E1 | E000E0BBP00E1
4368 | 4368 | 4368 | 4368 | SA24M005 | Set 2 High Impedance BBP |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks EHV Bus Bar Protection Set 2 High Impedance BBP | 2 | E0BBP | E000 | 00E2 | E000E0BBP00E2
4369 | 4369 | 4369 | 4369 | SA24M005 | Set-1 CT Supervision Relay Test for BBP |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks EHV Bus Bar Protection Set-1 CT Supervision Relay Test for BBP | 3 | E0BBP | E000 | 00E3 | E000E0BBP00E3
4370 | 4370 | 4370 | 4370 | SA24M005 | Set-2 CT Supervision Relay Test for BBP |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks EHV Bus Bar Protection Set-2 CT Supervision Relay Test for BBP | 4 | E0BBP | E000 | 00E4 | E000E0BBP00E4
4371 | 4371 | 4371 | 4371 | SA24M005 | Circuit Breaker Fail Protection |  | 5 | -1 | 0 |  |  | X
4372 | 4372 | 4372 | 4372 | SA24M005 | Set 1 CBF Relay Acceptance Test For EHV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Circuit Breaker Fail Protection Set 1 CBF Relay Acceptance Test For EHV | 1 | ECBF | E000 | 00E1 | E000ECBF00E1
4373 | 4373 | 4373 | 4373 | SA24M005 | Set 2 CBF Relay Acceptance Test For EHV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Circuit Breaker Fail Protection Set 2 CBF Relay Acceptance Test For EHV | 2 | ECBF | E000 | 00E2 | E000ECBF00E2
4374 | 4374 | 4374 | 4374 | SA24M005 | 13.8kV Feeder Protection |  | 5 | -1 | 0 |  |  | X
4375 | 4375 | 4375 | 4375 | SA24M005 | Over Current and Earth Fault Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks 13.8kV Feeder Protection Over Current and Earth Fault Relay Acceptance Test | 1 | PFOC | E000 | 00E1 | E000PFOC00E1
4376 | 4376 | 4376 | 4376 | SA24M005 | Sensitive Earth Fault Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks 13.8kV Feeder Protection Sensitive Earth Fault Relay Acceptance Test | 2 | PFOC | E000 | 00E2 | E000PFOC00E2
4377 | 4377 | 4377 | 4377 | SA24M005 | Synchronizing Check Relays |  | 5 | -1 | 0 |  |  | X
4378 | 4378 | 4378 | 4378 | SA24M005 | EHV Synchro-Check Relay |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Synchronizing Check Relays EHV Synchro-Check Relay | 1 | PSYNCR | E000 | 00E1 | E000PSYNCR00E1
4379 | 4379 | 4379 | 4379 | SA24M005 | Automatic Voltage Regulator |  | 5 | -1 | 0 |  |  | X | E000PSYNCR
4380 | 4380 | 4380 | 4380 | SA24M005 | AVC Relay Acceptance Test For EHV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Automatic Voltage Regulator AVC Relay Acceptance Test For EHV | 1 | 0AVRG | E000 | 00E1 | E0000AVRG00E1
4381 | 4381 | 4381 | 4381 | SA24M005 | AVC Relay Final Setting Test For EHV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Automatic Voltage Regulator AVC Relay Final Setting Test For EHV | 2 | 0AVRG | E000 | 00E2 | E0000AVRG00E2
4382 | 4382 | 4382 | 4382 | SA24M005 | Stability Test |  | 5 | -1 | 0 |  |  | X
4383 | 4383 | 4383 | 4383 | SA24M005 | EHV Busbar Protection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Stability Test EHV Busbar Protection | 1 | #nGyb | E000 | 00E1 | E000#nGyb00E1
4384 | 4384 | 4384 | 4384 | SA24M005 | EHV TEE Differential Protection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Stability Test EHV TEE Differential Protection | 2 | #nGyb | E000 | 00E2 | E000#nGyb00E2
4385 | 4385 | 4385 | 4385 | SA24M005 | EHV Shunt Reactor Differential/REF |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Stability Test EHV Shunt Reactor Differential/REF | 3 | #nGyb | E000 | 00E3 | E000#nGyb00E3
4386 | 4386 | 4386 | 4386 | SA24M005 | Advanced Metering Infrastructure |  | 5 | -1 | 0 |  |  | X
4387 | 4387 | 4387 | 4387 | SA24M005 | Revenue Meter |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Advanced Metering Infrastructure Revenue Meter | 1 | 0ARMI | E000 | 00E1 | E0000ARMI00E1
4388 | 4388 | 4388 | 4388 | SA24M005 | Power Quality Meter |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Advanced Metering Infrastructure Power Quality Meter | 2 | 0ARMI | E000 | 00E2 | E0000ARMI00E2
4389 | 4389 | 4389 | 4389 | SA24M005 | Switch Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Advanced Metering Infrastructure Switch Test | 3 | 0ARMI | E000 | 00E3 | E0000ARMI00E3
4390 | 4390 | 4390 | 4390 | SA24M005 | Scheme Check |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Advanced Metering Infrastructure Scheme Check | 4 | 0ARMI | E000 | 00E4 | E0000ARMI00E4
4391 | 4391 | 4391 | 4391 | SA24M005 | Operation Interlocking |  | 5 | -1 | 0 |  |  | X
4392 | 4392 | 4392 | 4392 | SA24M005 | Operation and Interlocking Test for EHV GIS |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Operation Interlocking Operation and Interlocking Test for EHV GIS | 1 | 0E0GIS | E000 | 00E1 | E0000E0GIS00E1
4393 | 4393 | 4393 | 4393 | SA24M005 | Operation And Interlocking Test for 13.8kV Switchgear |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks Operation Interlocking Operation And Interlocking Test for 13.8kV Switchgear | 2 | 0E0GIS | E000 | 00E2 | E0000E0GIS00E2
4394 | 4394 | 4394 | 4394 | SA24M005 | SAS Function Test |  | 5 | -1 | 0 |  |  | X
4395 | 4395 | 4395 | 4395 | SA24M005 | Alarm And Indication Check Up To SAS HMI And Gateway For MV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks SAS Function Test Alarm And Indication Check Up To SAS HMI And Gateway For MV | 1 | PSASF | E000 | 00E1 | E000PSASF00E1
4396 | 4396 | 4396 | 4396 | SA24M005 | Alarm And Indication Check Up To SAS HMI And Gateway For HV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks SAS Function Test Alarm And Indication Check Up To SAS HMI And Gateway For HV | 2 | PSASF | E000 | 00E2 | E000PSASF00E2
4397 | 4397 | 4397 | 4397 | SA24M005 | Alarm And Indication Check Up To SAS HMI And Gateway For EHV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks SAS Function Test Alarm And Indication Check Up To SAS HMI And Gateway For EHV | 3 | PSASF | E000 | 00E3 | E000PSASF00E3
4398 | 4398 | 4398 | 4398 | SA24M005 | Alarm And Imdication Check Up to SAS HMI And Gateway for Common Alarm |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks SAS Function Test Alarm And Imdication Check Up to SAS HMI And Gateway for Common Alarm | 4 | PSASF | E000 | 00E4 | E000PSASF00E4
4399 | 4399 | 4399 | 4399 | SA24M005 | Operation and Interlocking Test for 13.8kV Switchgear |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks SAS Function Test Operation and Interlocking Test for 13.8kV Switchgear | 5 | PSASF | E000 | 00E5 | E000PSASF00E5
4400 | 4400 | 4400 | 4400 | SA24M005 | Operation and Interlocking Test for HV Switchgear |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Prechecks SAS Function Test Operation and Interlocking Test for HV Switchgear | 6 | PSASF | E000 | 00E6 | E000PSASF00E6
4401 | 4401 | 4401 | 4401 | SA24M005 | Commissioning |  | 4 | -1 | 0 |  |  | X
4402 | 4402 | 4402 | 4402 | SA24M005 | DCDB |  | 5 | -1 | 0 |  |  | X
4403 | 4403 | 4403 | 4403 | SA24M005 | Contact Resistance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning DCDB Contact Resistance | 1 | DCDB | M000 | 00M1 | M000DCDB00M1
4404 | 4404 | 4404 | 4404 | SA24M005 | Components |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning DCDB Components | 2 | DCDB | M000 | 00M2 | M000DCDB00M2
4405 | 4405 | 4405 | 4405 | SA24M005 | Scheme Check |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning DCDB Scheme Check | 3 | DCDB | M000 | 00M3 | M000DCDB00M3
4406 | 4406 | 4406 | 4406 | SA24M005 | ACDB |  | 5 | -1 | 0 |  |  | X
4407 | 4407 | 4407 | 4407 | SA24M005 | Component |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning ACDB Component | 1 | ACDB | M000 | 00M1 | M000ACDB00M1
4408 | 4408 | 4408 | 4408 | SA24M005 | Contact Resistance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning ACDB Contact Resistance | 2 | ACDB | M000 | 00M2 | M000ACDB00M2
4409 | 4409 | 4409 | 4409 | SA24M005 | Protection Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning ACDB Protection Relay Acceptance Test | 3 | ACDB | M000 | 00M3 | M000ACDB00M3
4410 | 4410 | 4410 | 4410 | SA24M005 | Protection Relay Final Setting Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning ACDB Protection Relay Final Setting Test | 4 | ACDB | M000 | 00M4 | M000ACDB00M4
4411 | 4411 | 4411 | 4411 | SA24M005 | Scheme Check |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning ACDB Scheme Check | 5 | ACDB | M000 | 00M5 | M000ACDB00M5
4412 | 4412 | 4412 | 4412 | SA24M005 | High Voltage |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning ACDB High Voltage | 6 | ACDB | M000 | 00M6 | M000ACDB00M6
4413 | 4413 | 4413 | 4413 | SA24M005 | Extra High Voltage Switchgear(380kV GIS) |  | 5 | -1 | 0 |  |  | X
4414 | 4414 | 4414 | 4414 | SA24M005 | Auxiliary Relay Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Extra High Voltage Switchgear(380kV GIS) Auxiliary Relay Test | 1 | E0SWGR | E000 | 00E1 | E000#kHZV00E1
4415 | 4415 | 4415 | 4415 | SA24M005 | MCB And MCCB Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Extra High Voltage Switchgear(380kV GIS) MCB And MCCB Test | 2 | E0SWGR | E000 | 00E2 | E000#kHZV00E2
4416 | 4416 | 4416 | 4416 | SA24M005 | Meter Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Extra High Voltage Switchgear(380kV GIS) Meter Test | 3 | E0SWGR | E000 | 00E3 | E000#kHZV00E3
4417 | 4417 | 4417 | 4417 | SA24M005 | Annunciator |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Extra High Voltage Switchgear(380kV GIS) Annunciator | 4 | E0SWGR | E000 | 00E4 | E000#kHZV00E4
4418 | 4418 | 4418 | 4418 | SA24M005 | Calibration of SF6 Density Gauge and its Pressure Switch |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Extra High Voltage Switchgear(380kV GIS) Calibration of SF6 Density Gauge and its Pressure Switch | 5 | E0SWGR | E000 | 00E5 | E000#kHZV00E5
4419 | 4419 | 4419 | 4419 | SA24M005 | SF6 Gas Purity and Dew Point |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Extra High Voltage Switchgear(380kV GIS) SF6 Gas Purity and Dew Point | 6 | E0SWGR | E000 | 00E6 | E000#kHZV00E6
4420 | 4420 | 4420 | 4420 | SA24M005 | SF6 Gas Leakage Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Extra High Voltage Switchgear(380kV GIS) SF6 Gas Leakage Test | 7 | E0SWGR | E000 | 00E7 | E000#kHZV00E7
4421 | 4421 | 4421 | 4421 | SA24M005 | Contact Resistance test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Extra High Voltage Switchgear(380kV GIS) Contact Resistance test | 8 | E0SWGR | E000 | 00E8 | E000#kHZV00E8
4422 | 4422 | 4422 | 4422 | SA24M005 | CB Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Extra High Voltage Switchgear(380kV GIS) CB Test | 9 | E0SWGR | E000 | 00E9 | E000#kHZV00E9
4423 | 4423 | 4423 | 4423 | SA24M005 | ES & DS Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Extra High Voltage Switchgear(380kV GIS) ES & DS Test | 10 | E0SWGR | E000 | 0E10 | E000#kHZV0E10
4424 | 4424 | 4424 | 4424 | SA24M005 | ES 10KV TEST |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Extra High Voltage Switchgear(380kV GIS) ES 10KV TEST | 11 | E0SWGR | E000 | 0E11 | E000#kHZV0E11
4425 | 4425 | 4425 | 4425 | SA24M005 | CT Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Extra High Voltage Switchgear(380kV GIS) CT Test | 12 | E0SWGR | E000 | 0E12 | E000#kHZV0E12
4426 | 4426 | 4426 | 4426 | SA24M005 | CT Secondary Circuit Injection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Extra High Voltage Switchgear(380kV GIS) CT Secondary Circuit Injection | 13 | E0SWGR | E000 | 0E13 | E000#kHZV0E13
4427 | 4427 | 4427 | 4427 | SA24M005 | CT Loop Resistance and Single Earth Point |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Extra High Voltage Switchgear(380kV GIS) CT Loop Resistance and Single Earth Point | 14 | E0SWGR | E000 | 0E14 | E000#kHZV0E14
4428 | 4428 | 4428 | 4428 | SA24M005 | VT Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Extra High Voltage Switchgear(380kV GIS) VT Test | 15 | E0SWGR | E000 | 0E15 | E000#kHZV0E15
4429 | 4429 | 4429 | 4429 | SA24M005 | VT Secondary Circuit Injection & Loop Resistance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Extra High Voltage Switchgear(380kV GIS) VT Secondary Circuit Injection & Loop Resistance | 16 | E0SWGR | E000 | 0E16 | E000#kHZV0E16
4430 | 4430 | 4430 | 4430 | SA24M005 | Calibration of Partial Discharge Sensor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Extra High Voltage Switchgear(380kV GIS) Calibration of Partial Discharge Sensor | 17 | E0SWGR | E000 | 0E17 | E000#kHZV0E17
4431 | 4431 | 4431 | 4431 | SA24M005 | Metrosil |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Extra High Voltage Switchgear(380kV GIS) Metrosil | 18 | E0SWGR | E000 | 0E18 | E000#kHZV0E18
4432 | 4432 | 4432 | 4432 | SA24M005 | On-Line Partial Discharge Monitoring System |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Extra High Voltage Switchgear(380kV GIS) On-Line Partial Discharge Monitoring System | 19 | E0SWGR | E000 | 0E19 | E000#kHZV0E19
4433 | 4433 | 4433 | 4433 | SA24M005 | EHV Synchronizing Scheme Check |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Extra High Voltage Switchgear(380kV GIS) EHV Synchronizing Scheme Check | 20 | E0SWGR | E000 | 0E20 | E000#kHZV0E20
4434 | 4434 | 4434 | 4434 | SA24M005 | LCC Scheme Check |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Extra High Voltage Switchgear(380kV GIS) LCC Scheme Check | 21 | E0SWGR | E000 | 0E21 | E000#kHZV0E21
4435 | 4435 | 4435 | 4435 | SA24M005 | HV Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Extra High Voltage Switchgear(380kV GIS) HV Test | 22 | E0SWGR | E000 | 0E22 | E000#kHZV0E22
4436 | 4436 | 4436 | 4436 | SA24M005 | CT Primary Injection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Extra High Voltage Switchgear(380kV GIS) CT Primary Injection | 23 | E0SWGR | E000 | 0E23 | E000#kHZV0E23
4437 | 4437 | 4437 | 4437 | SA24M005 | Extra High Voltage Switchgear(380kV Hybird GIS) |  | 5 | -1 | 0 |  |  | X | E000#kHZV
4438 | 4438 | 4438 | 4438 | SA24M005 | Auxiliary Relay Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Extra High Voltage Switchgear(380kV Hybird GIS) Auxiliary Relay Test | 1 | E0SWGR | E000 | 00E1 | E000#WTTP00E1
4439 | 4439 | 4439 | 4439 | SA24M005 | MCB And MCCB Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Extra High Voltage Switchgear(380kV Hybird GIS) MCB And MCCB Test | 2 | E0SWGR | E000 | 00E2 | E000#WTTP00E2
4440 | 4440 | 4440 | 4440 | SA24M005 | Meter Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Extra High Voltage Switchgear(380kV Hybird GIS) Meter Test | 3 | E0SWGR | E000 | 00E3 | E000#WTTP00E3
4441 | 4441 | 4441 | 4441 | SA24M005 | Annunciator |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Extra High Voltage Switchgear(380kV Hybird GIS) Annunciator | 4 | E0SWGR | E000 | 00E4 | E000#WTTP00E4
4442 | 4442 | 4442 | 4442 | SA24M005 | Calibration of SF6 Density Gauge and its Pressure Switch |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Extra High Voltage Switchgear(380kV Hybird GIS) Calibration of SF6 Density Gauge and its Pressure Switch | 5 | E0SWGR | E000 | 00E5 | E000#WTTP00E5
4443 | 4443 | 4443 | 4443 | SA24M005 | SF6 Gas Purity and Dew Point |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Extra High Voltage Switchgear(380kV Hybird GIS) SF6 Gas Purity and Dew Point | 6 | E0SWGR | E000 | 00E6 | E000#WTTP00E6
4444 | 4444 | 4444 | 4444 | SA24M005 | SF6 Gas Leakage Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Extra High Voltage Switchgear(380kV Hybird GIS) SF6 Gas Leakage Test | 7 | E0SWGR | E000 | 00E7 | E000#WTTP00E7
4445 | 4445 | 4445 | 4445 | SA24M005 | Contact Resistance test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Extra High Voltage Switchgear(380kV Hybird GIS) Contact Resistance test | 8 | E0SWGR | E000 | 00E8 | E000#WTTP00E8
4446 | 4446 | 4446 | 4446 | SA24M005 | CB Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Extra High Voltage Switchgear(380kV Hybird GIS) CB Test | 9 | E0SWGR | E000 | 00E9 | E000#WTTP00E9
4447 | 4447 | 4447 | 4447 | SA24M005 | ES & DS Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Extra High Voltage Switchgear(380kV Hybird GIS) ES & DS Test | 10 | E0SWGR | E000 | 0E10 | E000#WTTP0E10
4448 | 4448 | 4448 | 4448 | SA24M005 | ES 10KV TEST |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Extra High Voltage Switchgear(380kV Hybird GIS) ES 10KV TEST | 11 | E0SWGR | E000 | 0E11 | E000#WTTP0E11
4449 | 4449 | 4449 | 4449 | SA24M005 | CT Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Extra High Voltage Switchgear(380kV Hybird GIS) CT Test | 12 | E0SWGR | E000 | 0E12 | E000#WTTP0E12
4450 | 4450 | 4450 | 4450 | SA24M005 | CT Secondary Circuit Injection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Extra High Voltage Switchgear(380kV Hybird GIS) CT Secondary Circuit Injection | 13 | E0SWGR | E000 | 0E13 | E000#WTTP0E13
4451 | 4451 | 4451 | 4451 | SA24M005 | CT Loop Resistance and Single Earth Point |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Extra High Voltage Switchgear(380kV Hybird GIS) CT Loop Resistance and Single Earth Point | 14 | E0SWGR | E000 | 0E14 | E000#WTTP0E14
4452 | 4452 | 4452 | 4452 | SA24M005 | Calibration of Partial Discharge Sensor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Extra High Voltage Switchgear(380kV Hybird GIS) Calibration of Partial Discharge Sensor | 15 | E0SWGR | E000 | 0E15 | E000#WTTP0E15
4453 | 4453 | 4453 | 4453 | SA24M005 | Metrosil |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Extra High Voltage Switchgear(380kV Hybird GIS) Metrosil | 16 | E0SWGR | E000 | 0E16 | E000#WTTP0E16
4454 | 4454 | 4454 | 4454 | SA24M005 | On-Line Partial Discharge Monitoring System |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Extra High Voltage Switchgear(380kV Hybird GIS) On-Line Partial Discharge Monitoring System | 17 | E0SWGR | E000 | 0E17 | E000#WTTP0E17
4455 | 4455 | 4455 | 4455 | SA24M005 | EHV Synchronizing Scheme Check |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Extra High Voltage Switchgear(380kV Hybird GIS) EHV Synchronizing Scheme Check | 18 | E0SWGR | E000 | 0E18 | E000#WTTP0E18
4456 | 4456 | 4456 | 4456 | SA24M005 | LCC Scheme Check |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Extra High Voltage Switchgear(380kV Hybird GIS) LCC Scheme Check | 19 | E0SWGR | E000 | 0E19 | E000#WTTP0E19
4457 | 4457 | 4457 | 4457 | SA24M005 | HV Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Extra High Voltage Switchgear(380kV Hybird GIS) HV Test | 20 | E0SWGR | E000 | 0E20 | E000#WTTP0E20
4458 | 4458 | 4458 | 4458 | SA24M005 | CT Primary Injection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Extra High Voltage Switchgear(380kV Hybird GIS) CT Primary Injection | 21 | E0SWGR | E000 | 0E21 | E000#WTTP0E21
4459 | 4459 | 4459 | 4459 | SA24M005 | 13.8 kV Switchgear |  | 5 | -1 | 0 |  |  | X | E000#WTTP
4460 | 4460 | 4460 | 4460 | SA24M005 | MCB And MCCB Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning 13.8 kV Switchgear MCB And MCCB Test | 1 | #jejs | E000 | 00E1 | E000#jejs00E1
4461 | 4461 | 4461 | 4461 | SA24M005 | Auxiliary Relay Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning 13.8 kV Switchgear Auxiliary Relay Test | 2 | #jejs | E000 | 00E2 | E000#jejs00E2
4462 | 4462 | 4462 | 4462 | SA24M005 | Meter Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning 13.8 kV Switchgear Meter Test | 3 | #jejs | E000 | 00E3 | E000#jejs00E3
4463 | 4463 | 4463 | 4463 | SA24M005 | CT Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning 13.8 kV Switchgear CT Test | 4 | #jejs | E000 | 00E4 | E000#jejs00E4
4464 | 4464 | 4464 | 4464 | SA24M005 | CT Loop Resistance and Single Earth Point |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning 13.8 kV Switchgear CT Loop Resistance and Single Earth Point | 5 | #jejs | E000 | 00E5 | E000#jejs00E5
4465 | 4465 | 4465 | 4465 | SA24M005 | CT Circuit Secondary Injection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning 13.8 kV Switchgear CT Circuit Secondary Injection | 6 | #jejs | E000 | 00E6 | E000#jejs00E6
4466 | 4466 | 4466 | 4466 | SA24M005 | VT Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning 13.8 kV Switchgear VT Test | 7 | #jejs | E000 | 00E7 | E000#jejs00E7
4467 | 4467 | 4467 | 4467 | SA24M005 | VT Secondary Circuit Injection & Loop Resistance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning 13.8 kV Switchgear VT Secondary Circuit Injection & Loop Resistance | 8 | #jejs | E000 | 00E8 | E000#jejs00E8
4468 | 4468 | 4468 | 4468 | SA24M005 | CB Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning 13.8 kV Switchgear CB Test | 9 | #jejs | E000 | 00E9 | E000#jejs00E9
4469 | 4469 | 4469 | 4469 | SA24M005 | BB Contact Resistance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning 13.8 kV Switchgear BB Contact Resistance Test | 10 | #jejs | E000 | 0E10 | E000#jejs0E10
4470 | 4470 | 4470 | 4470 | SA24M005 | ES Contact Resistance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning 13.8 kV Switchgear ES Contact Resistance Test | 11 | #jejs | E000 | 0E11 | E000#jejs0E11
4471 | 4471 | 4471 | 4471 | SA24M005 | Cooling Fans System |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning 13.8 kV Switchgear Cooling Fans System | 12 | #jejs | E000 | 0E12 | E000#jejs0E12
4472 | 4472 | 4472 | 4472 | SA24M005 | Scheme Check |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning 13.8 kV Switchgear Scheme Check | 13 | #jejs | E000 | 0E13 | E000#jejs0E13
4473 | 4473 | 4473 | 4473 | SA24M005 | HV Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning 13.8 kV Switchgear HV Test | 14 | #jejs | E000 | 0E14 | E000#jejs0E14
4474 | 4474 | 4474 | 4474 | SA24M005 | CT Primary Injection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning 13.8 kV Switchgear CT Primary Injection | 15 | #jejs | E000 | 0E15 | E000#jejs0E15
4475 | 4475 | 4475 | 4475 | SA24M005 | EHV Shunt Reactor |  | 5 | -1 | 0 |  |  | X
4476 | 4476 | 4476 | 4476 | SA24M005 | Visual Inspection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning EHV Shunt Reactor Visual Inspection | 1 | E0SHR | M000 | 00M1 | M000E0SHR00M1
4477 | 4477 | 4477 | 4477 | SA24M005 | Measurement of DC Insulation Resistance and check of Core Insulation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning EHV Shunt Reactor Measurement of DC Insulation Resistance and check of Core Insulation | 2 | E0SHR | M000 | 00M2 | M000E0SHR00M2
4478 | 4478 | 4478 | 4478 | SA24M005 | Measurement of Winding Resistance and Reactance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning EHV Shunt Reactor Measurement of Winding Resistance and Reactance Test | 3 | E0SHR | M000 | 00M3 | M000E0SHR00M3
4479 | 4479 | 4479 | 4479 | SA24M005 | Short Circuit (%Z), Zero Sequence Impedance (Z0),No Load, Vector Group & Magnetic Balance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning EHV Shunt Reactor Short Circuit (%Z), Zero Sequence Impedance (Z0),No Load, Vector Group & Magnetic Balance | 4 | E0SHR | M000 | 00M4 | M000E0SHR00M4
4480 | 4480 | 4480 | 4480 | SA24M005 | Measurement of Dissipation Factor(Tan Delta) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning EHV Shunt Reactor Measurement of Dissipation Factor(Tan Delta) | 5 | E0SHR | M000 | 00M5 | M000E0SHR00M5
4481 | 4481 | 4481 | 4481 | SA24M005 | Mechanical Protection Devices Test And MK Function Checks |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning EHV Shunt Reactor Mechanical Protection Devices Test And MK Function Checks | 6 | E0SHR | M000 | 00M6 | M000E0SHR00M6
4482 | 4482 | 4482 | 4482 | SA24M005 | Calibration of Winding & Oil Temperature Gauges |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning EHV Shunt Reactor Calibration of Winding & Oil Temperature Gauges | 7 | E0SHR | M000 | 00M7 | M000E0SHR00M7
4483 | 4483 | 4483 | 4483 | SA24M005 | Oil Dielectric Breakdown |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning EHV Shunt Reactor Oil Dielectric Breakdown | 8 | E0SHR | M000 | 00M8 | M000E0SHR00M8
4484 | 4484 | 4484 | 4484 | SA24M005 | On-Line Gas Analyzer Devices |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning EHV Shunt Reactor On-Line Gas Analyzer Devices | 9 | E0SHR | M000 | 00M9 | M000E0SHR00M9
4485 | 4485 | 4485 | 4485 | SA24M005 | Fans Motors, Oil Pumps, MCCB's,MCB's, Aux Relays and Meters |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning EHV Shunt Reactor Fans Motors, Oil Pumps, MCCB's,MCB's, Aux Relays and Meters | 10 | E0SHR | M000 | 0M10 | M000E0SHR0M10
4486 | 4486 | 4486 | 4486 | SA24M005 | Bushing CT |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning EHV Shunt Reactor Bushing CT | 11 | E0SHR | M000 | 0M11 | M000E0SHR0M11
4487 | 4487 | 4487 | 4487 | SA24M005 | BCT Secondary Circuits, Loop Resistance and Burden |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning EHV Shunt Reactor BCT Secondary Circuits, Loop Resistance and Burden | 12 | E0SHR | M000 | 0M12 | M000E0SHR0M12
4488 | 4488 | 4488 | 4488 | SA24M005 | Oil Leak Test With Pressure |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning EHV Shunt Reactor Oil Leak Test With Pressure | 13 | E0SHR | M000 | 0M13 | M000E0SHR0M13
4489 | 4489 | 4489 | 4489 | SA24M005 | Measurement of Frequency Response (Frequency Response Analysis FRA) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning EHV Shunt Reactor Measurement of Frequency Response (Frequency Response Analysis FRA) | 14 | E0SHR | M000 | 0M14 | M000E0SHR0M14
4490 | 4490 | 4490 | 4490 | SA24M005 | DGA Oil Sample At Third Party Lab |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning EHV Shunt Reactor DGA Oil Sample At Third Party Lab | 15 | E0SHR | M000 | 0M15 | M000E0SHR0M15
4491 | 4491 | 4491 | 4491 | SA24M005 | HV Shunt Reactor & Line Reactor |  | 5 | -1 | 0 |  |  | X
4492 | 4492 | 4492 | 4492 | SA24M005 | Visual Inspection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning HV Shunt Reactor & Line Reactor Visual Inspection | 1 | CHSR | M000 | 00M1 | M000CHSR00M1
4493 | 4493 | 4493 | 4493 | SA24M005 | Measurement of DC Insulation Resistance and check of Core Insulation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning HV Shunt Reactor & Line Reactor Measurement of DC Insulation Resistance and check of Core Insulation | 2 | CHSR | M000 | 00M2 | M000CHSR00M2
4494 | 4494 | 4494 | 4494 | SA24M005 | Measurement of Winding Resistance and Reactance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning HV Shunt Reactor & Line Reactor Measurement of Winding Resistance and Reactance Test | 3 | CHSR | M000 | 00M3 | M000CHSR00M3
4495 | 4495 | 4495 | 4495 | SA24M005 | Short Circuit (%Z), Zero Sequence Impedance (Z0),No Load, Vector Group & Magnetic Balance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning HV Shunt Reactor & Line Reactor Short Circuit (%Z), Zero Sequence Impedance (Z0),No Load, Vector Group & Magnetic Balance | 4 | CHSR | M000 | 00M4 | M000CHSR00M4
4496 | 4496 | 4496 | 4496 | SA24M005 | Measurement of Dissipation Factor(Tan Delta) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning HV Shunt Reactor & Line Reactor Measurement of Dissipation Factor(Tan Delta) | 5 | CHSR | M000 | 00M5 | M000CHSR00M5
4497 | 4497 | 4497 | 4497 | SA24M005 | Mechanical Protection Devices Test And MK Function Checks |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning HV Shunt Reactor & Line Reactor Mechanical Protection Devices Test And MK Function Checks | 6 | CHSR | M000 | 00M6 | M000CHSR00M6
4498 | 4498 | 4498 | 4498 | SA24M005 | Calibration of Winding & Oil Temperature Gauges |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning HV Shunt Reactor & Line Reactor Calibration of Winding & Oil Temperature Gauges | 7 | CHSR | M000 | 00M7 | M000CHSR00M7
4499 | 4499 | 4499 | 4499 | SA24M005 | Oil Dielectric Breakdown |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning HV Shunt Reactor & Line Reactor Oil Dielectric Breakdown | 8 | CHSR | M000 | 00M8 | M000CHSR00M8
4500 | 4500 | 4500 | 4500 | SA24M005 | On-Line Gas Analyzer Devices |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning HV Shunt Reactor & Line Reactor On-Line Gas Analyzer Devices | 9 | CHSR | M000 | 00M9 | M000CHSR00M9
4501 | 4501 | 4501 | 4501 | SA24M005 | Fans Motors, Oil Pumps, MCCB's,MCB's, Aux Relays and Meters |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning HV Shunt Reactor & Line Reactor Fans Motors, Oil Pumps, MCCB's,MCB's, Aux Relays and Meters | 10 | CHSR | M000 | 0M10 | M000CHSR0M10
4502 | 4502 | 4502 | 4502 | SA24M005 | Bushing CT |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning HV Shunt Reactor & Line Reactor Bushing CT | 11 | CHSR | M000 | 0M11 | M000CHSR0M11
4503 | 4503 | 4503 | 4503 | SA24M005 | BCT Secondary Circuits, Loop Resistance and Burden |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning HV Shunt Reactor & Line Reactor BCT Secondary Circuits, Loop Resistance and Burden | 12 | CHSR | M000 | 0M12 | M000CHSR0M12
4504 | 4504 | 4504 | 4504 | SA24M005 | Oil Leak Test With Pressure |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning HV Shunt Reactor & Line Reactor Oil Leak Test With Pressure | 13 | CHSR | M000 | 0M13 | M000CHSR0M13
4505 | 4505 | 4505 | 4505 | SA24M005 | Measurement of Frequency Response (Frequency Response Analysis FRA) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning HV Shunt Reactor & Line Reactor Measurement of Frequency Response (Frequency Response Analysis FRA) | 14 | CHSR | M000 | 0M14 | M000CHSR0M14
4506 | 4506 | 4506 | 4506 | SA24M005 | DGA Oil Sample At Third Party Lab |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning HV Shunt Reactor & Line Reactor DGA Oil Sample At Third Party Lab | 15 | CHSR | M000 | 0M15 | M000CHSR0M15
4507 | 4507 | 4507 | 4507 | SA24M005 | Auxiliary Transformer |  | 5 | -1 | 0 |  |  | X
4508 | 4508 | 4508 | 4508 | SA24M005 | Auxiliary Transformer |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Auxiliary Transformer Auxiliary Transformer | 1 | CAUXT | M000 | 00M1 | M000CAUXT00M1
4509 | 4509 | 4509 | 4509 | SA24M005 | Stand Alone Surge Arrester |  | 5 | -1 | 0 |  |  | X | M000CAUXT
4510 | 4510 | 4510 | 4510 | SA24M005 | EHV Stand Alone Surge Arrester |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Stand Alone Surge Arrester EHV Stand Alone Surge Arrester | 1 | ESURG | M000 | 00M1 | M000ESURG00M1
4511 | 4511 | 4511 | 4511 | SA24M005 | Stand Alone Current Transformer |  | 5 | -1 | 0 |  |  | X | M000ESURG
4512 | 4512 | 4512 | 4512 | SA24M005 | EHV Stand Alone CT |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Stand Alone Current Transformer EHV Stand Alone CT | 1 | E0STR | M000 | 00M1 | M000E0STR00M1
4513 | 4513 | 4513 | 4513 | SA24M005 | EHV Stand Alone CT Secondary Circuit Injection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Stand Alone Current Transformer EHV Stand Alone CT Secondary Circuit Injection | 2 | E0STR | M000 | 00M2 | M000E0STR00M2
4514 | 4514 | 4514 | 4514 | SA24M005 | EHV Stand Alone CT Loop Resistance and Single Earth Point |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Stand Alone Current Transformer EHV Stand Alone CT Loop Resistance and Single Earth Point | 3 | E0STR | M000 | 00M3 | M000E0STR00M3
4515 | 4515 | 4515 | 4515 | SA24M005 | EHV Stand Alone CT Primary Injection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Stand Alone Current Transformer EHV Stand Alone CT Primary Injection | 4 | E0STR | M000 | 00M4 | M000E0STR00M4
4516 | 4516 | 4516 | 4516 | SA24M005 | Low Voltage Cable |  | 5 | -1 | 0 |  |  | X
4517 | 4517 | 4517 | 4517 | SA24M005 | LV Cable Insulation Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Low Voltage Cable LV Cable Insulation Test | 1 | LVCBL | M000 | 00M1 | M000LVCBL00M1
4518 | 4518 | 4518 | 4518 | SA24M005 | LV Cable Phasing and Continuity Check |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Low Voltage Cable LV Cable Phasing and Continuity Check | 2 | LVCBL | M000 | 00M2 | M000LVCBL00M2
4519 | 4519 | 4519 | 4519 | SA24M005 | LV Cable HV Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Low Voltage Cable LV Cable HV Test | 3 | LVCBL | M000 | 00M3 | M000LVCBL00M3
4520 | 4520 | 4520 | 4520 | SA24M005 | Auxiliary/Trip Relay In Control And Protection Panels |  | 5 | -1 | 0 |  |  | X
4521 | 4521 | 4521 | 4521 | SA24M005 | Auxiliary Relays Test In Control Room Panels |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Auxiliary/Trip Relay In Control And Protection Panels Auxiliary Relays Test In Control Room Panels | 1 | CAUXR | E000 | 00E1 | E000CAUXR00E1
4522 | 4522 | 4522 | 4522 | SA24M005 | Trip Relays Test In Control Room Panels |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Auxiliary/Trip Relay In Control And Protection Panels Trip Relays Test In Control Room Panels | 2 | CAUXR | E000 | 00E2 | E000CAUXR00E2
4523 | 4523 | 4523 | 4523 | SA24M005 | MCB In Control And Protection Panels |  | 5 | -1 | 0 |  |  | X
4524 | 4524 | 4524 | 4524 | SA24M005 | MCB Test In Control And Protection Panels |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning MCB In Control And Protection Panels MCB Test In Control And Protection Panels | 1 | 0MCB | M000 | 00M1 | M0000MCB00M1
4525 | 4525 | 4525 | 4525 | SA24M005 | Scheme Check for Protection Panels |  | 5 | -1 | 0 |  |  | X | M0000MCB
4526 | 4526 | 4526 | 4526 | SA24M005 | EHV Line Protection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Scheme Check for Protection Panels EHV Line Protection | 1 | E0PLP | M000 | 00M1 | M000E0PLP00M1
4527 | 4527 | 4527 | 4527 | SA24M005 | EHV Auto Recloser Panel |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Scheme Check for Protection Panels EHV Auto Recloser Panel | 2 | E0PLP | M000 | 00M2 | M000E0PLP00M2
4528 | 4528 | 4528 | 4528 | SA24M005 | EHV Shunt Reactor Protection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Scheme Check for Protection Panels EHV Shunt Reactor Protection | 3 | E0PLP | M000 | 00M3 | M000E0PLP00M3
4529 | 4529 | 4529 | 4529 | SA24M005 | EHV Tee Protection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Scheme Check for Protection Panels EHV Tee Protection | 4 | E0PLP | M000 | 00M4 | M000E0PLP00M4
4530 | 4530 | 4530 | 4530 | SA24M005 | EHV BBP |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Scheme Check for Protection Panels EHV BBP | 5 | E0PLP | M000 | 00M5 | M000E0PLP00M5
4531 | 4531 | 4531 | 4531 | SA24M005 | EHV CBF |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Scheme Check for Protection Panels EHV CBF | 6 | E0PLP | M000 | 00M6 | M000E0PLP00M6
4532 | 4532 | 4532 | 4532 | SA24M005 | EHV Pole Discrepancy |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Scheme Check for Protection Panels EHV Pole Discrepancy | 7 | E0PLP | M000 | 00M7 | M000E0PLP00M7
4533 | 4533 | 4533 | 4533 | SA24M005 | EHV Trip Circuit Supervision |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Scheme Check for Protection Panels EHV Trip Circuit Supervision | 8 | E0PLP | M000 | 00M8 | M000E0PLP00M8
4534 | 4534 | 4534 | 4534 | SA24M005 | Transient Fault Recorder TFR Panel |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Scheme Check for Protection Panels Transient Fault Recorder TFR Panel | 9 | E0PLP | M000 | 00M9 | M000E0PLP00M9
4535 | 4535 | 4535 | 4535 | SA24M005 | DSM PANEL TESTING |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Scheme Check for Protection Panels DSM PANEL TESTING | 10 | E0PLP | M000 | 0M10 | M000E0PLP0M10
4536 | 4536 | 4536 | 4536 | SA24M005 | Energy Meter Panel Scheme Check |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Scheme Check for Protection Panels Energy Meter Panel Scheme Check | 11 | E0PLP | M000 | 0M11 | M000E0PLP0M11
4537 | 4537 | 4537 | 4537 | SA24M005 | EHV Line Protection (380kV Lines) |  | 5 | -1 | 0 |  |  | X
4538 | 4538 | 4538 | 4538 | SA24M005 | Main 1 Multifunction Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning EHV Line Protection (380kV Lines) Main 1 Multifunction Relay Acceptance Test | 1 | E0MFR | E000 | 00E1 | E000E0MFR00E1
4539 | 4539 | 4539 | 4539 | SA24M005 | Main 1 Multifunction Relay Final setting Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning EHV Line Protection (380kV Lines) Main 1 Multifunction Relay Final setting Test | 2 | E0MFR | E000 | 00E2 | E000E0MFR00E2
4540 | 4540 | 4540 | 4540 | SA24M005 | Main 2 Multifunction Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning EHV Line Protection (380kV Lines) Main 2 Multifunction Relay Acceptance Test | 3 | E0MFR | E000 | 00E3 | E000E0MFR00E3
4541 | 4541 | 4541 | 4541 | SA24M005 | Main 2 Multifunction Relay Final setting Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning EHV Line Protection (380kV Lines) Main 2 Multifunction Relay Final setting Test | 4 | E0MFR | E000 | 00E4 | E000E0MFR00E4
4542 | 4542 | 4542 | 4542 | SA24M005 | Undervoltage and Overvoltage Relay Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning EHV Line Protection (380kV Lines) Undervoltage and Overvoltage Relay Test | 5 | E0MFR | E000 | 00E5 | E000E0MFR00E5
4543 | 4543 | 4543 | 4543 | SA24M005 | Automatic Recloser |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning EHV Line Protection (380kV Lines) Automatic Recloser | 6 | E0MFR | E000 | 00E6 | E000E0MFR00E6
4544 | 4544 | 4544 | 4544 | SA24M005 | EHV Shunt Reactor Protection & Line Reactor |  | 5 | -1 | 0 |  |  | X
4545 | 4545 | 4545 | 4545 | SA24M005 | Set 1 Differential Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning EHV Shunt Reactor Protection & Line Reactor Set 1 Differential Relay Acceptance Test | 1 | E0SHR | E000 | 00E1 | E000#RTIh00E1
4546 | 4546 | 4546 | 4546 | SA24M005 | Set 1 Differential Relay Final Setting Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning EHV Shunt Reactor Protection & Line Reactor Set 1 Differential Relay Final Setting Test | 2 | E0SHR | E000 | 00E2 | E000#RTIh00E2
4547 | 4547 | 4547 | 4547 | SA24M005 | Set 2 Differential Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning EHV Shunt Reactor Protection & Line Reactor Set 2 Differential Relay Acceptance Test | 3 | E0SHR | E000 | 00E3 | E000#RTIh00E3
4548 | 4548 | 4548 | 4548 | SA24M005 | Set 2 Differential Relay Final setting Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning EHV Shunt Reactor Protection & Line Reactor Set 2 Differential Relay Final setting Test | 4 | E0SHR | E000 | 00E4 | E000#RTIh00E4
4549 | 4549 | 4549 | 4549 | SA24M005 | Overcurrent And Earth Fault Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning EHV Shunt Reactor Protection & Line Reactor Overcurrent And Earth Fault Relay Acceptance Test | 5 | E0SHR | E000 | 00E5 | E000#RTIh00E5
4550 | 4550 | 4550 | 4550 | SA24M005 | Overcurrent And Earth Fault Relay Final Setting Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning EHV Shunt Reactor Protection & Line Reactor Overcurrent And Earth Fault Relay Final Setting Test | 6 | E0SHR | E000 | 00E6 | E000#RTIh00E6
4551 | 4551 | 4551 | 4551 | SA24M005 | Under voltage and Over voltage relay |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning EHV Shunt Reactor Protection & Line Reactor Under voltage and Over voltage relay | 7 | E0SHR | E000 | 00E7 | E000#RTIh00E7
4552 | 4552 | 4552 | 4552 | SA24M005 | Set 1 CT Supervision Relay Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning EHV Shunt Reactor Protection & Line Reactor Set 1 CT Supervision Relay Test | 8 | E0SHR | E000 | 00E8 | E000#RTIh00E8
4553 | 4553 | 4553 | 4553 | SA24M005 | Set 2 CT Supervision Relay Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning EHV Shunt Reactor Protection & Line Reactor Set 2 CT Supervision Relay Test | 9 | E0SHR | E000 | 00E9 | E000#RTIh00E9
4554 | 4554 | 4554 | 4554 | SA24M005 | EHV TEE Protection |  | 5 | -1 | 0 |  |  | X | E000#RTIh
4555 | 4555 | 4555 | 4555 | SA24M005 | Set 1 Differential Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning EHV TEE Protection Set 1 Differential Relay Acceptance Test | 1 | E0TPS | E000 | 00E1 | E000E0TPS00E1
4556 | 4556 | 4556 | 4556 | SA24M005 | Set 1 Differential Relay Final Setting Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning EHV TEE Protection Set 1 Differential Relay Final Setting Test | 2 | E0TPS | E000 | 00E2 | E000E0TPS00E2
4557 | 4557 | 4557 | 4557 | SA24M005 | Set 2 Differential Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning EHV TEE Protection Set 2 Differential Relay Acceptance Test | 3 | E0TPS | E000 | 00E3 | E000E0TPS00E3
4558 | 4558 | 4558 | 4558 | SA24M005 | Set 2 Differential Relay Final Setting Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning EHV TEE Protection Set 2 Differential Relay Final Setting Test | 4 | E0TPS | E000 | 00E4 | E000E0TPS00E4
4559 | 4559 | 4559 | 4559 | SA24M005 | Set 1 CT Supervision Relay |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning EHV TEE Protection Set 1 CT Supervision Relay | 5 | E0TPS | E000 | 00E5 | E000E0TPS00E5
4560 | 4560 | 4560 | 4560 | SA24M005 | Set 2 CT Supervision Relay |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning EHV TEE Protection Set 2 CT Supervision Relay | 6 | E0TPS | E000 | 00E6 | E000E0TPS00E6
4561 | 4561 | 4561 | 4561 | SA24M005 | EHV STUB Protection |  | 5 | -1 | 0 |  |  | X
4562 | 4562 | 4562 | 4562 | SA24M005 | Set 1 Stub Protection Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning EHV STUB Protection Set 1 Stub Protection Relay Acceptance Test | 1 | E0STR | E000 | 00E1 | E000#AhHB00E1
4563 | 4563 | 4563 | 4563 | SA24M005 | Set 2 Stub Protection Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning EHV STUB Protection Set 2 Stub Protection Relay Acceptance Test | 2 | E0STR | E000 | 00E2 | E000#AhHB00E2
4564 | 4564 | 4564 | 4564 | SA24M005 | Set 1 Stub Protection Relay Final Setting Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning EHV STUB Protection Set 1 Stub Protection Relay Final Setting Test | 3 | E0STR | E000 | 00E3 | E000#AhHB00E3
4565 | 4565 | 4565 | 4565 | SA24M005 | Set 2 Stub Protection Relay Final Setting Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning EHV STUB Protection Set 2 Stub Protection Relay Final Setting Test | 4 | E0STR | E000 | 00E4 | E000#AhHB00E4
4566 | 4566 | 4566 | 4566 | SA24M005 | EHV Bus Bar Protection |  | 5 | -1 | 0 |  |  | X | E000#AhHB
4567 | 4567 | 4567 | 4567 | SA24M005 | Set 1 High Impedance BBP |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning EHV Bus Bar Protection Set 1 High Impedance BBP | 1 | E0BBP | M000 | 00M1 | M000E0BBP00M1
4568 | 4568 | 4568 | 4568 | SA24M005 | Set 2 High Impedance BBP |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning EHV Bus Bar Protection Set 2 High Impedance BBP | 2 | E0BBP | M000 | 00M2 | M000E0BBP00M2
4569 | 4569 | 4569 | 4569 | SA24M005 | Set-1 CT Supervision Relay Test for BBP |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning EHV Bus Bar Protection Set-1 CT Supervision Relay Test for BBP | 3 | E0BBP | M000 | 00M3 | M000E0BBP00M3
4570 | 4570 | 4570 | 4570 | SA24M005 | Set-2 CT Supervision Relay Test for BBP |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning EHV Bus Bar Protection Set-2 CT Supervision Relay Test for BBP | 4 | E0BBP | M000 | 00M4 | M000E0BBP00M4
4571 | 4571 | 4571 | 4571 | SA24M005 | Circuit Breaker Fail Protection |  | 5 | -1 | 0 |  |  | X
4572 | 4572 | 4572 | 4572 | SA24M005 | Set 1 CBF Relay Acceptance Test For EHV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Circuit Breaker Fail Protection Set 1 CBF Relay Acceptance Test For EHV | 1 | ECCBF | M000 | 00M1 | M000ECCBF00M1
4573 | 4573 | 4573 | 4573 | SA24M005 | Set 1 CBF Relay Final Setting Test For EHV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Circuit Breaker Fail Protection Set 1 CBF Relay Final Setting Test For EHV | 2 | ECCBF | M000 | 00M2 | M000ECCBF00M2
4574 | 4574 | 4574 | 4574 | SA24M005 | Set 2 CBF Relay Acceptance Test For EHV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Circuit Breaker Fail Protection Set 2 CBF Relay Acceptance Test For EHV | 3 | ECCBF | M000 | 00M3 | M000ECCBF00M3
4575 | 4575 | 4575 | 4575 | SA24M005 | Set 2 CBF Relay Final Setting Test For EHV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Circuit Breaker Fail Protection Set 2 CBF Relay Final Setting Test For EHV | 4 | ECCBF | M000 | 00M4 | M000ECCBF00M4
4576 | 4576 | 4576 | 4576 | SA24M005 | 13.8kV Feeder Protection |  | 5 | -1 | 0 |  |  | X
4577 | 4577 | 4577 | 4577 | SA24M005 | Over Current and Earth Fault Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning 13.8kV Feeder Protection Over Current and Earth Fault Relay Acceptance Test | 1 | 0FRPN | M000 | 00M1 | M0000FRPN00M1
4578 | 4578 | 4578 | 4578 | SA24M005 | Over Current and Earth Fault Relay Final Setting Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning 13.8kV Feeder Protection Over Current and Earth Fault Relay Final Setting Test | 2 | 0FRPN | M000 | 00M2 | M0000FRPN00M2
4579 | 4579 | 4579 | 4579 | SA24M005 | Sensitive Earth Fault Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning 13.8kV Feeder Protection Sensitive Earth Fault Relay Acceptance Test | 3 | 0FRPN | M000 | 00M3 | M0000FRPN00M3
4580 | 4580 | 4580 | 4580 | SA24M005 | Sensitive Earth Fault Relay Final Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning 13.8kV Feeder Protection Sensitive Earth Fault Relay Final Test | 4 | 0FRPN | M000 | 00M4 | M0000FRPN00M4
4581 | 4581 | 4581 | 4581 | SA24M005 | Synchronizing Check Relays |  | 5 | -1 | 0 |  |  | X
4582 | 4582 | 4582 | 4582 | SA24M005 | EHV Synchro-Check Relay |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Synchronizing Check Relays EHV Synchro-Check Relay | 1 | E0SYN | M000 | 00M1 | M000E0SYN00M1
4583 | 4583 | 4583 | 4583 | SA24M005 | Automatic Voltage Regulator |  | 5 | -1 | 0 |  |  | X | M000E0SYN
4584 | 4584 | 4584 | 4584 | SA24M005 | AVC Relay Acceptance Test For EHV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Automatic Voltage Regulator AVC Relay Acceptance Test For EHV | 1 | CAVR | M000 | 00M1 | M000CAVR00M1
4585 | 4585 | 4585 | 4585 | SA24M005 | AVC Relay Final Setting Test For EHV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Automatic Voltage Regulator AVC Relay Final Setting Test For EHV | 2 | CAVR | M000 | 00M2 | M000CAVR00M2
4586 | 4586 | 4586 | 4586 | SA24M005 | Stability Test |  | 5 | -1 | 0 |  |  | X
4587 | 4587 | 4587 | 4587 | SA24M005 | EHV Busbar Protection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Stability Test EHV Busbar Protection | 1 | ESTAB | M000 | 00M1 | M000ESTAB00M1
4588 | 4588 | 4588 | 4588 | SA24M005 | EHV TEE Differential Protection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Stability Test EHV TEE Differential Protection | 2 | ESTAB | M000 | 00M2 | M000ESTAB00M2
4589 | 4589 | 4589 | 4589 | SA24M005 | EHV Shunt Reactor Differential/REF |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Stability Test EHV Shunt Reactor Differential/REF | 3 | ESTAB | M000 | 00M3 | M000ESTAB00M3
4590 | 4590 | 4590 | 4590 | SA24M005 | Advanced Metering Infrastructure |  | 5 | -1 | 0 |  |  | X
4591 | 4591 | 4591 | 4591 | SA24M005 | Revenue Meter |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Advanced Metering Infrastructure Revenue Meter | 1 | A0AMI | E000 | 00E1 | E000A0AMI00E1
4592 | 4592 | 4592 | 4592 | SA24M005 | Power Quality Meter |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Advanced Metering Infrastructure Power Quality Meter | 2 | A0AMI | E000 | 00E2 | E000A0AMI00E2
4593 | 4593 | 4593 | 4593 | SA24M005 | Switch Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Advanced Metering Infrastructure Switch Test | 3 | A0AMI | E000 | 00E3 | E000A0AMI00E3
4594 | 4594 | 4594 | 4594 | SA24M005 | Scheme Check |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Advanced Metering Infrastructure Scheme Check | 4 | A0AMI | E000 | 00E4 | E000A0AMI00E4
4595 | 4595 | 4595 | 4595 | SA24M005 | Operation Interlocking |  | 5 | -1 | 0 |  |  | X
4596 | 4596 | 4596 | 4596 | SA24M005 | Operation and Interlocking Test for EHV GIS |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Operation Interlocking Operation and Interlocking Test for EHV GIS | 1 | E0GIS | E000 | 00E1 | E000#oGcy00E1
4597 | 4597 | 4597 | 4597 | SA24M005 | Operation and Interlocking Test for HV GIS |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Operation Interlocking Operation and Interlocking Test for HV GIS | 2 | E0GIS | E000 | 00E2 | E000#oGcy00E2
4598 | 4598 | 4598 | 4598 | SA24M005 | Operation And Interlocking Test for 13.8kV Switchgear |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Operation Interlocking Operation And Interlocking Test for 13.8kV Switchgear | 3 | E0GIS | E000 | 00E3 | E000#oGcy00E3
4599 | 4599 | 4599 | 4599 | SA24M005 | SAS Equipment Check |  | 5 | -1 | 0 |  |  | X | E000#oGcy
4600 | 4600 | 4600 | 4600 | SA24M005 | Fiber Optical Cables Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning SAS Equipment Check Fiber Optical Cables Test | 1 | CSAS | M000 | 00M1 | M000CSAS00M1
4601 | 4601 | 4601 | 4601 | SA24M005 | Maintenance Laptop check |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning SAS Equipment Check Maintenance Laptop check | 2 | CSAS | M000 | 00M2 | M000CSAS00M2
4602 | 4602 | 4602 | 4602 | SA24M005 | SAS Panels Inspection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning SAS Equipment Check SAS Panels Inspection | 3 | CSAS | M000 | 00M3 | M000CSAS00M3
4603 | 4603 | 4603 | 4603 | SA24M005 | SAS Computers (Server, OWS, EWS & Gateway) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning SAS Equipment Check SAS Computers (Server, OWS, EWS & Gateway) | 4 | CSAS | M000 | 00M4 | M000CSAS00M4
4604 | 4604 | 4604 | 4604 | SA24M005 | Ethernet Switch Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning SAS Equipment Check Ethernet Switch Test | 5 | CSAS | M000 | 00M5 | M000CSAS00M5
4605 | 4605 | 4605 | 4605 | SA24M005 | GPS |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning SAS Equipment Check GPS | 6 | CSAS | M000 | 00M6 | M000CSAS00M6
4606 | 4606 | 4606 | 4606 | SA24M005 | Check Of All Peripheral Devices & KVM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning SAS Equipment Check Check Of All Peripheral Devices & KVM | 7 | CSAS | M000 | 00M7 | M000CSAS00M7
4607 | 4607 | 4607 | 4607 | SA24M005 | IED Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning SAS Equipment Check IED Test | 8 | CSAS | M000 | 00M8 | M000CSAS00M8
4608 | 4608 | 4608 | 4608 | SA24M005 | SAS Function Test |  | 5 | -1 | 0 |  |  | X
4609 | 4609 | 4609 | 4609 | SA24M005 | Redundancy Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning SAS Function Test Redundancy Test | 1 | CSASFRT | E000 | 00E1 | E000CSASFRT00E1
4610 | 4610 | 4610 | 4610 | SA24M005 | Measurement Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning SAS Function Test Measurement Test | 2 | CSASFRT | E000 | 00E2 | E000CSASFRT00E2
4611 | 4611 | 4611 | 4611 | SA24M005 | Startup Behavior |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning SAS Function Test Startup Behavior | 3 | CSASFRT | E000 | 00E3 | E000CSASFRT00E3
4612 | 4612 | 4612 | 4612 | SA24M005 | User Access Level Management |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning SAS Function Test User Access Level Management | 4 | CSASFRT | E000 | 00E4 | E000CSASFRT00E4
4613 | 4613 | 4613 | 4613 | SA24M005 | Time Synchronization Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning SAS Function Test Time Synchronization Test | 5 | CSASFRT | E000 | 00E5 | E000CSASFRT00E5
4614 | 4614 | 4614 | 4614 | SA24M005 | SAS Control Authority (IED, HMI & Gateway) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning SAS Function Test SAS Control Authority (IED, HMI & Gateway) | 6 | CSASFRT | E000 | 00E6 | E000CSASFRT00E6
4615 | 4615 | 4615 | 4615 | SA24M005 | Alarm And Indication Check Up To SAS HMI And Gateway For MV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning SAS Function Test Alarm And Indication Check Up To SAS HMI And Gateway For MV | 7 | CSASFRT | E000 | 00E7 | E000CSASFRT00E7
4616 | 4616 | 4616 | 4616 | SA24M005 | Alarm And Indication Check Up To SAS HMI And Gateway For HV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning SAS Function Test Alarm And Indication Check Up To SAS HMI And Gateway For HV | 8 | CSASFRT | E000 | 00E8 | E000CSASFRT00E8
4617 | 4617 | 4617 | 4617 | SA24M005 | Alarm And Indication Check Up To SAS HMI And Gateway For EHV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning SAS Function Test Alarm And Indication Check Up To SAS HMI And Gateway For EHV | 9 | CSASFRT | E000 | 00E9 | E000CSASFRT00E9
4618 | 4618 | 4618 | 4618 | SA24M005 | Alarm And Imdication Check Up to SAS HMI And Gateway for Common Alarm |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning SAS Function Test Alarm And Imdication Check Up to SAS HMI And Gateway for Common Alarm | 10 | CSASFRT | E000 | 0E10 | E000CSASFRT0E10
4619 | 4619 | 4619 | 4619 | SA24M005 | Operation and Interlocking Test for 13.8kV Switchgear |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning SAS Function Test Operation and Interlocking Test for 13.8kV Switchgear | 11 | CSASFRT | E000 | 0E11 | E000CSASFRT0E11
4620 | 4620 | 4620 | 4620 | SA24M005 | Operation and Interlocking Test for HV Switchgear |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning SAS Function Test Operation and Interlocking Test for HV Switchgear | 12 | CSASFRT | E000 | 0E12 | E000CSASFRT0E12
4621 | 4621 | 4621 | 4621 | SA24M005 | Operation and Interlocking Test for EHV Switchgear |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning SAS Function Test Operation and Interlocking Test for EHV Switchgear | 13 | CSASFRT | E000 | 0E13 | E000CSASFRT0E13
4622 | 4622 | 4622 | 4622 | SA24M005 | 13.8kV Closed Loop test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning SAS Function Test 13.8kV Closed Loop test | 14 | CSASFRT | E000 | 0E14 | E000CSASFRT0E14
4623 | 4623 | 4623 | 4623 | SA24M005 | HV Closed Loop test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning SAS Function Test HV Closed Loop test | 15 | CSASFRT | E000 | 0E15 | E000CSASFRT0E15
4624 | 4624 | 4624 | 4624 | SA24M005 | EHV Closed Loop test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning SAS Function Test EHV Closed Loop test | 16 | CSASFRT | E000 | 0E16 | E000CSASFRT0E16
4625 | 4625 | 4625 | 4625 | SA24M005 | Closed loop Test for Common Alarm |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning SAS Function Test Closed loop Test for Common Alarm | 17 | CSASFRT | E000 | 0E17 | E000CSASFRT0E17
4626 | 4626 | 4626 | 4626 | SA24M005 | AMI/AMR Measurement Test with CRCC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning SAS Function Test AMI/AMR Measurement Test with CRCC | 18 | CSASFRT | E000 | 0E18 | E000CSASFRT0E18
4627 | 4627 | 4627 | 4627 | SA24M005 | Basic Function Check for SAS HMI |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning SAS Function Test Basic Function Check for SAS HMI | 19 | CSASFRT | E000 | 0E19 | E000CSASFRT0E19
4628 | 4628 | 4628 | 4628 | SA24M005 | Cyber Security Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning SAS Function Test Cyber Security Test | 20 | CSASFRT | E000 | 0E20 | E000CSASFRT0E20
4629 | 4629 | 4629 | 4629 | SA24M005 | End to End Test |  | 5 | -1 | 0 |  |  | X
4630 | 4630 | 4630 | 4630 | SA24M005 | EHV Line Feeder Set 1 Multifunction Relay |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning End to End Test EHV Line Feeder Set 1 Multifunction Relay | 1 | E0EHLF | M000 | 00M1 | M000E0EHLF00M1
4631 | 4631 | 4631 | 4631 | SA24M005 | EHV Line Feeder Set 2 Multifunction Relay |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning End to End Test EHV Line Feeder Set 2 Multifunction Relay | 2 | E0EHLF | M000 | 00M2 | M000E0EHLF00M2
4632 | 4632 | 4632 | 4632 | SA24M005 | HV Line Feeder Set 1 Multifunction Relay |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning End to End Test HV Line Feeder Set 1 Multifunction Relay | 3 | E0EHLF | M000 | 00M3 | M000E0EHLF00M3
4633 | 4633 | 4633 | 4633 | SA24M005 | HV Line Feeder Set 2 Multifunction Relay |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning End to End Test HV Line Feeder Set 2 Multifunction Relay | 4 | E0EHLF | M000 | 00M4 | M000E0EHLF00M4
4634 | 4634 | 4634 | 4634 | SA24M005 | Final Trip Test |  | 5 | -1 | 0 |  |  | X
4635 | 4635 | 4635 | 4635 | SA24M005 | Final Trip Test for EHV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Final Trip Test Final Trip Test for EHV | 1 | E0FRT | M000 | 00M1 | M000E0FRT00M1
4636 | 4636 | 4636 | 4636 | SA24M005 | Final Trip Test for EHV BBP |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Final Trip Test Final Trip Test for EHV BBP | 2 | E0FRT | M000 | 00M2 | M000E0FRT00M2
4637 | 4637 | 4637 | 4637 | SA24M005 | Final Trip Test for EHV TEE Protection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Final Trip Test Final Trip Test for EHV TEE Protection | 3 | E0FRT | M000 | 00M3 | M000E0FRT00M3
4638 | 4638 | 4638 | 4638 | SA24M005 | Final Trip Test for EHV STUB Protection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Final Trip Test Final Trip Test for EHV STUB Protection | 4 | E0FRT | M000 | 00M4 | M000E0FRT00M4
4639 | 4639 | 4639 | 4639 | SA24M005 | Final Trip Test for EHV Pole Discribancy |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Final Trip Test Final Trip Test for EHV Pole Discribancy | 5 | E0FRT | M000 | 00M5 | M000E0FRT00M5
4640 | 4640 | 4640 | 4640 | SA24M005 | Final Trip Test for EHV CBF |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Final Trip Test Final Trip Test for EHV CBF | 6 | E0FRT | M000 | 00M6 | M000E0FRT00M6
4641 | 4641 | 4641 | 4641 | SA24M005 | Final Trip Test for HV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Final Trip Test Final Trip Test for HV | 7 | E0FRT | M000 | 00M7 | M000E0FRT00M7
4642 | 4642 | 4642 | 4642 | SA24M005 | Final Trip Test for HV BBP |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Final Trip Test Final Trip Test for HV BBP | 8 | E0FRT | M000 | 00M8 | M000E0FRT00M8
4643 | 4643 | 4643 | 4643 | SA24M005 | Final Trip Test for 13.8kV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Final Trip Test Final Trip Test for 13.8kV | 9 | E0FRT | M000 | 00M9 | M000E0FRT00M9
4644 | 4644 | 4644 | 4644 | SA24M005 | Final Trip Test for ACDB |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Final Trip Test Final Trip Test for ACDB | 10 | E0FRT | M000 | 0M10 | M000E0FRT0M10
4645 | 4645 | 4645 | 4645 | SA24M005 | Relay Final Setting Review |  | 5 | -1 | 0 |  |  | X
4646 | 4646 | 4646 | 4646 | SA24M005 | Relay Final settings Review for EHV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Relay Final Setting Review Relay Final settings Review for EHV | 1 | E0REL | E000 | 00E1 | E000E0REL00E1
4647 | 4647 | 4647 | 4647 | SA24M005 | Relay Final settings Review for EHV TEE |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Relay Final Setting Review Relay Final settings Review for EHV TEE | 2 | E0REL | E000 | 00E2 | E000E0REL00E2
4648 | 4648 | 4648 | 4648 | SA24M005 | Relay Final settings Review for EHV CBF |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Relay Final Setting Review Relay Final settings Review for EHV CBF | 3 | E0REL | E000 | 00E3 | E000E0REL00E3
4649 | 4649 | 4649 | 4649 | SA24M005 | Relay Final settings Review for EHV BBP |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Relay Final Setting Review Relay Final settings Review for EHV BBP | 4 | E0REL | E000 | 00E4 | E000E0REL00E4
4650 | 4650 | 4650 | 4650 | SA24M005 | Relay Final settings Review for EHV AVC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Relay Final Setting Review Relay Final settings Review for EHV AVC | 5 | E0REL | E000 | 00E5 | E000E0REL00E5
4651 | 4651 | 4651 | 4651 | SA24M005 | Relay Final settings Review for HV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Relay Final Setting Review Relay Final settings Review for HV | 6 | E0REL | E000 | 00E6 | E000E0REL00E6
4652 | 4652 | 4652 | 4652 | SA24M005 | Relay Final settings Review for HV BBP |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Relay Final Setting Review Relay Final settings Review for HV BBP | 7 | E0REL | E000 | 00E7 | E000E0REL00E7
4653 | 4653 | 4653 | 4653 | SA24M005 | Relay Final settings Review for 13.8kV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Relay Final Setting Review Relay Final settings Review for 13.8kV | 8 | E0REL | E000 | 00E8 | E000E0REL00E8
4654 | 4654 | 4654 | 4654 | SA24M005 | Relay Final settings Review for ACDB |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Relay Final Setting Review Relay Final settings Review for ACDB | 9 | E0REL | E000 | 00E9 | E000E0REL00E9
4655 | 4655 | 4655 | 4655 | SA24M005 | Normalization Before Energization |  | 5 | -1 | 0 |  |  | X
4656 | 4656 | 4656 | 4656 | SA24M005 | Normalization Before Energization EHV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Normalization Before Energization Normalization Before Energization EHV | 1 | E0NBEN | E000 | 00E1 | E000E0NBEN00E1
4657 | 4657 | 4657 | 4657 | SA24M005 | Normalization Before Energization HV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Normalization Before Energization Normalization Before Energization HV | 2 | E0NBEN | E000 | 00E2 | E000E0NBEN00E2
4658 | 4658 | 4658 | 4658 | SA24M005 | Normalization Before Energization 13.8kV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Normalization Before Energization Normalization Before Energization 13.8kV | 3 | E0NBEN | E000 | 00E3 | E000E0NBEN00E3
4659 | 4659 | 4659 | 4659 | SA24M005 | Normalization Before Energization ACDB |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Normalization Before Energization Normalization Before Energization ACDB | 4 | E0NBEN | E000 | 00E4 | E000E0NBEN00E4
4660 | 4660 | 4660 | 4660 | SA24M005 | Normalization Before Energization DCDB |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Normalization Before Energization Normalization Before Energization DCDB | 5 | E0NBEN | E000 | 00E5 | E000E0NBEN00E5
4661 | 4661 | 4661 | 4661 | SA24M005 | End of Commissioning Documents Preparation |  | 5 | -1 | 0 |  |  | X
4662 | 4662 | 4662 | 4662 | SA24M005 | End of Commissioning Documents Preparation of EHV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning End of Commissioning Documents Preparation End of Commissioning Documents Preparation of EHV | 1 | E0EHC | M000 | 00M1 | M000E0EHC00M1
4663 | 4663 | 4663 | 4663 | SA24M005 | End of Commissioning Documents Preparation of HV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning End of Commissioning Documents Preparation End of Commissioning Documents Preparation of HV | 2 | E0EHC | M000 | 00M2 | M000E0EHC00M2
4664 | 4664 | 4664 | 4664 | SA24M005 | End of Commissioning Documents Preparation 13.8 kV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning End of Commissioning Documents Preparation End of Commissioning Documents Preparation 13.8 kV | 3 | E0EHC | M000 | 00M3 | M000E0EHC00M3
4665 | 4665 | 4665 | 4665 | SA24M005 | Energization |  | 5 | -1 | 0 |  |  | X
4666 | 4666 | 4666 | 4666 | SA24M005 | Energization for EHV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Energization Energization for EHV | 1 | E0EHG | E000 | 00E1 | E000E0EHG00E1
4667 | 4667 | 4667 | 4667 | SA24M005 | Energization for HV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Energization Energization for HV | 2 | E0EHG | E000 | 00E2 | E000E0EHG00E2
4668 | 4668 | 4668 | 4668 | SA24M005 | Energization for 13.8kV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning Energization Energization for 13.8kV | 3 | E0EHG | E000 | 00E3 | E000E0EHG00E3
4669 | 4669 | 4669 | 4669 | SA24M005 | OLT |  | 5 | -1 | 0 |  |  | X
4670 | 4670 | 4670 | 4670 | SA24M005 | On Load Test For EHV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning OLT On Load Test For EHV | 1 | 0OLT | M000 | 00M1 | M0000OLT00M1
4671 | 4671 | 4671 | 4671 | SA24M005 | On Load Test For HV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning OLT On Load Test For HV | 2 | 0OLT | M000 | 00M2 | M0000OLT00M2
4672 | 4672 | 4672 | 4672 | SA24M005 | On Load Test For 13.8 kV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning OLT On Load Test For 13.8 kV | 3 | 0OLT | M000 | 00M3 | M0000OLT00M3
4673 | 4673 | 4673 | 4673 | SA24M005 | On Load Test For Phase Synchronizing Device |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Testing, Commissioning & Energization Commissioning OLT On Load Test For Phase Synchronizing Device | 4 | 0OLT | M000 | 00M4 | M0000OLT00M4
4674 | 4674 | 4674 | 4674 | SA24M005 | Project Close Out Activities |  | 3 | -1 | 0 |  |  | X
4675 | 4675 | 4675 | 4675 | SA24M005 | As Built Drawings |  | 4 | -1 | 0 |  |  | X
4676 | 4676 | 4676 | 4676 | SA24M005 | Preparation of Red Mark Up From Site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Project Close Out Activities As Built Drawings Preparation of Red Mark Up From Site | 1 | A0RMR | C000 | 00C1 | C000#VyWK00C1
4677 | 4677 | 4677 | 4677 | SA24M005 | Preparation of Draft As Built Drawings |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Project Close Out Activities As Built Drawings Preparation of Draft As Built Drawings | 2 | A0RMR | C000 | 00C2 | C000#VyWK00C2
4678 | 4678 | 4678 | 4678 | SA24M005 | As Built Review and Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Project Close Out Activities As Built Drawings As Built Review and Approval | 3 | A0RMR | C000 | 00C3 | C000#VyWK00C3
4679 | 4679 | 4679 | 4679 | SA24M005 | SEED II - Drawings Submittal & Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Project Close Out Activities As Built Drawings SEED II - Drawings Submittal & Approval | 4 | A0RMR | C000 | 00C4 | C000#VyWK00C4
4680 | 4680 | 4680 | 4680 | SA24M005 | Demobilization |  | 4 | -1 | 0 |  |  | X | C000#VyWK
4681 | 4681 | 4681 | 4681 | SA24M005 | Removal of Temporary Facilities |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Project Close Out Activities Demobilization Removal of Temporary Facilities | 1 | DTEMF | C000 | 00C1 | C000#DiAM00C1
4682 | 4682 | 4682 | 4682 | SA24M005 | Removal of Camp Facilities |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Project Close Out Activities Demobilization Removal of Camp Facilities | 2 | DTEMF | C000 | 00C2 | C000#DiAM00C2
4683 | 4683 | 4683 | 4683 | SA24M005 | Demobilization & Clean up |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Project Close Out Activities Demobilization Demobilization & Clean up | 3 | DTEMF | C000 | 00C3 | C000#DiAM00C3
4684 | 4684 | 4684 | 4684 | SA24M005 | Training to client Personels |  | 4 | -1 | 0 |  |  | X | C000#DiAM
4685 | 4685 | 4685 | 4685 | SA24M005 | 380kV GIS (In Factory) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Project Close Out Activities Training to client Personels 380kV GIS (In Factory) | 1 | 00G0GIS | C000 | 00C1 | C00000G0GIS00C1
4686 | 4686 | 4686 | 4686 | SA24M005 | 380kV Reactors (In Factory) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Project Close Out Activities Training to client Personels 380kV Reactors (In Factory) | 2 | 00G0GIS | C000 | 00C2 | C00000G0GIS00C2
4687 | 4687 | 4687 | 4687 | SA24M005 | Protection & Control System (In Factory) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Project Close Out Activities Training to client Personels Protection & Control System (In Factory) | 3 | 00G0GIS | C000 | 00C3 | C00000G0GIS00C3
4688 | 4688 | 4688 | 4688 | SA24M005 | SAS (In Factory) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Project Close Out Activities Training to client Personels SAS (In Factory) | 4 | 00G0GIS | C000 | 00C4 | C00000G0GIS00C4
4689 | 4689 | 4689 | 4689 | SA24M005 | MPLS-TP & DVM (In Factory) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Project Close Out Activities Training to client Personels MPLS-TP & DVM (In Factory) | 5 | 00G0GIS | C000 | 00C5 | C00000G0GIS00C5
4690 | 4690 | 4690 | 4690 | SA24M005 | MPLS-TP & NMS (In Factory) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Project Close Out Activities Training to client Personels MPLS-TP & NMS (In Factory) | 6 | 00G0GIS | C000 | 00C6 | C00000G0GIS00C6
4691 | 4691 | 4691 | 4691 | SA24M005 | PSE & IEEE (In Factory) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Project Close Out Activities Training to client Personels PSE & IEEE (In Factory) | 7 | 00G0GIS | C000 | 00C7 | C00000G0GIS00C7
4692 | 4692 | 4692 | 4692 | SA24M005 | RFTS |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Project Close Out Activities Training to client Personels RFTS | 8 | 00G0GIS | C000 | 00C8 | C00000G0GIS00C8
4693 | 4693 | 4693 | 4693 | SA24M005 | Communication Grad 48V (In Factory) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Project Close Out Activities Training to client Personels Communication Grad 48V (In Factory) | 9 | 00G0GIS | C000 | 00C9 | C00000G0GIS00C9
4694 | 4694 | 4694 | 4694 | SA24M005 | SAS (On Site)- Full Time |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Project Close Out Activities Training to client Personels SAS (On Site)- Full Time | 10 | 00G0GIS | C000 | 0C10 | C00000G0GIS0C10
4695 | 4695 | 4695 | 4695 | SA24M005 | HVAC (On Site) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Project Close Out Activities Training to client Personels HVAC (On Site) | 11 | 00G0GIS | C000 | 0C11 | C00000G0GIS0C11
4696 | 4696 | 4696 | 4696 | SA24M005 | DSM (On SIte) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Project Close Out Activities Training to client Personels DSM (On SIte) | 12 | 00G0GIS | C000 | 0C12 | C00000G0GIS0C12
4697 | 4697 | 4697 | 4697 | SA24M005 | IP Telephone (on Site) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Project Close Out Activities Training to client Personels IP Telephone (on Site) | 13 | 00G0GIS | C000 | 0C13 | C00000G0GIS0C13
4698 | 4698 | 4698 | 4698 | SA24M005 | 380kV GIS (On Site)- Full Time |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Project Close Out Activities Training to client Personels 380kV GIS (On Site)- Full Time | 14 | 00G0GIS | C000 | 0C14 | C00000G0GIS0C14
4699 | 4699 | 4699 | 4699 | SA24M005 | Protection & Control System- Full Time |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Project Close Out Activities Training to client Personels Protection & Control System- Full Time | 15 | 00G0GIS | C000 | 0C15 | C00000G0GIS0C15
4700 | 4700 | 4700 | 4700 | SA24M005 | HVAC- Full Time |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Project Close Out Activities Training to client Personels HVAC- Full Time | 16 | 00G0GIS | C000 | 0C16 | C00000G0GIS0C16
4701 | 4701 | 4701 | 4701 | SA24M005 | 13.8kV Switchgear- Full Time |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Project Close Out Activities Training to client Personels 13.8kV Switchgear- Full Time | 17 | 00G0GIS | C000 | 0C17 | C00000G0GIS0C17
4702 | 4702 | 4702 | 4702 | SA24M005 | SAS- Full Time |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Project Close Out Activities Training to client Personels SAS- Full Time | 18 | 00G0GIS | C000 | 0C18 | C00000G0GIS0C18
4703 | 4703 | 4703 | 4703 | SA24M005 | SAS Operations - Full Time |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Project Close Out Activities Training to client Personels SAS Operations - Full Time | 19 | 00G0GIS | C000 | 0C19 | C00000G0GIS0C19
4704 | 4704 | 4704 | 4704 | SA24M005 | Special Tool for GIS |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Project Close Out Activities Training to client Personels Special Tool for GIS | 20 | 00G0GIS | C000 | 0C20 | C00000G0GIS0C20
4705 | 4705 | 4705 | 4705 | SA24M005 | Relay Test Room Facility |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Project Close Out Activities Training to client Personels Relay Test Room Facility | 21 | 00G0GIS | C000 | 0C21 | C00000G0GIS0C21
4706 | 4706 | 4706 | 4706 | SA24M005 | Erection & Maintanenance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Project Close Out Activities Training to client Personels Erection & Maintanenance | 22 | 00G0GIS | C000 | 0C22 | C00000G0GIS0C22
4707 | 4707 | 4707 | 4707 | SA24M005 | Adaptors of all type for SF6 gas filling & Evacuation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Project Close Out Activities Training to client Personels Adaptors of all type for SF6 gas filling & Evacuation | 23 | 00G0GIS | C000 | 0C23 | C00000G0GIS0C23
4708 | 4708 | 4708 | 4708 | SA24M005 | Standard Precision Oil / Air pressrure gauge |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Project Close Out Activities Training to client Personels Standard Precision Oil / Air pressrure gauge | 24 | 00G0GIS | C000 | 0C24 | C00000G0GIS0C24
4709 | 4709 | 4709 | 4709 | SA24M005 | Shields Complete with fixing bolts |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Project Close Out Activities Training to client Personels Shields Complete with fixing bolts | 25 | 00G0GIS | C000 | 0C25 | C00000G0GIS0C25
4710 | 4710 | 4710 | 4710 | SA24M005 | Acceptance Certificate |  | 3 | -1 | 0 |  |  | X
4711 | 4711 | 4711 | 4711 | SA24M005 | TCC (Technical Completion Certificate) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Acceptance Certificate TCC (Technical Completion Certificate) | 1 | ATCCC | E000 | 00E1 | E000ATCCC00E1
4712 | 4712 | 4712 | 4712 | SA24M005 | PAC (Preliminary Completion Certificate) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Acceptance Certificate PAC (Preliminary Completion Certificate) | 2 | ATCCC | E000 | 00E2 | E000ATCCC00E2
4713 | 4713 | 4713 | 4713 | SA24M005 | FAC (Final Acceptance Certificate) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Main Station- North Qassim 380kV BSP (9061 BSP) Acceptance Certificate FAC (Final Acceptance Certificate) | 3 | ATCCC | E000 | 00E3 | E000ATCCC00E3
4714 | 4714 | 4714 | 4714 | SA24M005 | Remote End Works |  | 2 | -1 | 0 |  |  | X
4715 | 4715 | 4715 | 4715 | SA24M005 | Remote End SS-1 (9010 BSP) |  | 3 | -1 | 0 |  |  | X
4716 | 4716 | 4716 | 4716 | SA24M005 | Engineering & Design (Phase VIII) |  | 4 | -1 | 0 |  |  | X
4717 | 4717 | 4717 | 4717 | SA24M005 | Modified Single Line Drawing |  | 5 | -1 | 0 |  |  | X
4718 | 4718 | 4718 | 4718 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Engineering & Design (Phase VIII) Modified Single Line Drawing Drafting / Preparation | 1 | E0SLD | E000 | 00E1 | E000#twBC00E1
4719 | 4719 | 4719 | 4719 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Engineering & Design (Phase VIII) Modified Single Line Drawing Submission | 2 | E0SLD | E000 | 00E2 | E000#twBC00E2
4720 | 4720 | 4720 | 4720 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Engineering & Design (Phase VIII) Modified Single Line Drawing Review / Evaluation | 3 | E0SLD | E000 | 00E3 | E000#twBC00E3
4721 | 4721 | 4721 | 4721 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Engineering & Design (Phase VIII) Modified Single Line Drawing Approval with Comments | 4 | E0SLD | E000 | 00E4 | E000#twBC00E4
4722 | 4722 | 4722 | 4722 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Engineering & Design (Phase VIII) Modified Single Line Drawing FINAL Approval | 5 | E0SLD | E000 | 00E5 | E000#twBC00E5
4723 | 4723 | 4723 | 4723 | SA24M005 | Modified Overall Layout |  | 5 | -1 | 0 |  |  | X | E000#twBC
4724 | 4724 | 4724 | 4724 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Engineering & Design (Phase VIII) Modified Overall Layout Drafting / Preparation | 1 | EQ0L | E000 | 00E1 | E000#KRUb00E1
4725 | 4725 | 4725 | 4725 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Engineering & Design (Phase VIII) Modified Overall Layout Submission | 2 | EQ0L | E000 | 00E2 | E000#KRUb00E2
4726 | 4726 | 4726 | 4726 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Engineering & Design (Phase VIII) Modified Overall Layout Review / Evaluation | 3 | EQ0L | E000 | 00E3 | E000#KRUb00E3
4727 | 4727 | 4727 | 4727 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Engineering & Design (Phase VIII) Modified Overall Layout Approval with Comments | 4 | EQ0L | E000 | 00E4 | E000#KRUb00E4
4728 | 4728 | 4728 | 4728 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Engineering & Design (Phase VIII) Modified Overall Layout FINAL Approval | 5 | EQ0L | E000 | 00E5 | E000#KRUb00E5
4729 | 4729 | 4729 | 4729 | SA24M005 | Material Procurement |  | 4 | -1 | 0 |  |  | X | E000#KRUb
4730 | 4730 | 4730 | 4730 | SA24M005 | Auxiliary Power Supply Reinforcement items |  | 5 | -1 | 0 |  |  | X | E000#KRUb
4731 | 4731 | 4731 | 4731 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Material Procurement Auxiliary Power Supply Reinforcement items Purchase Request to SCM | 1 | 0APSR | P000 | 00P1 | P000#YFXa00P1
4732 | 4732 | 4732 | 4732 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Material Procurement Auxiliary Power Supply Reinforcement items Issue of RFQ | 2 | 0APSR | P000 | 00P2 | P000#YFXa00P2
4733 | 4733 | 4733 | 4733 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Material Procurement Auxiliary Power Supply Reinforcement items Receipt of Technical offer from Vendor | 3 | 0APSR | P000 | 00P3 | P000#YFXa00P3
4734 | 4734 | 4734 | 4734 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Material Procurement Auxiliary Power Supply Reinforcement items Technical Evaluation by EDRC | 4 | 0APSR | P000 | 00P4 | P000#YFXa00P4
4735 | 4735 | 4735 | 4735 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Material Procurement Auxiliary Power Supply Reinforcement items Final technical compliance from Vendor | 5 | 0APSR | P000 | 00P5 | P000#YFXa00P5
4736 | 4736 | 4736 | 4736 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Material Procurement Auxiliary Power Supply Reinforcement items Technical clearance by EDRC | 6 | 0APSR | P000 | 00P6 | P000#YFXa00P6
4737 | 4737 | 4737 | 4737 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Material Procurement Auxiliary Power Supply Reinforcement items Commercial Evaluation by SCM | 7 | 0APSR | P000 | 00P7 | P000#YFXa00P7
4738 | 4738 | 4738 | 4738 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Material Procurement Auxiliary Power Supply Reinforcement items Vendor negotiation & Finalization | 8 | 0APSR | P000 | 00P8 | P000#YFXa00P8
4739 | 4739 | 4739 | 4739 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Material Procurement Auxiliary Power Supply Reinforcement items HPC Approval / PO release to vendor | 9 | 0APSR | P000 | 00P9 | P000#YFXa00P9
4740 | 4740 | 4740 | 4740 | SA24M005 | Protection Modification (SAS/SCADA integration/Telecommunication) |  | 5 | -1 | 0 |  |  | X | P000#YFXa
4741 | 4741 | 4741 | 4741 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Material Procurement Protection Modification (SAS/SCADA integration/Telecommunication) Purchase Request to SCM | 1 | PR0SCM | P000 | 00P1 | P000#iYFp00P1
4742 | 4742 | 4742 | 4742 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Material Procurement Protection Modification (SAS/SCADA integration/Telecommunication) Issue of RFQ | 2 | PR0SCM | P000 | 00P2 | P000#iYFp00P2
4743 | 4743 | 4743 | 4743 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Material Procurement Protection Modification (SAS/SCADA integration/Telecommunication) Receipt of Technical offer from Vendor | 3 | PR0SCM | P000 | 00P3 | P000#iYFp00P3
4744 | 4744 | 4744 | 4744 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Material Procurement Protection Modification (SAS/SCADA integration/Telecommunication) Technical Evaluation by EDRC | 4 | PR0SCM | P000 | 00P4 | P000#iYFp00P4
4745 | 4745 | 4745 | 4745 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Material Procurement Protection Modification (SAS/SCADA integration/Telecommunication) Final technical compliance from Vendor | 5 | PR0SCM | P000 | 00P5 | P000#iYFp00P5
4746 | 4746 | 4746 | 4746 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Material Procurement Protection Modification (SAS/SCADA integration/Telecommunication) Technical clearance by EDRC | 6 | PR0SCM | P000 | 00P6 | P000#iYFp00P6
4747 | 4747 | 4747 | 4747 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Material Procurement Protection Modification (SAS/SCADA integration/Telecommunication) Commercial Evaluation by SCM | 7 | PR0SCM | P000 | 00P7 | P000#iYFp00P7
4748 | 4748 | 4748 | 4748 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Material Procurement Protection Modification (SAS/SCADA integration/Telecommunication) Vendor negotiation & Finalization | 8 | PR0SCM | P000 | 00P8 | P000#iYFp00P8
4749 | 4749 | 4749 | 4749 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Material Procurement Protection Modification (SAS/SCADA integration/Telecommunication) HPC Approval / PO release to vendor | 9 | PR0SCM | P000 | 00P9 | P000#iYFp00P9
4750 | 4750 | 4750 | 4750 | SA24M005 | Free-stand CT/CTs with six cores |  | 5 | -1 | 0 |  |  | X | P000#iYFp
4751 | 4751 | 4751 | 4751 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Material Procurement Free-stand CT/CTs with six cores Purchase Request to SCM | 1 | FRCT | P000 | 00P1 | P000#ZKWt00P1
4752 | 4752 | 4752 | 4752 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Material Procurement Free-stand CT/CTs with six cores Issue of RFQ | 2 | FRCT | P000 | 00P2 | P000#ZKWt00P2
4753 | 4753 | 4753 | 4753 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Material Procurement Free-stand CT/CTs with six cores Receipt of Technical offer from Vendor | 3 | FRCT | P000 | 00P3 | P000#ZKWt00P3
4754 | 4754 | 4754 | 4754 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Material Procurement Free-stand CT/CTs with six cores Technical Evaluation by EDRC | 4 | FRCT | P000 | 00P4 | P000#ZKWt00P4
4755 | 4755 | 4755 | 4755 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Material Procurement Free-stand CT/CTs with six cores Final technical compliance from Vendor | 5 | FRCT | P000 | 00P5 | P000#ZKWt00P5
4756 | 4756 | 4756 | 4756 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Material Procurement Free-stand CT/CTs with six cores Technical clearance by EDRC | 6 | FRCT | P000 | 00P6 | P000#ZKWt00P6
4757 | 4757 | 4757 | 4757 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Material Procurement Free-stand CT/CTs with six cores Commercial Evaluation by SCM | 7 | FRCT | P000 | 00P7 | P000#ZKWt00P7
4758 | 4758 | 4758 | 4758 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Material Procurement Free-stand CT/CTs with six cores Vendor negotiation & Finalization | 8 | FRCT | P000 | 00P8 | P000#ZKWt00P8
4759 | 4759 | 4759 | 4759 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Material Procurement Free-stand CT/CTs with six cores HPC Approval / PO release to vendor | 9 | FRCT | P000 | 00P9 | P000#ZKWt00P9
4760 | 4760 | 4760 | 4760 | SA24M005 | Inspection & Delivery |  | 4 | -1 | 0 |  |  | X | P000#ZKWt
4761 | 4761 | 4761 | 4761 | SA24M005 | Auxiliary Power Supply Reinforcement items |  | 5 | -1 | 0 |  |  | X | P000#ZKWt
4762 | 4762 | 4762 | 4762 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Inspection & Delivery Auxiliary Power Supply Reinforcement items MQP / ITP Submission | 1 | 0APSR | I000 | 00I1 | I000#rFnP00I1
4763 | 4763 | 4763 | 4763 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Inspection & Delivery Auxiliary Power Supply Reinforcement items MQP / ITP Approval | 2 | 0APSR | I000 | 00I2 | I000#rFnP00I2
4764 | 4764 | 4764 | 4764 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Inspection & Delivery Auxiliary Power Supply Reinforcement items Issuance of MFC | 3 | 0APSR | I000 | 00I3 | I000#rFnP00I3
4765 | 4765 | 4765 | 4765 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Inspection & Delivery Auxiliary Power Supply Reinforcement items Lead Time For Manufacturing | 4 | 0APSR | I000 | 00I4 | I000#rFnP00I4
4766 | 4766 | 4766 | 4766 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Inspection & Delivery Auxiliary Power Supply Reinforcement items Material readiness / Inspection call | 5 | 0APSR | I000 | 00I5 | I000#rFnP00I5
4767 | 4767 | 4767 | 4767 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Inspection & Delivery Auxiliary Power Supply Reinforcement items Inspection by client personal / Third Party | 6 | 0APSR | I000 | 00I6 | I000#rFnP00I6
4768 | 4768 | 4768 | 4768 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Inspection & Delivery Auxiliary Power Supply Reinforcement items Submission of FAT Compliance by Vendor | 7 | 0APSR | I000 | 00I7 | I000#rFnP00I7
4769 | 4769 | 4769 | 4769 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Inspection & Delivery Auxiliary Power Supply Reinforcement items Dispatch Clearance to vendor | 8 | 0APSR | I000 | 00I8 | I000#rFnP00I8
4770 | 4770 | 4770 | 4770 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Inspection & Delivery Auxiliary Power Supply Reinforcement items Transportation and Custom clearance | 9 | 0APSR | I000 | 00I9 | I000#rFnP00I9
4771 | 4771 | 4771 | 4771 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Inspection & Delivery Auxiliary Power Supply Reinforcement items Receipt at site | 10 | 0APSR | I000 | 0I10 | I000#rFnP0I10
4772 | 4772 | 4772 | 4772 | SA24M005 | Protection Modification (SAS/SCADA integration/Telecommunication) |  | 5 | -1 | 0 |  |  | X | I000#rFnP
4773 | 4773 | 4773 | 4773 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Inspection & Delivery Protection Modification (SAS/SCADA integration/Telecommunication) MQP / ITP Submission | 1 | 0PRTM | I000 | 00I1 | I0000PRTM00I1
4774 | 4774 | 4774 | 4774 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Inspection & Delivery Protection Modification (SAS/SCADA integration/Telecommunication) MQP / ITP Approval | 2 | 0PRTM | I000 | 00I2 | I0000PRTM00I2
4775 | 4775 | 4775 | 4775 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Inspection & Delivery Protection Modification (SAS/SCADA integration/Telecommunication) Issuance of MFC | 3 | 0PRTM | I000 | 00I3 | I0000PRTM00I3
4776 | 4776 | 4776 | 4776 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Inspection & Delivery Protection Modification (SAS/SCADA integration/Telecommunication) Lead Time For Manufacturing | 4 | 0PRTM | I000 | 00I4 | I0000PRTM00I4
4777 | 4777 | 4777 | 4777 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Inspection & Delivery Protection Modification (SAS/SCADA integration/Telecommunication) Material readiness / Inspection call | 5 | 0PRTM | I000 | 00I5 | I0000PRTM00I5
4778 | 4778 | 4778 | 4778 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Inspection & Delivery Protection Modification (SAS/SCADA integration/Telecommunication) Inspection by client personal / Third Party | 6 | 0PRTM | I000 | 00I6 | I0000PRTM00I6
4779 | 4779 | 4779 | 4779 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Inspection & Delivery Protection Modification (SAS/SCADA integration/Telecommunication) Submission of FAT Compliance by Vendor | 7 | 0PRTM | I000 | 00I7 | I0000PRTM00I7
4780 | 4780 | 4780 | 4780 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Inspection & Delivery Protection Modification (SAS/SCADA integration/Telecommunication) Dispatch Clearance to vendor | 8 | 0PRTM | I000 | 00I8 | I0000PRTM00I8
4781 | 4781 | 4781 | 4781 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Inspection & Delivery Protection Modification (SAS/SCADA integration/Telecommunication) Transportation and Custom clearance | 9 | 0PRTM | I000 | 00I9 | I0000PRTM00I9
4782 | 4782 | 4782 | 4782 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Inspection & Delivery Protection Modification (SAS/SCADA integration/Telecommunication) Receipt at site | 10 | 0PRTM | I000 | 0I10 | I0000PRTM0I10
4783 | 4783 | 4783 | 4783 | SA24M005 | Free-stand CT/CTs with six cores |  | 5 | -1 | 0 |  |  | X
4784 | 4784 | 4784 | 4784 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Inspection & Delivery Free-stand CT/CTs with six cores MQP / ITP Submission | 1 | FRCT | I000 | 00I1 | I000#OyBr00I1
4785 | 4785 | 4785 | 4785 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Inspection & Delivery Free-stand CT/CTs with six cores MQP / ITP Approval | 2 | FRCT | I000 | 00I2 | I000#OyBr00I2
4786 | 4786 | 4786 | 4786 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Inspection & Delivery Free-stand CT/CTs with six cores Issuance of MFC | 3 | FRCT | I000 | 00I3 | I000#OyBr00I3
4787 | 4787 | 4787 | 4787 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Inspection & Delivery Free-stand CT/CTs with six cores Lead Time For Manufacturing | 4 | FRCT | I000 | 00I4 | I000#OyBr00I4
4788 | 4788 | 4788 | 4788 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Inspection & Delivery Free-stand CT/CTs with six cores Material readiness / Inspection call | 5 | FRCT | I000 | 00I5 | I000#OyBr00I5
4789 | 4789 | 4789 | 4789 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Inspection & Delivery Free-stand CT/CTs with six cores Inspection by client personal / Third Party | 6 | FRCT | I000 | 00I6 | I000#OyBr00I6
4790 | 4790 | 4790 | 4790 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Inspection & Delivery Free-stand CT/CTs with six cores Submission of FAT Compliance by Vendor | 7 | FRCT | I000 | 00I7 | I000#OyBr00I7
4791 | 4791 | 4791 | 4791 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Inspection & Delivery Free-stand CT/CTs with six cores Dispatch Clearance to vendor | 8 | FRCT | I000 | 00I8 | I000#OyBr00I8
4792 | 4792 | 4792 | 4792 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Inspection & Delivery Free-stand CT/CTs with six cores Transportation and Custom clearance | 9 | FRCT | I000 | 00I9 | I000#OyBr00I9
4793 | 4793 | 4793 | 4793 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Inspection & Delivery Free-stand CT/CTs with six cores Receipt at site | 10 | FRCT | I000 | 0I10 | I000#OyBr0I10
4794 | 4794 | 4794 | 4794 | SA24M005 | Construction & Installation Works |  | 4 | -1 | 0 |  |  | X | I000#OyBr
4795 | 4795 | 4795 | 4795 | SA24M005 | Auxiliary Power Reinforcement Works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Construction & Installation Works Auxiliary Power Reinforcement Works | 1 | C0ARW | C000 | 00C1 | C000C0ARW00C1
4796 | 4796 | 4796 | 4796 | SA24M005 | Protection Modification works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Construction & Installation Works Protection Modification works | 2 | C0ARW | C000 | 00C2 | C000C0ARW00C2
4797 | 4797 | 4797 | 4797 | SA24M005 | TeleCommunication Modification Works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Construction & Installation Works TeleCommunication Modification Works | 3 | C0ARW | C000 | 00C3 | C000C0ARW00C3
4798 | 4798 | 4798 | 4798 | SA24M005 | SAS/SCADA Integration Works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Construction & Installation Works SAS/SCADA Integration Works | 4 | C0ARW | C000 | 00C4 | C000C0ARW00C4
4799 | 4799 | 4799 | 4799 | SA24M005 | Testing & Commissioning |  | 4 | -1 | 0 |  |  | X
4800 | 4800 | 4800 | 4800 | SA24M005 | Prechecks |  | 5 | -1 | 0 |  |  | X
4801 | 4801 | 4801 | 4801 | SA24M005 | MCB Test In Control And Protection Panels |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Testing & Commissioning Prechecks MCB Test In Control And Protection Panels | 1 | **Prechecks MCB Test In Control And Protection Panels** **Purpose:** To verify the proper operation of the miniature circuit breakers (MCBs) installed in the control and protection panels. **Equipment:** * MCB tester * MCBs **Procedure:** 1. **Safety Precautions:** * Wear appropriate personal protective equipment (PPE). * Ensure the power supply to the control and protection panels is isolated. 2. **MCB Testing:** * Connect the MCB tester to the MCB terminals. * Set the MCB tester to the appropriate trip current. * Trip the MCB using the MCB tester. * Verify that the MCB trips within the specified time and current range. * Reset the MCB. * Repeat the test for all MCBs in the control and protection panels. 3. **Verification:** * Check that all MCBs trip and reset as expected. * Record the trip current and time for each MCB. **Acceptance Criteria:** * All MCBs shall trip within the specified time and current range. * All MCBs shall reset properly. **Reporting:** * Prepare a test report that includes the following information: * Date and time of testing * MCB identification * Trip current and time * Any discrepancies or observations | E000 | 00E1 | E000#qdft00E1
4802 | 4802 | 4802 | 4802 | SA24M005 | Auxiliary/Trip Relay Test In Control And Protection Panels |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Testing & Commissioning Prechecks Auxiliary/Trip Relay Test In Control And Protection Panels | 2 | **Prechecks MCB Test In Control And Protection Panels** **Purpose:** To verify the proper operation of the miniature circuit breakers (MCBs) installed in the control and protection panels. **Equipment:** * MCB tester * MCBs **Procedure:** 1. **Safety Precautions:** * Wear appropriate personal protective equipment (PPE). * Ensure the power supply to the control and protection panels is isolated. 2. **MCB Testing:** * Connect the MCB tester to the MCB terminals. * Set the MCB tester to the appropriate trip current. * Trip the MCB using the MCB tester. * Verify that the MCB trips within the specified time and current range. * Reset the MCB. * Repeat the test for all MCBs in the control and protection panels. 3. **Verification:** * Check that all MCBs trip and reset as expected. * Record the trip current and time for each MCB. **Acceptance Criteria:** * All MCBs shall trip within the specified time and current range. * All MCBs shall reset properly. **Reporting:** * Prepare a test report that includes the following information: * Date and time of testing * MCB identification * Trip current and time * Any discrepancies or observations | E000 | 00E2 | E000#qdft00E2
4803 | 4803 | 4803 | 4803 | SA24M005 | VT Secondary Circuit Injection & Loop Resistance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Testing & Commissioning Prechecks VT Secondary Circuit Injection & Loop Resistance | 3 | **Prechecks MCB Test In Control And Protection Panels** **Purpose:** To verify the proper operation of the miniature circuit breakers (MCBs) installed in the control and protection panels. **Equipment:** * MCB tester * MCBs **Procedure:** 1. **Safety Precautions:** * Wear appropriate personal protective equipment (PPE). * Ensure the power supply to the control and protection panels is isolated. 2. **MCB Testing:** * Connect the MCB tester to the MCB terminals. * Set the MCB tester to the appropriate trip current. * Trip the MCB using the MCB tester. * Verify that the MCB trips within the specified time and current range. * Reset the MCB. * Repeat the test for all MCBs in the control and protection panels. 3. **Verification:** * Check that all MCBs trip and reset as expected. * Record the trip current and time for each MCB. **Acceptance Criteria:** * All MCBs shall trip within the specified time and current range. * All MCBs shall reset properly. **Reporting:** * Prepare a test report that includes the following information: * Date and time of testing * MCB identification * Trip current and time * Any discrepancies or observations | E000 | 00E3 | E000#qdft00E3
4804 | 4804 | 4804 | 4804 | SA24M005 | CT Loop Resistance and Single Earth Point |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Testing & Commissioning Prechecks CT Loop Resistance and Single Earth Point | 4 | **Prechecks MCB Test In Control And Protection Panels** **Purpose:** To verify the proper operation of the miniature circuit breakers (MCBs) installed in the control and protection panels. **Equipment:** * MCB tester * MCBs **Procedure:** 1. **Safety Precautions:** * Wear appropriate personal protective equipment (PPE). * Ensure the power supply to the control and protection panels is isolated. 2. **MCB Testing:** * Connect the MCB tester to the MCB terminals. * Set the MCB tester to the appropriate trip current. * Trip the MCB using the MCB tester. * Verify that the MCB trips within the specified time and current range. * Reset the MCB. * Repeat the test for all MCBs in the control and protection panels. 3. **Verification:** * Check that all MCBs trip and reset as expected. * Record the trip current and time for each MCB. **Acceptance Criteria:** * All MCBs shall trip within the specified time and current range. * All MCBs shall reset properly. **Reporting:** * Prepare a test report that includes the following information: * Date and time of testing * MCB identification * Trip current and time * Any discrepancies or observations | E000 | 00E4 | E000#qdft00E4
4805 | 4805 | 4805 | 4805 | SA24M005 | Scheme Check For Line Protection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Testing & Commissioning Prechecks Scheme Check For Line Protection | 5 | **Prechecks MCB Test In Control And Protection Panels** **Purpose:** To verify the proper operation of the miniature circuit breakers (MCBs) installed in the control and protection panels. **Equipment:** * MCB tester * MCBs **Procedure:** 1. **Safety Precautions:** * Wear appropriate personal protective equipment (PPE). * Ensure the power supply to the control and protection panels is isolated. 2. **MCB Testing:** * Connect the MCB tester to the MCB terminals. * Set the MCB tester to the appropriate trip current. * Trip the MCB using the MCB tester. * Verify that the MCB trips within the specified time and current range. * Reset the MCB. * Repeat the test for all MCBs in the control and protection panels. 3. **Verification:** * Check that all MCBs trip and reset as expected. * Record the trip current and time for each MCB. **Acceptance Criteria:** * All MCBs shall trip within the specified time and current range. * All MCBs shall reset properly. **Reporting:** * Prepare a test report that includes the following information: * Date and time of testing * MCB identification * Trip current and time * Any discrepancies or observations | E000 | 00E5 | E000#qdft00E5
4806 | 4806 | 4806 | 4806 | SA24M005 | Set 1 Line Differential Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Testing & Commissioning Prechecks Set 1 Line Differential Relay Acceptance Test | 6 | **Prechecks MCB Test In Control And Protection Panels** **Purpose:** To verify the proper operation of the miniature circuit breakers (MCBs) installed in the control and protection panels. **Equipment:** * MCB tester * MCBs **Procedure:** 1. **Safety Precautions:** * Wear appropriate personal protective equipment (PPE). * Ensure the power supply to the control and protection panels is isolated. 2. **MCB Testing:** * Connect the MCB tester to the MCB terminals. * Set the MCB tester to the appropriate trip current. * Trip the MCB using the MCB tester. * Verify that the MCB trips within the specified time and current range. * Reset the MCB. * Repeat the test for all MCBs in the control and protection panels. 3. **Verification:** * Check that all MCBs trip and reset as expected. * Record the trip current and time for each MCB. **Acceptance Criteria:** * All MCBs shall trip within the specified time and current range. * All MCBs shall reset properly. **Reporting:** * Prepare a test report that includes the following information: * Date and time of testing * MCB identification * Trip current and time * Any discrepancies or observations | E000 | 00E6 | E000#qdft00E6
4807 | 4807 | 4807 | 4807 | SA24M005 | Set 2 Line Differential Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Testing & Commissioning Prechecks Set 2 Line Differential Relay Acceptance Test | 7 | **Prechecks MCB Test In Control And Protection Panels** **Purpose:** To verify the proper operation of the miniature circuit breakers (MCBs) installed in the control and protection panels. **Equipment:** * MCB tester * MCBs **Procedure:** 1. **Safety Precautions:** * Wear appropriate personal protective equipment (PPE). * Ensure the power supply to the control and protection panels is isolated. 2. **MCB Testing:** * Connect the MCB tester to the MCB terminals. * Set the MCB tester to the appropriate trip current. * Trip the MCB using the MCB tester. * Verify that the MCB trips within the specified time and current range. * Reset the MCB. * Repeat the test for all MCBs in the control and protection panels. 3. **Verification:** * Check that all MCBs trip and reset as expected. * Record the trip current and time for each MCB. **Acceptance Criteria:** * All MCBs shall trip within the specified time and current range. * All MCBs shall reset properly. **Reporting:** * Prepare a test report that includes the following information: * Date and time of testing * MCB identification * Trip current and time * Any discrepancies or observations | E000 | 00E7 | E000#qdft00E7
4808 | 4808 | 4808 | 4808 | SA24M005 | Alarm And Indication Check Up To SAS HMI And Gateway For EHV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Testing & Commissioning Prechecks Alarm And Indication Check Up To SAS HMI And Gateway For EHV | 8 | **Prechecks MCB Test In Control And Protection Panels** **Purpose:** To verify the proper operation of the miniature circuit breakers (MCBs) installed in the control and protection panels. **Equipment:** * MCB tester * MCBs **Procedure:** 1. **Safety Precautions:** * Wear appropriate personal protective equipment (PPE). * Ensure the power supply to the control and protection panels is isolated. 2. **MCB Testing:** * Connect the MCB tester to the MCB terminals. * Set the MCB tester to the appropriate trip current. * Trip the MCB using the MCB tester. * Verify that the MCB trips within the specified time and current range. * Reset the MCB. * Repeat the test for all MCBs in the control and protection panels. 3. **Verification:** * Check that all MCBs trip and reset as expected. * Record the trip current and time for each MCB. **Acceptance Criteria:** * All MCBs shall trip within the specified time and current range. * All MCBs shall reset properly. **Reporting:** * Prepare a test report that includes the following information: * Date and time of testing * MCB identification * Trip current and time * Any discrepancies or observations | E000 | 00E8 | E000#qdft00E8
4809 | 4809 | 4809 | 4809 | SA24M005 | Commissioning |  | 5 | -1 | 0 |  |  | X
4810 | 4810 | 4810 | 4810 | SA24M005 | MCB Test In Control And Protection Panels |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Testing & Commissioning Commissioning MCB Test In Control And Protection Panels | 1 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCCBs) installed in the control and protection panels. **Equipment:** * MCCB tester * MCCBs under test **Procedure:** 1. Set up the MCCB tester according to the manufacturer's instructions. 2. Connect the MCCB tester to the MCCB under test. 3. Set the MCCB tester to the desired test current. 4. Initiate the test. 5. Observe the MCCB's response to the test current. 6. Repeat steps 2-5 for each MCCB under test. **Acceptance Criteria:** * The MCCB should trip within the specified time delay. * The MCCB should not trip prematurely. * The MCCB should reset properly after tripping. | E000 | 00E1 | M000#dfui000M1
4811 | 4811 | 4811 | 4811 | SA24M005 | Auxiliary/Trip Relay Test In Control And Protection Panels |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Testing & Commissioning Commissioning Auxiliary/Trip Relay Test In Control And Protection Panels | 2 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCCBs) installed in the control and protection panels. **Equipment:** * MCCB tester * MCCBs under test **Procedure:** 1. Set up the MCCB tester according to the manufacturer's instructions. 2. Connect the MCCB tester to the MCCB under test. 3. Set the MCCB tester to the desired test current. 4. Initiate the test. 5. Observe the MCCB's response to the test current. 6. Repeat steps 2-5 for each MCCB under test. **Acceptance Criteria:** * The MCCB should trip within the specified time delay. * The MCCB should not trip prematurely. * The MCCB should reset properly after tripping. | E000 | 00E2 | M000#dfui000M2
4812 | 4812 | 4812 | 4812 | SA24M005 | VT Secondary Circuit Injection & Loop Resistance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Testing & Commissioning Commissioning VT Secondary Circuit Injection & Loop Resistance | 3 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCCBs) installed in the control and protection panels. **Equipment:** * MCCB tester * MCCBs under test **Procedure:** 1. Set up the MCCB tester according to the manufacturer's instructions. 2. Connect the MCCB tester to the MCCB under test. 3. Set the MCCB tester to the desired test current. 4. Initiate the test. 5. Observe the MCCB's response to the test current. 6. Repeat steps 2-5 for each MCCB under test. **Acceptance Criteria:** * The MCCB should trip within the specified time delay. * The MCCB should not trip prematurely. * The MCCB should reset properly after tripping. | E000 | 00E3 | M000#dfui000M3
4813 | 4813 | 4813 | 4813 | SA24M005 | CT Loop Resistance and Single Earth Point |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Testing & Commissioning Commissioning CT Loop Resistance and Single Earth Point | 4 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCCBs) installed in the control and protection panels. **Equipment:** * MCCB tester * MCCBs under test **Procedure:** 1. Set up the MCCB tester according to the manufacturer's instructions. 2. Connect the MCCB tester to the MCCB under test. 3. Set the MCCB tester to the desired test current. 4. Initiate the test. 5. Observe the MCCB's response to the test current. 6. Repeat steps 2-5 for each MCCB under test. **Acceptance Criteria:** * The MCCB should trip within the specified time delay. * The MCCB should not trip prematurely. * The MCCB should reset properly after tripping. | E000 | 00E4 | M000#dfui000M4
4814 | 4814 | 4814 | 4814 | SA24M005 | Scheme Check For Line Protection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Testing & Commissioning Commissioning Scheme Check For Line Protection | 5 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCCBs) installed in the control and protection panels. **Equipment:** * MCCB tester * MCCBs under test **Procedure:** 1. Set up the MCCB tester according to the manufacturer's instructions. 2. Connect the MCCB tester to the MCCB under test. 3. Set the MCCB tester to the desired test current. 4. Initiate the test. 5. Observe the MCCB's response to the test current. 6. Repeat steps 2-5 for each MCCB under test. **Acceptance Criteria:** * The MCCB should trip within the specified time delay. * The MCCB should not trip prematurely. * The MCCB should reset properly after tripping. | E000 | 00E5 | M000#dfui000M5
4815 | 4815 | 4815 | 4815 | SA24M005 | Set 1 Line Differential Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Testing & Commissioning Commissioning Set 1 Line Differential Relay Acceptance Test | 6 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCCBs) installed in the control and protection panels. **Equipment:** * MCCB tester * MCCBs under test **Procedure:** 1. Set up the MCCB tester according to the manufacturer's instructions. 2. Connect the MCCB tester to the MCCB under test. 3. Set the MCCB tester to the desired test current. 4. Initiate the test. 5. Observe the MCCB's response to the test current. 6. Repeat steps 2-5 for each MCCB under test. **Acceptance Criteria:** * The MCCB should trip within the specified time delay. * The MCCB should not trip prematurely. * The MCCB should reset properly after tripping. | E000 | 00E6 | M000#dfui000M6
4816 | 4816 | 4816 | 4816 | SA24M005 | Set 2 Line Differential Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Testing & Commissioning Commissioning Set 2 Line Differential Relay Acceptance Test | 7 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCCBs) installed in the control and protection panels. **Equipment:** * MCCB tester * MCCBs under test **Procedure:** 1. Set up the MCCB tester according to the manufacturer's instructions. 2. Connect the MCCB tester to the MCCB under test. 3. Set the MCCB tester to the desired test current. 4. Initiate the test. 5. Observe the MCCB's response to the test current. 6. Repeat steps 2-5 for each MCCB under test. **Acceptance Criteria:** * The MCCB should trip within the specified time delay. * The MCCB should not trip prematurely. * The MCCB should reset properly after tripping. | E000 | 00E7 | M000#dfui000M7
4817 | 4817 | 4817 | 4817 | SA24M005 | Main 1 Multifunction Relay Final Setting Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Testing & Commissioning Commissioning Main 1 Multifunction Relay Final Setting Test | 8 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCCBs) installed in the control and protection panels. **Equipment:** * MCCB tester * MCCBs under test **Procedure:** 1. Set up the MCCB tester according to the manufacturer's instructions. 2. Connect the MCCB tester to the MCCB under test. 3. Set the MCCB tester to the desired test current. 4. Initiate the test. 5. Observe the MCCB's response to the test current. 6. Repeat steps 2-5 for each MCCB under test. **Acceptance Criteria:** * The MCCB should trip within the specified time delay. * The MCCB should not trip prematurely. * The MCCB should reset properly after tripping. | E000 | 00E8 | M000#dfui000M8
4818 | 4818 | 4818 | 4818 | SA24M005 | Main 2 Multifunction Relay Final setting Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Testing & Commissioning Commissioning Main 2 Multifunction Relay Final setting Test | 9 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCCBs) installed in the control and protection panels. **Equipment:** * MCCB tester * MCCBs under test **Procedure:** 1. Set up the MCCB tester according to the manufacturer's instructions. 2. Connect the MCCB tester to the MCCB under test. 3. Set the MCCB tester to the desired test current. 4. Initiate the test. 5. Observe the MCCB's response to the test current. 6. Repeat steps 2-5 for each MCCB under test. **Acceptance Criteria:** * The MCCB should trip within the specified time delay. * The MCCB should not trip prematurely. * The MCCB should reset properly after tripping. | E000 | 00E9 | M000#dfui000M9
4819 | 4819 | 4819 | 4819 | SA24M005 | Alarm And Indication Check Up To SAS HMI And Gateway For EHV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Testing & Commissioning Commissioning Alarm And Indication Check Up To SAS HMI And Gateway For EHV | 10 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCCBs) installed in the control and protection panels. **Equipment:** * MCCB tester * MCCBs under test **Procedure:** 1. Set up the MCCB tester according to the manufacturer's instructions. 2. Connect the MCCB tester to the MCCB under test. 3. Set the MCCB tester to the desired test current. 4. Initiate the test. 5. Observe the MCCB's response to the test current. 6. Repeat steps 2-5 for each MCCB under test. **Acceptance Criteria:** * The MCCB should trip within the specified time delay. * The MCCB should not trip prematurely. * The MCCB should reset properly after tripping. | E000 | 0E10 | M000#dfui000M10
4820 | 4820 | 4820 | 4820 | SA24M005 | Closed Loop Test EHV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Testing & Commissioning Commissioning Closed Loop Test EHV | 11 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCCBs) installed in the control and protection panels. **Equipment:** * MCCB tester * MCCBs under test **Procedure:** 1. Set up the MCCB tester according to the manufacturer's instructions. 2. Connect the MCCB tester to the MCCB under test. 3. Set the MCCB tester to the desired test current. 4. Initiate the test. 5. Observe the MCCB's response to the test current. 6. Repeat steps 2-5 for each MCCB under test. **Acceptance Criteria:** * The MCCB should trip within the specified time delay. * The MCCB should not trip prematurely. * The MCCB should reset properly after tripping. | E000 | 0E11 | M000#dfui000M11
4821 | 4821 | 4821 | 4821 | SA24M005 | EHV Line Feeder Set 1 Multifunction Relay |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Testing & Commissioning Commissioning EHV Line Feeder Set 1 Multifunction Relay | 12 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCCBs) installed in the control and protection panels. **Equipment:** * MCCB tester * MCCBs under test **Procedure:** 1. Set up the MCCB tester according to the manufacturer's instructions. 2. Connect the MCCB tester to the MCCB under test. 3. Set the MCCB tester to the desired test current. 4. Initiate the test. 5. Observe the MCCB's response to the test current. 6. Repeat steps 2-5 for each MCCB under test. **Acceptance Criteria:** * The MCCB should trip within the specified time delay. * The MCCB should not trip prematurely. * The MCCB should reset properly after tripping. | E000 | 0E12 | M000#dfui000M12
4822 | 4822 | 4822 | 4822 | SA24M005 | EHV Line Feeder Set 2 Multifunction Relay |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Testing & Commissioning Commissioning EHV Line Feeder Set 2 Multifunction Relay | 13 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCCBs) installed in the control and protection panels. **Equipment:** * MCCB tester * MCCBs under test **Procedure:** 1. Set up the MCCB tester according to the manufacturer's instructions. 2. Connect the MCCB tester to the MCCB under test. 3. Set the MCCB tester to the desired test current. 4. Initiate the test. 5. Observe the MCCB's response to the test current. 6. Repeat steps 2-5 for each MCCB under test. **Acceptance Criteria:** * The MCCB should trip within the specified time delay. * The MCCB should not trip prematurely. * The MCCB should reset properly after tripping. | E000 | 0E13 | M000#dfui000M13
4823 | 4823 | 4823 | 4823 | SA24M005 | Final Trip Test for EHV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Testing & Commissioning Commissioning Final Trip Test for EHV | 14 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCCBs) installed in the control and protection panels. **Equipment:** * MCCB tester * MCCBs under test **Procedure:** 1. Set up the MCCB tester according to the manufacturer's instructions. 2. Connect the MCCB tester to the MCCB under test. 3. Set the MCCB tester to the desired test current. 4. Initiate the test. 5. Observe the MCCB's response to the test current. 6. Repeat steps 2-5 for each MCCB under test. **Acceptance Criteria:** * The MCCB should trip within the specified time delay. * The MCCB should not trip prematurely. * The MCCB should reset properly after tripping. | E000 | 0E14 | M000#dfui000M14
4824 | 4824 | 4824 | 4824 | SA24M005 | Relay Final settings Review for EHV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Testing & Commissioning Commissioning Relay Final settings Review for EHV | 15 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCCBs) installed in the control and protection panels. **Equipment:** * MCCB tester * MCCBs under test **Procedure:** 1. Set up the MCCB tester according to the manufacturer's instructions. 2. Connect the MCCB tester to the MCCB under test. 3. Set the MCCB tester to the desired test current. 4. Initiate the test. 5. Observe the MCCB's response to the test current. 6. Repeat steps 2-5 for each MCCB under test. **Acceptance Criteria:** * The MCCB should trip within the specified time delay. * The MCCB should not trip prematurely. * The MCCB should reset properly after tripping. | E000 | 0E15 | M000#dfui000M15
4825 | 4825 | 4825 | 4825 | SA24M005 | Normalization Before Energization EHV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Testing & Commissioning Commissioning Normalization Before Energization EHV | 16 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCCBs) installed in the control and protection panels. **Equipment:** * MCCB tester * MCCBs under test **Procedure:** 1. Set up the MCCB tester according to the manufacturer's instructions. 2. Connect the MCCB tester to the MCCB under test. 3. Set the MCCB tester to the desired test current. 4. Initiate the test. 5. Observe the MCCB's response to the test current. 6. Repeat steps 2-5 for each MCCB under test. **Acceptance Criteria:** * The MCCB should trip within the specified time delay. * The MCCB should not trip prematurely. * The MCCB should reset properly after tripping. | E000 | 0E16 | M000#dfui000M16
4826 | 4826 | 4826 | 4826 | SA24M005 | Post Energization In Service Test for EHV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Testing & Commissioning Commissioning Post Energization In Service Test for EHV | 17 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCCBs) installed in the control and protection panels. **Equipment:** * MCCB tester * MCCBs under test **Procedure:** 1. Set up the MCCB tester according to the manufacturer's instructions. 2. Connect the MCCB tester to the MCCB under test. 3. Set the MCCB tester to the desired test current. 4. Initiate the test. 5. Observe the MCCB's response to the test current. 6. Repeat steps 2-5 for each MCCB under test. **Acceptance Criteria:** * The MCCB should trip within the specified time delay. * The MCCB should not trip prematurely. * The MCCB should reset properly after tripping. | E000 | 0E17 | M000#dfui000M17
4827 | 4827 | 4827 | 4827 | SA24M005 | Energization for EHV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-1 (9010 BSP) Testing & Commissioning Commissioning Energization for EHV | 18 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCCBs) installed in the control and protection panels. **Equipment:** * MCCB tester * MCCBs under test **Procedure:** 1. Set up the MCCB tester according to the manufacturer's instructions. 2. Connect the MCCB tester to the MCCB under test. 3. Set the MCCB tester to the desired test current. 4. Initiate the test. 5. Observe the MCCB's response to the test current. 6. Repeat steps 2-5 for each MCCB under test. **Acceptance Criteria:** * The MCCB should trip within the specified time delay. * The MCCB should not trip prematurely. * The MCCB should reset properly after tripping. | E000 | 0E18 | M000#dfui000M18
4828 | 4828 | 4828 | 4828 | SA24M005 | Remote End SS-2 (9006 BSP) |  | 3 | -1 | 0 |  |  | X | M000#dfui000M19
4829 | 4829 | 4829 | 4829 | SA24M005 | Engineering & Design (Phase VIII) |  | 4 | -1 | 0 |  |  | X
4830 | 4830 | 4830 | 4830 | SA24M005 | Modified Single Line Drawing |  | 5 | -1 | 0 |  |  | X
4831 | 4831 | 4831 | 4831 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Engineering & Design (Phase VIII) Modified Single Line Drawing Drafting / Preparation | 1 | E0SLD | E000 | 00E1 | E000#UJPy00E1
4832 | 4832 | 4832 | 4832 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Engineering & Design (Phase VIII) Modified Single Line Drawing Submission | 2 | E0SLD | E000 | 00E2 | E000#UJPy00E2
4833 | 4833 | 4833 | 4833 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Engineering & Design (Phase VIII) Modified Single Line Drawing Review / Evaluation | 3 | E0SLD | E000 | 00E3 | E000#UJPy00E3
4834 | 4834 | 4834 | 4834 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Engineering & Design (Phase VIII) Modified Single Line Drawing Approval with Comments | 4 | E0SLD | E000 | 00E4 | E000#UJPy00E4
4835 | 4835 | 4835 | 4835 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Engineering & Design (Phase VIII) Modified Single Line Drawing FINAL Approval | 5 | E0SLD | E000 | 00E5 | E000#UJPy00E5
4836 | 4836 | 4836 | 4836 | SA24M005 | Modified Overall Layout |  | 5 | -1 | 0 |  |  | X | E000#UJPy
4837 | 4837 | 4837 | 4837 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Engineering & Design (Phase VIII) Modified Overall Layout Drafting / Preparation | 1 | EQASS | E000 | 00E1 | E000EQASS00E1
4838 | 4838 | 4838 | 4838 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Engineering & Design (Phase VIII) Modified Overall Layout Submission | 2 | EQASS | E000 | 00E2 | E000EQASS00E2
4839 | 4839 | 4839 | 4839 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Engineering & Design (Phase VIII) Modified Overall Layout Review / Evaluation | 3 | EQASS | E000 | 00E3 | E000EQASS00E3
4840 | 4840 | 4840 | 4840 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Engineering & Design (Phase VIII) Modified Overall Layout Approval with Comments | 4 | EQASS | E000 | 00E4 | E000EQASS00E4
4841 | 4841 | 4841 | 4841 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Engineering & Design (Phase VIII) Modified Overall Layout FINAL Approval | 5 | EQASS | E000 | 00E5 | E000EQASS00E5
4842 | 4842 | 4842 | 4842 | SA24M005 | Material Procurement |  | 4 | -1 | 0 |  |  | X
4843 | 4843 | 4843 | 4843 | SA24M005 | Auxiliary Power Supply Reinforcement items |  | 5 | -1 | 0 |  |  | X
4844 | 4844 | 4844 | 4844 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Material Procurement Auxiliary Power Supply Reinforcement items Purchase Request to SCM | 1 | 0APSR | P000 | 00P1 | P000#hMdU00P1
4845 | 4845 | 4845 | 4845 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Material Procurement Auxiliary Power Supply Reinforcement items Issue of RFQ | 2 | 0APSR | P000 | 00P2 | P000#hMdU00P2
4846 | 4846 | 4846 | 4846 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Material Procurement Auxiliary Power Supply Reinforcement items Receipt of Technical offer from Vendor | 3 | 0APSR | P000 | 00P3 | P000#hMdU00P3
4847 | 4847 | 4847 | 4847 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Material Procurement Auxiliary Power Supply Reinforcement items Technical Evaluation by EDRC | 4 | 0APSR | P000 | 00P4 | P000#hMdU00P4
4848 | 4848 | 4848 | 4848 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Material Procurement Auxiliary Power Supply Reinforcement items Final technical compliance from Vendor | 5 | 0APSR | P000 | 00P5 | P000#hMdU00P5
4849 | 4849 | 4849 | 4849 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Material Procurement Auxiliary Power Supply Reinforcement items Technical clearance by EDRC | 6 | 0APSR | P000 | 00P6 | P000#hMdU00P6
4850 | 4850 | 4850 | 4850 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Material Procurement Auxiliary Power Supply Reinforcement items Commercial Evaluation by SCM | 7 | 0APSR | P000 | 00P7 | P000#hMdU00P7
4851 | 4851 | 4851 | 4851 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Material Procurement Auxiliary Power Supply Reinforcement items Vendor negotiation & Finalization | 8 | 0APSR | P000 | 00P8 | P000#hMdU00P8
4852 | 4852 | 4852 | 4852 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Material Procurement Auxiliary Power Supply Reinforcement items HPC Approval / PO release to vendor | 9 | 0APSR | P000 | 00P9 | P000#hMdU00P9
4853 | 4853 | 4853 | 4853 | SA24M005 | Surge Arrestor Modules |  | 5 | -1 | 0 |  |  | X | P000#hMdU
4854 | 4854 | 4854 | 4854 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Material Procurement Surge Arrestor Modules Purchase Request to SCM | 1 | SRGA | P000 | 00P1 | P000#WEPN00P1
4855 | 4855 | 4855 | 4855 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Material Procurement Surge Arrestor Modules Issue of RFQ | 2 | SRGA | P000 | 00P2 | P000#WEPN00P2
4856 | 4856 | 4856 | 4856 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Material Procurement Surge Arrestor Modules Receipt of Technical offer from Vendor | 3 | SRGA | P000 | 00P3 | P000#WEPN00P3
4857 | 4857 | 4857 | 4857 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Material Procurement Surge Arrestor Modules Technical Evaluation by EDRC | 4 | SRGA | P000 | 00P4 | P000#WEPN00P4
4858 | 4858 | 4858 | 4858 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Material Procurement Surge Arrestor Modules Final technical compliance from Vendor | 5 | SRGA | P000 | 00P5 | P000#WEPN00P5
4859 | 4859 | 4859 | 4859 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Material Procurement Surge Arrestor Modules Technical clearance by EDRC | 6 | SRGA | P000 | 00P6 | P000#WEPN00P6
4860 | 4860 | 4860 | 4860 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Material Procurement Surge Arrestor Modules Commercial Evaluation by SCM | 7 | SRGA | P000 | 00P7 | P000#WEPN00P7
4861 | 4861 | 4861 | 4861 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Material Procurement Surge Arrestor Modules Vendor negotiation & Finalization | 8 | SRGA | P000 | 00P8 | P000#WEPN00P8
4862 | 4862 | 4862 | 4862 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Material Procurement Surge Arrestor Modules HPC Approval / PO release to vendor | 9 | SRGA | P000 | 00P9 | P000#WEPN00P9
4863 | 4863 | 4863 | 4863 | SA24M005 | Protection Modification (SAS/SCADA integration/Telecommunication) |  | 5 | -1 | 0 |  |  | X | P000#WEPN
4864 | 4864 | 4864 | 4864 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Material Procurement Protection Modification (SAS/SCADA integration/Telecommunication) Purchase Request to SCM | 1 | PR0SCM | P000 | 00P1 | P000#vBWC00P1
4865 | 4865 | 4865 | 4865 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Material Procurement Protection Modification (SAS/SCADA integration/Telecommunication) Issue of RFQ | 2 | PR0SCM | P000 | 00P2 | P000#vBWC00P2
4866 | 4866 | 4866 | 4866 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Material Procurement Protection Modification (SAS/SCADA integration/Telecommunication) Receipt of Technical offer from Vendor | 3 | PR0SCM | P000 | 00P3 | P000#vBWC00P3
4867 | 4867 | 4867 | 4867 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Material Procurement Protection Modification (SAS/SCADA integration/Telecommunication) Technical Evaluation by EDRC | 4 | PR0SCM | P000 | 00P4 | P000#vBWC00P4
4868 | 4868 | 4868 | 4868 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Material Procurement Protection Modification (SAS/SCADA integration/Telecommunication) Final technical compliance from Vendor | 5 | PR0SCM | P000 | 00P5 | P000#vBWC00P5
4869 | 4869 | 4869 | 4869 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Material Procurement Protection Modification (SAS/SCADA integration/Telecommunication) Technical clearance by EDRC | 6 | PR0SCM | P000 | 00P6 | P000#vBWC00P6
4870 | 4870 | 4870 | 4870 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Material Procurement Protection Modification (SAS/SCADA integration/Telecommunication) Commercial Evaluation by SCM | 7 | PR0SCM | P000 | 00P7 | P000#vBWC00P7
4871 | 4871 | 4871 | 4871 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Material Procurement Protection Modification (SAS/SCADA integration/Telecommunication) Vendor negotiation & Finalization | 8 | PR0SCM | P000 | 00P8 | P000#vBWC00P8
4872 | 4872 | 4872 | 4872 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Material Procurement Protection Modification (SAS/SCADA integration/Telecommunication) HPC Approval / PO release to vendor | 9 | PR0SCM | P000 | 00P9 | P000#vBWC00P9
4873 | 4873 | 4873 | 4873 | SA24M005 | Free-stand CT/CTs with six cores |  | 5 | -1 | 0 |  |  | X | P000#vBWC
4874 | 4874 | 4874 | 4874 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Material Procurement Free-stand CT/CTs with six cores Purchase Request to SCM | 1 | FRCT | P000 | 00P1 | P000#UiPl00P1
4875 | 4875 | 4875 | 4875 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Material Procurement Free-stand CT/CTs with six cores Issue of RFQ | 2 | FRCT | P000 | 00P2 | P000#UiPl00P2
4876 | 4876 | 4876 | 4876 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Material Procurement Free-stand CT/CTs with six cores Receipt of Technical offer from Vendor | 3 | FRCT | P000 | 00P3 | P000#UiPl00P3
4877 | 4877 | 4877 | 4877 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Material Procurement Free-stand CT/CTs with six cores Technical Evaluation by EDRC | 4 | FRCT | P000 | 00P4 | P000#UiPl00P4
4878 | 4878 | 4878 | 4878 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Material Procurement Free-stand CT/CTs with six cores Final technical compliance from Vendor | 5 | FRCT | P000 | 00P5 | P000#UiPl00P5
4879 | 4879 | 4879 | 4879 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Material Procurement Free-stand CT/CTs with six cores Technical clearance by EDRC | 6 | FRCT | P000 | 00P6 | P000#UiPl00P6
4880 | 4880 | 4880 | 4880 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Material Procurement Free-stand CT/CTs with six cores Commercial Evaluation by SCM | 7 | FRCT | P000 | 00P7 | P000#UiPl00P7
4881 | 4881 | 4881 | 4881 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Material Procurement Free-stand CT/CTs with six cores Vendor negotiation & Finalization | 8 | FRCT | P000 | 00P8 | P000#UiPl00P8
4882 | 4882 | 4882 | 4882 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Material Procurement Free-stand CT/CTs with six cores HPC Approval / PO release to vendor | 9 | FRCT | P000 | 00P9 | P000#UiPl00P9
4883 | 4883 | 4883 | 4883 | SA24M005 | Inspection & Delivery |  | 4 | -1 | 0 |  |  | X | P000#UiPl
4884 | 4884 | 4884 | 4884 | SA24M005 | Auxiliary Power Supply Reinforcement items |  | 5 | -1 | 0 |  |  | X | P000#UiPl
4885 | 4885 | 4885 | 4885 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Inspection & Delivery Auxiliary Power Supply Reinforcement items MQP / ITP Submission | 1 | 0APSR | I000 | 00I1 | I000#aEFN00I1
4886 | 4886 | 4886 | 4886 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Inspection & Delivery Auxiliary Power Supply Reinforcement items MQP / ITP Approval | 2 | 0APSR | I000 | 00I2 | I000#aEFN00I2
4887 | 4887 | 4887 | 4887 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Inspection & Delivery Auxiliary Power Supply Reinforcement items Issuance of MFC | 3 | 0APSR | I000 | 00I3 | I000#aEFN00I3
4888 | 4888 | 4888 | 4888 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Inspection & Delivery Auxiliary Power Supply Reinforcement items Lead Time For Manufacturing | 4 | 0APSR | I000 | 00I4 | I000#aEFN00I4
4889 | 4889 | 4889 | 4889 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Inspection & Delivery Auxiliary Power Supply Reinforcement items Material readiness / Inspection call | 5 | 0APSR | I000 | 00I5 | I000#aEFN00I5
4890 | 4890 | 4890 | 4890 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Inspection & Delivery Auxiliary Power Supply Reinforcement items Inspection by client personal / Third Party | 6 | 0APSR | I000 | 00I6 | I000#aEFN00I6
4891 | 4891 | 4891 | 4891 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Inspection & Delivery Auxiliary Power Supply Reinforcement items Submission of FAT Compliance by Vendor | 7 | 0APSR | I000 | 00I7 | I000#aEFN00I7
4892 | 4892 | 4892 | 4892 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Inspection & Delivery Auxiliary Power Supply Reinforcement items Dispatch Clearance to vendor | 8 | 0APSR | I000 | 00I8 | I000#aEFN00I8
4893 | 4893 | 4893 | 4893 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Inspection & Delivery Auxiliary Power Supply Reinforcement items Transportation and Custom clearance | 9 | 0APSR | I000 | 00I9 | I000#aEFN00I9
4894 | 4894 | 4894 | 4894 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Inspection & Delivery Auxiliary Power Supply Reinforcement items Receipt at site | 10 | 0APSR | I000 | 0I10 | I000#aEFN0I10
4895 | 4895 | 4895 | 4895 | SA24M005 | Surge Arrestor Modules |  | 5 | -1 | 0 |  |  | X | I000#aEFN
4896 | 4896 | 4896 | 4896 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Inspection & Delivery Surge Arrestor Modules MQP / ITP Submission | 1 | SRGA | I000 | 00I1 | I000#EGyf00I1
4897 | 4897 | 4897 | 4897 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Inspection & Delivery Surge Arrestor Modules MQP / ITP Approval | 2 | SRGA | I000 | 00I2 | I000#EGyf00I2
4898 | 4898 | 4898 | 4898 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Inspection & Delivery Surge Arrestor Modules Issuance of MFC | 3 | SRGA | I000 | 00I3 | I000#EGyf00I3
4899 | 4899 | 4899 | 4899 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Inspection & Delivery Surge Arrestor Modules Lead Time For Manufacturing | 4 | SRGA | I000 | 00I4 | I000#EGyf00I4
4900 | 4900 | 4900 | 4900 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Inspection & Delivery Surge Arrestor Modules Material readiness / Inspection call | 5 | SRGA | I000 | 00I5 | I000#EGyf00I5
4901 | 4901 | 4901 | 4901 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Inspection & Delivery Surge Arrestor Modules Inspection by client personal / Third Party | 6 | SRGA | I000 | 00I6 | I000#EGyf00I6
4902 | 4902 | 4902 | 4902 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Inspection & Delivery Surge Arrestor Modules Submission of FAT Compliance by Vendor | 7 | SRGA | I000 | 00I7 | I000#EGyf00I7
4903 | 4903 | 4903 | 4903 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Inspection & Delivery Surge Arrestor Modules Dispatch Clearance to vendor | 8 | SRGA | I000 | 00I8 | I000#EGyf00I8
4904 | 4904 | 4904 | 4904 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Inspection & Delivery Surge Arrestor Modules Transportation and Custom clearance | 9 | SRGA | I000 | 00I9 | I000#EGyf00I9
4905 | 4905 | 4905 | 4905 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Inspection & Delivery Surge Arrestor Modules Receipt at site | 10 | SRGA | I000 | 0I10 | I000#EGyf0I10
4906 | 4906 | 4906 | 4906 | SA24M005 | Protection Modification (SAS/SCADA integration/Telecommunication) |  | 5 | -1 | 0 |  |  | X | I000#EGyf
4907 | 4907 | 4907 | 4907 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Inspection & Delivery Protection Modification (SAS/SCADA integration/Telecommunication) MQP / ITP Submission | 1 | 0PQM | E000 | 00E1 | E0000PQM00E1
4908 | 4908 | 4908 | 4908 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Inspection & Delivery Protection Modification (SAS/SCADA integration/Telecommunication) MQP / ITP Approval | 2 | 0PQM | E000 | 00E2 | E0000PQM00E2
4909 | 4909 | 4909 | 4909 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Inspection & Delivery Protection Modification (SAS/SCADA integration/Telecommunication) Issuance of MFC | 3 | 0PQM | E000 | 00E3 | E0000PQM00E3
4910 | 4910 | 4910 | 4910 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Inspection & Delivery Protection Modification (SAS/SCADA integration/Telecommunication) Lead Time For Manufacturing | 4 | 0PQM | E000 | 00E4 | E0000PQM00E4
4911 | 4911 | 4911 | 4911 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Inspection & Delivery Protection Modification (SAS/SCADA integration/Telecommunication) Material readiness / Inspection call | 5 | 0PQM | E000 | 00E5 | E0000PQM00E5
4912 | 4912 | 4912 | 4912 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Inspection & Delivery Protection Modification (SAS/SCADA integration/Telecommunication) Inspection by client personal / Third Party | 6 | 0PQM | E000 | 00E6 | E0000PQM00E6
4913 | 4913 | 4913 | 4913 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Inspection & Delivery Protection Modification (SAS/SCADA integration/Telecommunication) Submission of FAT Compliance by Vendor | 7 | 0PQM | E000 | 00E7 | E0000PQM00E7
4914 | 4914 | 4914 | 4914 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Inspection & Delivery Protection Modification (SAS/SCADA integration/Telecommunication) Dispatch Clearance to vendor | 8 | 0PQM | E000 | 00E8 | E0000PQM00E8
4915 | 4915 | 4915 | 4915 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Inspection & Delivery Protection Modification (SAS/SCADA integration/Telecommunication) Transportation and Custom clearance | 9 | 0PQM | E000 | 00E9 | E0000PQM00E9
4916 | 4916 | 4916 | 4916 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Inspection & Delivery Protection Modification (SAS/SCADA integration/Telecommunication) Receipt at site | 10 | 0PQM | E000 | 0E10 | E0000PQM0E10
4917 | 4917 | 4917 | 4917 | SA24M005 | Free-stand CT/CTs with six cores |  | 5 | -1 | 0 |  |  | X
4918 | 4918 | 4918 | 4918 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Inspection & Delivery Free-stand CT/CTs with six cores MQP / ITP Submission | 1 | FRCT | I000 | 00I1 | I000#lfeX00I1
4919 | 4919 | 4919 | 4919 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Inspection & Delivery Free-stand CT/CTs with six cores MQP / ITP Approval | 2 | FRCT | I000 | 00I2 | I000#lfeX00I2
4920 | 4920 | 4920 | 4920 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Inspection & Delivery Free-stand CT/CTs with six cores Issuance of MFC | 3 | FRCT | I000 | 00I3 | I000#lfeX00I3
4921 | 4921 | 4921 | 4921 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Inspection & Delivery Free-stand CT/CTs with six cores Lead Time For Manufacturing | 4 | FRCT | I000 | 00I4 | I000#lfeX00I4
4922 | 4922 | 4922 | 4922 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Inspection & Delivery Free-stand CT/CTs with six cores Material readiness / Inspection call | 5 | FRCT | I000 | 00I5 | I000#lfeX00I5
4923 | 4923 | 4923 | 4923 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Inspection & Delivery Free-stand CT/CTs with six cores Inspection by client personal / Third Party | 6 | FRCT | I000 | 00I6 | I000#lfeX00I6
4924 | 4924 | 4924 | 4924 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Inspection & Delivery Free-stand CT/CTs with six cores Submission of FAT Compliance by Vendor | 7 | FRCT | I000 | 00I7 | I000#lfeX00I7
4925 | 4925 | 4925 | 4925 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Inspection & Delivery Free-stand CT/CTs with six cores Dispatch Clearance to vendor | 8 | FRCT | I000 | 00I8 | I000#lfeX00I8
4926 | 4926 | 4926 | 4926 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Inspection & Delivery Free-stand CT/CTs with six cores Transportation and Custom clearance | 9 | FRCT | I000 | 00I9 | I000#lfeX00I9
4927 | 4927 | 4927 | 4927 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Inspection & Delivery Free-stand CT/CTs with six cores Receipt at site | 10 | FRCT | I000 | 0I10 | I000#lfeX0I10
4928 | 4928 | 4928 | 4928 | SA24M005 | Construction & Installation Works |  | 4 | -1 | 0 |  |  | X | I000#lfeX
4929 | 4929 | 4929 | 4929 | SA24M005 | Auxiliary Power Reinforcement Works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Construction & Installation Works Auxiliary Power Reinforcement Works | 1 | CAUXP | C000 | 00C1 | C000#xCwy00C1
4930 | 4930 | 4930 | 4930 | SA24M005 | Protection Modification works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Construction & Installation Works Protection Modification works | 2 | CAUXP | C000 | 00C2 | C000#xCwy00C2
4931 | 4931 | 4931 | 4931 | SA24M005 | TeleCommunication Modification Works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Construction & Installation Works TeleCommunication Modification Works | 3 | CAUXP | C000 | 00C3 | C000#xCwy00C3
4932 | 4932 | 4932 | 4932 | SA24M005 | SAS/SCADA Integration Works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Construction & Installation Works SAS/SCADA Integration Works | 4 | CAUXP | C000 | 00C4 | C000#xCwy00C4
4933 | 4933 | 4933 | 4933 | SA24M005 | Testing & Commissioning |  | 4 | -1 | 0 |  |  | X | C000#xCwy
4934 | 4934 | 4934 | 4934 | SA24M005 | Prechecks |  | 5 | -1 | 0 |  |  | X | C000#xCwy
4935 | 4935 | 4935 | 4935 | SA24M005 | MCB Test In Control And Protection Panels |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Testing & Commissioning Prechecks MCB Test In Control And Protection Panels | 1 | PRECHECKMCB | E000 | 00E1 | M000PRECHECKMCB00M1
4936 | 4936 | 4936 | 4936 | SA24M005 | Auxiliary/Trip Relay Test In Control And Protection Panels |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Testing & Commissioning Prechecks Auxiliary/Trip Relay Test In Control And Protection Panels | 2 | PRECHECKMCB | E000 | 00E2 | M000PRECHECKMCB00M2
4937 | 4937 | 4937 | 4937 | SA24M005 | VT Secondary Circuit Injection & Loop Resistance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Testing & Commissioning Prechecks VT Secondary Circuit Injection & Loop Resistance | 3 | PRECHECKMCB | E000 | 00E3 | M000PRECHECKMCB00M3
4938 | 4938 | 4938 | 4938 | SA24M005 | CT Loop Resistance and Single Earth Point |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Testing & Commissioning Prechecks CT Loop Resistance and Single Earth Point | 4 | PRECHECKMCB | E000 | 00E4 | M000PRECHECKMCB00M4
4939 | 4939 | 4939 | 4939 | SA24M005 | Scheme Check For Line Protection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Testing & Commissioning Prechecks Scheme Check For Line Protection | 5 | PRECHECKMCB | E000 | 00E5 | M000PRECHECKMCB00M5
4940 | 4940 | 4940 | 4940 | SA24M005 | Set 1 Line Differential Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Testing & Commissioning Prechecks Set 1 Line Differential Relay Acceptance Test | 6 | PRECHECKMCB | E000 | 00E6 | M000PRECHECKMCB00M6
4941 | 4941 | 4941 | 4941 | SA24M005 | Set 2 Line Differential Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Testing & Commissioning Prechecks Set 2 Line Differential Relay Acceptance Test | 7 | PRECHECKMCB | E000 | 00E7 | M000PRECHECKMCB00M7
4942 | 4942 | 4942 | 4942 | SA24M005 | Commissioning |  | 5 | -1 | 0 |  |  | X
4943 | 4943 | 4943 | 4943 | SA24M005 | MCB Test In Control And Protection Panels |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Testing & Commissioning Commissioning MCB Test In Control And Protection Panels | 1 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCBs) in the control and protection panels. **Equipment:** * MCB tester * MCBs under test **Procedure:** 1. Set the MCB tester to the appropriate trip current. 2. Connect the MCB tester to the MCB under test. 3. Trip the MCB using the MCB tester. 4. Verify that the MCB trips within the specified time delay. 5. Reset the MCB and repeat the test for all MCBs under test. **Acceptance Criteria:** * All MCBs shall trip within the specified time delay. * All MCBs shall reset properly after tripping. | E000 | 00E1 | M000#ghio00M1
4944 | 4944 | 4944 | 4944 | SA24M005 | Auxiliary/Trip Relay Test In Control And Protection Panels |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Testing & Commissioning Commissioning Auxiliary/Trip Relay Test In Control And Protection Panels | 2 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCBs) in the control and protection panels. **Equipment:** * MCB tester * MCBs under test **Procedure:** 1. Set the MCB tester to the appropriate trip current. 2. Connect the MCB tester to the MCB under test. 3. Trip the MCB using the MCB tester. 4. Verify that the MCB trips within the specified time delay. 5. Reset the MCB and repeat the test for all MCBs under test. **Acceptance Criteria:** * All MCBs shall trip within the specified time delay. * All MCBs shall reset properly after tripping. | E000 | 00E2 | M000#ghio00M2
4945 | 4945 | 4945 | 4945 | SA24M005 | VT Secondary Circuit Injection & Loop Resistance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Testing & Commissioning Commissioning VT Secondary Circuit Injection & Loop Resistance | 3 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCBs) in the control and protection panels. **Equipment:** * MCB tester * MCBs under test **Procedure:** 1. Set the MCB tester to the appropriate trip current. 2. Connect the MCB tester to the MCB under test. 3. Trip the MCB using the MCB tester. 4. Verify that the MCB trips within the specified time delay. 5. Reset the MCB and repeat the test for all MCBs under test. **Acceptance Criteria:** * All MCBs shall trip within the specified time delay. * All MCBs shall reset properly after tripping. | E000 | 00E3 | M000#ghio00M3
4946 | 4946 | 4946 | 4946 | SA24M005 | CT Loop Resistance and Single Earth Point |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Testing & Commissioning Commissioning CT Loop Resistance and Single Earth Point | 4 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCBs) in the control and protection panels. **Equipment:** * MCB tester * MCBs under test **Procedure:** 1. Set the MCB tester to the appropriate trip current. 2. Connect the MCB tester to the MCB under test. 3. Trip the MCB using the MCB tester. 4. Verify that the MCB trips within the specified time delay. 5. Reset the MCB and repeat the test for all MCBs under test. **Acceptance Criteria:** * All MCBs shall trip within the specified time delay. * All MCBs shall reset properly after tripping. | E000 | 00E4 | M000#ghio00M4
4947 | 4947 | 4947 | 4947 | SA24M005 | Scheme Check For Line Protection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Testing & Commissioning Commissioning Scheme Check For Line Protection | 5 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCBs) in the control and protection panels. **Equipment:** * MCB tester * MCBs under test **Procedure:** 1. Set the MCB tester to the appropriate trip current. 2. Connect the MCB tester to the MCB under test. 3. Trip the MCB using the MCB tester. 4. Verify that the MCB trips within the specified time delay. 5. Reset the MCB and repeat the test for all MCBs under test. **Acceptance Criteria:** * All MCBs shall trip within the specified time delay. * All MCBs shall reset properly after tripping. | E000 | 00E5 | M000#ghio00M5
4948 | 4948 | 4948 | 4948 | SA24M005 | Set 1 Line Differential Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Testing & Commissioning Commissioning Set 1 Line Differential Relay Acceptance Test | 6 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCBs) in the control and protection panels. **Equipment:** * MCB tester * MCBs under test **Procedure:** 1. Set the MCB tester to the appropriate trip current. 2. Connect the MCB tester to the MCB under test. 3. Trip the MCB using the MCB tester. 4. Verify that the MCB trips within the specified time delay. 5. Reset the MCB and repeat the test for all MCBs under test. **Acceptance Criteria:** * All MCBs shall trip within the specified time delay. * All MCBs shall reset properly after tripping. | E000 | 00E6 | M000#ghio00M6
4949 | 4949 | 4949 | 4949 | SA24M005 | Set 2 Line Differential Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Testing & Commissioning Commissioning Set 2 Line Differential Relay Acceptance Test | 7 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCBs) in the control and protection panels. **Equipment:** * MCB tester * MCBs under test **Procedure:** 1. Set the MCB tester to the appropriate trip current. 2. Connect the MCB tester to the MCB under test. 3. Trip the MCB using the MCB tester. 4. Verify that the MCB trips within the specified time delay. 5. Reset the MCB and repeat the test for all MCBs under test. **Acceptance Criteria:** * All MCBs shall trip within the specified time delay. * All MCBs shall reset properly after tripping. | E000 | 00E7 | M000#ghio00M7
4950 | 4950 | 4950 | 4950 | SA24M005 | Main 1 Multifunction Relay Final Setting Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Testing & Commissioning Commissioning Main 1 Multifunction Relay Final Setting Test | 8 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCBs) in the control and protection panels. **Equipment:** * MCB tester * MCBs under test **Procedure:** 1. Set the MCB tester to the appropriate trip current. 2. Connect the MCB tester to the MCB under test. 3. Trip the MCB using the MCB tester. 4. Verify that the MCB trips within the specified time delay. 5. Reset the MCB and repeat the test for all MCBs under test. **Acceptance Criteria:** * All MCBs shall trip within the specified time delay. * All MCBs shall reset properly after tripping. | E000 | 00E8 | M000#ghio00M8
4951 | 4951 | 4951 | 4951 | SA24M005 | Main 2 Multifunction Relay Final setting Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Testing & Commissioning Commissioning Main 2 Multifunction Relay Final setting Test | 9 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCBs) in the control and protection panels. **Equipment:** * MCB tester * MCBs under test **Procedure:** 1. Set the MCB tester to the appropriate trip current. 2. Connect the MCB tester to the MCB under test. 3. Trip the MCB using the MCB tester. 4. Verify that the MCB trips within the specified time delay. 5. Reset the MCB and repeat the test for all MCBs under test. **Acceptance Criteria:** * All MCBs shall trip within the specified time delay. * All MCBs shall reset properly after tripping. | E000 | 00E9 | M000#ghio00M9
4952 | 4952 | 4952 | 4952 | SA24M005 | Alarm And Indication Check Up To SAS HMI And Gateway For EHV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Testing & Commissioning Commissioning Alarm And Indication Check Up To SAS HMI And Gateway For EHV | 10 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCBs) in the control and protection panels. **Equipment:** * MCB tester * MCBs under test **Procedure:** 1. Set the MCB tester to the appropriate trip current. 2. Connect the MCB tester to the MCB under test. 3. Trip the MCB using the MCB tester. 4. Verify that the MCB trips within the specified time delay. 5. Reset the MCB and repeat the test for all MCBs under test. **Acceptance Criteria:** * All MCBs shall trip within the specified time delay. * All MCBs shall reset properly after tripping. | E000 | 0E10 | M000#ghio00M10
4953 | 4953 | 4953 | 4953 | SA24M005 | Closed Loop Test EHV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Testing & Commissioning Commissioning Closed Loop Test EHV | 11 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCBs) in the control and protection panels. **Equipment:** * MCB tester * MCBs under test **Procedure:** 1. Set the MCB tester to the appropriate trip current. 2. Connect the MCB tester to the MCB under test. 3. Trip the MCB using the MCB tester. 4. Verify that the MCB trips within the specified time delay. 5. Reset the MCB and repeat the test for all MCBs under test. **Acceptance Criteria:** * All MCBs shall trip within the specified time delay. * All MCBs shall reset properly after tripping. | E000 | 0E11 | M000#ghio00M11
4954 | 4954 | 4954 | 4954 | SA24M005 | EHV Line Feeder Set 1 Multifunction Relay |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Testing & Commissioning Commissioning EHV Line Feeder Set 1 Multifunction Relay | 12 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCBs) in the control and protection panels. **Equipment:** * MCB tester * MCBs under test **Procedure:** 1. Set the MCB tester to the appropriate trip current. 2. Connect the MCB tester to the MCB under test. 3. Trip the MCB using the MCB tester. 4. Verify that the MCB trips within the specified time delay. 5. Reset the MCB and repeat the test for all MCBs under test. **Acceptance Criteria:** * All MCBs shall trip within the specified time delay. * All MCBs shall reset properly after tripping. | E000 | 0E12 | M000#ghio00M12
4955 | 4955 | 4955 | 4955 | SA24M005 | EHV Line Feeder Set 2 Multifunction Relay |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Testing & Commissioning Commissioning EHV Line Feeder Set 2 Multifunction Relay | 13 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCBs) in the control and protection panels. **Equipment:** * MCB tester * MCBs under test **Procedure:** 1. Set the MCB tester to the appropriate trip current. 2. Connect the MCB tester to the MCB under test. 3. Trip the MCB using the MCB tester. 4. Verify that the MCB trips within the specified time delay. 5. Reset the MCB and repeat the test for all MCBs under test. **Acceptance Criteria:** * All MCBs shall trip within the specified time delay. * All MCBs shall reset properly after tripping. | E000 | 0E13 | M000#ghio00M13
4956 | 4956 | 4956 | 4956 | SA24M005 | Final Trip Test for EHV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Testing & Commissioning Commissioning Final Trip Test for EHV | 14 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCBs) in the control and protection panels. **Equipment:** * MCB tester * MCBs under test **Procedure:** 1. Set the MCB tester to the appropriate trip current. 2. Connect the MCB tester to the MCB under test. 3. Trip the MCB using the MCB tester. 4. Verify that the MCB trips within the specified time delay. 5. Reset the MCB and repeat the test for all MCBs under test. **Acceptance Criteria:** * All MCBs shall trip within the specified time delay. * All MCBs shall reset properly after tripping. | E000 | 0E14 | M000#ghio00M14
4957 | 4957 | 4957 | 4957 | SA24M005 | Relay Final settings Review for EHV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Testing & Commissioning Commissioning Relay Final settings Review for EHV | 15 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCBs) in the control and protection panels. **Equipment:** * MCB tester * MCBs under test **Procedure:** 1. Set the MCB tester to the appropriate trip current. 2. Connect the MCB tester to the MCB under test. 3. Trip the MCB using the MCB tester. 4. Verify that the MCB trips within the specified time delay. 5. Reset the MCB and repeat the test for all MCBs under test. **Acceptance Criteria:** * All MCBs shall trip within the specified time delay. * All MCBs shall reset properly after tripping. | E000 | 0E15 | M000#ghio00M15
4958 | 4958 | 4958 | 4958 | SA24M005 | Normalization Before Energization EHV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Testing & Commissioning Commissioning Normalization Before Energization EHV | 16 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCBs) in the control and protection panels. **Equipment:** * MCB tester * MCBs under test **Procedure:** 1. Set the MCB tester to the appropriate trip current. 2. Connect the MCB tester to the MCB under test. 3. Trip the MCB using the MCB tester. 4. Verify that the MCB trips within the specified time delay. 5. Reset the MCB and repeat the test for all MCBs under test. **Acceptance Criteria:** * All MCBs shall trip within the specified time delay. * All MCBs shall reset properly after tripping. | E000 | 0E16 | M000#ghio00M16
4959 | 4959 | 4959 | 4959 | SA24M005 | Post Energization In Service Test for EHV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Testing & Commissioning Commissioning Post Energization In Service Test for EHV | 17 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCBs) in the control and protection panels. **Equipment:** * MCB tester * MCBs under test **Procedure:** 1. Set the MCB tester to the appropriate trip current. 2. Connect the MCB tester to the MCB under test. 3. Trip the MCB using the MCB tester. 4. Verify that the MCB trips within the specified time delay. 5. Reset the MCB and repeat the test for all MCBs under test. **Acceptance Criteria:** * All MCBs shall trip within the specified time delay. * All MCBs shall reset properly after tripping. | E000 | 0E17 | M000#ghio00M17
4960 | 4960 | 4960 | 4960 | SA24M005 | Energization for EHV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-2 (9006 BSP) Testing & Commissioning Commissioning Energization for EHV | 18 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCBs) in the control and protection panels. **Equipment:** * MCB tester * MCBs under test **Procedure:** 1. Set the MCB tester to the appropriate trip current. 2. Connect the MCB tester to the MCB under test. 3. Trip the MCB using the MCB tester. 4. Verify that the MCB trips within the specified time delay. 5. Reset the MCB and repeat the test for all MCBs under test. **Acceptance Criteria:** * All MCBs shall trip within the specified time delay. * All MCBs shall reset properly after tripping. | E000 | 0E18 | M000#ghio00M18
4961 | 4961 | 4961 | 4961 | SA24M005 | Remote End SS-3 (9029 BSP) |  | 3 | -1 | 0 |  |  | X
4962 | 4962 | 4962 | 4962 | SA24M005 | Engineering & Design (Phase VIII) |  | 4 | -1 | 0 |  |  | X
4963 | 4963 | 4963 | 4963 | SA24M005 | Modified Single Line Drawing |  | 5 | -1 | 0 |  |  | X
4964 | 4964 | 4964 | 4964 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Engineering & Design (Phase VIII) Modified Single Line Drawing Drafting / Preparation | 1 | E0SLD | E000 | 00E1 | E000#KPDI00E1
4965 | 4965 | 4965 | 4965 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Engineering & Design (Phase VIII) Modified Single Line Drawing Submission | 2 | E0SLD | E000 | 00E2 | E000#KPDI00E2
4966 | 4966 | 4966 | 4966 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Engineering & Design (Phase VIII) Modified Single Line Drawing Review / Evaluation | 3 | E0SLD | E000 | 00E3 | E000#KPDI00E3
4967 | 4967 | 4967 | 4967 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Engineering & Design (Phase VIII) Modified Single Line Drawing Approval with Comments | 4 | E0SLD | E000 | 00E4 | E000#KPDI00E4
4968 | 4968 | 4968 | 4968 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Engineering & Design (Phase VIII) Modified Single Line Drawing FINAL Approval | 5 | E0SLD | E000 | 00E5 | E000#KPDI00E5
4969 | 4969 | 4969 | 4969 | SA24M005 | Modified Overall Layout |  | 5 | -1 | 0 |  |  | X | E000#KPDI
4970 | 4970 | 4970 | 4970 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Engineering & Design (Phase VIII) Modified Overall Layout Drafting / Preparation | 1 | EQ0L | E000 | 00E1 | E000#AFRX00E1
4971 | 4971 | 4971 | 4971 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Engineering & Design (Phase VIII) Modified Overall Layout Submission | 2 | EQ0L | E000 | 00E2 | E000#AFRX00E2
4972 | 4972 | 4972 | 4972 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Engineering & Design (Phase VIII) Modified Overall Layout Review / Evaluation | 3 | EQ0L | E000 | 00E3 | E000#AFRX00E3
4973 | 4973 | 4973 | 4973 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Engineering & Design (Phase VIII) Modified Overall Layout Approval with Comments | 4 | EQ0L | E000 | 00E4 | E000#AFRX00E4
4974 | 4974 | 4974 | 4974 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Engineering & Design (Phase VIII) Modified Overall Layout FINAL Approval | 5 | EQ0L | E000 | 00E5 | E000#AFRX00E5
4975 | 4975 | 4975 | 4975 | SA24M005 | Material Procurement |  | 4 | -1 | 0 |  |  | X | E000#AFRX
4976 | 4976 | 4976 | 4976 | SA24M005 | Auxiliary Power Supply Reinforcement items |  | 5 | -1 | 0 |  |  | X | E000#AFRX
4977 | 4977 | 4977 | 4977 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Auxiliary Power Supply Reinforcement items Purchase Request to SCM | 1 | 0APSR | P000 | 00P1 | P000#yDwR00P1
4978 | 4978 | 4978 | 4978 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Auxiliary Power Supply Reinforcement items Issue of RFQ | 2 | 0APSR | P000 | 00P2 | P000#yDwR00P2
4979 | 4979 | 4979 | 4979 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Auxiliary Power Supply Reinforcement items Receipt of Technical offer from Vendor | 3 | 0APSR | P000 | 00P3 | P000#yDwR00P3
4980 | 4980 | 4980 | 4980 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Auxiliary Power Supply Reinforcement items Technical Evaluation by EDRC | 4 | 0APSR | P000 | 00P4 | P000#yDwR00P4
4981 | 4981 | 4981 | 4981 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Auxiliary Power Supply Reinforcement items Final technical compliance from Vendor | 5 | 0APSR | P000 | 00P5 | P000#yDwR00P5
4982 | 4982 | 4982 | 4982 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Auxiliary Power Supply Reinforcement items Technical clearance by EDRC | 6 | 0APSR | P000 | 00P6 | P000#yDwR00P6
4983 | 4983 | 4983 | 4983 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Auxiliary Power Supply Reinforcement items Commercial Evaluation by SCM | 7 | 0APSR | P000 | 00P7 | P000#yDwR00P7
4984 | 4984 | 4984 | 4984 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Auxiliary Power Supply Reinforcement items Vendor negotiation & Finalization | 8 | 0APSR | P000 | 00P8 | P000#yDwR00P8
4985 | 4985 | 4985 | 4985 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Auxiliary Power Supply Reinforcement items HPC Approval / PO release to vendor | 9 | 0APSR | P000 | 00P9 | P000#yDwR00P9
4986 | 4986 | 4986 | 4986 | SA24M005 | Protection Modification (SAS/SCADA integration/Telecommunication) |  | 5 | -1 | 0 |  |  | X | P000#yDwR
4987 | 4987 | 4987 | 4987 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Protection Modification (SAS/SCADA integration/Telecommunication) Purchase Request to SCM | 1 | PR0SCM | P000 | 00P1 | P000#MADt00P1
4988 | 4988 | 4988 | 4988 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Protection Modification (SAS/SCADA integration/Telecommunication) Issue of RFQ | 2 | PR0SCM | P000 | 00P2 | P000#MADt00P2
4989 | 4989 | 4989 | 4989 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Protection Modification (SAS/SCADA integration/Telecommunication) Receipt of Technical offer from Vendor | 3 | PR0SCM | P000 | 00P3 | P000#MADt00P3
4990 | 4990 | 4990 | 4990 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Protection Modification (SAS/SCADA integration/Telecommunication) Technical Evaluation by EDRC | 4 | PR0SCM | P000 | 00P4 | P000#MADt00P4
4991 | 4991 | 4991 | 4991 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Protection Modification (SAS/SCADA integration/Telecommunication) Final technical compliance from Vendor | 5 | PR0SCM | P000 | 00P5 | P000#MADt00P5
4992 | 4992 | 4992 | 4992 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Protection Modification (SAS/SCADA integration/Telecommunication) Technical clearance by EDRC | 6 | PR0SCM | P000 | 00P6 | P000#MADt00P6
4993 | 4993 | 4993 | 4993 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Protection Modification (SAS/SCADA integration/Telecommunication) Commercial Evaluation by SCM | 7 | PR0SCM | P000 | 00P7 | P000#MADt00P7
4994 | 4994 | 4994 | 4994 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Protection Modification (SAS/SCADA integration/Telecommunication) Vendor negotiation & Finalization | 8 | PR0SCM | P000 | 00P8 | P000#MADt00P8
4995 | 4995 | 4995 | 4995 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Protection Modification (SAS/SCADA integration/Telecommunication) HPC Approval / PO release to vendor | 9 | PR0SCM | P000 | 00P9 | P000#MADt00P9
4996 | 4996 | 4996 | 4996 | SA24M005 | CB Modules, 3150A |  | 5 | -1 | 0 |  |  | X | P000#MADt
4997 | 4997 | 4997 | 4997 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement CB Modules, 3150A Purchase Request to SCM | 1 | CB00RM | P000 | 00P1 | P000CB00RM00P1
4998 | 4998 | 4998 | 4998 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement CB Modules, 3150A Issue of RFQ | 2 | CB00RM | P000 | 00P2 | P000CB00RM00P2
4999 | 4999 | 4999 | 4999 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement CB Modules, 3150A Receipt of Technical offer from Vendor | 3 | CB00RM | P000 | 00P3 | P000CB00RM00P3
5000 | 5000 | 5000 | 5000 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement CB Modules, 3150A Technical Evaluation by EDRC | 4 | CB00RM | P000 | 00P4 | P000CB00RM00P4
5001 | 5001 | 5001 | 5001 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement CB Modules, 3150A Final technical compliance from Vendor | 5 | CB00RM | P000 | 00P5 | P000CB00RM00P5
5002 | 5002 | 5002 | 5002 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement CB Modules, 3150A Technical clearance by EDRC | 6 | CB00RM | P000 | 00P6 | P000CB00RM00P6
5003 | 5003 | 5003 | 5003 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement CB Modules, 3150A Commercial Evaluation by SCM | 7 | CB00RM | P000 | 00P7 | P000CB00RM00P7
5004 | 5004 | 5004 | 5004 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement CB Modules, 3150A Vendor negotiation & Finalization | 8 | CB00RM | P000 | 00P8 | P000CB00RM00P8
5005 | 5005 | 5005 | 5005 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement CB Modules, 3150A HPC Approval / PO release to vendor | 9 | CB00RM | P000 | 00P9 | P000CB00RM00P9
5006 | 5006 | 5006 | 5006 | SA24M005 | Disconnector Switch Modules |  | 5 | -1 | 0 |  |  | X
5007 | 5007 | 5007 | 5007 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Disconnector Switch Modules Purchase Request to SCM | 1 | 00DSCM | P000 | 00P1 | P00000DSCM00P1
5008 | 5008 | 5008 | 5008 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Disconnector Switch Modules Issue of RFQ | 2 | 00DSCM | P000 | 00P2 | P00000DSCM00P2
5009 | 5009 | 5009 | 5009 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Disconnector Switch Modules Receipt of Technical offer from Vendor | 3 | 00DSCM | P000 | 00P3 | P00000DSCM00P3
5010 | 5010 | 5010 | 5010 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Disconnector Switch Modules Technical Evaluation by EDRC | 4 | 00DSCM | P000 | 00P4 | P00000DSCM00P4
5011 | 5011 | 5011 | 5011 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Disconnector Switch Modules Final technical compliance from Vendor | 5 | 00DSCM | P000 | 00P5 | P00000DSCM00P5
5012 | 5012 | 5012 | 5012 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Disconnector Switch Modules Technical clearance by EDRC | 6 | 00DSCM | P000 | 00P6 | P00000DSCM00P6
5013 | 5013 | 5013 | 5013 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Disconnector Switch Modules Commercial Evaluation by SCM | 7 | 00DSCM | P000 | 00P7 | P00000DSCM00P7
5014 | 5014 | 5014 | 5014 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Disconnector Switch Modules Vendor negotiation & Finalization | 8 | 00DSCM | P000 | 00P8 | P00000DSCM00P8
5015 | 5015 | 5015 | 5015 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Disconnector Switch Modules HPC Approval / PO release to vendor | 9 | 00DSCM | P000 | 00P9 | P00000DSCM00P9
5016 | 5016 | 5016 | 5016 | SA24M005 | Grounding Switch Modules |  | 5 | -1 | 0 |  |  | X
5017 | 5017 | 5017 | 5017 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Grounding Switch Modules Purchase Request to SCM | 1 | 0GRSW | P000 | 00P1 | P0000GRSW00P1
5018 | 5018 | 5018 | 5018 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Grounding Switch Modules Issue of RFQ | 2 | 0GRSW | P000 | 00P2 | P0000GRSW00P2
5019 | 5019 | 5019 | 5019 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Grounding Switch Modules Receipt of Technical offer from Vendor | 3 | 0GRSW | P000 | 00P3 | P0000GRSW00P3
5020 | 5020 | 5020 | 5020 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Grounding Switch Modules Technical Evaluation by EDRC | 4 | 0GRSW | P000 | 00P4 | P0000GRSW00P4
5021 | 5021 | 5021 | 5021 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Grounding Switch Modules Final technical compliance from Vendor | 5 | 0GRSW | P000 | 00P5 | P0000GRSW00P5
5022 | 5022 | 5022 | 5022 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Grounding Switch Modules Technical clearance by EDRC | 6 | 0GRSW | P000 | 00P6 | P0000GRSW00P6
5023 | 5023 | 5023 | 5023 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Grounding Switch Modules Commercial Evaluation by SCM | 7 | 0GRSW | P000 | 00P7 | P0000GRSW00P7
5024 | 5024 | 5024 | 5024 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Grounding Switch Modules Vendor negotiation & Finalization | 8 | 0GRSW | P000 | 00P8 | P0000GRSW00P8
5025 | 5025 | 5025 | 5025 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Grounding Switch Modules HPC Approval / PO release to vendor | 9 | 0GRSW | P000 | 00P9 | P0000GRSW00P9
5026 | 5026 | 5026 | 5026 | SA24M005 | Current Transformer Modules |  | 5 | -1 | 0 |  |  | X
5027 | 5027 | 5027 | 5027 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Current Transformer Modules Purchase Request to SCM | 1 | 0CTRM | P000 | 00P1 | P0000CTRM00P1
5028 | 5028 | 5028 | 5028 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Current Transformer Modules Issue of RFQ | 2 | 0CTRM | P000 | 00P2 | P0000CTRM00P2
5029 | 5029 | 5029 | 5029 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Current Transformer Modules Receipt of Technical offer from Vendor | 3 | 0CTRM | P000 | 00P3 | P0000CTRM00P3
5030 | 5030 | 5030 | 5030 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Current Transformer Modules Technical Evaluation by EDRC | 4 | 0CTRM | P000 | 00P4 | P0000CTRM00P4
5031 | 5031 | 5031 | 5031 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Current Transformer Modules Final technical compliance from Vendor | 5 | 0CTRM | P000 | 00P5 | P0000CTRM00P5
5032 | 5032 | 5032 | 5032 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Current Transformer Modules Technical clearance by EDRC | 6 | 0CTRM | P000 | 00P6 | P0000CTRM00P6
5033 | 5033 | 5033 | 5033 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Current Transformer Modules Commercial Evaluation by SCM | 7 | 0CTRM | P000 | 00P7 | P0000CTRM00P7
5034 | 5034 | 5034 | 5034 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Current Transformer Modules Vendor negotiation & Finalization | 8 | 0CTRM | P000 | 00P8 | P0000CTRM00P8
5035 | 5035 | 5035 | 5035 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Current Transformer Modules HPC Approval / PO release to vendor | 9 | 0CTRM | P000 | 00P9 | P0000CTRM00P9
5036 | 5036 | 5036 | 5036 | SA24M005 | Surge Arrestor Modules |  | 5 | -1 | 0 |  |  | X
5037 | 5037 | 5037 | 5037 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Surge Arrestor Modules Purchase Request to SCM | 1 | SRGA | P000 | 00P1 | P000#MSPd00P1
5038 | 5038 | 5038 | 5038 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Surge Arrestor Modules Issue of RFQ | 2 | SRGA | P000 | 00P2 | P000#MSPd00P2
5039 | 5039 | 5039 | 5039 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Surge Arrestor Modules Receipt of Technical offer from Vendor | 3 | SRGA | P000 | 00P3 | P000#MSPd00P3
5040 | 5040 | 5040 | 5040 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Surge Arrestor Modules Technical Evaluation by EDRC | 4 | SRGA | P000 | 00P4 | P000#MSPd00P4
5041 | 5041 | 5041 | 5041 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Surge Arrestor Modules Final technical compliance from Vendor | 5 | SRGA | P000 | 00P5 | P000#MSPd00P5
5042 | 5042 | 5042 | 5042 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Surge Arrestor Modules Technical clearance by EDRC | 6 | SRGA | P000 | 00P6 | P000#MSPd00P6
5043 | 5043 | 5043 | 5043 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Surge Arrestor Modules Commercial Evaluation by SCM | 7 | SRGA | P000 | 00P7 | P000#MSPd00P7
5044 | 5044 | 5044 | 5044 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Surge Arrestor Modules Vendor negotiation & Finalization | 8 | SRGA | P000 | 00P8 | P000#MSPd00P8
5045 | 5045 | 5045 | 5045 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement Surge Arrestor Modules HPC Approval / PO release to vendor | 9 | SRGA | P000 | 00P9 | P000#MSPd00P9
5046 | 5046 | 5046 | 5046 | SA24M005 | LCC Panels |  | 5 | -1 | 0 |  |  | X | P000#MSPd
5047 | 5047 | 5047 | 5047 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement LCC Panels Purchase Request to SCM | 1 | LCCPNL | P000 | 00P1 | P000LCCPNL00P1
5048 | 5048 | 5048 | 5048 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement LCC Panels Issue of RFQ | 2 | LCCPNL | P000 | 00P2 | P000LCCPNL00P2
5049 | 5049 | 5049 | 5049 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement LCC Panels Receipt of Technical offer from Vendor | 3 | LCCPNL | P000 | 00P3 | P000LCCPNL00P3
5050 | 5050 | 5050 | 5050 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement LCC Panels Technical Evaluation by EDRC | 4 | LCCPNL | P000 | 00P4 | P000LCCPNL00P4
5051 | 5051 | 5051 | 5051 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement LCC Panels Final technical compliance from Vendor | 5 | LCCPNL | P000 | 00P5 | P000LCCPNL00P5
5052 | 5052 | 5052 | 5052 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement LCC Panels Technical clearance by EDRC | 6 | LCCPNL | P000 | 00P6 | P000LCCPNL00P6
5053 | 5053 | 5053 | 5053 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement LCC Panels Commercial Evaluation by SCM | 7 | LCCPNL | P000 | 00P7 | P000LCCPNL00P7
5054 | 5054 | 5054 | 5054 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement LCC Panels Vendor negotiation & Finalization | 8 | LCCPNL | P000 | 00P8 | P000LCCPNL00P8
5055 | 5055 | 5055 | 5055 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement LCC Panels HPC Approval / PO release to vendor | 9 | LCCPNL | P000 | 00P9 | P000LCCPNL00P9
5056 | 5056 | 5056 | 5056 | SA24M005 | PDMS Panels & Accessories |  | 5 | -1 | 0 |  |  | X
5057 | 5057 | 5057 | 5057 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement PDMS Panels & Accessories Purchase Request to SCM | 1 | PDMS | P000 | 00P1 | P000#MgpE00P1
5058 | 5058 | 5058 | 5058 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement PDMS Panels & Accessories Issue of RFQ | 2 | PDMS | P000 | 00P2 | P000#MgpE00P2
5059 | 5059 | 5059 | 5059 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement PDMS Panels & Accessories Receipt of Technical offer from Vendor | 3 | PDMS | P000 | 00P3 | P000#MgpE00P3
5060 | 5060 | 5060 | 5060 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement PDMS Panels & Accessories Technical Evaluation by EDRC | 4 | PDMS | P000 | 00P4 | P000#MgpE00P4
5061 | 5061 | 5061 | 5061 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement PDMS Panels & Accessories Final technical compliance from Vendor | 5 | PDMS | P000 | 00P5 | P000#MgpE00P5
5062 | 5062 | 5062 | 5062 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement PDMS Panels & Accessories Technical clearance by EDRC | 6 | PDMS | P000 | 00P6 | P000#MgpE00P6
5063 | 5063 | 5063 | 5063 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement PDMS Panels & Accessories Commercial Evaluation by SCM | 7 | PDMS | P000 | 00P7 | P000#MgpE00P7
5064 | 5064 | 5064 | 5064 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement PDMS Panels & Accessories Vendor negotiation & Finalization | 8 | PDMS | P000 | 00P8 | P000#MgpE00P8
5065 | 5065 | 5065 | 5065 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement PDMS Panels & Accessories HPC Approval / PO release to vendor | 9 | PDMS | P000 | 00P9 | P000#MgpE00P9
5066 | 5066 | 5066 | 5066 | SA24M005 | 80MVAR Line Reactor & Accessories |  | 5 | -1 | 0 |  |  | X | P000#MgpE
5067 | 5067 | 5067 | 5067 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement 80MVAR Line Reactor & Accessories Purchase Request to SCM | 1 | #NMZr | P000 | 00P1 | P000#NMZr00P1
5068 | 5068 | 5068 | 5068 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement 80MVAR Line Reactor & Accessories Issue of RFQ | 2 | #NMZr | P000 | 00P2 | P000#NMZr00P2
5069 | 5069 | 5069 | 5069 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement 80MVAR Line Reactor & Accessories Receipt of Technical offer from Vendor | 3 | #NMZr | P000 | 00P3 | P000#NMZr00P3
5070 | 5070 | 5070 | 5070 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement 80MVAR Line Reactor & Accessories Technical Evaluation by EDRC | 4 | #NMZr | P000 | 00P4 | P000#NMZr00P4
5071 | 5071 | 5071 | 5071 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement 80MVAR Line Reactor & Accessories Final technical compliance from Vendor | 5 | #NMZr | P000 | 00P5 | P000#NMZr00P5
5072 | 5072 | 5072 | 5072 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement 80MVAR Line Reactor & Accessories Technical clearance by EDRC | 6 | #NMZr | P000 | 00P6 | P000#NMZr00P6
5073 | 5073 | 5073 | 5073 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement 80MVAR Line Reactor & Accessories Commercial Evaluation by SCM | 7 | #NMZr | P000 | 00P7 | P000#NMZr00P7
5074 | 5074 | 5074 | 5074 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement 80MVAR Line Reactor & Accessories Vendor negotiation & Finalization | 8 | #NMZr | P000 | 00P8 | P000#NMZr00P8
5075 | 5075 | 5075 | 5075 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Material Procurement 80MVAR Line Reactor & Accessories HPC Approval / PO release to vendor | 9 | #NMZr | P000 | 00P9 | P000#NMZr00P9
5076 | 5076 | 5076 | 5076 | SA24M005 | Inspection & Delivery |  | 4 | -1 | 0 |  |  | X
5077 | 5077 | 5077 | 5077 | SA24M005 | Auxiliary Power Supply Reinforcement items |  | 5 | -1 | 0 |  |  | X
5078 | 5078 | 5078 | 5078 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Auxiliary Power Supply Reinforcement items MQP / ITP Submission | 1 | 0APSR | I000 | 00I1 | I000#LmcY00I1
5079 | 5079 | 5079 | 5079 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Auxiliary Power Supply Reinforcement items MQP / ITP Approval | 2 | 0APSR | I000 | 00I2 | I000#LmcY00I2
5080 | 5080 | 5080 | 5080 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Auxiliary Power Supply Reinforcement items Issuance of MFC | 3 | 0APSR | I000 | 00I3 | I000#LmcY00I3
5081 | 5081 | 5081 | 5081 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Auxiliary Power Supply Reinforcement items Lead Time For Manufacturing | 4 | 0APSR | I000 | 00I4 | I000#LmcY00I4
5082 | 5082 | 5082 | 5082 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Auxiliary Power Supply Reinforcement items Material readiness / Inspection call | 5 | 0APSR | I000 | 00I5 | I000#LmcY00I5
5083 | 5083 | 5083 | 5083 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Auxiliary Power Supply Reinforcement items Inspection by client personal / Third Party | 6 | 0APSR | I000 | 00I6 | I000#LmcY00I6
5084 | 5084 | 5084 | 5084 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Auxiliary Power Supply Reinforcement items Submission of FAT Compliance by Vendor | 7 | 0APSR | I000 | 00I7 | I000#LmcY00I7
5085 | 5085 | 5085 | 5085 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Auxiliary Power Supply Reinforcement items Dispatch Clearance to vendor | 8 | 0APSR | I000 | 00I8 | I000#LmcY00I8
5086 | 5086 | 5086 | 5086 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Auxiliary Power Supply Reinforcement items Transportation and Custom clearance | 9 | 0APSR | I000 | 00I9 | I000#LmcY00I9
5087 | 5087 | 5087 | 5087 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Auxiliary Power Supply Reinforcement items Receipt at site | 10 | 0APSR | I000 | 0I10 | I000#LmcY0I10
5088 | 5088 | 5088 | 5088 | SA24M005 | Protection Modification (SAS/SCADA integration/Telecommunication) |  | 5 | -1 | 0 |  |  | X | I000#LmcY
5089 | 5089 | 5089 | 5089 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Protection Modification (SAS/SCADA integration/Telecommunication) MQP / ITP Submission | 1 | 0PQM | I000 | 00I1 | I000#gvBE00I1
5090 | 5090 | 5090 | 5090 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Protection Modification (SAS/SCADA integration/Telecommunication) MQP / ITP Approval | 2 | 0PQM | I000 | 00I2 | I000#gvBE00I2
5091 | 5091 | 5091 | 5091 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Protection Modification (SAS/SCADA integration/Telecommunication) Issuance of MFC | 3 | 0PQM | I000 | 00I3 | I000#gvBE00I3
5092 | 5092 | 5092 | 5092 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Protection Modification (SAS/SCADA integration/Telecommunication) Lead Time For Manufacturing | 4 | 0PQM | I000 | 00I4 | I000#gvBE00I4
5093 | 5093 | 5093 | 5093 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Protection Modification (SAS/SCADA integration/Telecommunication) Material readiness / Inspection call | 5 | 0PQM | I000 | 00I5 | I000#gvBE00I5
5094 | 5094 | 5094 | 5094 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Protection Modification (SAS/SCADA integration/Telecommunication) Inspection by client personal / Third Party | 6 | 0PQM | I000 | 00I6 | I000#gvBE00I6
5095 | 5095 | 5095 | 5095 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Protection Modification (SAS/SCADA integration/Telecommunication) Submission of FAT Compliance by Vendor | 7 | 0PQM | I000 | 00I7 | I000#gvBE00I7
5096 | 5096 | 5096 | 5096 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Protection Modification (SAS/SCADA integration/Telecommunication) Dispatch Clearance to vendor | 8 | 0PQM | I000 | 00I8 | I000#gvBE00I8
5097 | 5097 | 5097 | 5097 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Protection Modification (SAS/SCADA integration/Telecommunication) Transportation and Custom clearance | 9 | 0PQM | I000 | 00I9 | I000#gvBE00I9
5098 | 5098 | 5098 | 5098 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Protection Modification (SAS/SCADA integration/Telecommunication) Receipt at site | 10 | 0PQM | I000 | 0I10 | I000#gvBE0I10
5099 | 5099 | 5099 | 5099 | SA24M005 | CB Modules, 3150A |  | 5 | -1 | 0 |  |  | X | I000#gvBE
5100 | 5100 | 5100 | 5100 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery CB Modules, 3150A MQP / ITP Submission | 1 | CB0M0CB | I000 | 00I1 | I000CB0M0CB00I1
5101 | 5101 | 5101 | 5101 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery CB Modules, 3150A MQP / ITP Approval | 2 | CB0M0CB | I000 | 00I2 | I000CB0M0CB00I2
5102 | 5102 | 5102 | 5102 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery CB Modules, 3150A Issuance of MFC | 3 | CB0M0CB | I000 | 00I3 | I000CB0M0CB00I3
5103 | 5103 | 5103 | 5103 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery CB Modules, 3150A Lead Time For Manufacturing | 4 | CB0M0CB | I000 | 00I4 | I000CB0M0CB00I4
5104 | 5104 | 5104 | 5104 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery CB Modules, 3150A Material readiness / Inspection call | 5 | CB0M0CB | I000 | 00I5 | I000CB0M0CB00I5
5105 | 5105 | 5105 | 5105 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery CB Modules, 3150A Inspection by client personal / Third Party | 6 | CB0M0CB | I000 | 00I6 | I000CB0M0CB00I6
5106 | 5106 | 5106 | 5106 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery CB Modules, 3150A Submission of FAT Compliance by Vendor | 7 | CB0M0CB | I000 | 00I7 | I000CB0M0CB00I7
5107 | 5107 | 5107 | 5107 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery CB Modules, 3150A Dispatch Clearance to vendor | 8 | CB0M0CB | I000 | 00I8 | I000CB0M0CB00I8
5108 | 5108 | 5108 | 5108 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery CB Modules, 3150A Transportation and Custom clearance | 9 | CB0M0CB | I000 | 00I9 | I000CB0M0CB00I9
5109 | 5109 | 5109 | 5109 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery CB Modules, 3150A Receipt at site | 10 | CB0M0CB | I000 | 0I10 | I000CB0M0CB0I10
5110 | 5110 | 5110 | 5110 | SA24M005 | Disconnector Switch Modules |  | 5 | -1 | 0 |  |  | X
5111 | 5111 | 5111 | 5111 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Disconnector Switch Modules MQP / ITP Submission | 1 | DISC | I000 | 00I1 | I000DISC00I1
5112 | 5112 | 5112 | 5112 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Disconnector Switch Modules MQP / ITP Approval | 2 | DISC | I000 | 00I2 | I000DISC00I2
5113 | 5113 | 5113 | 5113 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Disconnector Switch Modules Issuance of MFC | 3 | DISC | I000 | 00I3 | I000DISC00I3
5114 | 5114 | 5114 | 5114 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Disconnector Switch Modules Lead Time For Manufacturing | 4 | DISC | I000 | 00I4 | I000DISC00I4
5115 | 5115 | 5115 | 5115 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Disconnector Switch Modules Material readiness / Inspection call | 5 | DISC | I000 | 00I5 | I000DISC00I5
5116 | 5116 | 5116 | 5116 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Disconnector Switch Modules Inspection by client personal / Third Party | 6 | DISC | I000 | 00I6 | I000DISC00I6
5117 | 5117 | 5117 | 5117 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Disconnector Switch Modules Submission of FAT Compliance by Vendor | 7 | DISC | I000 | 00I7 | I000DISC00I7
5118 | 5118 | 5118 | 5118 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Disconnector Switch Modules Dispatch Clearance to vendor | 8 | DISC | I000 | 00I8 | I000DISC00I8
5119 | 5119 | 5119 | 5119 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Disconnector Switch Modules Transportation and Custom clearance | 9 | DISC | I000 | 00I9 | I000DISC00I9
5120 | 5120 | 5120 | 5120 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Disconnector Switch Modules Receipt at site | 10 | DISC | I000 | 0I10 | I000DISC0I10
5121 | 5121 | 5121 | 5121 | SA24M005 | Grounding Switch Modules |  | 5 | -1 | 0 |  |  | X
5122 | 5122 | 5122 | 5122 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Grounding Switch Modules MQP / ITP Submission | 1 | 0GRND | I000 | 00I1 | I0000GRND00I1
5123 | 5123 | 5123 | 5123 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Grounding Switch Modules MQP / ITP Approval | 2 | 0GRND | I000 | 00I2 | I0000GRND00I2
5124 | 5124 | 5124 | 5124 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Grounding Switch Modules Issuance of MFC | 3 | 0GRND | I000 | 00I3 | I0000GRND00I3
5125 | 5125 | 5125 | 5125 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Grounding Switch Modules Lead Time For Manufacturing | 4 | 0GRND | I000 | 00I4 | I0000GRND00I4
5126 | 5126 | 5126 | 5126 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Grounding Switch Modules Material readiness / Inspection call | 5 | 0GRND | I000 | 00I5 | I0000GRND00I5
5127 | 5127 | 5127 | 5127 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Grounding Switch Modules Inspection by client personal / Third Party | 6 | 0GRND | I000 | 00I6 | I0000GRND00I6
5128 | 5128 | 5128 | 5128 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Grounding Switch Modules Submission of FAT Compliance by Vendor | 7 | 0GRND | I000 | 00I7 | I0000GRND00I7
5129 | 5129 | 5129 | 5129 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Grounding Switch Modules Dispatch Clearance to vendor | 8 | 0GRND | I000 | 00I8 | I0000GRND00I8
5130 | 5130 | 5130 | 5130 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Grounding Switch Modules Transportation and Custom clearance | 9 | 0GRND | I000 | 00I9 | I0000GRND00I9
5131 | 5131 | 5131 | 5131 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Grounding Switch Modules Receipt at site | 10 | 0GRND | I000 | 0I10 | I0000GRND0I10
5132 | 5132 | 5132 | 5132 | SA24M005 | Current Transformer Modules |  | 5 | -1 | 0 |  |  | X
5133 | 5133 | 5133 | 5133 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Current Transformer Modules MQP / ITP Submission | 1 | 0CTRM | I000 | 00I1 | I0000CTRM00I1
5134 | 5134 | 5134 | 5134 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Current Transformer Modules MQP / ITP Approval | 2 | 0CTRM | I000 | 00I2 | I0000CTRM00I2
5135 | 5135 | 5135 | 5135 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Current Transformer Modules Issuance of MFC | 3 | 0CTRM | I000 | 00I3 | I0000CTRM00I3
5136 | 5136 | 5136 | 5136 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Current Transformer Modules Lead Time For Manufacturing | 4 | 0CTRM | I000 | 00I4 | I0000CTRM00I4
5137 | 5137 | 5137 | 5137 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Current Transformer Modules Material readiness / Inspection call | 5 | 0CTRM | I000 | 00I5 | I0000CTRM00I5
5138 | 5138 | 5138 | 5138 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Current Transformer Modules Inspection by client personal / Third Party | 6 | 0CTRM | I000 | 00I6 | I0000CTRM00I6
5139 | 5139 | 5139 | 5139 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Current Transformer Modules Submission of FAT Compliance by Vendor | 7 | 0CTRM | I000 | 00I7 | I0000CTRM00I7
5140 | 5140 | 5140 | 5140 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Current Transformer Modules Dispatch Clearance to vendor | 8 | 0CTRM | I000 | 00I8 | I0000CTRM00I8
5141 | 5141 | 5141 | 5141 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Current Transformer Modules Transportation and Custom clearance | 9 | 0CTRM | I000 | 00I9 | I0000CTRM00I9
5142 | 5142 | 5142 | 5142 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Current Transformer Modules Receipt at site | 10 | 0CTRM | I000 | 0I10 | I0000CTRM0I10
5143 | 5143 | 5143 | 5143 | SA24M005 | Surge Arrestor Modules |  | 5 | -1 | 0 |  |  | X
5144 | 5144 | 5144 | 5144 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Surge Arrestor Modules MQP / ITP Submission | 1 | SRGA | I000 | 00I1 | I000#fgLp00I1
5145 | 5145 | 5145 | 5145 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Surge Arrestor Modules MQP / ITP Approval | 2 | SRGA | I000 | 00I2 | I000#fgLp00I2
5146 | 5146 | 5146 | 5146 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Surge Arrestor Modules Issuance of MFC | 3 | SRGA | I000 | 00I3 | I000#fgLp00I3
5147 | 5147 | 5147 | 5147 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Surge Arrestor Modules Lead Time For Manufacturing | 4 | SRGA | I000 | 00I4 | I000#fgLp00I4
5148 | 5148 | 5148 | 5148 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Surge Arrestor Modules Material readiness / Inspection call | 5 | SRGA | I000 | 00I5 | I000#fgLp00I5
5149 | 5149 | 5149 | 5149 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Surge Arrestor Modules Inspection by client personal / Third Party | 6 | SRGA | I000 | 00I6 | I000#fgLp00I6
5150 | 5150 | 5150 | 5150 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Surge Arrestor Modules Submission of FAT Compliance by Vendor | 7 | SRGA | I000 | 00I7 | I000#fgLp00I7
5151 | 5151 | 5151 | 5151 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Surge Arrestor Modules Dispatch Clearance to vendor | 8 | SRGA | I000 | 00I8 | I000#fgLp00I8
5152 | 5152 | 5152 | 5152 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Surge Arrestor Modules Transportation and Custom clearance | 9 | SRGA | I000 | 00I9 | I000#fgLp00I9
5153 | 5153 | 5153 | 5153 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery Surge Arrestor Modules Receipt at site | 10 | SRGA | I000 | 0I10 | I000#fgLp0I10
5154 | 5154 | 5154 | 5154 | SA24M005 | LCC Panels |  | 5 | -1 | 0 |  |  | X | I000#fgLp
5155 | 5155 | 5155 | 5155 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery LCC Panels MQP / ITP Submission | 1 | LCCPN | I000 | 00I1 | I000LCCPN00I1
5156 | 5156 | 5156 | 5156 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery LCC Panels MQP / ITP Approval | 2 | LCCPN | I000 | 00I2 | I000LCCPN00I2
5157 | 5157 | 5157 | 5157 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery LCC Panels Issuance of MFC | 3 | LCCPN | I000 | 00I3 | I000LCCPN00I3
5158 | 5158 | 5158 | 5158 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery LCC Panels Lead Time For Manufacturing | 4 | LCCPN | I000 | 00I4 | I000LCCPN00I4
5159 | 5159 | 5159 | 5159 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery LCC Panels Material readiness / Inspection call | 5 | LCCPN | I000 | 00I5 | I000LCCPN00I5
5160 | 5160 | 5160 | 5160 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery LCC Panels Inspection by client personal / Third Party | 6 | LCCPN | I000 | 00I6 | I000LCCPN00I6
5161 | 5161 | 5161 | 5161 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery LCC Panels Submission of FAT Compliance by Vendor | 7 | LCCPN | I000 | 00I7 | I000LCCPN00I7
5162 | 5162 | 5162 | 5162 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery LCC Panels Dispatch Clearance to vendor | 8 | LCCPN | I000 | 00I8 | I000LCCPN00I8
5163 | 5163 | 5163 | 5163 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery LCC Panels Transportation and Custom clearance | 9 | LCCPN | I000 | 00I9 | I000LCCPN00I9
5164 | 5164 | 5164 | 5164 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery LCC Panels Receipt at site | 10 | LCCPN | I000 | 0I10 | I000LCCPN0I10
5165 | 5165 | 5165 | 5165 | SA24M005 | PDMS Panels & Accessories |  | 5 | -1 | 0 |  |  | X
5166 | 5166 | 5166 | 5166 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery PDMS Panels & Accessories MQP / ITP Submission | 1 | PDMS | I000 | 00I1 | I000#dxMr00I1
5167 | 5167 | 5167 | 5167 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery PDMS Panels & Accessories MQP / ITP Approval | 2 | PDMS | I000 | 00I2 | I000#dxMr00I2
5168 | 5168 | 5168 | 5168 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery PDMS Panels & Accessories Issuance of MFC | 3 | PDMS | I000 | 00I3 | I000#dxMr00I3
5169 | 5169 | 5169 | 5169 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery PDMS Panels & Accessories Lead Time For Manufacturing | 4 | PDMS | I000 | 00I4 | I000#dxMr00I4
5170 | 5170 | 5170 | 5170 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery PDMS Panels & Accessories Material readiness / Inspection call | 5 | PDMS | I000 | 00I5 | I000#dxMr00I5
5171 | 5171 | 5171 | 5171 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery PDMS Panels & Accessories Inspection by client personal / Third Party | 6 | PDMS | I000 | 00I6 | I000#dxMr00I6
5172 | 5172 | 5172 | 5172 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery PDMS Panels & Accessories Submission of FAT Compliance by Vendor | 7 | PDMS | I000 | 00I7 | I000#dxMr00I7
5173 | 5173 | 5173 | 5173 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery PDMS Panels & Accessories Dispatch Clearance to vendor | 8 | PDMS | I000 | 00I8 | I000#dxMr00I8
5174 | 5174 | 5174 | 5174 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery PDMS Panels & Accessories Transportation and Custom clearance | 9 | PDMS | I000 | 00I9 | I000#dxMr00I9
5175 | 5175 | 5175 | 5175 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery PDMS Panels & Accessories Receipt at site | 10 | PDMS | I000 | 0I10 | I000#dxMr0I10
5176 | 5176 | 5176 | 5176 | SA24M005 | 80MVAR Line Reactor & Accessories |  | 5 | -1 | 0 |  |  | X | I000#dxMr
5177 | 5177 | 5177 | 5177 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery 80MVAR Line Reactor & Accessories MQP / ITP Submission | 1 | 00LRA | I000 | 00I1 | I00000LRA00I1
5178 | 5178 | 5178 | 5178 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery 80MVAR Line Reactor & Accessories MQP / ITP Approval | 2 | 00LRA | I000 | 00I2 | I00000LRA00I2
5179 | 5179 | 5179 | 5179 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery 80MVAR Line Reactor & Accessories Issuance of MFC | 3 | 00LRA | I000 | 00I3 | I00000LRA00I3
5180 | 5180 | 5180 | 5180 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery 80MVAR Line Reactor & Accessories Lead Time For Manufacturing | 4 | 00LRA | I000 | 00I4 | I00000LRA00I4
5181 | 5181 | 5181 | 5181 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery 80MVAR Line Reactor & Accessories Material readiness / Inspection call | 5 | 00LRA | I000 | 00I5 | I00000LRA00I5
5182 | 5182 | 5182 | 5182 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery 80MVAR Line Reactor & Accessories Inspection by client personal / Third Party | 6 | 00LRA | I000 | 00I6 | I00000LRA00I6
5183 | 5183 | 5183 | 5183 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery 80MVAR Line Reactor & Accessories Submission of FAT Compliance by Vendor | 7 | 00LRA | I000 | 00I7 | I00000LRA00I7
5184 | 5184 | 5184 | 5184 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery 80MVAR Line Reactor & Accessories Dispatch Clearance to vendor | 8 | 00LRA | I000 | 00I8 | I00000LRA00I8
5185 | 5185 | 5185 | 5185 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery 80MVAR Line Reactor & Accessories Transportation and Custom clearance | 9 | 00LRA | I000 | 00I9 | I00000LRA00I9
5186 | 5186 | 5186 | 5186 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Inspection & Delivery 80MVAR Line Reactor & Accessories Receipt at site | 10 | 00LRA | I000 | 0I10 | I00000LRA0I10
5187 | 5187 | 5187 | 5187 | SA24M005 | Construction & Installation Works |  | 4 | -1 | 0 |  |  | X
5188 | 5188 | 5188 | 5188 | SA24M005 | 80MVAR Line Reactor- Civil Works |  | 5 | -1 | 0 |  |  | X
5189 | 5189 | 5189 | 5189 | SA24M005 | Excavation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Construction & Installation Works 80MVAR Line Reactor- Civil Works Excavation | 1 | 00LR | C000 | 00C1 | C000#mraK00C1
5190 | 5190 | 5190 | 5190 | SA24M005 | Compaction |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Construction & Installation Works 80MVAR Line Reactor- Civil Works Compaction | 2 | 00LR | C000 | 00C2 | C000#mraK00C2
5191 | 5191 | 5191 | 5191 | SA24M005 | Lean Concrete under Raft Foundation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Construction & Installation Works 80MVAR Line Reactor- Civil Works Lean Concrete under Raft Foundation | 3 | 00LR | C000 | 00C3 | C000#mraK00C3
5192 | 5192 | 5192 | 5192 | SA24M005 | Horizontal Waterproofing for Raft Foundation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Construction & Installation Works 80MVAR Line Reactor- Civil Works Horizontal Waterproofing for Raft Foundation | 4 | 00LR | C000 | 00C4 | C000#mraK00C4
5193 | 5193 | 5193 | 5193 | SA24M005 | Screed Layer Over Waterproofing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Construction & Installation Works 80MVAR Line Reactor- Civil Works Screed Layer Over Waterproofing | 5 | 00LR | C000 | 00C5 | C000#mraK00C5
5194 | 5194 | 5194 | 5194 | SA24M005 | R.C for Raft Foundation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Construction & Installation Works 80MVAR Line Reactor- Civil Works R.C for Raft Foundation | 6 | 00LR | C000 | 00C6 | C000#mraK00C6
5195 | 5195 | 5195 | 5195 | SA24M005 | R.C for Pedestal & Catch Basin Walls |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Construction & Installation Works 80MVAR Line Reactor- Civil Works R.C for Pedestal & Catch Basin Walls | 7 | 00LR | C000 | 00C7 | C000#mraK00C7
5196 | 5196 | 5196 | 5196 | SA24M005 | Vertical Waterproofing & Protection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Construction & Installation Works 80MVAR Line Reactor- Civil Works Vertical Waterproofing & Protection | 8 | 00LR | C000 | 00C8 | C000#mraK00C8
5197 | 5197 | 5197 | 5197 | SA24M005 | Installation of Rail Tracks |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Construction & Installation Works 80MVAR Line Reactor- Civil Works Installation of Rail Tracks | 9 | 00LR | C000 | 00C9 | C000#mraK00C9
5198 | 5198 | 5198 | 5198 | SA24M005 | Cementious Coating & Painting |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Construction & Installation Works 80MVAR Line Reactor- Civil Works Cementious Coating & Painting | 10 | 00LR | C000 | 0C10 | C000#mraK0C10
5199 | 5199 | 5199 | 5199 | SA24M005 | Installation of H-Beams and Gratings |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Construction & Installation Works 80MVAR Line Reactor- Civil Works Installation of H-Beams and Gratings | 11 | 00LR | C000 | 0C11 | C000#mraK0C11
5200 | 5200 | 5200 | 5200 | SA24M005 | Readyness for Installation of Transformer |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Construction & Installation Works 80MVAR Line Reactor- Civil Works Readyness for Installation of Transformer | 12 | 00LR | C000 | 0C12 | C000#mraK0C12
5201 | 5201 | 5201 | 5201 | SA24M005 | Crash Barier |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Construction & Installation Works 80MVAR Line Reactor- Civil Works Crash Barier | 13 | 00LR | C000 | 0C13 | C000#mraK0C13
5202 | 5202 | 5202 | 5202 | SA24M005 | Gravel filling above grating |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Construction & Installation Works 80MVAR Line Reactor- Civil Works Gravel filling above grating | 14 | 00LR | C000 | 0C14 | C000#mraK0C14
5203 | 5203 | 5203 | 5203 | SA24M005 | Backfilling Compaction up to Design Level |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Construction & Installation Works 80MVAR Line Reactor- Civil Works Backfilling Compaction up to Design Level | 15 | 00LR | C000 | 0C15 | C000#mraK0C15
5204 | 5204 | 5204 | 5204 | SA24M005 | 80 MVAR Line Reactor- Installation Works |  | 5 | -1 | 0 |  |  | X | C000#mraK
5205 | 5205 | 5205 | 5205 | SA24M005 | Erection of Reactor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Construction & Installation Works 80 MVAR Line Reactor- Installation Works Erection of Reactor | 1 | 00LR | C000 | 00C1 | C000#MwgC00C1
5206 | 5206 | 5206 | 5206 | SA24M005 | Erection of accessories |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Construction & Installation Works 80 MVAR Line Reactor- Installation Works Erection of accessories | 2 | 00LR | C000 | 00C2 | C000#MwgC00C2
5207 | 5207 | 5207 | 5207 | SA24M005 | Earthing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Construction & Installation Works 80 MVAR Line Reactor- Installation Works Earthing | 3 | 00LR | C000 | 00C3 | C000#MwgC00C3
5208 | 5208 | 5208 | 5208 | SA24M005 | Checking of tightness and leaks |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Construction & Installation Works 80 MVAR Line Reactor- Installation Works Checking of tightness and leaks | 4 | 00LR | C000 | 00C4 | C000#MwgC00C4
5209 | 5209 | 5209 | 5209 | SA24M005 | Vacuuming |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Construction & Installation Works 80 MVAR Line Reactor- Installation Works Vacuuming | 5 | 00LR | C000 | 00C5 | C000#MwgC00C5
5210 | 5210 | 5210 | 5210 | SA24M005 | Oil Filtration of Reactor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Construction & Installation Works 80 MVAR Line Reactor- Installation Works Oil Filtration of Reactor | 6 | 00LR | C000 | 00C6 | C000#MwgC00C6
5211 | 5211 | 5211 | 5211 | SA24M005 | Oil Test Report of Reactor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Construction & Installation Works 80 MVAR Line Reactor- Installation Works Oil Test Report of Reactor | 7 | 00LR | C000 | 00C7 | C000#MwgC00C7
5212 | 5212 | 5212 | 5212 | SA24M005 | Power/Control cable laying to Reactor MB box |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Construction & Installation Works 80 MVAR Line Reactor- Installation Works Power/Control cable laying to Reactor MB box | 8 | 00LR | C000 | 00C8 | C000#MwgC00C8
5213 | 5213 | 5213 | 5213 | SA24M005 | Power/Control cable termination to Reactor MB box |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Construction & Installation Works 80 MVAR Line Reactor- Installation Works Power/Control cable termination to Reactor MB box | 9 | 00LR | C000 | 00C9 | C000#MwgC00C9
5214 | 5214 | 5214 | 5214 | SA24M005 | IPS tube / Conductor connection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Construction & Installation Works 80 MVAR Line Reactor- Installation Works IPS tube / Conductor connection | 10 | 00LR | C000 | 0C10 | C000#MwgC0C10
5215 | 5215 | 5215 | 5215 | SA24M005 | Cabling & Termination |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Construction & Installation Works 80 MVAR Line Reactor- Installation Works Cabling & Termination | 11 | 00LR | C000 | 0C11 | C000#MwgC0C11
5216 | 5216 | 5216 | 5216 | SA24M005 | Other Misc. Works |  | 5 | -1 | 0 |  |  | X | C000#MwgC
5217 | 5217 | 5217 | 5217 | SA24M005 | Auxiliary Power Reinforcement Works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Construction & Installation Works Other Misc. Works Auxiliary Power Reinforcement Works | 1 | OAUXW | C000 | 00C1 | C000OAUXW00C1
5218 | 5218 | 5218 | 5218 | SA24M005 | Protection Modification works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Construction & Installation Works Other Misc. Works Protection Modification works | 2 | OAUXW | C000 | 00C2 | C000OAUXW00C2
5219 | 5219 | 5219 | 5219 | SA24M005 | TeleCommunication Modification Works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Construction & Installation Works Other Misc. Works TeleCommunication Modification Works | 3 | OAUXW | C000 | 00C3 | C000OAUXW00C3
5220 | 5220 | 5220 | 5220 | SA24M005 | SAS/SCADA Integration Works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Construction & Installation Works Other Misc. Works SAS/SCADA Integration Works | 4 | OAUXW | C000 | 00C4 | C000OAUXW00C4
5221 | 5221 | 5221 | 5221 | SA24M005 | Testing & Commissioning |  | 4 | -1 | 0 |  |  | X
5222 | 5222 | 5222 | 5222 | SA24M005 | Prechecks |  | 5 | -1 | 0 |  |  | X
5223 | 5223 | 5223 | 5223 | SA24M005 | Remote Extra High Voltage Switchgear(380kV Hybird GIS) |  | 6 | -1 | 0 |  |  | X
5224 | 5224 | 5224 | 5224 | SA24M005 | Auxiliary Relay Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote Extra High Voltage Switchgear(380kV Hybird GIS) Auxiliary Relay Test | 1 | 0ARSW | E000 | 00E1 | E0000ARSW00E1
5225 | 5225 | 5225 | 5225 | SA24M005 | MCB And MCCB Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote Extra High Voltage Switchgear(380kV Hybird GIS) MCB And MCCB Test | 2 | 0ARSW | E000 | 00E2 | E0000ARSW00E2
5226 | 5226 | 5226 | 5226 | SA24M005 | Meter Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote Extra High Voltage Switchgear(380kV Hybird GIS) Meter Test | 3 | 0ARSW | E000 | 00E3 | E0000ARSW00E3
5227 | 5227 | 5227 | 5227 | SA24M005 | Annunciator |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote Extra High Voltage Switchgear(380kV Hybird GIS) Annunciator | 4 | 0ARSW | E000 | 00E4 | E0000ARSW00E4
5228 | 5228 | 5228 | 5228 | SA24M005 | Calibration of SF6 Density Gauge and its Pressure Switch |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote Extra High Voltage Switchgear(380kV Hybird GIS) Calibration of SF6 Density Gauge and its Pressure Switch | 5 | 0ARSW | E000 | 00E5 | E0000ARSW00E5
5229 | 5229 | 5229 | 5229 | SA24M005 | SF6 Gas Purity and Dew Point |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote Extra High Voltage Switchgear(380kV Hybird GIS) SF6 Gas Purity and Dew Point | 6 | 0ARSW | E000 | 00E6 | E0000ARSW00E6
5230 | 5230 | 5230 | 5230 | SA24M005 | SF6 Gas Leakage Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote Extra High Voltage Switchgear(380kV Hybird GIS) SF6 Gas Leakage Test | 7 | 0ARSW | E000 | 00E7 | E0000ARSW00E7
5231 | 5231 | 5231 | 5231 | SA24M005 | Contact Resistance test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote Extra High Voltage Switchgear(380kV Hybird GIS) Contact Resistance test | 8 | 0ARSW | E000 | 00E8 | E0000ARSW00E8
5232 | 5232 | 5232 | 5232 | SA24M005 | CB Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote Extra High Voltage Switchgear(380kV Hybird GIS) CB Test | 9 | 0ARSW | E000 | 00E9 | E0000ARSW00E9
5233 | 5233 | 5233 | 5233 | SA24M005 | ES & DS Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote Extra High Voltage Switchgear(380kV Hybird GIS) ES & DS Test | 10 | 0ARSW | E000 | 0E10 | E0000ARSW0E10
5234 | 5234 | 5234 | 5234 | SA24M005 | ES 10KV TEST |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote Extra High Voltage Switchgear(380kV Hybird GIS) ES 10KV TEST | 11 | 0ARSW | E000 | 0E11 | E0000ARSW0E11
5235 | 5235 | 5235 | 5235 | SA24M005 | CT Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote Extra High Voltage Switchgear(380kV Hybird GIS) CT Test | 12 | 0ARSW | E000 | 0E12 | E0000ARSW0E12
5236 | 5236 | 5236 | 5236 | SA24M005 | CT Secondary Circuit Injection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote Extra High Voltage Switchgear(380kV Hybird GIS) CT Secondary Circuit Injection | 13 | 0ARSW | E000 | 0E13 | E0000ARSW0E13
5237 | 5237 | 5237 | 5237 | SA24M005 | CT Loop Resistance and Single Earth Point |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote Extra High Voltage Switchgear(380kV Hybird GIS) CT Loop Resistance and Single Earth Point | 14 | 0ARSW | E000 | 0E14 | E0000ARSW0E14
5238 | 5238 | 5238 | 5238 | SA24M005 | Calibration of Partial Discharge Sensor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote Extra High Voltage Switchgear(380kV Hybird GIS) Calibration of Partial Discharge Sensor | 15 | 0ARSW | E000 | 0E15 | E0000ARSW0E15
5239 | 5239 | 5239 | 5239 | SA24M005 | Metrosil |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote Extra High Voltage Switchgear(380kV Hybird GIS) Metrosil | 16 | 0ARSW | E000 | 0E16 | E0000ARSW0E16
5240 | 5240 | 5240 | 5240 | SA24M005 | On-Line Partial Discharge Monitoring System |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote Extra High Voltage Switchgear(380kV Hybird GIS) On-Line Partial Discharge Monitoring System | 17 | 0ARSW | E000 | 0E17 | E0000ARSW0E17
5241 | 5241 | 5241 | 5241 | SA24M005 | EHV Synchronizing Scheme Check |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote Extra High Voltage Switchgear(380kV Hybird GIS) EHV Synchronizing Scheme Check | 18 | 0ARSW | E000 | 0E18 | E0000ARSW0E18
5242 | 5242 | 5242 | 5242 | SA24M005 | LCC Scheme Check |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote Extra High Voltage Switchgear(380kV Hybird GIS) LCC Scheme Check | 19 | 0ARSW | E000 | 0E19 | E0000ARSW0E19
5243 | 5243 | 5243 | 5243 | SA24M005 | Remote Stand Alone Surge Arrester |  | 6 | -1 | 0 |  |  | X
5244 | 5244 | 5244 | 5244 | SA24M005 | EHV Stand Alone Surge Arrester |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote Stand Alone Surge Arrester EHV Stand Alone Surge Arrester | 1 | PRECSA | E000 | 00E1 | E000PRECSA00E1
5245 | 5245 | 5245 | 5245 | SA24M005 | Remote Stand Alone Current Transformer |  | 6 | -1 | 0 |  |  | X | E000PRECSA
5246 | 5246 | 5246 | 5246 | SA24M005 | EHV Stand Alone CT |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote Stand Alone Current Transformer EHV Stand Alone CT | 1 | PREC0CTRM | E000 | 00E1 | E000PREC0CTRM00E1
5247 | 5247 | 5247 | 5247 | SA24M005 | EHV Stand Alone CT Secondary Circuit Injection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote Stand Alone Current Transformer EHV Stand Alone CT Secondary Circuit Injection | 2 | PREC0CTRM | E000 | 00E2 | E000PREC0CTRM00E2
5248 | 5248 | 5248 | 5248 | SA24M005 | EHV Stand Alone CT Loop Resistance and Single Earth Point |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote Stand Alone Current Transformer EHV Stand Alone CT Loop Resistance and Single Earth Point | 3 | PREC0CTRM | E000 | 00E3 | E000PREC0CTRM00E3
5249 | 5249 | 5249 | 5249 | SA24M005 | EHV Stand Alone CT Primary Injection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote Stand Alone Current Transformer EHV Stand Alone CT Primary Injection | 4 | PREC0CTRM | E000 | 00E4 | E000PREC0CTRM00E4
5250 | 5250 | 5250 | 5250 | SA24M005 | Remote Scheme Check for Protection Panels |  | 6 | -1 | 0 |  |  | X
5251 | 5251 | 5251 | 5251 | SA24M005 | EHV Line Protection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote Scheme Check for Protection Panels EHV Line Protection | 1 | PREC0E0PLP | E000 | 00E1 | E000PREC0E0PLP00E1
5252 | 5252 | 5252 | 5252 | SA24M005 | EHV Auto Recloser Panel |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote Scheme Check for Protection Panels EHV Auto Recloser Panel | 2 | PREC0E0PLP | E000 | 00E2 | E000PREC0E0PLP00E2
5253 | 5253 | 5253 | 5253 | SA24M005 | EHV Shunt Reactor Protection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote Scheme Check for Protection Panels EHV Shunt Reactor Protection | 3 | PREC0E0PLP | E000 | 00E3 | E000PREC0E0PLP00E3
5254 | 5254 | 5254 | 5254 | SA24M005 | EHV Pole Discrepancy |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote Scheme Check for Protection Panels EHV Pole Discrepancy | 4 | PREC0E0PLP | E000 | 00E4 | E000PREC0E0PLP00E4
5255 | 5255 | 5255 | 5255 | SA24M005 | EHV Trip Circuit Supervision |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote Scheme Check for Protection Panels EHV Trip Circuit Supervision | 5 | PREC0E0PLP | E000 | 00E5 | E000PREC0E0PLP00E5
5256 | 5256 | 5256 | 5256 | SA24M005 | Transient Fault Recorder TFR Panel |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote Scheme Check for Protection Panels Transient Fault Recorder TFR Panel | 6 | PREC0E0PLP | E000 | 00E6 | E000PREC0E0PLP00E6
5257 | 5257 | 5257 | 5257 | SA24M005 | EHV On Line Partial Discharge Monitoring System |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote Scheme Check for Protection Panels EHV On Line Partial Discharge Monitoring System | 7 | PREC0E0PLP | E000 | 00E7 | E000PREC0E0PLP00E7
5258 | 5258 | 5258 | 5258 | SA24M005 | Remote EHV Line Protection Relay |  | 6 | -1 | 0 |  |  | X
5259 | 5259 | 5259 | 5259 | SA24M005 | Main 1 Multifunction Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote EHV Line Protection Relay Main 1 Multifunction Relay Acceptance Test | 1 | PREC0E0PR | E000 | 00E1 | E000PREC0E0PR00E1
5260 | 5260 | 5260 | 5260 | SA24M005 | Main 2 Multifunction Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote EHV Line Protection Relay Main 2 Multifunction Relay Acceptance Test | 2 | PREC0E0PR | E000 | 00E2 | E000PREC0E0PR00E2
5261 | 5261 | 5261 | 5261 | SA24M005 | Undervoltage and Overvoltage Relay Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote EHV Line Protection Relay Undervoltage and Overvoltage Relay Test | 3 | PREC0E0PR | E000 | 00E3 | E000PREC0E0PR00E3
5262 | 5262 | 5262 | 5262 | SA24M005 | Automatic Recloser |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote EHV Line Protection Relay Automatic Recloser | 4 | PREC0E0PR | E000 | 00E4 | E000PREC0E0PR00E4
5263 | 5263 | 5263 | 5263 | SA24M005 | Remote EHV Shunt Reactor Protection |  | 6 | -1 | 0 |  |  | X
5264 | 5264 | 5264 | 5264 | SA24M005 | Set 1 Differential Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote EHV Shunt Reactor Protection Set 1 Differential Relay Acceptance Test | 1 | 0E0SR | E000 | 00E1 | E0000E0SR00E1
5265 | 5265 | 5265 | 5265 | SA24M005 | Set 2 Differential Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote EHV Shunt Reactor Protection Set 2 Differential Relay Acceptance Test | 2 | 0E0SR | E000 | 00E2 | E0000E0SR00E2
5266 | 5266 | 5266 | 5266 | SA24M005 | Overcurrent And Earth Fault Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote EHV Shunt Reactor Protection Overcurrent And Earth Fault Relay Acceptance Test | 3 | 0E0SR | E000 | 00E3 | E0000E0SR00E3
5267 | 5267 | 5267 | 5267 | SA24M005 | Under voltage and Over voltage relay |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote EHV Shunt Reactor Protection Under voltage and Over voltage relay | 4 | 0E0SR | E000 | 00E4 | E0000E0SR00E4
5268 | 5268 | 5268 | 5268 | SA24M005 | Set 1 CT Supervision Relay Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote EHV Shunt Reactor Protection Set 1 CT Supervision Relay Test | 5 | 0E0SR | E000 | 00E5 | E0000E0SR00E5
5269 | 5269 | 5269 | 5269 | SA24M005 | Set 2 CT Supervision Relay Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote EHV Shunt Reactor Protection Set 2 CT Supervision Relay Test | 6 | 0E0SR | E000 | 00E6 | E0000E0SR00E6
5270 | 5270 | 5270 | 5270 | SA24M005 | Remote EHV STUB Protection |  | 6 | -1 | 0 |  |  | X
5271 | 5271 | 5271 | 5271 | SA24M005 | Set 1 Stub Protection Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote EHV STUB Protection Set 1 Stub Protection Relay Acceptance Test | 1 | PREC0E0SRP | E000 | 00E1 | E000PREC0E0SRP00E1
5272 | 5272 | 5272 | 5272 | SA24M005 | Set 1 Stub Protection Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote EHV STUB Protection Set 1 Stub Protection Relay Acceptance Test | 2 | PREC0E0SRP | E000 | 00E2 | E000PREC0E0SRP00E2
5273 | 5273 | 5273 | 5273 | SA24M005 | Remote Auxiliary/Trip Relay In Control And Protection Panels |  | 6 | -1 | 0 |  |  | X
5274 | 5274 | 5274 | 5274 | SA24M005 | Auxiliary Relays Test In Control Room Panels |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote Auxiliary/Trip Relay In Control And Protection Panels Auxiliary Relays Test In Control Room Panels | 1 | 0ARTR | E000 | 00E1 | E0000ARTR00E1
5275 | 5275 | 5275 | 5275 | SA24M005 | Trip Relays Test In Control Room Panels |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote Auxiliary/Trip Relay In Control And Protection Panels Trip Relays Test In Control Room Panels | 2 | 0ARTR | E000 | 00E2 | E0000ARTR00E2
5276 | 5276 | 5276 | 5276 | SA24M005 | Remote MCB In Control And Protection Panels |  | 6 | -1 | 0 |  |  | X
5277 | 5277 | 5277 | 5277 | SA24M005 | MCB Test In Control And Protection Panels |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote MCB In Control And Protection Panels MCB Test In Control And Protection Panels | 1 | 0MCB | E000 | 00E1 | E000#rBLy00E1
5278 | 5278 | 5278 | 5278 | SA24M005 | Remote Operation Interlocking |  | 6 | -1 | 0 |  |  | X | E000#rBLy
5279 | 5279 | 5279 | 5279 | SA24M005 | Operation and Interlocking Test for EHV GIS |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Prechecks Remote Operation Interlocking Operation and Interlocking Test for EHV GIS | 1 | **Prechecks for Remote Operation Interlocking Operation and Interlocking Test for EHV GIS** **00E0GIS** | E000 | 00E1 | E000#jkoi00E1
5280 | 5280 | 5280 | 5280 | SA24M005 | Commissioning |  | 5 | -1 | 0 |  |  | X | E000#jkoi
5281 | 5281 | 5281 | 5281 | SA24M005 | Remote Extra High Voltage Switchgear(380kV Hybird GIS) |  | 6 | -1 | 0 |  |  | X | E000#jkoi
5282 | 5282 | 5282 | 5282 | SA24M005 | Auxiliary Relay Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote Extra High Voltage Switchgear(380kV Hybird GIS) Auxiliary Relay Test | 1 | CREHVSW | E000 | 00E1 | E000CREHVSW00E1
5283 | 5283 | 5283 | 5283 | SA24M005 | MCB And MCCB Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote Extra High Voltage Switchgear(380kV Hybird GIS) MCB And MCCB Test | 2 | CREHVSW | E000 | 00E2 | E000CREHVSW00E2
5284 | 5284 | 5284 | 5284 | SA24M005 | Meter Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote Extra High Voltage Switchgear(380kV Hybird GIS) Meter Test | 3 | CREHVSW | E000 | 00E3 | E000CREHVSW00E3
5285 | 5285 | 5285 | 5285 | SA24M005 | Annunciator |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote Extra High Voltage Switchgear(380kV Hybird GIS) Annunciator | 4 | CREHVSW | E000 | 00E4 | E000CREHVSW00E4
5286 | 5286 | 5286 | 5286 | SA24M005 | Calibration of SF6 Density Gauge and its Pressure Switch |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote Extra High Voltage Switchgear(380kV Hybird GIS) Calibration of SF6 Density Gauge and its Pressure Switch | 5 | CREHVSW | E000 | 00E5 | E000CREHVSW00E5
5287 | 5287 | 5287 | 5287 | SA24M005 | SF6 Gas Purity and Dew Point |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote Extra High Voltage Switchgear(380kV Hybird GIS) SF6 Gas Purity and Dew Point | 6 | CREHVSW | E000 | 00E6 | E000CREHVSW00E6
5288 | 5288 | 5288 | 5288 | SA24M005 | SF6 Gas Leakage Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote Extra High Voltage Switchgear(380kV Hybird GIS) SF6 Gas Leakage Test | 7 | CREHVSW | E000 | 00E7 | E000CREHVSW00E7
5289 | 5289 | 5289 | 5289 | SA24M005 | Contact Resistance test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote Extra High Voltage Switchgear(380kV Hybird GIS) Contact Resistance test | 8 | CREHVSW | E000 | 00E8 | E000CREHVSW00E8
5290 | 5290 | 5290 | 5290 | SA24M005 | CB Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote Extra High Voltage Switchgear(380kV Hybird GIS) CB Test | 9 | CREHVSW | E000 | 00E9 | E000CREHVSW00E9
5291 | 5291 | 5291 | 5291 | SA24M005 | ES & DS Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote Extra High Voltage Switchgear(380kV Hybird GIS) ES & DS Test | 10 | CREHVSW | E000 | 0E10 | E000CREHVSW0E10
5292 | 5292 | 5292 | 5292 | SA24M005 | ES 10KV TEST |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote Extra High Voltage Switchgear(380kV Hybird GIS) ES 10KV TEST | 11 | CREHVSW | E000 | 0E11 | E000CREHVSW0E11
5293 | 5293 | 5293 | 5293 | SA24M005 | CT Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote Extra High Voltage Switchgear(380kV Hybird GIS) CT Test | 12 | CREHVSW | E000 | 0E12 | E000CREHVSW0E12
5294 | 5294 | 5294 | 5294 | SA24M005 | CT Secondary Circuit Injection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote Extra High Voltage Switchgear(380kV Hybird GIS) CT Secondary Circuit Injection | 13 | CREHVSW | E000 | 0E13 | E000CREHVSW0E13
5295 | 5295 | 5295 | 5295 | SA24M005 | CT Loop Resistance and Single Earth Point |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote Extra High Voltage Switchgear(380kV Hybird GIS) CT Loop Resistance and Single Earth Point | 14 | CREHVSW | E000 | 0E14 | E000CREHVSW0E14
5296 | 5296 | 5296 | 5296 | SA24M005 | Calibration of Partial Discharge Sensor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote Extra High Voltage Switchgear(380kV Hybird GIS) Calibration of Partial Discharge Sensor | 15 | CREHVSW | E000 | 0E15 | E000CREHVSW0E15
5297 | 5297 | 5297 | 5297 | SA24M005 | Metrosil |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote Extra High Voltage Switchgear(380kV Hybird GIS) Metrosil | 16 | CREHVSW | E000 | 0E16 | E000CREHVSW0E16
5298 | 5298 | 5298 | 5298 | SA24M005 | On-Line Partial Discharge Monitoring System |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote Extra High Voltage Switchgear(380kV Hybird GIS) On-Line Partial Discharge Monitoring System | 17 | CREHVSW | E000 | 0E17 | E000CREHVSW0E17
5299 | 5299 | 5299 | 5299 | SA24M005 | EHV Synchronizing Scheme Check |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote Extra High Voltage Switchgear(380kV Hybird GIS) EHV Synchronizing Scheme Check | 18 | CREHVSW | E000 | 0E18 | E000CREHVSW0E18
5300 | 5300 | 5300 | 5300 | SA24M005 | LCC Scheme Check |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote Extra High Voltage Switchgear(380kV Hybird GIS) LCC Scheme Check | 19 | CREHVSW | E000 | 0E19 | E000CREHVSW0E19
5301 | 5301 | 5301 | 5301 | SA24M005 | HV Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote Extra High Voltage Switchgear(380kV Hybird GIS) HV Test | 20 | CREHVSW | E000 | 0E20 | E000CREHVSW0E20
5302 | 5302 | 5302 | 5302 | SA24M005 | CT Primary Injection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote Extra High Voltage Switchgear(380kV Hybird GIS) CT Primary Injection | 21 | CREHVSW | E000 | 0E21 | E000CREHVSW0E21
5303 | 5303 | 5303 | 5303 | SA24M005 | Remote EHV Shunt Reactor |  | 6 | -1 | 0 |  |  | X
5304 | 5304 | 5304 | 5304 | SA24M005 | Visual Inspection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote EHV Shunt Reactor Visual Inspection | 1 | CRE0SR | M000 | 00M1 | M000CRE0SR00M1
5305 | 5305 | 5305 | 5305 | SA24M005 | Measurement of DC Insulation Resistance and check of Core Insulation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote EHV Shunt Reactor Measurement of DC Insulation Resistance and check of Core Insulation | 2 | CRE0SR | M000 | 00M2 | M000CRE0SR00M2
5306 | 5306 | 5306 | 5306 | SA24M005 | Measurement of Winding Resistance and Reactance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote EHV Shunt Reactor Measurement of Winding Resistance and Reactance Test | 3 | CRE0SR | M000 | 00M3 | M000CRE0SR00M3
5307 | 5307 | 5307 | 5307 | SA24M005 | Short Circuit (%Z), Zero Sequence Impedance (Z0),No Load, Vector Group & Magnetic Balance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote EHV Shunt Reactor Short Circuit (%Z), Zero Sequence Impedance (Z0),No Load, Vector Group & Magnetic Balance | 4 | CRE0SR | M000 | 00M4 | M000CRE0SR00M4
5308 | 5308 | 5308 | 5308 | SA24M005 | Measurement of Dissipation Factor(Tan Delta) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote EHV Shunt Reactor Measurement of Dissipation Factor(Tan Delta) | 5 | CRE0SR | M000 | 00M5 | M000CRE0SR00M5
5309 | 5309 | 5309 | 5309 | SA24M005 | Mechanical Protection Devices Test And MK Function Checks |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote EHV Shunt Reactor Mechanical Protection Devices Test And MK Function Checks | 6 | CRE0SR | M000 | 00M6 | M000CRE0SR00M6
5310 | 5310 | 5310 | 5310 | SA24M005 | Calibration of Winding & Oil Temperature Gauges |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote EHV Shunt Reactor Calibration of Winding & Oil Temperature Gauges | 7 | CRE0SR | M000 | 00M7 | M000CRE0SR00M7
5311 | 5311 | 5311 | 5311 | SA24M005 | Oil Dielectric Breakdown |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote EHV Shunt Reactor Oil Dielectric Breakdown | 8 | CRE0SR | M000 | 00M8 | M000CRE0SR00M8
5312 | 5312 | 5312 | 5312 | SA24M005 | On-Line Gas Analyzer Devices |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote EHV Shunt Reactor On-Line Gas Analyzer Devices | 9 | CRE0SR | M000 | 00M9 | M000CRE0SR00M9
5313 | 5313 | 5313 | 5313 | SA24M005 | Fans Motors, Oil Pumps, MCCB's,MCB's, Aux Relays and Meters |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote EHV Shunt Reactor Fans Motors, Oil Pumps, MCCB's,MCB's, Aux Relays and Meters | 10 | CRE0SR | M000 | 0M10 | M000CRE0SR0M10
5314 | 5314 | 5314 | 5314 | SA24M005 | Bushing CT |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote EHV Shunt Reactor Bushing CT | 11 | CRE0SR | M000 | 0M11 | M000CRE0SR0M11
5315 | 5315 | 5315 | 5315 | SA24M005 | BCT Secondary Circuits, Loop Resistance and Burden |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote EHV Shunt Reactor BCT Secondary Circuits, Loop Resistance and Burden | 12 | CRE0SR | M000 | 0M12 | M000CRE0SR0M12
5316 | 5316 | 5316 | 5316 | SA24M005 | Oil Leak Test With Pressure |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote EHV Shunt Reactor Oil Leak Test With Pressure | 13 | CRE0SR | M000 | 0M13 | M000CRE0SR0M13
5317 | 5317 | 5317 | 5317 | SA24M005 | Measurement of Frequency Response (Frequency Response Analysis FRA) |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote EHV Shunt Reactor Measurement of Frequency Response (Frequency Response Analysis FRA) | 14 | CRE0SR | M000 | 0M14 | M000CRE0SR0M14
5318 | 5318 | 5318 | 5318 | SA24M005 | DGA Oil Sample At Third Party Lab |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote EHV Shunt Reactor DGA Oil Sample At Third Party Lab | 15 | CRE0SR | M000 | 0M15 | M000CRE0SR0M15
5319 | 5319 | 5319 | 5319 | SA24M005 | Remote Stand Alone Surge Arrester |  | 6 | -1 | 0 |  |  | X
5320 | 5320 | 5320 | 5320 | SA24M005 | EHV Stand Alone Surge Arrester |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote Stand Alone Surge Arrester EHV Stand Alone Surge Arrester | 1 | RSA0SRGA | M000 | 00M1 | M000RSA0SRGA00M1
5321 | 5321 | 5321 | 5321 | SA24M005 | Remote Stand Alone Current Transformer |  | 6 | -1 | 0 |  |  | X | M000RSA0SRGA
5322 | 5322 | 5322 | 5322 | SA24M005 | EHV Stand Alone CT |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote Stand Alone Current Transformer EHV Stand Alone CT | 1 | CRSTC | M000 | 00M1 | M000CRSTC00M1
5323 | 5323 | 5323 | 5323 | SA24M005 | EHV Stand Alone CT Secondary Circuit Injection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote Stand Alone Current Transformer EHV Stand Alone CT Secondary Circuit Injection | 2 | CRSTC | M000 | 00M2 | M000CRSTC00M2
5324 | 5324 | 5324 | 5324 | SA24M005 | EHV Stand Alone CT Loop Resistance and Single Earth Point |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote Stand Alone Current Transformer EHV Stand Alone CT Loop Resistance and Single Earth Point | 3 | CRSTC | M000 | 00M3 | M000CRSTC00M3
5325 | 5325 | 5325 | 5325 | SA24M005 | EHV Stand Alone CT Primary Injection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote Stand Alone Current Transformer EHV Stand Alone CT Primary Injection | 4 | CRSTC | M000 | 00M4 | M000CRSTC00M4
5326 | 5326 | 5326 | 5326 | SA24M005 | Remote Scheme Check for Protection Panels |  | 6 | -1 | 0 |  |  | X
5327 | 5327 | 5327 | 5327 | SA24M005 | EHV Line Protection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote Scheme Check for Protection Panels EHV Line Protection | 1 | CRSCP | M000 | 00M1 | M000CRSCP00M1
5328 | 5328 | 5328 | 5328 | SA24M005 | EHV Auto Recloser Panel |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote Scheme Check for Protection Panels EHV Auto Recloser Panel | 2 | CRSCP | M000 | 00M2 | M000CRSCP00M2
5329 | 5329 | 5329 | 5329 | SA24M005 | EHV Shunt Reactor Protection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote Scheme Check for Protection Panels EHV Shunt Reactor Protection | 3 | CRSCP | M000 | 00M3 | M000CRSCP00M3
5330 | 5330 | 5330 | 5330 | SA24M005 | EHV Pole Discrepancy |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote Scheme Check for Protection Panels EHV Pole Discrepancy | 4 | CRSCP | M000 | 00M4 | M000CRSCP00M4
5331 | 5331 | 5331 | 5331 | SA24M005 | EHV Trip Circuit Supervision |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote Scheme Check for Protection Panels EHV Trip Circuit Supervision | 5 | CRSCP | M000 | 00M5 | M000CRSCP00M5
5332 | 5332 | 5332 | 5332 | SA24M005 | Transient Fault Recorder TFR Panel |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote Scheme Check for Protection Panels Transient Fault Recorder TFR Panel | 6 | CRSCP | M000 | 00M6 | M000CRSCP00M6
5333 | 5333 | 5333 | 5333 | SA24M005 | EHV On Line Partial Discharge Monitoring System |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote Scheme Check for Protection Panels EHV On Line Partial Discharge Monitoring System | 7 | CRSCP | M000 | 00M7 | M000CRSCP00M7
5334 | 5334 | 5334 | 5334 | SA24M005 | DSM PANEL TESTING |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote Scheme Check for Protection Panels DSM PANEL TESTING | 8 | CRSCP | M000 | 00M8 | M000CRSCP00M8
5335 | 5335 | 5335 | 5335 | SA24M005 | Energy Meter Panel Scheme Check |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote Scheme Check for Protection Panels Energy Meter Panel Scheme Check | 9 | CRSCP | M000 | 00M9 | M000CRSCP00M9
5336 | 5336 | 5336 | 5336 | SA24M005 | Remote EHV Line Protection Relay |  | 6 | -1 | 0 |  |  | X
5337 | 5337 | 5337 | 5337 | SA24M005 | Main 1 Multifunction Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote EHV Line Protection Relay Main 1 Multifunction Relay Acceptance Test | 1 | CRE00MFR | E000 | 00E1 | E000CRE00MFR00E1
5338 | 5338 | 5338 | 5338 | SA24M005 | Main 1 Multifunction Relay Final setting Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote EHV Line Protection Relay Main 1 Multifunction Relay Final setting Test | 2 | CRE00MFR | E000 | 00E2 | E000CRE00MFR00E2
5339 | 5339 | 5339 | 5339 | SA24M005 | Main 2 Multifunction Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote EHV Line Protection Relay Main 2 Multifunction Relay Acceptance Test | 3 | CRE00MFR | E000 | 00E3 | E000CRE00MFR00E3
5340 | 5340 | 5340 | 5340 | SA24M005 | Main 2 Multifunction Relay Final setting Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote EHV Line Protection Relay Main 2 Multifunction Relay Final setting Test | 4 | CRE00MFR | E000 | 00E4 | E000CRE00MFR00E4
5341 | 5341 | 5341 | 5341 | SA24M005 | Undervoltage and Overvoltage Relay Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote EHV Line Protection Relay Undervoltage and Overvoltage Relay Test | 5 | CRE00MFR | E000 | 00E5 | E000CRE00MFR00E5
5342 | 5342 | 5342 | 5342 | SA24M005 | Automatic Recloser |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote EHV Line Protection Relay Automatic Recloser | 6 | CRE00MFR | E000 | 00E6 | E000CRE00MFR00E6
5343 | 5343 | 5343 | 5343 | SA24M005 | Remote EHV Shunt Reactor Protection |  | 6 | -1 | 0 |  |  | X
5344 | 5344 | 5344 | 5344 | SA24M005 | Set 1 Differential Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote EHV Shunt Reactor Protection Set 1 Differential Relay Acceptance Test | 1 | CRE0SR | E000 | 00E1 | E000CRE0SR00E1
5345 | 5345 | 5345 | 5345 | SA24M005 | Set 1 Differential Relay Final Setting Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote EHV Shunt Reactor Protection Set 1 Differential Relay Final Setting Test | 2 | CRE0SR | E000 | 00E2 | E000CRE0SR00E2
5346 | 5346 | 5346 | 5346 | SA24M005 | Set 2 Differential Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote EHV Shunt Reactor Protection Set 2 Differential Relay Acceptance Test | 3 | CRE0SR | E000 | 00E3 | E000CRE0SR00E3
5347 | 5347 | 5347 | 5347 | SA24M005 | Set 2 Differential Relay Final setting Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote EHV Shunt Reactor Protection Set 2 Differential Relay Final setting Test | 4 | CRE0SR | E000 | 00E4 | E000CRE0SR00E4
5348 | 5348 | 5348 | 5348 | SA24M005 | Overcurrent And Earth Fault Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote EHV Shunt Reactor Protection Overcurrent And Earth Fault Relay Acceptance Test | 5 | CRE0SR | E000 | 00E5 | E000CRE0SR00E5
5349 | 5349 | 5349 | 5349 | SA24M005 | Overcurrent And Earth Fault Relay Final Setting Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote EHV Shunt Reactor Protection Overcurrent And Earth Fault Relay Final Setting Test | 6 | CRE0SR | E000 | 00E6 | E000CRE0SR00E6
5350 | 5350 | 5350 | 5350 | SA24M005 | Under voltage and Over voltage relay |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote EHV Shunt Reactor Protection Under voltage and Over voltage relay | 7 | CRE0SR | E000 | 00E7 | E000CRE0SR00E7
5351 | 5351 | 5351 | 5351 | SA24M005 | Set 1 CT Supervision Relay Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote EHV Shunt Reactor Protection Set 1 CT Supervision Relay Test | 8 | CRE0SR | E000 | 00E8 | E000CRE0SR00E8
5352 | 5352 | 5352 | 5352 | SA24M005 | Set 2 CT Supervision Relay Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote EHV Shunt Reactor Protection Set 2 CT Supervision Relay Test | 9 | CRE0SR | E000 | 00E9 | E000CRE0SR00E9
5353 | 5353 | 5353 | 5353 | SA24M005 | Remote EHV STUB Protection |  | 6 | -1 | 0 |  |  | X
5354 | 5354 | 5354 | 5354 | SA24M005 | Set 1 Stub Protection Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote EHV STUB Protection Set 1 Stub Protection Relay Acceptance Test | 1 | CRE0SRP | M000 | 00M1 | M000CRE0SRP00M1
5355 | 5355 | 5355 | 5355 | SA24M005 | Set 1 Stub Protection Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote EHV STUB Protection Set 1 Stub Protection Relay Acceptance Test | 2 | CRE0SRP | M000 | 00M2 | M000CRE0SRP00M2
5356 | 5356 | 5356 | 5356 | SA24M005 | Set 1 Stub Protection Relay Final Setting Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote EHV STUB Protection Set 1 Stub Protection Relay Final Setting Test | 3 | CRE0SRP | M000 | 00M3 | M000CRE0SRP00M3
5357 | 5357 | 5357 | 5357 | SA24M005 | Set 2 Stub Protection Relay Final Setting Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote EHV STUB Protection Set 2 Stub Protection Relay Final Setting Test | 4 | CRE0SRP | M000 | 00M4 | M000CRE0SRP00M4
5358 | 5358 | 5358 | 5358 | SA24M005 | Remote Stability Test |  | 6 | -1 | 0 |  |  | X
5359 | 5359 | 5359 | 5359 | SA24M005 | EHV TEE Differential Protection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote Stability Test EHV TEE Differential Protection | 1 | CRSTB | M000 | 00M1 | M000CRSTB00M1
5360 | 5360 | 5360 | 5360 | SA24M005 | EHV Shunt Reactor Differential/REF |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote Stability Test EHV Shunt Reactor Differential/REF | 2 | CRSTB | M000 | 00M2 | M000CRSTB00M2
5361 | 5361 | 5361 | 5361 | SA24M005 | Remote Auxiliary/Trip Relay In Control And Protection Panels |  | 6 | -1 | 0 |  |  | X
5362 | 5362 | 5362 | 5362 | SA24M005 | Auxiliary Relays Test In Control Room Panels |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote Auxiliary/Trip Relay In Control And Protection Panels Auxiliary Relays Test In Control Room Panels | 1 | CR0ATR | E000 | 00E1 | E000CR0ATR00E1
5363 | 5363 | 5363 | 5363 | SA24M005 | Trip Relays Test In Control Room Panels |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote Auxiliary/Trip Relay In Control And Protection Panels Trip Relays Test In Control Room Panels | 2 | CR0ATR | E000 | 00E2 | E000CR0ATR00E2
5364 | 5364 | 5364 | 5364 | SA24M005 | Remote MCB In Control And Protection Panels |  | 6 | -1 | 0 |  |  | X
5365 | 5365 | 5365 | 5365 | SA24M005 | MCB Test In Control And Protection Panels |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote MCB In Control And Protection Panels MCB Test In Control And Protection Panels | 1 | CRM0CB | E000 | 00E1 | E000CRM0CB00E1
5366 | 5366 | 5366 | 5366 | SA24M005 | Remote Operation Interlocking |  | 6 | -1 | 0 |  |  | X | E000CRM0CB
5367 | 5367 | 5367 | 5367 | SA24M005 | Operation and Interlocking Test for EHV GIS |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote Operation Interlocking Operation and Interlocking Test for EHV GIS | 1 | **00E0GIS | E000 | 00E1 | E000**00E0GIS00E1
5368 | 5368 | 5368 | 5368 | SA24M005 | Remote SAS Function Test |  | 6 | -1 | 0 |  |  | X | E000**00E0GIS
5369 | 5369 | 5369 | 5369 | SA24M005 | Alarm And Indication Check Up To SAS HMI And Gateway For EHV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote SAS Function Test Alarm And Indication Check Up To SAS HMI And Gateway For EHV | 1 | CRSAS | C000 | 00C1 | C000CRSAS00C1
5370 | 5370 | 5370 | 5370 | SA24M005 | Alarm And Imdication Check Up to SAS HMI And Gateway for Common Alarm |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote SAS Function Test Alarm And Imdication Check Up to SAS HMI And Gateway for Common Alarm | 2 | CRSAS | C000 | 00C2 | C000CRSAS00C2
5371 | 5371 | 5371 | 5371 | SA24M005 | EHV Closed Loop test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote SAS Function Test EHV Closed Loop test | 3 | CRSAS | C000 | 00C3 | C000CRSAS00C3
5372 | 5372 | 5372 | 5372 | SA24M005 | Closed loop Test for Common Alarm |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote SAS Function Test Closed loop Test for Common Alarm | 4 | CRSAS | C000 | 00C4 | C000CRSAS00C4
5373 | 5373 | 5373 | 5373 | SA24M005 | Operation and Interlocking Test for EHV Switchgear |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote SAS Function Test Operation and Interlocking Test for EHV Switchgear | 5 | CRSAS | C000 | 00C5 | C000CRSAS00C5
5374 | 5374 | 5374 | 5374 | SA24M005 | Remote End to End Test |  | 6 | -1 | 0 |  |  | X
5375 | 5375 | 5375 | 5375 | SA24M005 | EHV Line Feeder Set 1 Multifunction Relay |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote End to End Test EHV Line Feeder Set 1 Multifunction Relay | 1 | CRE0E | M000 | 00M1 | M000CRE0E00M1
5376 | 5376 | 5376 | 5376 | SA24M005 | EHV Line Feeder Set 2 Multifunction Relay |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote End to End Test EHV Line Feeder Set 2 Multifunction Relay | 2 | CRE0E | M000 | 00M2 | M000CRE0E00M2
5377 | 5377 | 5377 | 5377 | SA24M005 | HV Line Feeder Set 1 Multifunction Relay |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote End to End Test HV Line Feeder Set 1 Multifunction Relay | 3 | CRE0E | M000 | 00M3 | M000CRE0E00M3
5378 | 5378 | 5378 | 5378 | SA24M005 | HV Line Feeder Set 2 Multifunction Relay |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote End to End Test HV Line Feeder Set 2 Multifunction Relay | 4 | CRE0E | M000 | 00M4 | M000CRE0E00M4
5379 | 5379 | 5379 | 5379 | SA24M005 | Remote Final Trip Test |  | 6 | -1 | 0 |  |  | X
5380 | 5380 | 5380 | 5380 | SA24M005 | Final Trip Test for EHV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote Final Trip Test Final Trip Test for EHV | 1 | 0FRTT | M000 | 00M1 | M0000FRTT00M1
5381 | 5381 | 5381 | 5381 | SA24M005 | Remote Relay Final Setting Review |  | 6 | -1 | 0 |  |  | X | M0000FRTT
5382 | 5382 | 5382 | 5382 | SA24M005 | Relay Final settings Review for EHV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-3 (9029 BSP) Testing & Commissioning Commissioning Remote Relay Final Setting Review Relay Final settings Review for EHV | 1 | CREFR | E000 | 00E1 | E000CREFR00E1
5383 | 5383 | 5383 | 5383 | SA24M005 | Remote End SS-4 (9064 BSP) |  | 3 | -1 | 0 |  |  | X | E000CREFR
5384 | 5384 | 5384 | 5384 | SA24M005 | Engineering & Design (Phasr VIII) |  | 4 | -1 | 0 |  |  | X | E000CREFR
5385 | 5385 | 5385 | 5385 | SA24M005 | Modified Single Line Drawing |  | 5 | -1 | 0 |  |  | X | E000CREFR
5386 | 5386 | 5386 | 5386 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Engineering & Design (Phasr VIII) Modified Single Line Drawing Drafting / Preparation | 1 | E0SLD | E000 | 00E1 | E000#HWGK00E1
5387 | 5387 | 5387 | 5387 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Engineering & Design (Phasr VIII) Modified Single Line Drawing Submission | 2 | E0SLD | E000 | 00E2 | E000#HWGK00E2
5388 | 5388 | 5388 | 5388 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Engineering & Design (Phasr VIII) Modified Single Line Drawing Review / Evaluation | 3 | E0SLD | E000 | 00E3 | E000#HWGK00E3
5389 | 5389 | 5389 | 5389 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Engineering & Design (Phasr VIII) Modified Single Line Drawing Approval with Comments | 4 | E0SLD | E000 | 00E4 | E000#HWGK00E4
5390 | 5390 | 5390 | 5390 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Engineering & Design (Phasr VIII) Modified Single Line Drawing FINAL Approval | 5 | E0SLD | E000 | 00E5 | E000#HWGK00E5
5391 | 5391 | 5391 | 5391 | SA24M005 | Modified Overall Layout |  | 5 | -1 | 0 |  |  | X | E000#HWGK
5392 | 5392 | 5392 | 5392 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Engineering & Design (Phasr VIII) Modified Overall Layout Drafting / Preparation | 1 | EQ0L | E000 | 00E1 | E000#qcKv00E1
5393 | 5393 | 5393 | 5393 | SA24M005 | Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Engineering & Design (Phasr VIII) Modified Overall Layout Submission | 2 | EQ0L | E000 | 00E2 | E000#qcKv00E2
5394 | 5394 | 5394 | 5394 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Engineering & Design (Phasr VIII) Modified Overall Layout Review / Evaluation | 3 | EQ0L | E000 | 00E3 | E000#qcKv00E3
5395 | 5395 | 5395 | 5395 | SA24M005 | Approval with Comments |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Engineering & Design (Phasr VIII) Modified Overall Layout Approval with Comments | 4 | EQ0L | E000 | 00E4 | E000#qcKv00E4
5396 | 5396 | 5396 | 5396 | SA24M005 | FINAL Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Engineering & Design (Phasr VIII) Modified Overall Layout FINAL Approval | 5 | EQ0L | E000 | 00E5 | E000#qcKv00E5
5397 | 5397 | 5397 | 5397 | SA24M005 | Material Procurement |  | 4 | -1 | 0 |  |  | X | E000#qcKv
5398 | 5398 | 5398 | 5398 | SA24M005 | Auxiliary Power Supply Reinforcement items |  | 5 | -1 | 0 |  |  | X | E000#qcKv
5399 | 5399 | 5399 | 5399 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Material Procurement Auxiliary Power Supply Reinforcement items Purchase Request to SCM | 1 | 0APSR | P000 | 00P1 | P000#zxrM00P1
5400 | 5400 | 5400 | 5400 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Material Procurement Auxiliary Power Supply Reinforcement items Issue of RFQ | 2 | 0APSR | P000 | 00P2 | P000#zxrM00P2
5401 | 5401 | 5401 | 5401 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Material Procurement Auxiliary Power Supply Reinforcement items Receipt of Technical offer from Vendor | 3 | 0APSR | P000 | 00P3 | P000#zxrM00P3
5402 | 5402 | 5402 | 5402 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Material Procurement Auxiliary Power Supply Reinforcement items Technical Evaluation by EDRC | 4 | 0APSR | P000 | 00P4 | P000#zxrM00P4
5403 | 5403 | 5403 | 5403 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Material Procurement Auxiliary Power Supply Reinforcement items Final technical compliance from Vendor | 5 | 0APSR | P000 | 00P5 | P000#zxrM00P5
5404 | 5404 | 5404 | 5404 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Material Procurement Auxiliary Power Supply Reinforcement items Technical clearance by EDRC | 6 | 0APSR | P000 | 00P6 | P000#zxrM00P6
5405 | 5405 | 5405 | 5405 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Material Procurement Auxiliary Power Supply Reinforcement items Commercial Evaluation by SCM | 7 | 0APSR | P000 | 00P7 | P000#zxrM00P7
5406 | 5406 | 5406 | 5406 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Material Procurement Auxiliary Power Supply Reinforcement items Vendor negotiation & Finalization | 8 | 0APSR | P000 | 00P8 | P000#zxrM00P8
5407 | 5407 | 5407 | 5407 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Material Procurement Auxiliary Power Supply Reinforcement items HPC Approval / PO release to vendor | 9 | 0APSR | P000 | 00P9 | P000#zxrM00P9
5408 | 5408 | 5408 | 5408 | SA24M005 | Protection Modification (SAS/SCADA integration/Telecommunication) |  | 5 | -1 | 0 |  |  | X | P000#zxrM
5409 | 5409 | 5409 | 5409 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Material Procurement Protection Modification (SAS/SCADA integration/Telecommunication) Purchase Request to SCM | 1 | PR0SCM | P000 | 00P1 | P000#AQAX00P1
5410 | 5410 | 5410 | 5410 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Material Procurement Protection Modification (SAS/SCADA integration/Telecommunication) Issue of RFQ | 2 | PR0SCM | P000 | 00P2 | P000#AQAX00P2
5411 | 5411 | 5411 | 5411 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Material Procurement Protection Modification (SAS/SCADA integration/Telecommunication) Receipt of Technical offer from Vendor | 3 | PR0SCM | P000 | 00P3 | P000#AQAX00P3
5412 | 5412 | 5412 | 5412 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Material Procurement Protection Modification (SAS/SCADA integration/Telecommunication) Technical Evaluation by EDRC | 4 | PR0SCM | P000 | 00P4 | P000#AQAX00P4
5413 | 5413 | 5413 | 5413 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Material Procurement Protection Modification (SAS/SCADA integration/Telecommunication) Final technical compliance from Vendor | 5 | PR0SCM | P000 | 00P5 | P000#AQAX00P5
5414 | 5414 | 5414 | 5414 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Material Procurement Protection Modification (SAS/SCADA integration/Telecommunication) Technical clearance by EDRC | 6 | PR0SCM | P000 | 00P6 | P000#AQAX00P6
5415 | 5415 | 5415 | 5415 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Material Procurement Protection Modification (SAS/SCADA integration/Telecommunication) Commercial Evaluation by SCM | 7 | PR0SCM | P000 | 00P7 | P000#AQAX00P7
5416 | 5416 | 5416 | 5416 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Material Procurement Protection Modification (SAS/SCADA integration/Telecommunication) Vendor negotiation & Finalization | 8 | PR0SCM | P000 | 00P8 | P000#AQAX00P8
5417 | 5417 | 5417 | 5417 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Material Procurement Protection Modification (SAS/SCADA integration/Telecommunication) HPC Approval / PO release to vendor | 9 | PR0SCM | P000 | 00P9 | P000#AQAX00P9
5418 | 5418 | 5418 | 5418 | SA24M005 | Inspection & Delivery |  | 4 | -1 | 0 |  |  | X | P000#AQAX
5419 | 5419 | 5419 | 5419 | SA24M005 | Auxiliary Power Supply Reinforcement items |  | 5 | -1 | 0 |  |  | X | P000#AQAX
5420 | 5420 | 5420 | 5420 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Inspection & Delivery Auxiliary Power Supply Reinforcement items MQP / ITP Submission | 1 | 0APSR | I000 | 00I1 | I000#NnVp00I1
5421 | 5421 | 5421 | 5421 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Inspection & Delivery Auxiliary Power Supply Reinforcement items MQP / ITP Approval | 2 | 0APSR | I000 | 00I2 | I000#NnVp00I2
5422 | 5422 | 5422 | 5422 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Inspection & Delivery Auxiliary Power Supply Reinforcement items Issuance of MFC | 3 | 0APSR | I000 | 00I3 | I000#NnVp00I3
5423 | 5423 | 5423 | 5423 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Inspection & Delivery Auxiliary Power Supply Reinforcement items Lead Time For Manufacturing | 4 | 0APSR | I000 | 00I4 | I000#NnVp00I4
5424 | 5424 | 5424 | 5424 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Inspection & Delivery Auxiliary Power Supply Reinforcement items Material readiness / Inspection call | 5 | 0APSR | I000 | 00I5 | I000#NnVp00I5
5425 | 5425 | 5425 | 5425 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Inspection & Delivery Auxiliary Power Supply Reinforcement items Inspection by client personal / Third Party | 6 | 0APSR | I000 | 00I6 | I000#NnVp00I6
5426 | 5426 | 5426 | 5426 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Inspection & Delivery Auxiliary Power Supply Reinforcement items Submission of FAT Compliance by Vendor | 7 | 0APSR | I000 | 00I7 | I000#NnVp00I7
5427 | 5427 | 5427 | 5427 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Inspection & Delivery Auxiliary Power Supply Reinforcement items Dispatch Clearance to vendor | 8 | 0APSR | I000 | 00I8 | I000#NnVp00I8
5428 | 5428 | 5428 | 5428 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Inspection & Delivery Auxiliary Power Supply Reinforcement items Transportation and Custom clearance | 9 | 0APSR | I000 | 00I9 | I000#NnVp00I9
5429 | 5429 | 5429 | 5429 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Inspection & Delivery Auxiliary Power Supply Reinforcement items Receipt at site | 10 | 0APSR | I000 | 0I10 | I000#NnVp0I10
5430 | 5430 | 5430 | 5430 | SA24M005 | Protection Modification (SAS/SCADA integration/Telecommunication) |  | 5 | -1 | 0 |  |  | X | I000#NnVp
5431 | 5431 | 5431 | 5431 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Inspection & Delivery Protection Modification (SAS/SCADA integration/Telecommunication) MQP / ITP Submission | 1 | 0PQM | I000 | 00I1 | I000#QErG00I1
5432 | 5432 | 5432 | 5432 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Inspection & Delivery Protection Modification (SAS/SCADA integration/Telecommunication) MQP / ITP Approval | 2 | 0PQM | I000 | 00I2 | I000#QErG00I2
5433 | 5433 | 5433 | 5433 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Inspection & Delivery Protection Modification (SAS/SCADA integration/Telecommunication) Issuance of MFC | 3 | 0PQM | I000 | 00I3 | I000#QErG00I3
5434 | 5434 | 5434 | 5434 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Inspection & Delivery Protection Modification (SAS/SCADA integration/Telecommunication) Lead Time For Manufacturing | 4 | 0PQM | I000 | 00I4 | I000#QErG00I4
5435 | 5435 | 5435 | 5435 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Inspection & Delivery Protection Modification (SAS/SCADA integration/Telecommunication) Material readiness / Inspection call | 5 | 0PQM | I000 | 00I5 | I000#QErG00I5
5436 | 5436 | 5436 | 5436 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Inspection & Delivery Protection Modification (SAS/SCADA integration/Telecommunication) Inspection by client personal / Third Party | 6 | 0PQM | I000 | 00I6 | I000#QErG00I6
5437 | 5437 | 5437 | 5437 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Inspection & Delivery Protection Modification (SAS/SCADA integration/Telecommunication) Submission of FAT Compliance by Vendor | 7 | 0PQM | I000 | 00I7 | I000#QErG00I7
5438 | 5438 | 5438 | 5438 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Inspection & Delivery Protection Modification (SAS/SCADA integration/Telecommunication) Dispatch Clearance to vendor | 8 | 0PQM | I000 | 00I8 | I000#QErG00I8
5439 | 5439 | 5439 | 5439 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Inspection & Delivery Protection Modification (SAS/SCADA integration/Telecommunication) Transportation and Custom clearance | 9 | 0PQM | I000 | 00I9 | I000#QErG00I9
5440 | 5440 | 5440 | 5440 | SA24M005 | Receipt at site |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Inspection & Delivery Protection Modification (SAS/SCADA integration/Telecommunication) Receipt at site | 10 | 0PQM | I000 | 0I10 | I000#QErG0I10
5441 | 5441 | 5441 | 5441 | SA24M005 | Construction & Installation Works |  | 4 | -1 | 0 |  |  | X | I000#QErG
5442 | 5442 | 5442 | 5442 | SA24M005 | Auxiliary Power Reinforcement Works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Construction & Installation Works Auxiliary Power Reinforcement Works | 1 | CAUXP | C000 | 00C1 | C000#nGDc00C1
5443 | 5443 | 5443 | 5443 | SA24M005 | Protection Modification works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Construction & Installation Works Protection Modification works | 2 | CAUXP | C000 | 00C2 | C000#nGDc00C2
5444 | 5444 | 5444 | 5444 | SA24M005 | TeleCommunication Modification Works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Construction & Installation Works TeleCommunication Modification Works | 3 | CAUXP | C000 | 00C3 | C000#nGDc00C3
5445 | 5445 | 5445 | 5445 | SA24M005 | SAS/SCADA Integration Works |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Construction & Installation Works SAS/SCADA Integration Works | 4 | CAUXP | C000 | 00C4 | C000#nGDc00C4
5446 | 5446 | 5446 | 5446 | SA24M005 | Testing & Commissioning |  | 4 | -1 | 0 |  |  | X | C000#nGDc
5447 | 5447 | 5447 | 5447 | SA24M005 | Prechecks |  | 5 | -1 | 0 |  |  | X | C000#nGDc
5448 | 5448 | 5448 | 5448 | SA24M005 | MCB Test In Control And Protection Panels |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Testing & Commissioning Prechecks MCB Test In Control And Protection Panels | 1 | PRECHECKMCB | E000 | 00E1 | E000PRECHECKMCB00E1
5449 | 5449 | 5449 | 5449 | SA24M005 | Auxiliary/Trip Relay Test In Control And Protection Panels |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Testing & Commissioning Prechecks Auxiliary/Trip Relay Test In Control And Protection Panels | 2 | PRECHECKMCB | E000 | 00E2 | E000PRECHECKMCB00E2
5450 | 5450 | 5450 | 5450 | SA24M005 | VT Secondary Circuit Injection & Loop Resistance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Testing & Commissioning Prechecks VT Secondary Circuit Injection & Loop Resistance | 3 | PRECHECKMCB | E000 | 00E3 | E000PRECHECKMCB00E3
5451 | 5451 | 5451 | 5451 | SA24M005 | CT Loop Resistance and Single Earth Point |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Testing & Commissioning Prechecks CT Loop Resistance and Single Earth Point | 4 | PRECHECKMCB | E000 | 00E4 | E000PRECHECKMCB00E4
5452 | 5452 | 5452 | 5452 | SA24M005 | Scheme Check For Line Protection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Testing & Commissioning Prechecks Scheme Check For Line Protection | 5 | PRECHECKMCB | E000 | 00E5 | E000PRECHECKMCB00E5
5453 | 5453 | 5453 | 5453 | SA24M005 | Set 1 Line Differential Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Testing & Commissioning Prechecks Set 1 Line Differential Relay Acceptance Test | 6 | PRECHECKMCB | E000 | 00E6 | E000PRECHECKMCB00E6
5454 | 5454 | 5454 | 5454 | SA24M005 | Set 2 Line Differential Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Testing & Commissioning Prechecks Set 2 Line Differential Relay Acceptance Test | 7 | PRECHECKMCB | E000 | 00E7 | E000PRECHECKMCB00E7
5455 | 5455 | 5455 | 5455 | SA24M005 | Commissioning |  | 5 | -1 | 0 |  |  | X
5456 | 5456 | 5456 | 5456 | SA24M005 | MCB Test In Control And Protection Panels |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Testing & Commissioning Commissioning MCB Test In Control And Protection Panels | 1 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCBs) in the control and protection panels. **Equipment:** * MCB tester * MCBs under test **Procedure:** 1. Set the MCB tester to the appropriate trip current. 2. Connect the MCB tester to the MCB under test. 3. Trip the MCB using the MCB tester. 4. Verify that the MCB trips within the specified time delay. 5. Reset the MCB and repeat the test for all MCBs under test. **Acceptance Criteria:** * All MCBs shall trip within the specified time delay. * All MCBs shall reset properly after tripping. | E000 | 00E1 | E00#bhui00E1
5457 | 5457 | 5457 | 5457 | SA24M005 | Auxiliary/Trip Relay Test In Control And Protection Panels |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Testing & Commissioning Commissioning Auxiliary/Trip Relay Test In Control And Protection Panels | 2 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCBs) in the control and protection panels. **Equipment:** * MCB tester * MCBs under test **Procedure:** 1. Set the MCB tester to the appropriate trip current. 2. Connect the MCB tester to the MCB under test. 3. Trip the MCB using the MCB tester. 4. Verify that the MCB trips within the specified time delay. 5. Reset the MCB and repeat the test for all MCBs under test. **Acceptance Criteria:** * All MCBs shall trip within the specified time delay. * All MCBs shall reset properly after tripping. | E000 | 00E2 | E00#bhui00E2
5458 | 5458 | 5458 | 5458 | SA24M005 | VT Secondary Circuit Injection & Loop Resistance |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Testing & Commissioning Commissioning VT Secondary Circuit Injection & Loop Resistance | 3 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCBs) in the control and protection panels. **Equipment:** * MCB tester * MCBs under test **Procedure:** 1. Set the MCB tester to the appropriate trip current. 2. Connect the MCB tester to the MCB under test. 3. Trip the MCB using the MCB tester. 4. Verify that the MCB trips within the specified time delay. 5. Reset the MCB and repeat the test for all MCBs under test. **Acceptance Criteria:** * All MCBs shall trip within the specified time delay. * All MCBs shall reset properly after tripping. | E000 | 00E3 | E00#bhui00E3
5459 | 5459 | 5459 | 5459 | SA24M005 | CT Loop Resistance and Single Earth Point |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Testing & Commissioning Commissioning CT Loop Resistance and Single Earth Point | 4 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCBs) in the control and protection panels. **Equipment:** * MCB tester * MCBs under test **Procedure:** 1. Set the MCB tester to the appropriate trip current. 2. Connect the MCB tester to the MCB under test. 3. Trip the MCB using the MCB tester. 4. Verify that the MCB trips within the specified time delay. 5. Reset the MCB and repeat the test for all MCBs under test. **Acceptance Criteria:** * All MCBs shall trip within the specified time delay. * All MCBs shall reset properly after tripping. | E000 | 00E4 | E00#bhui00E4
5460 | 5460 | 5460 | 5460 | SA24M005 | Scheme Check For Line Protection |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Testing & Commissioning Commissioning Scheme Check For Line Protection | 5 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCBs) in the control and protection panels. **Equipment:** * MCB tester * MCBs under test **Procedure:** 1. Set the MCB tester to the appropriate trip current. 2. Connect the MCB tester to the MCB under test. 3. Trip the MCB using the MCB tester. 4. Verify that the MCB trips within the specified time delay. 5. Reset the MCB and repeat the test for all MCBs under test. **Acceptance Criteria:** * All MCBs shall trip within the specified time delay. * All MCBs shall reset properly after tripping. | E000 | 00E5 | E00#bhui00E5
5461 | 5461 | 5461 | 5461 | SA24M005 | Set 1 Line Differential Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Testing & Commissioning Commissioning Set 1 Line Differential Relay Acceptance Test | 6 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCBs) in the control and protection panels. **Equipment:** * MCB tester * MCBs under test **Procedure:** 1. Set the MCB tester to the appropriate trip current. 2. Connect the MCB tester to the MCB under test. 3. Trip the MCB using the MCB tester. 4. Verify that the MCB trips within the specified time delay. 5. Reset the MCB and repeat the test for all MCBs under test. **Acceptance Criteria:** * All MCBs shall trip within the specified time delay. * All MCBs shall reset properly after tripping. | E000 | 00E6 | E00#bhui00E6
5462 | 5462 | 5462 | 5462 | SA24M005 | Set 2 Line Differential Relay Acceptance Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Testing & Commissioning Commissioning Set 2 Line Differential Relay Acceptance Test | 7 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCBs) in the control and protection panels. **Equipment:** * MCB tester * MCBs under test **Procedure:** 1. Set the MCB tester to the appropriate trip current. 2. Connect the MCB tester to the MCB under test. 3. Trip the MCB using the MCB tester. 4. Verify that the MCB trips within the specified time delay. 5. Reset the MCB and repeat the test for all MCBs under test. **Acceptance Criteria:** * All MCBs shall trip within the specified time delay. * All MCBs shall reset properly after tripping. | E000 | 00E7 | E00#bhui00E7
5463 | 5463 | 5463 | 5463 | SA24M005 | Main 1 Multifunction Relay Final Setting Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Testing & Commissioning Commissioning Main 1 Multifunction Relay Final Setting Test | 8 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCBs) in the control and protection panels. **Equipment:** * MCB tester * MCBs under test **Procedure:** 1. Set the MCB tester to the appropriate trip current. 2. Connect the MCB tester to the MCB under test. 3. Trip the MCB using the MCB tester. 4. Verify that the MCB trips within the specified time delay. 5. Reset the MCB and repeat the test for all MCBs under test. **Acceptance Criteria:** * All MCBs shall trip within the specified time delay. * All MCBs shall reset properly after tripping. | E000 | 00E8 | E00#bhui00E8
5464 | 5464 | 5464 | 5464 | SA24M005 | Main 2 Multifunction Relay Final setting Test |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Testing & Commissioning Commissioning Main 2 Multifunction Relay Final setting Test | 9 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCBs) in the control and protection panels. **Equipment:** * MCB tester * MCBs under test **Procedure:** 1. Set the MCB tester to the appropriate trip current. 2. Connect the MCB tester to the MCB under test. 3. Trip the MCB using the MCB tester. 4. Verify that the MCB trips within the specified time delay. 5. Reset the MCB and repeat the test for all MCBs under test. **Acceptance Criteria:** * All MCBs shall trip within the specified time delay. * All MCBs shall reset properly after tripping. | E000 | 00E9 | E00#bhui00E9
5465 | 5465 | 5465 | 5465 | SA24M005 | Alarm And Indication Check Up To SAS HMI And Gateway For EHV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Testing & Commissioning Commissioning Alarm And Indication Check Up To SAS HMI And Gateway For EHV | 10 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCBs) in the control and protection panels. **Equipment:** * MCB tester * MCBs under test **Procedure:** 1. Set the MCB tester to the appropriate trip current. 2. Connect the MCB tester to the MCB under test. 3. Trip the MCB using the MCB tester. 4. Verify that the MCB trips within the specified time delay. 5. Reset the MCB and repeat the test for all MCBs under test. **Acceptance Criteria:** * All MCBs shall trip within the specified time delay. * All MCBs shall reset properly after tripping. | E000 | 0E10 | E00#bhui0E10
5466 | 5466 | 5466 | 5466 | SA24M005 | Closed Loop Test EHV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Testing & Commissioning Commissioning Closed Loop Test EHV | 11 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCBs) in the control and protection panels. **Equipment:** * MCB tester * MCBs under test **Procedure:** 1. Set the MCB tester to the appropriate trip current. 2. Connect the MCB tester to the MCB under test. 3. Trip the MCB using the MCB tester. 4. Verify that the MCB trips within the specified time delay. 5. Reset the MCB and repeat the test for all MCBs under test. **Acceptance Criteria:** * All MCBs shall trip within the specified time delay. * All MCBs shall reset properly after tripping. | E000 | 0E11 | E00#bhui0E11
5467 | 5467 | 5467 | 5467 | SA24M005 | EHV Line Feeder Set 1 Multifunction Relay |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Testing & Commissioning Commissioning EHV Line Feeder Set 1 Multifunction Relay | 12 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCBs) in the control and protection panels. **Equipment:** * MCB tester * MCBs under test **Procedure:** 1. Set the MCB tester to the appropriate trip current. 2. Connect the MCB tester to the MCB under test. 3. Trip the MCB using the MCB tester. 4. Verify that the MCB trips within the specified time delay. 5. Reset the MCB and repeat the test for all MCBs under test. **Acceptance Criteria:** * All MCBs shall trip within the specified time delay. * All MCBs shall reset properly after tripping. | E000 | 0E12 | E00#bhui0E12
5468 | 5468 | 5468 | 5468 | SA24M005 | EHV Line Feeder Set 2 Multifunction Relay |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Testing & Commissioning Commissioning EHV Line Feeder Set 2 Multifunction Relay | 13 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCBs) in the control and protection panels. **Equipment:** * MCB tester * MCBs under test **Procedure:** 1. Set the MCB tester to the appropriate trip current. 2. Connect the MCB tester to the MCB under test. 3. Trip the MCB using the MCB tester. 4. Verify that the MCB trips within the specified time delay. 5. Reset the MCB and repeat the test for all MCBs under test. **Acceptance Criteria:** * All MCBs shall trip within the specified time delay. * All MCBs shall reset properly after tripping. | E000 | 0E13 | E00#bhui0E13
5469 | 5469 | 5469 | 5469 | SA24M005 | Final Trip Test for EHV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Testing & Commissioning Commissioning Final Trip Test for EHV | 14 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCBs) in the control and protection panels. **Equipment:** * MCB tester * MCBs under test **Procedure:** 1. Set the MCB tester to the appropriate trip current. 2. Connect the MCB tester to the MCB under test. 3. Trip the MCB using the MCB tester. 4. Verify that the MCB trips within the specified time delay. 5. Reset the MCB and repeat the test for all MCBs under test. **Acceptance Criteria:** * All MCBs shall trip within the specified time delay. * All MCBs shall reset properly after tripping. | E000 | 0E14 | E00#bhui0E14
5470 | 5470 | 5470 | 5470 | SA24M005 | Relay Final settings Review for EHV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Testing & Commissioning Commissioning Relay Final settings Review for EHV | 15 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCBs) in the control and protection panels. **Equipment:** * MCB tester * MCBs under test **Procedure:** 1. Set the MCB tester to the appropriate trip current. 2. Connect the MCB tester to the MCB under test. 3. Trip the MCB using the MCB tester. 4. Verify that the MCB trips within the specified time delay. 5. Reset the MCB and repeat the test for all MCBs under test. **Acceptance Criteria:** * All MCBs shall trip within the specified time delay. * All MCBs shall reset properly after tripping. | E000 | 0E15 | E00#bhui0E15
5471 | 5471 | 5471 | 5471 | SA24M005 | Normalization Before Energization EHV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Testing & Commissioning Commissioning Normalization Before Energization EHV | 16 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCBs) in the control and protection panels. **Equipment:** * MCB tester * MCBs under test **Procedure:** 1. Set the MCB tester to the appropriate trip current. 2. Connect the MCB tester to the MCB under test. 3. Trip the MCB using the MCB tester. 4. Verify that the MCB trips within the specified time delay. 5. Reset the MCB and repeat the test for all MCBs under test. **Acceptance Criteria:** * All MCBs shall trip within the specified time delay. * All MCBs shall reset properly after tripping. | E000 | 0E16 | E00#bhui0E16
5472 | 5472 | 5472 | 5472 | SA24M005 | Post Energization In Service Test for EHV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Testing & Commissioning Commissioning Post Energization In Service Test for EHV | 17 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCBs) in the control and protection panels. **Equipment:** * MCB tester * MCBs under test **Procedure:** 1. Set the MCB tester to the appropriate trip current. 2. Connect the MCB tester to the MCB under test. 3. Trip the MCB using the MCB tester. 4. Verify that the MCB trips within the specified time delay. 5. Reset the MCB and repeat the test for all MCBs under test. **Acceptance Criteria:** * All MCBs shall trip within the specified time delay. * All MCBs shall reset properly after tripping. | E000 | 0E17 | E00#bhui0E17
5473 | 5473 | 5473 | 5473 | SA24M005 | Energization for EHV |  | 0 | Project Portion- I (Construction of North Qassim 380kV BSP & Installation of New Reactors Remote End Works Remote End SS-4 (9064 BSP) Testing & Commissioning Commissioning Energization for EHV | 18 | **MCB Test** **Purpose:** To verify the proper operation of the molded case circuit breakers (MCBs) in the control and protection panels. **Equipment:** * MCB tester * MCBs under test **Procedure:** 1. Set the MCB tester to the appropriate trip current. 2. Connect the MCB tester to the MCB under test. 3. Trip the MCB using the MCB tester. 4. Verify that the MCB trips within the specified time delay. 5. Reset the MCB and repeat the test for all MCBs under test. **Acceptance Criteria:** * All MCBs shall trip within the specified time delay. * All MCBs shall reset properly after tripping. | E000 | 0E18 | E00#bhui0E18
5474 | 5474 | 5474 | 5474 | SA24M005 | Project Portion- II (Construction of 380kV OHTL's) |  | 1 | -1 | 0 |  |  | X
5475 | 5475 | 5475 | 5475 | SA24M005 | Engineering & Design |  | 2 | -1 | 0 |  |  | X
5476 | 5476 | 5476 | 5476 | SA24M005 | Basic Design (Phase- I) |  | 3 | -1 | 0 |  |  | X
5477 | 5477 | 5477 | 5477 | SA24M005 | Electrical |  | 4 | -1 | 0 |  |  | X
5478 | 5478 | 5478 | 5478 | SA24M005 | Drawing Control Sheet |  | 5 | -1 | 0 |  |  | X
5479 | 5479 | 5479 | 5479 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Drawing Control Sheet Drafting / Preparation | 1 | E0DCS | E000 | 00E1 | E000#fLIk00E1
5480 | 5480 | 5480 | 5480 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Drawing Control Sheet Submission | 2 | E0DCS | E000 | 00E2 | E000#fLIk00E2
5481 | 5481 | 5481 | 5481 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Drawing Control Sheet Review / Evaluation | 3 | E0DCS | E000 | 00E3 | E000#fLIk00E3
5482 | 5482 | 5482 | 5482 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Drawing Control Sheet Approval with Comments | 4 | E0DCS | E000 | 00E4 | E000#fLIk00E4
5483 | 5483 | 5483 | 5483 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Drawing Control Sheet FINAL Approval | 5 | E0DCS | E000 | 00E5 | E000#fLIk00E5
5484 | 5484 | 5484 | 5484 | SA24M005 | Documents Control Sheet Document Transmittal Sheet |  | 5 | -1 | 0 |  |  | X | E000#fLIk
5485 | 5485 | 5485 | 5485 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Documents Control Sheet Document Transmittal Sheet Drafting / Preparation | 1 | E0DCS | E000 | 00E1 | E000#nygr00E1
5486 | 5486 | 5486 | 5486 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Documents Control Sheet Document Transmittal Sheet Submission | 2 | E0DCS | E000 | 00E2 | E000#nygr00E2
5487 | 5487 | 5487 | 5487 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Documents Control Sheet Document Transmittal Sheet Review / Evaluation | 3 | E0DCS | E000 | 00E3 | E000#nygr00E3
5488 | 5488 | 5488 | 5488 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Documents Control Sheet Document Transmittal Sheet Approval with Comments | 4 | E0DCS | E000 | 00E4 | E000#nygr00E4
5489 | 5489 | 5489 | 5489 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Documents Control Sheet Document Transmittal Sheet FINAL Approval | 5 | E0DCS | E000 | 00E5 | E000#nygr00E5
5490 | 5490 | 5490 | 5490 | SA24M005 | Document Title Block |  | 5 | -1 | 0 |  |  | X | E000#nygr
5491 | 5491 | 5491 | 5491 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Document Title Block Drafting / Preparation | 1 | E0DBT | E000 | 00E1 | E000#pwZh00E1
5492 | 5492 | 5492 | 5492 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Document Title Block Submission | 2 | E0DBT | E000 | 00E2 | E000#pwZh00E2
5493 | 5493 | 5493 | 5493 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Document Title Block Review / Evaluation | 3 | E0DBT | E000 | 00E3 | E000#pwZh00E3
5494 | 5494 | 5494 | 5494 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Document Title Block Approval with Comments | 4 | E0DBT | E000 | 00E4 | E000#pwZh00E4
5495 | 5495 | 5495 | 5495 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Document Title Block FINAL Approval | 5 | E0DBT | E000 | 00E5 | E000#pwZh00E5
5496 | 5496 | 5496 | 5496 | SA24M005 | Drawing Title Block |  | 5 | -1 | 0 |  |  | X | E000#pwZh
5497 | 5497 | 5497 | 5497 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Drawing Title Block Drafting / Preparation | 1 | E0DBT | E000 | 00E1 | E000#mKOy00E1
5498 | 5498 | 5498 | 5498 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Drawing Title Block Submission | 2 | E0DBT | E000 | 00E2 | E000#mKOy00E2
5499 | 5499 | 5499 | 5499 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Drawing Title Block Review / Evaluation | 3 | E0DBT | E000 | 00E3 | E000#mKOy00E3
5500 | 5500 | 5500 | 5500 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Drawing Title Block Approval with Comments | 4 | E0DBT | E000 | 00E4 | E000#mKOy00E4
5501 | 5501 | 5501 | 5501 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Drawing Title Block FINAL Approval | 5 | E0DBT | E000 | 00E5 | E000#mKOy00E5
5502 | 5502 | 5502 | 5502 | SA24M005 | Quality Assurance and Quality Control Plan |  | 5 | -1 | 0 |  |  | X | E000#mKOy
5503 | 5503 | 5503 | 5503 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Quality Assurance and Quality Control Plan Drafting / Preparation | 1 | EQAQC | E000 | 00E1 | E000#ulzL00E1
5504 | 5504 | 5504 | 5504 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Quality Assurance and Quality Control Plan Submission | 2 | EQAQC | E000 | 00E2 | E000#ulzL00E2
5505 | 5505 | 5505 | 5505 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Quality Assurance and Quality Control Plan Review / Evaluation | 3 | EQAQC | E000 | 00E3 | E000#ulzL00E3
5506 | 5506 | 5506 | 5506 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Quality Assurance and Quality Control Plan Approval with Comments | 4 | EQAQC | E000 | 00E4 | E000#ulzL00E4
5507 | 5507 | 5507 | 5507 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Quality Assurance and Quality Control Plan FINAL Approval | 5 | EQAQC | E000 | 00E5 | E000#ulzL00E5
5508 | 5508 | 5508 | 5508 | SA24M005 | Technical Submittal for Conductor |  | 5 | -1 | 0 |  |  | X | E000#ulzL
5509 | 5509 | 5509 | 5509 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Technical Submittal for Conductor Drafting / Preparation | 1 | E0COND | E000 | 00E1 | E000E0COND00E1
5510 | 5510 | 5510 | 5510 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Technical Submittal for Conductor Submission | 2 | E0COND | E000 | 00E2 | E000E0COND00E2
5511 | 5511 | 5511 | 5511 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Technical Submittal for Conductor Review / Evaluation | 3 | E0COND | E000 | 00E3 | E000E0COND00E3
5512 | 5512 | 5512 | 5512 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Technical Submittal for Conductor Approval with Comments | 4 | E0COND | E000 | 00E4 | E000E0COND00E4
5513 | 5513 | 5513 | 5513 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Technical Submittal for Conductor FINAL Approval | 5 | E0COND | E000 | 00E5 | E000E0COND00E5
5514 | 5514 | 5514 | 5514 | SA24M005 | Technical Submittal for Insulators |  | 5 | -1 | 0 |  |  | X
5515 | 5515 | 5515 | 5515 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Technical Submittal for Insulators Drafting / Preparation | 1 | E0INS | E000 | 00E1 | E000E0INS00E1
5516 | 5516 | 5516 | 5516 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Technical Submittal for Insulators Submission | 2 | E0INS | E000 | 00E2 | E000E0INS00E2
5517 | 5517 | 5517 | 5517 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Technical Submittal for Insulators Review / Evaluation | 3 | E0INS | E000 | 00E3 | E000E0INS00E3
5518 | 5518 | 5518 | 5518 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Technical Submittal for Insulators Approval with Comments | 4 | E0INS | E000 | 00E4 | E000E0INS00E4
5519 | 5519 | 5519 | 5519 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Technical Submittal for Insulators FINAL Approval | 5 | E0INS | E000 | 00E5 | E000E0INS00E5
5520 | 5520 | 5520 | 5520 | SA24M005 | Insulator set assembly details |  | 5 | -1 | 0 |  |  | X
5521 | 5521 | 5521 | 5521 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Insulator set assembly details Drafting / Preparation | 1 | #Bjqz | E000 | 00E1 | E000#Bjqz00E1
5522 | 5522 | 5522 | 5522 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Insulator set assembly details Submission | 2 | #Bjqz | E000 | 00E2 | E000#Bjqz00E2
5523 | 5523 | 5523 | 5523 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Insulator set assembly details Review / Evaluation | 3 | #Bjqz | E000 | 00E3 | E000#Bjqz00E3
5524 | 5524 | 5524 | 5524 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Insulator set assembly details Approval with Comments | 4 | #Bjqz | E000 | 00E4 | E000#Bjqz00E4
5525 | 5525 | 5525 | 5525 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Insulator set assembly details FINAL Approval | 5 | #Bjqz | E000 | 00E5 | E000#Bjqz00E5
5526 | 5526 | 5526 | 5526 | SA24M005 | Technical Submittal for Grounding Materials (including Grounding Conductor & Grounding Rod) |  | 5 | -1 | 0 |  |  | X
5527 | 5527 | 5527 | 5527 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Technical Submittal for Grounding Materials (including Grounding Conductor & Grounding Rod) Drafting / Preparation | 1 | EGRND | E000 | 00E1 | E000#bHwm00E1
5528 | 5528 | 5528 | 5528 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Technical Submittal for Grounding Materials (including Grounding Conductor & Grounding Rod) Submission | 2 | EGRND | E000 | 00E2 | E000#bHwm00E2
5529 | 5529 | 5529 | 5529 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Technical Submittal for Grounding Materials (including Grounding Conductor & Grounding Rod) Review / Evaluation | 3 | EGRND | E000 | 00E3 | E000#bHwm00E3
5530 | 5530 | 5530 | 5530 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Technical Submittal for Grounding Materials (including Grounding Conductor & Grounding Rod) Approval with Comments | 4 | EGRND | E000 | 00E4 | E000#bHwm00E4
5531 | 5531 | 5531 | 5531 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Technical Submittal for Grounding Materials (including Grounding Conductor & Grounding Rod) FINAL Approval | 5 | EGRND | E000 | 00E5 | E000#bHwm00E5
5532 | 5532 | 5532 | 5532 | SA24M005 | Sag & Tension Calculations for Conductor & OPGW |  | 5 | -1 | 0 |  |  | X | E000#bHwm
5533 | 5533 | 5533 | 5533 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Sag & Tension Calculations for Conductor & OPGW Drafting / Preparation | 1 | ESAGTC | E000 | 00E1 | E000ESAGTC00E1
5534 | 5534 | 5534 | 5534 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Sag & Tension Calculations for Conductor & OPGW Submission | 2 | ESAGTC | E000 | 00E2 | E000ESAGTC00E2
5535 | 5535 | 5535 | 5535 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Sag & Tension Calculations for Conductor & OPGW Review / Evaluation | 3 | ESAGTC | E000 | 00E3 | E000ESAGTC00E3
5536 | 5536 | 5536 | 5536 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Sag & Tension Calculations for Conductor & OPGW Approval with Comments | 4 | ESAGTC | E000 | 00E4 | E000ESAGTC00E4
5537 | 5537 | 5537 | 5537 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Sag & Tension Calculations for Conductor & OPGW FINAL Approval | 5 | ESAGTC | E000 | 00E5 | E000ESAGTC00E5
5538 | 5538 | 5538 | 5538 | SA24M005 | Sag Template |  | 5 | -1 | 0 |  |  | X
5539 | 5539 | 5539 | 5539 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Sag Template Drafting / Preparation | 1 | ESAG | E000 | 00E1 | E000ESAG00E1
5540 | 5540 | 5540 | 5540 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Sag Template Submission | 2 | ESAG | E000 | 00E2 | E000ESAG00E2
5541 | 5541 | 5541 | 5541 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Sag Template Review / Evaluation | 3 | ESAG | E000 | 00E3 | E000ESAG00E3
5542 | 5542 | 5542 | 5542 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Sag Template Approval with Comments | 4 | ESAG | E000 | 00E4 | E000ESAG00E4
5543 | 5543 | 5543 | 5543 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Sag Template FINAL Approval | 5 | ESAG | E000 | 00E5 | E000ESAG00E5
5544 | 5544 | 5544 | 5544 | SA24M005 | Method Statement for Stringing of Conductor & OPGW Crossing Highway & existing transmission line |  | 5 | -1 | 0 |  |  | X
5545 | 5545 | 5545 | 5545 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Method Statement for Stringing of Conductor & OPGW Crossing Highway & existing transmission line Drafting / Preparation | 1 |  | E000 | 00E1 | E000nan00E1
5546 | 5546 | 5546 | 5546 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Method Statement for Stringing of Conductor & OPGW Crossing Highway & existing transmission line Submission | 2 | **Method Statement for Stringing of Conductor & OPGW Crossing Highway & Existing Transmission Line** **1.0 Purpose** This method statement outlines the procedures for stringing conductors and OPGW across highways and existing transmission lines. **2.0 Scope** This method statement applies to all stringing operations conducted by the Contractor, including: * Conductor stringing * OPGW stringing * Crossing highways * Crossing existing transmission lines **3.0 Responsibilities** The following personnel are responsible for implementing this method statement: * Stringing Supervisor * Stringing Crew * Safety Officer **4.0 Safety Precautions** The following safety precautions shall be observed during stringing operations: * All personnel involved in stringing operations shall wear appropriate personal protective equipment (PPE), including hard hats, safety glasses, gloves, and high-visibility vests. * Stringing operations shall be conducted in accordance with all applicable safety regulations and guidelines. * Stringing operations shall be suspended during inclement weather, such as high winds, lightning, or heavy rain. * Stringing operations shall be conducted in a manner that minimizes the risk of damage to property or injury to personnel. **5.0 Equipment** The following equipment shall be used during stringing operations: * Stringing blocks * Stringing sheave * Stringing line * Conductor grips * OPGW grips * Tensioning equipment * Safety harnesses **6.0 Procedure** **6.1 Crossing Highways** * Obtain necessary permits and approvals from the highway authority. * Establish a safe work zone and traffic control measures. * String the conductor or OPGW across the highway using a helicopter or other approved method. * Ensure that the conductor or OPGW is properly tensioned and secured. * Remove all equipment and materials from the work zone. **6.2 Crossing Existing Transmission Lines** * Coordinate with the owner of the existing transmission line to obtain necessary clearances and approvals. * Establish a safe work zone and traffic control measures. * String the conductor or OPGW across the existing transmission line using a helicopter or other approved method. * Ensure that the conductor or OPGW is properly tensioned and secured. * Remove all equipment and materials from the work zone. **7.0 Quality Control** The following quality control measures shall be implemented during stringing operations: * The conductor or OPGW shall be inspected for any damage or defects prior to stringing. * The conductor or OPGW shall be tensioned to the specified value. * The conductor or OPGW shall be secured to the insulators and hardware in accordance with the manufacturer's instructions. * The stringing operation shall be documented with photographs and videos. **8.0 Training** All personnel involved in stringing operations shall be trained on the contents of this method statement. | E000 | 00E2 | E000nan00E2
5547 | 5547 | 5547 | 5547 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Method Statement for Stringing of Conductor & OPGW Crossing Highway & existing transmission line Review / Evaluation | 3 | **Method Statement for Stringing of Conductor & OPGW Crossing Highway & Existing Transmission Line** **1.0 Purpose** This method statement outlines the procedures for stringing conductors and OPGW across highways and existing transmission lines. **2.0 Scope** This method statement applies to all stringing operations conducted by the Contractor, including: * Conductor stringing * OPGW stringing * Crossing highways * Crossing existing transmission lines **3.0 Responsibilities** The following personnel are responsible for implementing this method statement: * Stringing Supervisor * Stringing Crew * Safety Officer **4.0 Safety Precautions** The following safety precautions shall be observed during stringing operations: * All personnel involved in stringing operations shall wear appropriate personal protective equipment (PPE), including hard hats, safety glasses, gloves, and high-visibility vests. * Stringing operations shall be conducted in accordance with all applicable safety regulations and guidelines. * Stringing operations shall be suspended during inclement weather, such as high winds, lightning, or heavy rain. * Stringing operations shall be conducted in a manner that minimizes the risk of damage to property or injury to personnel. **5.0 Equipment** The following equipment shall be used during stringing operations: * Stringing blocks * Stringing sheave * Stringing line * Conductor grips * OPGW grips * Tensioning equipment * Safety harnesses **6.0 Procedure** **6.1 Crossing Highways** * Obtain necessary permits and approvals from the highway authority. * Establish a safe work zone and traffic control measures. * String the conductor or OPGW across the highway using a helicopter or other approved method. * Ensure that the conductor or OPGW is properly tensioned and secured. * Remove all equipment and materials from the work zone. **6.2 Crossing Existing Transmission Lines** * Coordinate with the owner of the existing transmission line to obtain necessary clearances and approvals. * Establish a safe work zone and traffic control measures. * String the conductor or OPGW across the existing transmission line using a helicopter or other approved method. * Ensure that the conductor or OPGW is properly tensioned and secured. * Remove all equipment and materials from the work zone. **7.0 Quality Control** The following quality control measures shall be implemented during stringing operations: * The conductor or OPGW shall be inspected for any damage or defects prior to stringing. * The conductor or OPGW shall be tensioned to the specified value. * The conductor or OPGW shall be secured to the insulators and hardware in accordance with the manufacturer's instructions. * The stringing operation shall be documented with photographs and videos. **8.0 Training** All personnel involved in stringing operations shall be trained on the contents of this method statement. | E000 | 00E3 | E000nan00E3
5548 | 5548 | 5548 | 5548 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Method Statement for Stringing of Conductor & OPGW Crossing Highway & existing transmission line Approval with Comments | 4 | **Method Statement for Stringing of Conductor & OPGW Crossing Highway & Existing Transmission Line** **1.0 Purpose** This method statement outlines the procedures for stringing conductors and OPGW across highways and existing transmission lines. **2.0 Scope** This method statement applies to all stringing operations conducted by the Contractor, including: * Conductor stringing * OPGW stringing * Crossing highways * Crossing existing transmission lines **3.0 Responsibilities** The following personnel are responsible for implementing this method statement: * Stringing Supervisor * Stringing Crew * Safety Officer **4.0 Safety Precautions** The following safety precautions shall be observed during stringing operations: * All personnel involved in stringing operations shall wear appropriate personal protective equipment (PPE), including hard hats, safety glasses, gloves, and high-visibility vests. * Stringing operations shall be conducted in accordance with all applicable safety regulations and guidelines. * Stringing operations shall be suspended during inclement weather, such as high winds, lightning, or heavy rain. * Stringing operations shall be conducted in a manner that minimizes the risk of damage to property or injury to personnel. **5.0 Equipment** The following equipment shall be used during stringing operations: * Stringing blocks * Stringing sheave * Stringing line * Conductor grips * OPGW grips * Tensioning equipment * Safety harnesses **6.0 Procedure** **6.1 Crossing Highways** * Obtain necessary permits and approvals from the highway authority. * Establish a safe work zone and traffic control measures. * String the conductor or OPGW across the highway using a helicopter or other approved method. * Ensure that the conductor or OPGW is properly tensioned and secured. * Remove all equipment and materials from the work zone. **6.2 Crossing Existing Transmission Lines** * Coordinate with the owner of the existing transmission line to obtain necessary clearances and approvals. * Establish a safe work zone and traffic control measures. * String the conductor or OPGW across the existing transmission line using a helicopter or other approved method. * Ensure that the conductor or OPGW is properly tensioned and secured. * Remove all equipment and materials from the work zone. **7.0 Quality Control** The following quality control measures shall be implemented during stringing operations: * The conductor or OPGW shall be inspected for any damage or defects prior to stringing. * The conductor or OPGW shall be tensioned to the specified value. * The conductor or OPGW shall be secured to the insulators and hardware in accordance with the manufacturer's instructions. * The stringing operation shall be documented with photographs and videos. **8.0 Training** All personnel involved in stringing operations shall be trained on the contents of this method statement. | E000 | 00E4 | E000nan00E4
5549 | 5549 | 5549 | 5549 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Method Statement for Stringing of Conductor & OPGW Crossing Highway & existing transmission line FINAL Approval | 5 | **Method Statement for Stringing of Conductor & OPGW Crossing Highway & Existing Transmission Line** **1.0 Purpose** This method statement outlines the procedures for stringing conductors and OPGW across highways and existing transmission lines. **2.0 Scope** This method statement applies to all stringing operations conducted by the Contractor, including: * Conductor stringing * OPGW stringing * Crossing highways * Crossing existing transmission lines **3.0 Responsibilities** The following personnel are responsible for implementing this method statement: * Stringing Supervisor * Stringing Crew * Safety Officer **4.0 Safety Precautions** The following safety precautions shall be observed during stringing operations: * All personnel involved in stringing operations shall wear appropriate personal protective equipment (PPE), including hard hats, safety glasses, gloves, and high-visibility vests. * Stringing operations shall be conducted in accordance with all applicable safety regulations and guidelines. * Stringing operations shall be suspended during inclement weather, such as high winds, lightning, or heavy rain. * Stringing operations shall be conducted in a manner that minimizes the risk of damage to property or injury to personnel. **5.0 Equipment** The following equipment shall be used during stringing operations: * Stringing blocks * Stringing sheave * Stringing line * Conductor grips * OPGW grips * Tensioning equipment * Safety harnesses **6.0 Procedure** **6.1 Crossing Highways** * Obtain necessary permits and approvals from the highway authority. * Establish a safe work zone and traffic control measures. * String the conductor or OPGW across the highway using a helicopter or other approved method. * Ensure that the conductor or OPGW is properly tensioned and secured. * Remove all equipment and materials from the work zone. **6.2 Crossing Existing Transmission Lines** * Coordinate with the owner of the existing transmission line to obtain necessary clearances and approvals. * Establish a safe work zone and traffic control measures. * String the conductor or OPGW across the existing transmission line using a helicopter or other approved method. * Ensure that the conductor or OPGW is properly tensioned and secured. * Remove all equipment and materials from the work zone. **7.0 Quality Control** The following quality control measures shall be implemented during stringing operations: * The conductor or OPGW shall be inspected for any damage or defects prior to stringing. * The conductor or OPGW shall be tensioned to the specified value. * The conductor or OPGW shall be secured to the insulators and hardware in accordance with the manufacturer's instructions. * The stringing operation shall be documented with photographs and videos. **8.0 Training** All personnel involved in stringing operations shall be trained on the contents of this method statement. | E000 | 00E5 | E000nan00E5
5550 | 5550 | 5550 | 5550 | SA24M005 | Conductor Jumper Details/Placement Chart |  | 5 | -1 | 0 |  |  | X
5551 | 5551 | 5551 | 5551 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Conductor Jumper Details/Placement Chart Drafting / Preparation | 1 | E0CND | E000 | 00E1 | E000E0CND00E1
5552 | 5552 | 5552 | 5552 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Conductor Jumper Details/Placement Chart Submission | 2 | E0CND | E000 | 00E2 | E000E0CND00E2
5553 | 5553 | 5553 | 5553 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Conductor Jumper Details/Placement Chart Review / Evaluation | 3 | E0CND | E000 | 00E3 | E000E0CND00E3
5554 | 5554 | 5554 | 5554 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Conductor Jumper Details/Placement Chart Approval with Comments | 4 | E0CND | E000 | 00E4 | E000E0CND00E4
5555 | 5555 | 5555 | 5555 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Conductor Jumper Details/Placement Chart FINAL Approval | 5 | E0CND | E000 | 00E5 | E000E0CND00E5
5556 | 5556 | 5556 | 5556 | SA24M005 | OPGW Joint Box Mounting Arrangements on Steel Structures |  | 5 | -1 | 0 |  |  | X
5557 | 5557 | 5557 | 5557 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical OPGW Joint Box Mounting Arrangements on Steel Structures Drafting / Preparation | 1 | EOPGW | E000 | 00E1 | E000#hMEM00E1
5558 | 5558 | 5558 | 5558 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical OPGW Joint Box Mounting Arrangements on Steel Structures Submission | 2 | EOPGW | E000 | 00E2 | E000#hMEM00E2
5559 | 5559 | 5559 | 5559 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical OPGW Joint Box Mounting Arrangements on Steel Structures Review / Evaluation | 3 | EOPGW | E000 | 00E3 | E000#hMEM00E3
5560 | 5560 | 5560 | 5560 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical OPGW Joint Box Mounting Arrangements on Steel Structures Approval with Comments | 4 | EOPGW | E000 | 00E4 | E000#hMEM00E4
5561 | 5561 | 5561 | 5561 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical OPGW Joint Box Mounting Arrangements on Steel Structures FINAL Approval | 5 | EOPGW | E000 | 00E5 | E000#hMEM00E5
5562 | 5562 | 5562 | 5562 | SA24M005 | OPGW Joint Box Mounting Arrangements on Take-offStructure (with Conduit Mounting Details |  | 5 | -1 | 0 |  |  | X | E000#hMEM
5563 | 5563 | 5563 | 5563 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical OPGW Joint Box Mounting Arrangements on Take-offStructure (with Conduit Mounting Details Drafting / Preparation | 1 | EOPGW | E000 | 00E1 | E000#mnQL00E1
5564 | 5564 | 5564 | 5564 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical OPGW Joint Box Mounting Arrangements on Take-offStructure (with Conduit Mounting Details Submission | 2 | EOPGW | E000 | 00E2 | E000#mnQL00E2
5565 | 5565 | 5565 | 5565 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical OPGW Joint Box Mounting Arrangements on Take-offStructure (with Conduit Mounting Details Review / Evaluation | 3 | EOPGW | E000 | 00E3 | E000#mnQL00E3
5566 | 5566 | 5566 | 5566 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical OPGW Joint Box Mounting Arrangements on Take-offStructure (with Conduit Mounting Details Approval with Comments | 4 | EOPGW | E000 | 00E4 | E000#mnQL00E4
5567 | 5567 | 5567 | 5567 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical OPGW Joint Box Mounting Arrangements on Take-offStructure (with Conduit Mounting Details FINAL Approval | 5 | EOPGW | E000 | 00E5 | E000#mnQL00E5
5568 | 5568 | 5568 | 5568 | SA24M005 | Technical Submittal for Insulator String Fittings and Hardware Assembly Details |  | 5 | -1 | 0 |  |  | X | E000#mnQL
5569 | 5569 | 5569 | 5569 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Technical Submittal for Insulator String Fittings and Hardware Assembly Details Drafting / Preparation | 1 | #XPxp | E000 | 00E1 | E000#XPxp00E1
5570 | 5570 | 5570 | 5570 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Technical Submittal for Insulator String Fittings and Hardware Assembly Details Submission | 2 | #XPxp | E000 | 00E2 | E000#XPxp00E2
5571 | 5571 | 5571 | 5571 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Technical Submittal for Insulator String Fittings and Hardware Assembly Details Review / Evaluation | 3 | #XPxp | E000 | 00E3 | E000#XPxp00E3
5572 | 5572 | 5572 | 5572 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Technical Submittal for Insulator String Fittings and Hardware Assembly Details Approval with Comments | 4 | #XPxp | E000 | 00E4 | E000#XPxp00E4
5573 | 5573 | 5573 | 5573 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Technical Submittal for Insulator String Fittings and Hardware Assembly Details FINAL Approval | 5 | #XPxp | E000 | 00E5 | E000#XPxp00E5
5574 | 5574 | 5574 | 5574 | SA24M005 | Technical Submittal for OPGW Fittings , Spacer Damper, Vibration Dampers & Hardware Assembly Details |  | 5 | -1 | 0 |  |  | X
5575 | 5575 | 5575 | 5575 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Technical Submittal for OPGW Fittings , Spacer Damper, Vibration Dampers & Hardware Assembly Details Drafting / Preparation | 1 | E0OPGW | E000 | 00E1 | E000E0OPGW00E1
5576 | 5576 | 5576 | 5576 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Technical Submittal for OPGW Fittings , Spacer Damper, Vibration Dampers & Hardware Assembly Details Submission | 2 | E0OPGW | E000 | 00E2 | E000E0OPGW00E2
5577 | 5577 | 5577 | 5577 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Technical Submittal for OPGW Fittings , Spacer Damper, Vibration Dampers & Hardware Assembly Details Review / Evaluation | 3 | E0OPGW | E000 | 00E3 | E000E0OPGW00E3
5578 | 5578 | 5578 | 5578 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Technical Submittal for OPGW Fittings , Spacer Damper, Vibration Dampers & Hardware Assembly Details Approval with Comments | 4 | E0OPGW | E000 | 00E4 | E000E0OPGW00E4
5579 | 5579 | 5579 | 5579 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Technical Submittal for OPGW Fittings , Spacer Damper, Vibration Dampers & Hardware Assembly Details FINAL Approval | 5 | E0OPGW | E000 | 00E5 | E000E0OPGW00E5
5580 | 5580 | 5580 | 5580 | SA24M005 | Structure Grounding Details & Layout Drawings |  | 5 | -1 | 0 |  |  | X
5581 | 5581 | 5581 | 5581 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Structure Grounding Details & Layout Drawings Drafting / Preparation | 1 | E0STRG | E000 | 00E1 | E000E0STRG00E1
5582 | 5582 | 5582 | 5582 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Structure Grounding Details & Layout Drawings Submission | 2 | E0STRG | E000 | 00E2 | E000E0STRG00E2
5583 | 5583 | 5583 | 5583 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Structure Grounding Details & Layout Drawings Review / Evaluation | 3 | E0STRG | E000 | 00E3 | E000E0STRG00E3
5584 | 5584 | 5584 | 5584 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Structure Grounding Details & Layout Drawings Approval with Comments | 4 | E0STRG | E000 | 00E4 | E000E0STRG00E4
5585 | 5585 | 5585 | 5585 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Electrical Structure Grounding Details & Layout Drawings FINAL Approval | 5 | E0STRG | E000 | 00E5 | E000E0STRG00E5
5586 | 5586 | 5586 | 5586 | SA24M005 | Civil |  | 4 | -1 | 0 |  |  | X
5587 | 5587 | 5587 | 5587 | SA24M005 | Technical Submittal for Structure Material |  | 5 | -1 | 0 |  |  | X
5588 | 5588 | 5588 | 5588 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Technical Submittal for Structure Material Drafting / Preparation | 1 | CTSRM | E000 | 00E1 | E000CTSRM00E1
5589 | 5589 | 5589 | 5589 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Technical Submittal for Structure Material Submission | 2 | CTSRM | E000 | 00E2 | E000CTSRM00E2
5590 | 5590 | 5590 | 5590 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Technical Submittal for Structure Material Review / Evaluation | 3 | CTSRM | E000 | 00E3 | E000CTSRM00E3
5591 | 5591 | 5591 | 5591 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Technical Submittal for Structure Material Approval with Comments | 4 | CTSRM | E000 | 00E4 | E000CTSRM00E4
5592 | 5592 | 5592 | 5592 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Technical Submittal for Structure Material FINAL Approval | 5 | CTSRM | E000 | 00E5 | E000CTSRM00E5
5593 | 5593 | 5593 | 5593 | SA24M005 | Concrete Protective Coating Materials |  | 5 | -1 | 0 |  |  | X
5594 | 5594 | 5594 | 5594 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Concrete Protective Coating Materials Drafting / Preparation | 1 | CCPCM | E000 | 00E1 | E000CCPCM00E1
5595 | 5595 | 5595 | 5595 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Concrete Protective Coating Materials Submission | 2 | CCPCM | E000 | 00E2 | E000CCPCM00E2
5596 | 5596 | 5596 | 5596 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Concrete Protective Coating Materials Review / Evaluation | 3 | CCPCM | E000 | 00E3 | E000CCPCM00E3
5597 | 5597 | 5597 | 5597 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Concrete Protective Coating Materials Approval with Comments | 4 | CCPCM | E000 | 00E4 | E000CCPCM00E4
5598 | 5598 | 5598 | 5598 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Concrete Protective Coating Materials FINAL Approval | 5 | CCPCM | E000 | 00E5 | E000CCPCM00E5
5599 | 5599 | 5599 | 5599 | SA24M005 | Concrete Bonding Agent |  | 5 | -1 | 0 |  |  | X
5600 | 5600 | 5600 | 5600 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Concrete Bonding Agent Drafting / Preparation | 1 | CBCA | E000 | 00E1 | E000CBCA00E1
5601 | 5601 | 5601 | 5601 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Concrete Bonding Agent Submission | 2 | CBCA | E000 | 00E2 | E000CBCA00E2
5602 | 5602 | 5602 | 5602 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Concrete Bonding Agent Review / Evaluation | 3 | CBCA | E000 | 00E3 | E000CBCA00E3
5603 | 5603 | 5603 | 5603 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Concrete Bonding Agent Approval with Comments | 4 | CBCA | E000 | 00E4 | E000CBCA00E4
5604 | 5604 | 5604 | 5604 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Concrete Bonding Agent FINAL Approval | 5 | CBCA | E000 | 00E5 | E000CBCA00E5
5605 | 5605 | 5605 | 5605 | SA24M005 | Concrete Repair Mortar |  | 5 | -1 | 0 |  |  | X
5606 | 5606 | 5606 | 5606 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Concrete Repair Mortar Drafting / Preparation | 1 | C0CRM | E000 | 00E1 | E000#hBrJ00E1
5607 | 5607 | 5607 | 5607 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Concrete Repair Mortar Submission | 2 | C0CRM | E000 | 00E2 | E000#hBrJ00E2
5608 | 5608 | 5608 | 5608 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Concrete Repair Mortar Review / Evaluation | 3 | C0CRM | E000 | 00E3 | E000#hBrJ00E3
5609 | 5609 | 5609 | 5609 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Concrete Repair Mortar Approval with Comments | 4 | C0CRM | E000 | 00E4 | E000#hBrJ00E4
5610 | 5610 | 5610 | 5610 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Concrete Repair Mortar FINAL Approval | 5 | C0CRM | E000 | 00E5 | E000#hBrJ00E5
5611 | 5611 | 5611 | 5611 | SA24M005 | General Civil/Structural Notes |  | 5 | -1 | 0 |  |  | X | E000#hBrJ
5612 | 5612 | 5612 | 5612 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil General Civil/Structural Notes Drafting / Preparation | 1 | CGCSN | E000 | 00E1 | E000CGCSN00E1
5613 | 5613 | 5613 | 5613 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil General Civil/Structural Notes Submission | 2 | CGCSN | E000 | 00E2 | E000CGCSN00E2
5614 | 5614 | 5614 | 5614 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil General Civil/Structural Notes Review / Evaluation | 3 | CGCSN | E000 | 00E3 | E000CGCSN00E3
5615 | 5615 | 5615 | 5615 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil General Civil/Structural Notes Approval with Comments | 4 | CGCSN | E000 | 00E4 | E000CGCSN00E4
5616 | 5616 | 5616 | 5616 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil General Civil/Structural Notes FINAL Approval | 5 | CGCSN | E000 | 00E5 | E000CGCSN00E5
5617 | 5617 | 5617 | 5617 | SA24M005 | Crash Barrier for Tower |  | 5 | -1 | 0 |  |  | X
5618 | 5618 | 5618 | 5618 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Crash Barrier for Tower Drafting / Preparation | 1 | CBCRW | E000 | 00E1 | E000CBCRW00E1
5619 | 5619 | 5619 | 5619 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Crash Barrier for Tower Submission | 2 | CBCRW | E000 | 00E2 | E000CBCRW00E2
5620 | 5620 | 5620 | 5620 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Crash Barrier for Tower Review / Evaluation | 3 | CBCRW | E000 | 00E3 | E000CBCRW00E3
5621 | 5621 | 5621 | 5621 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Crash Barrier for Tower Approval with Comments | 4 | CBCRW | E000 | 00E4 | E000CBCRW00E4
5622 | 5622 | 5622 | 5622 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Crash Barrier for Tower FINAL Approval | 5 | CBCRW | E000 | 00E5 | E000CBCRW00E5
5623 | 5623 | 5623 | 5623 | SA24M005 | Temporary sign board |  | 5 | -1 | 0 |  |  | X
5624 | 5624 | 5624 | 5624 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Temporary sign board Drafting / Preparation | 1 | CTSB | E000 | 00E1 | E000CTSB00E1
5625 | 5625 | 5625 | 5625 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Temporary sign board Submission | 2 | CTSB | E000 | 00E2 | E000CTSB00E2
5626 | 5626 | 5626 | 5626 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Temporary sign board Review / Evaluation | 3 | CTSB | E000 | 00E3 | E000CTSB00E3
5627 | 5627 | 5627 | 5627 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Temporary sign board Approval with Comments | 4 | CTSB | E000 | 00E4 | E000CTSB00E4
5628 | 5628 | 5628 | 5628 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Temporary sign board FINAL Approval | 5 | CTSB | E000 | 00E5 | E000CTSB00E5
5629 | 5629 | 5629 | 5629 | SA24M005 | Structure identification |  | 5 | -1 | 0 |  |  | X
5630 | 5630 | 5630 | 5630 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Structure identification Drafting / Preparation | 1 | CSTRC | E000 | 00E1 | E000#tIIS00E1
5631 | 5631 | 5631 | 5631 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Structure identification Submission | 2 | CSTRC | E000 | 00E2 | E000#tIIS00E2
5632 | 5632 | 5632 | 5632 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Structure identification Review / Evaluation | 3 | CSTRC | E000 | 00E3 | E000#tIIS00E3
5633 | 5633 | 5633 | 5633 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Structure identification Approval with Comments | 4 | CSTRC | E000 | 00E4 | E000#tIIS00E4
5634 | 5634 | 5634 | 5634 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Structure identification FINAL Approval | 5 | CSTRC | E000 | 00E5 | E000#tIIS00E5
5635 | 5635 | 5635 | 5635 | SA24M005 | Barbed Wire for Installation of ACD |  | 5 | -1 | 0 |  |  | X | E000#tIIS
5636 | 5636 | 5636 | 5636 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Barbed Wire for Installation of ACD Drafting / Preparation | 1 | CBW | E000 | 00E1 | E000CBW00E1
5637 | 5637 | 5637 | 5637 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Barbed Wire for Installation of ACD Submission | 2 | CBW | E000 | 00E2 | E000CBW00E2
5638 | 5638 | 5638 | 5638 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Barbed Wire for Installation of ACD Review / Evaluation | 3 | CBW | E000 | 00E3 | E000CBW00E3
5639 | 5639 | 5639 | 5639 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Barbed Wire for Installation of ACD Approval with Comments | 4 | CBW | E000 | 00E4 | E000CBW00E4
5640 | 5640 | 5640 | 5640 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Barbed Wire for Installation of ACD FINAL Approval | 5 | CBW | E000 | 00E5 | E000CBW00E5
5641 | 5641 | 5641 | 5641 | SA24M005 | Shop & Erection Drawings for F-T2 Tower (0-2) degrees |  | 5 | -1 | 0 |  |  | X
5642 | 5642 | 5642 | 5642 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Shop & Erection Drawings for F-T2 Tower (0-2) degrees Drafting / Preparation | 1 | C0F0T | E000 | 00E1 | E000C0F0T00E1
5643 | 5643 | 5643 | 5643 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Shop & Erection Drawings for F-T2 Tower (0-2) degrees Submission | 2 | C0F0T | E000 | 00E2 | E000C0F0T00E2
5644 | 5644 | 5644 | 5644 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Shop & Erection Drawings for F-T2 Tower (0-2) degrees Review / Evaluation | 3 | C0F0T | E000 | 00E3 | E000C0F0T00E3
5645 | 5645 | 5645 | 5645 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Shop & Erection Drawings for F-T2 Tower (0-2) degrees Approval with Comments | 4 | C0F0T | E000 | 00E4 | E000C0F0T00E4
5646 | 5646 | 5646 | 5646 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Shop & Erection Drawings for F-T2 Tower (0-2) degrees FINAL Approval | 5 | C0F0T | E000 | 00E5 | E000C0F0T00E5
5647 | 5647 | 5647 | 5647 | SA24M005 | Shop & Erection Drawings for F-SA10 Small Angle Tower (2-10) degrees |  | 5 | -1 | 0 |  |  | X
5648 | 5648 | 5648 | 5648 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Shop & Erection Drawings for F-SA10 Small Angle Tower (2-10) degrees Drafting / Preparation | 1 | #PnId | E000 | 00E1 | E000#PnId00E1
5649 | 5649 | 5649 | 5649 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Shop & Erection Drawings for F-SA10 Small Angle Tower (2-10) degrees Submission | 2 | #PnId | E000 | 00E2 | E000#PnId00E2
5650 | 5650 | 5650 | 5650 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Shop & Erection Drawings for F-SA10 Small Angle Tower (2-10) degrees Review / Evaluation | 3 | #PnId | E000 | 00E3 | E000#PnId00E3
5651 | 5651 | 5651 | 5651 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Shop & Erection Drawings for F-SA10 Small Angle Tower (2-10) degrees Approval with Comments | 4 | #PnId | E000 | 00E4 | E000#PnId00E4
5652 | 5652 | 5652 | 5652 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Shop & Erection Drawings for F-SA10 Small Angle Tower (2-10) degrees FINAL Approval | 5 | #PnId | E000 | 00E5 | E000#PnId00E5
5653 | 5653 | 5653 | 5653 | SA24M005 | Shop & Erection Drawings for F-MA35 Medium Angle Tower (10-35) degrees |  | 5 | -1 | 0 |  |  | X
5654 | 5654 | 5654 | 5654 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Shop & Erection Drawings for F-MA35 Medium Angle Tower (10-35) degrees Drafting / Preparation | 1 | F-MA35 | E000 | 00E1 | E000F-MA3500E1
5655 | 5655 | 5655 | 5655 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Shop & Erection Drawings for F-MA35 Medium Angle Tower (10-35) degrees Submission | 2 | F-MA35 | E000 | 00E2 | E000F-MA3500E2
5656 | 5656 | 5656 | 5656 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Shop & Erection Drawings for F-MA35 Medium Angle Tower (10-35) degrees Review / Evaluation | 3 | F-MA35 | E000 | 00E3 | E000F-MA3500E3
5657 | 5657 | 5657 | 5657 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Shop & Erection Drawings for F-MA35 Medium Angle Tower (10-35) degrees Approval with Comments | 4 | F-MA35 | E000 | 00E4 | E000F-MA3500E4
5658 | 5658 | 5658 | 5658 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Shop & Erection Drawings for F-MA35 Medium Angle Tower (10-35) degrees FINAL Approval | 5 | F-MA35 | E000 | 00E5 | E000F-MA3500E5
5659 | 5659 | 5659 | 5659 | SA24M005 | Shop & Erection Drawings for F-LA60 Large Angle Tower (35-60) degrees |  | 5 | -1 | 0 |  |  | X
5660 | 5660 | 5660 | 5660 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Shop & Erection Drawings for F-LA60 Large Angle Tower (35-60) degrees Drafting / Preparation | 1 | F-LA60 | C000 | 00C1 | C000F-LA6000C1
5661 | 5661 | 5661 | 5661 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Shop & Erection Drawings for F-LA60 Large Angle Tower (35-60) degrees Submission | 2 | F-LA60 | C000 | 00C2 | C000F-LA6000C2
5662 | 5662 | 5662 | 5662 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Shop & Erection Drawings for F-LA60 Large Angle Tower (35-60) degrees Review / Evaluation | 3 | F-LA60 | C000 | 00C3 | C000F-LA6000C3
5663 | 5663 | 5663 | 5663 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Shop & Erection Drawings for F-LA60 Large Angle Tower (35-60) degrees Approval with Comments | 4 | F-LA60 | C000 | 00C4 | C000F-LA6000C4
5664 | 5664 | 5664 | 5664 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Shop & Erection Drawings for F-LA60 Large Angle Tower (35-60) degrees FINAL Approval | 5 | F-LA60 | C000 | 00C5 | C000F-LA6000C5
5665 | 5665 | 5665 | 5665 | SA24M005 | Shop & Erection Drawings for F-HA90 Heavy Angle Tower (60-90) degrees |  | 5 | -1 | 0 |  |  | X
5666 | 5666 | 5666 | 5666 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Shop & Erection Drawings for F-HA90 Heavy Angle Tower (60-90) degrees Drafting / Preparation | 1 | CSHAT | E000 | 00E1 | E000CSHAT00E1
5667 | 5667 | 5667 | 5667 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Shop & Erection Drawings for F-HA90 Heavy Angle Tower (60-90) degrees Submission | 2 | CSHAT | E000 | 00E2 | E000CSHAT00E2
5668 | 5668 | 5668 | 5668 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Shop & Erection Drawings for F-HA90 Heavy Angle Tower (60-90) degrees Review / Evaluation | 3 | CSHAT | E000 | 00E3 | E000CSHAT00E3
5669 | 5669 | 5669 | 5669 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Shop & Erection Drawings for F-HA90 Heavy Angle Tower (60-90) degrees Approval with Comments | 4 | CSHAT | E000 | 00E4 | E000CSHAT00E4
5670 | 5670 | 5670 | 5670 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Shop & Erection Drawings for F-HA90 Heavy Angle Tower (60-90) degrees FINAL Approval | 5 | CSHAT | E000 | 00E5 | E000CSHAT00E5
5671 | 5671 | 5671 | 5671 | SA24M005 | Shop & Erection Drawings for F-DE30 Dead- End/Terminal Tower (0-30) degrees |  | 5 | -1 | 0 |  |  | X
5672 | 5672 | 5672 | 5672 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Shop & Erection Drawings for F-DE30 Dead- End/Terminal Tower (0-30) degrees Drafting / Preparation | 1 | C0DET | E000 | 00E1 | E000C0DET00E1
5673 | 5673 | 5673 | 5673 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Shop & Erection Drawings for F-DE30 Dead- End/Terminal Tower (0-30) degrees Submission | 2 | C0DET | E000 | 00E2 | E000C0DET00E2
5674 | 5674 | 5674 | 5674 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Shop & Erection Drawings for F-DE30 Dead- End/Terminal Tower (0-30) degrees Review / Evaluation | 3 | C0DET | E000 | 00E3 | E000C0DET00E3
5675 | 5675 | 5675 | 5675 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Shop & Erection Drawings for F-DE30 Dead- End/Terminal Tower (0-30) degrees Approval with Comments | 4 | C0DET | E000 | 00E4 | E000C0DET00E4
5676 | 5676 | 5676 | 5676 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Shop & Erection Drawings for F-DE30 Dead- End/Terminal Tower (0-30) degrees FINAL Approval | 5 | C0DET | E000 | 00E5 | E000C0DET00E5
5677 | 5677 | 5677 | 5677 | SA24M005 | Shop & Erection Drawings for F-AN3 Anchor Tower (0- 3) degrees |  | 5 | -1 | 0 |  |  | X
5678 | 5678 | 5678 | 5678 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Shop & Erection Drawings for F-AN3 Anchor Tower (0- 3) degrees Drafting / Preparation | 1 | CSERF | E000 | 00E1 | E000CSERF00E1
5679 | 5679 | 5679 | 5679 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Shop & Erection Drawings for F-AN3 Anchor Tower (0- 3) degrees Submission | 2 | CSERF | E000 | 00E2 | E000CSERF00E2
5680 | 5680 | 5680 | 5680 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Shop & Erection Drawings for F-AN3 Anchor Tower (0- 3) degrees Review / Evaluation | 3 | CSERF | E000 | 00E3 | E000CSERF00E3
5681 | 5681 | 5681 | 5681 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Shop & Erection Drawings for F-AN3 Anchor Tower (0- 3) degrees Approval with Comments | 4 | CSERF | E000 | 00E4 | E000CSERF00E4
5682 | 5682 | 5682 | 5682 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Shop & Erection Drawings for F-AN3 Anchor Tower (0- 3) degrees FINAL Approval | 5 | CSERF | E000 | 00E5 | E000CSERF00E5
5683 | 5683 | 5683 | 5683 | SA24M005 | Shop & Erection Drawings for F-TR3 Transposition Tower (0-3) degrees |  | 5 | -1 | 0 |  |  | X
5684 | 5684 | 5684 | 5684 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Shop & Erection Drawings for F-TR3 Transposition Tower (0-3) degrees Drafting / Preparation | 1 | C0FTR | C000 | 00C1 | C000C0FTR00C1
5685 | 5685 | 5685 | 5685 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Shop & Erection Drawings for F-TR3 Transposition Tower (0-3) degrees Submission | 2 | C0FTR | C000 | 00C2 | C000C0FTR00C2
5686 | 5686 | 5686 | 5686 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Shop & Erection Drawings for F-TR3 Transposition Tower (0-3) degrees Review / Evaluation | 3 | C0FTR | C000 | 00C3 | C000C0FTR00C3
5687 | 5687 | 5687 | 5687 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Shop & Erection Drawings for F-TR3 Transposition Tower (0-3) degrees Approval with Comments | 4 | C0FTR | C000 | 00C4 | C000C0FTR00C4
5688 | 5688 | 5688 | 5688 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Shop & Erection Drawings for F-TR3 Transposition Tower (0-3) degrees FINAL Approval | 5 | C0FTR | C000 | 00C5 | C000C0FTR00C5
5689 | 5689 | 5689 | 5689 | SA24M005 | Stub & cleats + Stub setting template |  | 5 | -1 | 0 |  |  | X
5690 | 5690 | 5690 | 5690 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Stub & cleats + Stub setting template Drafting / Preparation | 1 | CSCB | E000 | 00E1 | E000CSCB00E1
5691 | 5691 | 5691 | 5691 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Stub & cleats + Stub setting template Submission | 2 | CSCB | E000 | 00E2 | E000CSCB00E2
5692 | 5692 | 5692 | 5692 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Stub & cleats + Stub setting template Review / Evaluation | 3 | CSCB | E000 | 00E3 | E000CSCB00E3
5693 | 5693 | 5693 | 5693 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Stub & cleats + Stub setting template Approval with Comments | 4 | CSCB | E000 | 00E4 | E000CSCB00E4
5694 | 5694 | 5694 | 5694 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Stub & cleats + Stub setting template FINAL Approval | 5 | CSCB | E000 | 00E5 | E000CSCB00E5
5695 | 5695 | 5695 | 5695 | SA24M005 | Detail of anti-theft bolt for all tower types |  | 5 | -1 | 0 |  |  | X
5696 | 5696 | 5696 | 5696 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Detail of anti-theft bolt for all tower types Drafting / Preparation | 1 | C0ATB | E000 | 00E1 | E000C0ATB00E1
5697 | 5697 | 5697 | 5697 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Detail of anti-theft bolt for all tower types Submission | 2 | C0ATB | E000 | 00E2 | E000C0ATB00E2
5698 | 5698 | 5698 | 5698 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Detail of anti-theft bolt for all tower types Review / Evaluation | 3 | C0ATB | E000 | 00E3 | E000C0ATB00E3
5699 | 5699 | 5699 | 5699 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Detail of anti-theft bolt for all tower types Approval with Comments | 4 | C0ATB | E000 | 00E4 | E000C0ATB00E4
5700 | 5700 | 5700 | 5700 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Detail of anti-theft bolt for all tower types FINAL Approval | 5 | C0ATB | E000 | 00E5 | E000C0ATB00E5
5701 | 5701 | 5701 | 5701 | SA24M005 | Details of step bolt for all tower types |  | 5 | -1 | 0 |  |  | X
5702 | 5702 | 5702 | 5702 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Details of step bolt for all tower types Drafting / Preparation | 1 | CSTEPB | E000 | 00E1 | E000CSTEPB00E1
5703 | 5703 | 5703 | 5703 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Details of step bolt for all tower types Submission | 2 | CSTEPB | E000 | 00E2 | E000CSTEPB00E2
5704 | 5704 | 5704 | 5704 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Details of step bolt for all tower types Review / Evaluation | 3 | CSTEPB | E000 | 00E3 | E000CSTEPB00E3
5705 | 5705 | 5705 | 5705 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Details of step bolt for all tower types Approval with Comments | 4 | CSTEPB | E000 | 00E4 | E000CSTEPB00E4
5706 | 5706 | 5706 | 5706 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Details of step bolt for all tower types FINAL Approval | 5 | CSTEPB | E000 | 00E5 | E000CSTEPB00E5
5707 | 5707 | 5707 | 5707 | SA24M005 | Anti Climbing Barrier/Device Details |  | 5 | -1 | 0 |  |  | X
5708 | 5708 | 5708 | 5708 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Anti Climbing Barrier/Device Details Drafting / Preparation | 1 | CBARB | E000 | 00E1 | E000CBARB00E1
5709 | 5709 | 5709 | 5709 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Anti Climbing Barrier/Device Details Submission | 2 | CBARB | E000 | 00E2 | E000CBARB00E2
5710 | 5710 | 5710 | 5710 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Anti Climbing Barrier/Device Details Review / Evaluation | 3 | CBARB | E000 | 00E3 | E000CBARB00E3
5711 | 5711 | 5711 | 5711 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Anti Climbing Barrier/Device Details Approval with Comments | 4 | CBARB | E000 | 00E4 | E000CBARB00E4
5712 | 5712 | 5712 | 5712 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Anti Climbing Barrier/Device Details FINAL Approval | 5 | CBARB | E000 | 00E5 | E000CBARB00E5
5713 | 5713 | 5713 | 5713 | SA24M005 | Foundation test for Structures |  | 5 | -1 | 0 |  |  | X
5714 | 5714 | 5714 | 5714 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Foundation test for Structures Drafting / Preparation | 1 | CFSTR | E000 | 00E1 | E000#Ergn00E1
5715 | 5715 | 5715 | 5715 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Foundation test for Structures Submission | 2 | CFSTR | E000 | 00E2 | E000#Ergn00E2
5716 | 5716 | 5716 | 5716 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Foundation test for Structures Review / Evaluation | 3 | CFSTR | E000 | 00E3 | E000#Ergn00E3
5717 | 5717 | 5717 | 5717 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Foundation test for Structures Approval with Comments | 4 | CFSTR | E000 | 00E4 | E000#Ergn00E4
5718 | 5718 | 5718 | 5718 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Basic Design (Phase- I) Civil Foundation test for Structures FINAL Approval | 5 | CFSTR | E000 | 00E5 | E000#Ergn00E5
5719 | 5719 | 5719 | 5719 | SA24M005 | Linewise Design (Phase- II) |  | 3 | -1 | 0 |  |  | X | E000#Ergn
5720 | 5720 | 5720 | 5720 | SA24M005 | Electrical |  | 4 | -1 | 0 |  |  | X | E000#Ergn
5721 | 5721 | 5721 | 5721 | SA24M005 | Transmission Line Route Plan - Route-A (9061-9010/9029) |  | 5 | -1 | 0 |  |  | X | E000#Ergn
5722 | 5722 | 5722 | 5722 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Transmission Line Route Plan - Route-A (9061-9010/9029) Drafting / Preparation | 1 | E0TRL | E000 | 00E1 | E000#gpxH00E1
5723 | 5723 | 5723 | 5723 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Transmission Line Route Plan - Route-A (9061-9010/9029) Submission | 2 | E0TRL | E000 | 00E2 | E000#gpxH00E2
5724 | 5724 | 5724 | 5724 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Transmission Line Route Plan - Route-A (9061-9010/9029) Review / Evaluation | 3 | E0TRL | E000 | 00E3 | E000#gpxH00E3
5725 | 5725 | 5725 | 5725 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Transmission Line Route Plan - Route-A (9061-9010/9029) Approval with Comments | 4 | E0TRL | E000 | 00E4 | E000#gpxH00E4
5726 | 5726 | 5726 | 5726 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Transmission Line Route Plan - Route-A (9061-9010/9029) FINAL Approval | 5 | E0TRL | E000 | 00E5 | E000#gpxH00E5
5727 | 5727 | 5727 | 5727 | SA24M005 | Transmission Line Route Plan - Route-B (9061-9010) |  | 5 | -1 | 0 |  |  | X | E000#gpxH
5728 | 5728 | 5728 | 5728 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Transmission Line Route Plan - Route-B (9061-9010) Drafting / Preparation | 1 | E0TRL | E000 | 00E1 | E000#Stmb00E1
5729 | 5729 | 5729 | 5729 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Transmission Line Route Plan - Route-B (9061-9010) Submission | 2 | E0TRL | E000 | 00E2 | E000#Stmb00E2
5730 | 5730 | 5730 | 5730 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Transmission Line Route Plan - Route-B (9061-9010) Review / Evaluation | 3 | E0TRL | E000 | 00E3 | E000#Stmb00E3
5731 | 5731 | 5731 | 5731 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Transmission Line Route Plan - Route-B (9061-9010) Approval with Comments | 4 | E0TRL | E000 | 00E4 | E000#Stmb00E4
5732 | 5732 | 5732 | 5732 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Transmission Line Route Plan - Route-B (9061-9010) FINAL Approval | 5 | E0TRL | E000 | 00E5 | E000#Stmb00E5
5733 | 5733 | 5733 | 5733 | SA24M005 | Transmission Line Route Plan - Route-C (9061-9006/9032) |  | 5 | -1 | 0 |  |  | X | E000#Stmb
5734 | 5734 | 5734 | 5734 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Transmission Line Route Plan - Route-C (9061-9006/9032) Drafting / Preparation | 1 | E0TRL | E000 | 00E1 | E000#WPza00E1
5735 | 5735 | 5735 | 5735 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Transmission Line Route Plan - Route-C (9061-9006/9032) Submission | 2 | E0TRL | E000 | 00E2 | E000#WPza00E2
5736 | 5736 | 5736 | 5736 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Transmission Line Route Plan - Route-C (9061-9006/9032) Review / Evaluation | 3 | E0TRL | E000 | 00E3 | E000#WPza00E3
5737 | 5737 | 5737 | 5737 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Transmission Line Route Plan - Route-C (9061-9006/9032) Approval with Comments | 4 | E0TRL | E000 | 00E4 | E000#WPza00E4
5738 | 5738 | 5738 | 5738 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Transmission Line Route Plan - Route-C (9061-9006/9032) FINAL Approval | 5 | E0TRL | E000 | 00E5 | E000#WPza00E5
5739 | 5739 | 5739 | 5739 | SA24M005 | Transmission Line Route Plan - Route-D (9061-9064) |  | 5 | -1 | 0 |  |  | X | E000#WPza
5740 | 5740 | 5740 | 5740 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Transmission Line Route Plan - Route-D (9061-9064) Drafting / Preparation | 1 | E0TRL | E000 | 00E1 | E000#FvFb00E1
5741 | 5741 | 5741 | 5741 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Transmission Line Route Plan - Route-D (9061-9064) Submission | 2 | E0TRL | E000 | 00E2 | E000#FvFb00E2
5742 | 5742 | 5742 | 5742 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Transmission Line Route Plan - Route-D (9061-9064) Review / Evaluation | 3 | E0TRL | E000 | 00E3 | E000#FvFb00E3
5743 | 5743 | 5743 | 5743 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Transmission Line Route Plan - Route-D (9061-9064) Approval with Comments | 4 | E0TRL | E000 | 00E4 | E000#FvFb00E4
5744 | 5744 | 5744 | 5744 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Transmission Line Route Plan - Route-D (9061-9064) FINAL Approval | 5 | E0TRL | E000 | 00E5 | E000#FvFb00E5
5745 | 5745 | 5745 | 5745 | SA24M005 | Transmission Line Circuit IdentificationTransposition and Phasing ArrangementPhase Sequence Diagram |  | 5 | -1 | 0 |  |  | X | E000#FvFb
5746 | 5746 | 5746 | 5746 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Transmission Line Circuit IdentificationTransposition and Phasing ArrangementPhase Sequence Diagram Drafting / Preparation | 1 | E0TLC | E000 | 00E1 | E000E0TLC00E1
5747 | 5747 | 5747 | 5747 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Transmission Line Circuit IdentificationTransposition and Phasing ArrangementPhase Sequence Diagram Submission | 2 | E0TLC | E000 | 00E2 | E000E0TLC00E2
5748 | 5748 | 5748 | 5748 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Transmission Line Circuit IdentificationTransposition and Phasing ArrangementPhase Sequence Diagram Review / Evaluation | 3 | E0TLC | E000 | 00E3 | E000E0TLC00E3
5749 | 5749 | 5749 | 5749 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Transmission Line Circuit IdentificationTransposition and Phasing ArrangementPhase Sequence Diagram Approval with Comments | 4 | E0TLC | E000 | 00E4 | E000E0TLC00E4
5750 | 5750 | 5750 | 5750 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Transmission Line Circuit IdentificationTransposition and Phasing ArrangementPhase Sequence Diagram FINAL Approval | 5 | E0TLC | E000 | 00E5 | E000E0TLC00E5
5751 | 5751 | 5751 | 5751 | SA24M005 | Key Map Showing OPGW joint Boxes Locations along with Splicing Arrangement |  | 5 | -1 | 0 |  |  | X
5752 | 5752 | 5752 | 5752 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Key Map Showing OPGW joint Boxes Locations along with Splicing Arrangement Drafting / Preparation | 1 | E0KMB | E000 | 00E1 | E000E0KMB00E1
5753 | 5753 | 5753 | 5753 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Key Map Showing OPGW joint Boxes Locations along with Splicing Arrangement Submission | 2 | E0KMB | E000 | 00E2 | E000E0KMB00E2
5754 | 5754 | 5754 | 5754 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Key Map Showing OPGW joint Boxes Locations along with Splicing Arrangement Review / Evaluation | 3 | E0KMB | E000 | 00E3 | E000E0KMB00E3
5755 | 5755 | 5755 | 5755 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Key Map Showing OPGW joint Boxes Locations along with Splicing Arrangement Approval with Comments | 4 | E0KMB | E000 | 00E4 | E000E0KMB00E4
5756 | 5756 | 5756 | 5756 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Key Map Showing OPGW joint Boxes Locations along with Splicing Arrangement FINAL Approval | 5 | E0KMB | E000 | 00E5 | E000E0KMB00E5
5757 | 5757 | 5757 | 5757 | SA24M005 | Structure Height Templates with Conductor Attachment Heights |  | 5 | -1 | 0 |  |  | X
5758 | 5758 | 5758 | 5758 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Structure Height Templates with Conductor Attachment Heights Drafting / Preparation | 1 | E0STR | E000 | 00E1 | E000#GtlJ00E1
5759 | 5759 | 5759 | 5759 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Structure Height Templates with Conductor Attachment Heights Submission | 2 | E0STR | E000 | 00E2 | E000#GtlJ00E2
5760 | 5760 | 5760 | 5760 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Structure Height Templates with Conductor Attachment Heights Review / Evaluation | 3 | E0STR | E000 | 00E3 | E000#GtlJ00E3
5761 | 5761 | 5761 | 5761 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Structure Height Templates with Conductor Attachment Heights Approval with Comments | 4 | E0STR | E000 | 00E4 | E000#GtlJ00E4
5762 | 5762 | 5762 | 5762 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Structure Height Templates with Conductor Attachment Heights FINAL Approval | 5 | E0STR | E000 | 00E5 | E000#GtlJ00E5
5763 | 5763 | 5763 | 5763 | SA24M005 | Sag Template Curves |  | 5 | -1 | 0 |  |  | X | E000#GtlJ
5764 | 5764 | 5764 | 5764 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Sag Template Curves Drafting / Preparation | 1 | ESAGT | E000 | 00E1 | E000ESAGT00E1
5765 | 5765 | 5765 | 5765 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Sag Template Curves Submission | 2 | ESAGT | E000 | 00E2 | E000ESAGT00E2
5766 | 5766 | 5766 | 5766 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Sag Template Curves Review / Evaluation | 3 | ESAGT | E000 | 00E3 | E000ESAGT00E3
5767 | 5767 | 5767 | 5767 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Sag Template Curves Approval with Comments | 4 | ESAGT | E000 | 00E4 | E000ESAGT00E4
5768 | 5768 | 5768 | 5768 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Sag Template Curves FINAL Approval | 5 | ESAGT | E000 | 00E5 | E000ESAGT00E5
5769 | 5769 | 5769 | 5769 | SA24M005 | Plan and Profile with Spotted Structures -Route-A (9061-9010/9029) |  | 5 | -1 | 0 |  |  | X
5770 | 5770 | 5770 | 5770 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Plan and Profile with Spotted Structures -Route-A (9061-9010/9029) Drafting / Preparation | 1 | E0PSS | E000 | 00E1 | E000#dMUA00E1
5771 | 5771 | 5771 | 5771 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Plan and Profile with Spotted Structures -Route-A (9061-9010/9029) Submission | 2 | E0PSS | E000 | 00E2 | E000#dMUA00E2
5772 | 5772 | 5772 | 5772 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Plan and Profile with Spotted Structures -Route-A (9061-9010/9029) Review / Evaluation | 3 | E0PSS | E000 | 00E3 | E000#dMUA00E3
5773 | 5773 | 5773 | 5773 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Plan and Profile with Spotted Structures -Route-A (9061-9010/9029) Approval with Comments | 4 | E0PSS | E000 | 00E4 | E000#dMUA00E4
5774 | 5774 | 5774 | 5774 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Plan and Profile with Spotted Structures -Route-A (9061-9010/9029) FINAL Approval | 5 | E0PSS | E000 | 00E5 | E000#dMUA00E5
5775 | 5775 | 5775 | 5775 | SA24M005 | Plan and Profile with Spotted Structures -Route-B (9061-9010) |  | 5 | -1 | 0 |  |  | X | E000#dMUA
5776 | 5776 | 5776 | 5776 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Plan and Profile with Spotted Structures -Route-B (9061-9010) Drafting / Preparation | 1 | E0PSS | E000 | 00E1 | E000#IVMw00E1
5777 | 5777 | 5777 | 5777 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Plan and Profile with Spotted Structures -Route-B (9061-9010) Submission | 2 | E0PSS | E000 | 00E2 | E000#IVMw00E2
5778 | 5778 | 5778 | 5778 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Plan and Profile with Spotted Structures -Route-B (9061-9010) Review / Evaluation | 3 | E0PSS | E000 | 00E3 | E000#IVMw00E3
5779 | 5779 | 5779 | 5779 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Plan and Profile with Spotted Structures -Route-B (9061-9010) Approval with Comments | 4 | E0PSS | E000 | 00E4 | E000#IVMw00E4
5780 | 5780 | 5780 | 5780 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Plan and Profile with Spotted Structures -Route-B (9061-9010) FINAL Approval | 5 | E0PSS | E000 | 00E5 | E000#IVMw00E5
5781 | 5781 | 5781 | 5781 | SA24M005 | Plan and Profile with Spotted Structures -Route-C (9061-9006/9032) |  | 5 | -1 | 0 |  |  | X | E000#IVMw
5782 | 5782 | 5782 | 5782 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Plan and Profile with Spotted Structures -Route-C (9061-9006/9032) Drafting / Preparation | 1 | E0PSS | E000 | 00E1 | E000#oLKS00E1
5783 | 5783 | 5783 | 5783 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Plan and Profile with Spotted Structures -Route-C (9061-9006/9032) Submission | 2 | E0PSS | E000 | 00E2 | E000#oLKS00E2
5784 | 5784 | 5784 | 5784 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Plan and Profile with Spotted Structures -Route-C (9061-9006/9032) Review / Evaluation | 3 | E0PSS | E000 | 00E3 | E000#oLKS00E3
5785 | 5785 | 5785 | 5785 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Plan and Profile with Spotted Structures -Route-C (9061-9006/9032) Approval with Comments | 4 | E0PSS | E000 | 00E4 | E000#oLKS00E4
5786 | 5786 | 5786 | 5786 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Plan and Profile with Spotted Structures -Route-C (9061-9006/9032) FINAL Approval | 5 | E0PSS | E000 | 00E5 | E000#oLKS00E5
5787 | 5787 | 5787 | 5787 | SA24M005 | Plan and Profile with Spotted Structures -Route-D (9061-9064) |  | 5 | -1 | 0 |  |  | X | E000#oLKS
5788 | 5788 | 5788 | 5788 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Plan and Profile with Spotted Structures -Route-D (9061-9064) Drafting / Preparation | 1 | EPLAN | E000 | 00E1 | E000EPLAN00E1
5789 | 5789 | 5789 | 5789 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Plan and Profile with Spotted Structures -Route-D (9061-9064) Submission | 2 | EPLAN | E000 | 00E2 | E000EPLAN00E2
5790 | 5790 | 5790 | 5790 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Plan and Profile with Spotted Structures -Route-D (9061-9064) Review / Evaluation | 3 | EPLAN | E000 | 00E3 | E000EPLAN00E3
5791 | 5791 | 5791 | 5791 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Plan and Profile with Spotted Structures -Route-D (9061-9064) Approval with Comments | 4 | EPLAN | E000 | 00E4 | E000EPLAN00E4
5792 | 5792 | 5792 | 5792 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Plan and Profile with Spotted Structures -Route-D (9061-9064) FINAL Approval | 5 | EPLAN | E000 | 00E5 | E000EPLAN00E5
5793 | 5793 | 5793 | 5793 | SA24M005 | Structure List Route-A (9061-9010/9029) |  | 5 | -1 | 0 |  |  | X
5794 | 5794 | 5794 | 5794 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Structure List Route-A (9061-9010/9029) Drafting / Preparation | 1 | E0STR | E000 | 00E1 | E000#Qqwq00E1
5795 | 5795 | 5795 | 5795 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Structure List Route-A (9061-9010/9029) Submission | 2 | E0STR | E000 | 00E2 | E000#Qqwq00E2
5796 | 5796 | 5796 | 5796 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Structure List Route-A (9061-9010/9029) Review / Evaluation | 3 | E0STR | E000 | 00E3 | E000#Qqwq00E3
5797 | 5797 | 5797 | 5797 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Structure List Route-A (9061-9010/9029) Approval with Comments | 4 | E0STR | E000 | 00E4 | E000#Qqwq00E4
5798 | 5798 | 5798 | 5798 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Structure List Route-A (9061-9010/9029) FINAL Approval | 5 | E0STR | E000 | 00E5 | E000#Qqwq00E5
5799 | 5799 | 5799 | 5799 | SA24M005 | Structure List Route-B (9061-9010) |  | 5 | -1 | 0 |  |  | X | E000#Qqwq
5800 | 5800 | 5800 | 5800 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Structure List Route-B (9061-9010) Drafting / Preparation | 1 | E0STR | E000 | 00E1 | E000#tWeN00E1
5801 | 5801 | 5801 | 5801 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Structure List Route-B (9061-9010) Submission | 2 | E0STR | E000 | 00E2 | E000#tWeN00E2
5802 | 5802 | 5802 | 5802 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Structure List Route-B (9061-9010) Review / Evaluation | 3 | E0STR | E000 | 00E3 | E000#tWeN00E3
5803 | 5803 | 5803 | 5803 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Structure List Route-B (9061-9010) Approval with Comments | 4 | E0STR | E000 | 00E4 | E000#tWeN00E4
5804 | 5804 | 5804 | 5804 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Structure List Route-B (9061-9010) FINAL Approval | 5 | E0STR | E000 | 00E5 | E000#tWeN00E5
5805 | 5805 | 5805 | 5805 | SA24M005 | Structure List Route-C (9061-9006/9032) |  | 5 | -1 | 0 |  |  | X | E000#tWeN
5806 | 5806 | 5806 | 5806 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Structure List Route-C (9061-9006/9032) Drafting / Preparation | 1 | E0STR | E000 | 00E1 | E000#WObP00E1
5807 | 5807 | 5807 | 5807 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Structure List Route-C (9061-9006/9032) Submission | 2 | E0STR | E000 | 00E2 | E000#WObP00E2
5808 | 5808 | 5808 | 5808 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Structure List Route-C (9061-9006/9032) Review / Evaluation | 3 | E0STR | E000 | 00E3 | E000#WObP00E3
5809 | 5809 | 5809 | 5809 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Structure List Route-C (9061-9006/9032) Approval with Comments | 4 | E0STR | E000 | 00E4 | E000#WObP00E4
5810 | 5810 | 5810 | 5810 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Structure List Route-C (9061-9006/9032) FINAL Approval | 5 | E0STR | E000 | 00E5 | E000#WObP00E5
5811 | 5811 | 5811 | 5811 | SA24M005 | Structure List Route-D (9061-9064) |  | 5 | -1 | 0 |  |  | X | E000#WObP
5812 | 5812 | 5812 | 5812 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Structure List Route-D (9061-9064) Drafting / Preparation | 1 | E0STR | E000 | 00E1 | E000#TpJu00E1
5813 | 5813 | 5813 | 5813 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Structure List Route-D (9061-9064) Submission | 2 | E0STR | E000 | 00E2 | E000#TpJu00E2
5814 | 5814 | 5814 | 5814 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Structure List Route-D (9061-9064) Review / Evaluation | 3 | E0STR | E000 | 00E3 | E000#TpJu00E3
5815 | 5815 | 5815 | 5815 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Structure List Route-D (9061-9064) Approval with Comments | 4 | E0STR | E000 | 00E4 | E000#TpJu00E4
5816 | 5816 | 5816 | 5816 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Structure List Route-D (9061-9064) FINAL Approval | 5 | E0STR | E000 | 00E5 | E000#TpJu00E5
5817 | 5817 | 5817 | 5817 | SA24M005 | Stringing Charts - from Route-A (9061-9010/9029) |  | 5 | -1 | 0 |  |  | X | E000#TpJu
5818 | 5818 | 5818 | 5818 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Stringing Charts - from Route-A (9061-9010/9029) Drafting / Preparation | 1 | E0STR | E000 | 00E1 | E000#JxoX00E1
5819 | 5819 | 5819 | 5819 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Stringing Charts - from Route-A (9061-9010/9029) Submission | 2 | E0STR | E000 | 00E2 | E000#JxoX00E2
5820 | 5820 | 5820 | 5820 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Stringing Charts - from Route-A (9061-9010/9029) Review / Evaluation | 3 | E0STR | E000 | 00E3 | E000#JxoX00E3
5821 | 5821 | 5821 | 5821 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Stringing Charts - from Route-A (9061-9010/9029) Approval with Comments | 4 | E0STR | E000 | 00E4 | E000#JxoX00E4
5822 | 5822 | 5822 | 5822 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Stringing Charts - from Route-A (9061-9010/9029) FINAL Approval | 5 | E0STR | E000 | 00E5 | E000#JxoX00E5
5823 | 5823 | 5823 | 5823 | SA24M005 | Stringing Charts - from Route-B (9061-9010) |  | 5 | -1 | 0 |  |  | X | E000#JxoX
5824 | 5824 | 5824 | 5824 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Stringing Charts - from Route-B (9061-9010) Drafting / Preparation | 1 | E0STR | E000 | 00E1 | E000#xobK00E1
5825 | 5825 | 5825 | 5825 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Stringing Charts - from Route-B (9061-9010) Submission | 2 | E0STR | E000 | 00E2 | E000#xobK00E2
5826 | 5826 | 5826 | 5826 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Stringing Charts - from Route-B (9061-9010) Review / Evaluation | 3 | E0STR | E000 | 00E3 | E000#xobK00E3
5827 | 5827 | 5827 | 5827 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Stringing Charts - from Route-B (9061-9010) Approval with Comments | 4 | E0STR | E000 | 00E4 | E000#xobK00E4
5828 | 5828 | 5828 | 5828 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Stringing Charts - from Route-B (9061-9010) FINAL Approval | 5 | E0STR | E000 | 00E5 | E000#xobK00E5
5829 | 5829 | 5829 | 5829 | SA24M005 | Stringing Charts - from Route-C (9061-9006/9032) |  | 5 | -1 | 0 |  |  | X | E000#xobK
5830 | 5830 | 5830 | 5830 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Stringing Charts - from Route-C (9061-9006/9032) Drafting / Preparation | 1 | E0STR | E000 | 00E1 | E000#Swbj00E1
5831 | 5831 | 5831 | 5831 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Stringing Charts - from Route-C (9061-9006/9032) Submission | 2 | E0STR | E000 | 00E2 | E000#Swbj00E2
5832 | 5832 | 5832 | 5832 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Stringing Charts - from Route-C (9061-9006/9032) Review / Evaluation | 3 | E0STR | E000 | 00E3 | E000#Swbj00E3
5833 | 5833 | 5833 | 5833 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Stringing Charts - from Route-C (9061-9006/9032) Approval with Comments | 4 | E0STR | E000 | 00E4 | E000#Swbj00E4
5834 | 5834 | 5834 | 5834 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Stringing Charts - from Route-C (9061-9006/9032) FINAL Approval | 5 | E0STR | E000 | 00E5 | E000#Swbj00E5
5835 | 5835 | 5835 | 5835 | SA24M005 | Stringing Charts - from -Route-D (9061-9064) |  | 5 | -1 | 0 |  |  | X | E000#Swbj
5836 | 5836 | 5836 | 5836 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Stringing Charts - from -Route-D (9061-9064) Drafting / Preparation | 1 | E0STR | E000 | 00E1 | E000#LWpi00E1
5837 | 5837 | 5837 | 5837 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Stringing Charts - from -Route-D (9061-9064) Submission | 2 | E0STR | E000 | 00E2 | E000#LWpi00E2
5838 | 5838 | 5838 | 5838 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Stringing Charts - from -Route-D (9061-9064) Review / Evaluation | 3 | E0STR | E000 | 00E3 | E000#LWpi00E3
5839 | 5839 | 5839 | 5839 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Stringing Charts - from -Route-D (9061-9064) Approval with Comments | 4 | E0STR | E000 | 00E4 | E000#LWpi00E4
5840 | 5840 | 5840 | 5840 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Stringing Charts - from -Route-D (9061-9064) FINAL Approval | 5 | E0STR | E000 | 00E5 | E000#LWpi00E5
5841 | 5841 | 5841 | 5841 | SA24M005 | Soil Resistivity Test Report -Route-A (9061-9010/9029) |  | 5 | -1 | 0 |  |  | X | E000#LWpi
5842 | 5842 | 5842 | 5842 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Soil Resistivity Test Report -Route-A (9061-9010/9029) Drafting / Preparation | 1 | E0STR | E000 | 00E1 | E000#LtTS00E1
5843 | 5843 | 5843 | 5843 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Soil Resistivity Test Report -Route-A (9061-9010/9029) Submission | 2 | E0STR | E000 | 00E2 | E000#LtTS00E2
5844 | 5844 | 5844 | 5844 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Soil Resistivity Test Report -Route-A (9061-9010/9029) Review / Evaluation | 3 | E0STR | E000 | 00E3 | E000#LtTS00E3
5845 | 5845 | 5845 | 5845 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Soil Resistivity Test Report -Route-A (9061-9010/9029) Approval with Comments | 4 | E0STR | E000 | 00E4 | E000#LtTS00E4
5846 | 5846 | 5846 | 5846 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Soil Resistivity Test Report -Route-A (9061-9010/9029) FINAL Approval | 5 | E0STR | E000 | 00E5 | E000#LtTS00E5
5847 | 5847 | 5847 | 5847 | SA24M005 | Soil Resistivity Test Report -Route-B (9061-9010) |  | 5 | -1 | 0 |  |  | X | E000#LtTS
5848 | 5848 | 5848 | 5848 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Soil Resistivity Test Report -Route-B (9061-9010) Drafting / Preparation | 1 | E0STR | E000 | 00E1 | E000#JbWf00E1
5849 | 5849 | 5849 | 5849 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Soil Resistivity Test Report -Route-B (9061-9010) Submission | 2 | E0STR | E000 | 00E2 | E000#JbWf00E2
5850 | 5850 | 5850 | 5850 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Soil Resistivity Test Report -Route-B (9061-9010) Review / Evaluation | 3 | E0STR | E000 | 00E3 | E000#JbWf00E3
5851 | 5851 | 5851 | 5851 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Soil Resistivity Test Report -Route-B (9061-9010) Approval with Comments | 4 | E0STR | E000 | 00E4 | E000#JbWf00E4
5852 | 5852 | 5852 | 5852 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Soil Resistivity Test Report -Route-B (9061-9010) FINAL Approval | 5 | E0STR | E000 | 00E5 | E000#JbWf00E5
5853 | 5853 | 5853 | 5853 | SA24M005 | Soil Resistivity Test Report -Route-C (9061-9006/9032) |  | 5 | -1 | 0 |  |  | X | E000#JbWf
5854 | 5854 | 5854 | 5854 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Soil Resistivity Test Report -Route-C (9061-9006/9032) Drafting / Preparation | 1 | E0STR | E000 | 00E1 | E000#ZWnV00E1
5855 | 5855 | 5855 | 5855 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Soil Resistivity Test Report -Route-C (9061-9006/9032) Submission | 2 | E0STR | E000 | 00E2 | E000#ZWnV00E2
5856 | 5856 | 5856 | 5856 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Soil Resistivity Test Report -Route-C (9061-9006/9032) Review / Evaluation | 3 | E0STR | E000 | 00E3 | E000#ZWnV00E3
5857 | 5857 | 5857 | 5857 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Soil Resistivity Test Report -Route-C (9061-9006/9032) Approval with Comments | 4 | E0STR | E000 | 00E4 | E000#ZWnV00E4
5858 | 5858 | 5858 | 5858 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Soil Resistivity Test Report -Route-C (9061-9006/9032) FINAL Approval | 5 | E0STR | E000 | 00E5 | E000#ZWnV00E5
5859 | 5859 | 5859 | 5859 | SA24M005 | Soil Resistivity Test Report -Route-D (9061-9064) |  | 5 | -1 | 0 |  |  | X | E000#ZWnV
5860 | 5860 | 5860 | 5860 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Soil Resistivity Test Report -Route-D (9061-9064) Drafting / Preparation | 1 | E0STR | E000 | 00E1 | E000#kabj00E1
5861 | 5861 | 5861 | 5861 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Soil Resistivity Test Report -Route-D (9061-9064) Submission | 2 | E0STR | E000 | 00E2 | E000#kabj00E2
5862 | 5862 | 5862 | 5862 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Soil Resistivity Test Report -Route-D (9061-9064) Review / Evaluation | 3 | E0STR | E000 | 00E3 | E000#kabj00E3
5863 | 5863 | 5863 | 5863 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Soil Resistivity Test Report -Route-D (9061-9064) Approval with Comments | 4 | E0STR | E000 | 00E4 | E000#kabj00E4
5864 | 5864 | 5864 | 5864 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Electrical Soil Resistivity Test Report -Route-D (9061-9064) FINAL Approval | 5 | E0STR | E000 | 00E5 | E000#kabj00E5
5865 | 5865 | 5865 | 5865 | SA24M005 | Civil |  | 4 | -1 | 0 |  |  | X | E000#kabj
5866 | 5866 | 5866 | 5866 | SA24M005 | Borehole Location Plan -Route-A (9061-9010/9029) |  | 5 | -1 | 0 |  |  | X | E000#kabj
5867 | 5867 | 5867 | 5867 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Borehole Location Plan -Route-A (9061-9010/9029) Drafting / Preparation | 1 | CBORL | E000 | 00E1 | E000#vQve00E1
5868 | 5868 | 5868 | 5868 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Borehole Location Plan -Route-A (9061-9010/9029) Submission | 2 | CBORL | E000 | 00E2 | E000#vQve00E2
5869 | 5869 | 5869 | 5869 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Borehole Location Plan -Route-A (9061-9010/9029) Review / Evaluation | 3 | CBORL | E000 | 00E3 | E000#vQve00E3
5870 | 5870 | 5870 | 5870 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Borehole Location Plan -Route-A (9061-9010/9029) Approval with Comments | 4 | CBORL | E000 | 00E4 | E000#vQve00E4
5871 | 5871 | 5871 | 5871 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Borehole Location Plan -Route-A (9061-9010/9029) FINAL Approval | 5 | CBORL | E000 | 00E5 | E000#vQve00E5
5872 | 5872 | 5872 | 5872 | SA24M005 | Borehole Location Plan -Route-B (9061-9010) |  | 5 | -1 | 0 |  |  | X | E000#vQve
5873 | 5873 | 5873 | 5873 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Borehole Location Plan -Route-B (9061-9010) Drafting / Preparation | 1 | CBORL | E000 | 00E1 | E000#IUjq00E1
5874 | 5874 | 5874 | 5874 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Borehole Location Plan -Route-B (9061-9010) Submission | 2 | CBORL | E000 | 00E2 | E000#IUjq00E2
5875 | 5875 | 5875 | 5875 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Borehole Location Plan -Route-B (9061-9010) Review / Evaluation | 3 | CBORL | E000 | 00E3 | E000#IUjq00E3
5876 | 5876 | 5876 | 5876 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Borehole Location Plan -Route-B (9061-9010) Approval with Comments | 4 | CBORL | E000 | 00E4 | E000#IUjq00E4
5877 | 5877 | 5877 | 5877 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Borehole Location Plan -Route-B (9061-9010) FINAL Approval | 5 | CBORL | E000 | 00E5 | E000#IUjq00E5
5878 | 5878 | 5878 | 5878 | SA24M005 | Borehole Location Plan -Route-C (9061-9006/9032) |  | 5 | -1 | 0 |  |  | X | E000#IUjq
5879 | 5879 | 5879 | 5879 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Borehole Location Plan -Route-C (9061-9006/9032) Drafting / Preparation | 1 | CBORL | E000 | 00E1 | E000#hVlO00E1
5880 | 5880 | 5880 | 5880 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Borehole Location Plan -Route-C (9061-9006/9032) Submission | 2 | CBORL | E000 | 00E2 | E000#hVlO00E2
5881 | 5881 | 5881 | 5881 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Borehole Location Plan -Route-C (9061-9006/9032) Review / Evaluation | 3 | CBORL | E000 | 00E3 | E000#hVlO00E3
5882 | 5882 | 5882 | 5882 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Borehole Location Plan -Route-C (9061-9006/9032) Approval with Comments | 4 | CBORL | E000 | 00E4 | E000#hVlO00E4
5883 | 5883 | 5883 | 5883 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Borehole Location Plan -Route-C (9061-9006/9032) FINAL Approval | 5 | CBORL | E000 | 00E5 | E000#hVlO00E5
5884 | 5884 | 5884 | 5884 | SA24M005 | Borehole Location Plan -Route-D (9061-9064) |  | 5 | -1 | 0 |  |  | X | E000#hVlO
5885 | 5885 | 5885 | 5885 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Borehole Location Plan -Route-D (9061-9064) Drafting / Preparation | 1 | CBORL | E000 | 00E1 | E000#SOhE00E1
5886 | 5886 | 5886 | 5886 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Borehole Location Plan -Route-D (9061-9064) Submission | 2 | CBORL | E000 | 00E2 | E000#SOhE00E2
5887 | 5887 | 5887 | 5887 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Borehole Location Plan -Route-D (9061-9064) Review / Evaluation | 3 | CBORL | E000 | 00E3 | E000#SOhE00E3
5888 | 5888 | 5888 | 5888 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Borehole Location Plan -Route-D (9061-9064) Approval with Comments | 4 | CBORL | E000 | 00E4 | E000#SOhE00E4
5889 | 5889 | 5889 | 5889 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Borehole Location Plan -Route-D (9061-9064) FINAL Approval | 5 | CBORL | E000 | 00E5 | E000#SOhE00E5
5890 | 5890 | 5890 | 5890 | SA24M005 | Method Statement for Soil Investigation |  | 5 | -1 | 0 |  |  | X | E000#SOhE
5891 | 5891 | 5891 | 5891 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Method Statement for Soil Investigation Drafting / Preparation | 1 | CSISD | E000 | 00E1 | E000CSISD00E1
5892 | 5892 | 5892 | 5892 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Method Statement for Soil Investigation Submission | 2 | CSISD | E000 | 00E2 | E000CSISD00E2
5893 | 5893 | 5893 | 5893 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Method Statement for Soil Investigation Review / Evaluation | 3 | CSISD | E000 | 00E3 | E000CSISD00E3
5894 | 5894 | 5894 | 5894 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Method Statement for Soil Investigation Approval with Comments | 4 | CSISD | E000 | 00E4 | E000CSISD00E4
5895 | 5895 | 5895 | 5895 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Method Statement for Soil Investigation FINAL Approval | 5 | CSISD | E000 | 00E5 | E000CSISD00E5
5896 | 5896 | 5896 | 5896 | SA24M005 | Geotechnical Soil Investigation Report -Route-A (9061-9010/9029) |  | 5 | -1 | 0 |  |  | X
5897 | 5897 | 5897 | 5897 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Geotechnical Soil Investigation Report -Route-A (9061-9010/9029) Drafting / Preparation | 1 | C0GSI | E000 | 00E1 | E000C0GSI00E1
5898 | 5898 | 5898 | 5898 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Geotechnical Soil Investigation Report -Route-A (9061-9010/9029) Submission | 2 | C0GSI | E000 | 00E2 | E000C0GSI00E2
5899 | 5899 | 5899 | 5899 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Geotechnical Soil Investigation Report -Route-A (9061-9010/9029) Review / Evaluation | 3 | C0GSI | E000 | 00E3 | E000C0GSI00E3
5900 | 5900 | 5900 | 5900 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Geotechnical Soil Investigation Report -Route-A (9061-9010/9029) Approval with Comments | 4 | C0GSI | E000 | 00E4 | E000C0GSI00E4
5901 | 5901 | 5901 | 5901 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Geotechnical Soil Investigation Report -Route-A (9061-9010/9029) FINAL Approval | 5 | C0GSI | E000 | 00E5 | E000C0GSI00E5
5902 | 5902 | 5902 | 5902 | SA24M005 | Geotechnical Soil Investigation Report -Route-B (9061-9010) |  | 5 | -1 | 0 |  |  | X
5903 | 5903 | 5903 | 5903 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Geotechnical Soil Investigation Report -Route-B (9061-9010) Drafting / Preparation | 1 | C0SIR | E000 | 00E1 | E000#MOuo00E1
5904 | 5904 | 5904 | 5904 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Geotechnical Soil Investigation Report -Route-B (9061-9010) Submission | 2 | C0SIR | E000 | 00E2 | E000#MOuo00E2
5905 | 5905 | 5905 | 5905 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Geotechnical Soil Investigation Report -Route-B (9061-9010) Review / Evaluation | 3 | C0SIR | E000 | 00E3 | E000#MOuo00E3
5906 | 5906 | 5906 | 5906 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Geotechnical Soil Investigation Report -Route-B (9061-9010) Approval with Comments | 4 | C0SIR | E000 | 00E4 | E000#MOuo00E4
5907 | 5907 | 5907 | 5907 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Geotechnical Soil Investigation Report -Route-B (9061-9010) FINAL Approval | 5 | C0SIR | E000 | 00E5 | E000#MOuo00E5
5908 | 5908 | 5908 | 5908 | SA24M005 | Geotechnical Soil Investigation Report -Route-C (9061-9006/9032) |  | 5 | -1 | 0 |  |  | X | E000#MOuo
5909 | 5909 | 5909 | 5909 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Geotechnical Soil Investigation Report -Route-C (9061-9006/9032) Drafting / Preparation | 1 | C0SIR | E000 | 00E1 | E000#GtJJ00E1
5910 | 5910 | 5910 | 5910 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Geotechnical Soil Investigation Report -Route-C (9061-9006/9032) Submission | 2 | C0SIR | E000 | 00E2 | E000#GtJJ00E2
5911 | 5911 | 5911 | 5911 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Geotechnical Soil Investigation Report -Route-C (9061-9006/9032) Review / Evaluation | 3 | C0SIR | E000 | 00E3 | E000#GtJJ00E3
5912 | 5912 | 5912 | 5912 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Geotechnical Soil Investigation Report -Route-C (9061-9006/9032) Approval with Comments | 4 | C0SIR | E000 | 00E4 | E000#GtJJ00E4
5913 | 5913 | 5913 | 5913 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Geotechnical Soil Investigation Report -Route-C (9061-9006/9032) FINAL Approval | 5 | C0SIR | E000 | 00E5 | E000#GtJJ00E5
5914 | 5914 | 5914 | 5914 | SA24M005 | Geotechnical Soil Investigation Report -Route-D (9061-9064) |  | 5 | -1 | 0 |  |  | X | E000#GtJJ
5915 | 5915 | 5915 | 5915 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Geotechnical Soil Investigation Report -Route-D (9061-9064) Drafting / Preparation | 1 | C0SIR | E000 | 00E1 | E000#hrzk00E1
5916 | 5916 | 5916 | 5916 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Geotechnical Soil Investigation Report -Route-D (9061-9064) Submission | 2 | C0SIR | E000 | 00E2 | E000#hrzk00E2
5917 | 5917 | 5917 | 5917 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Geotechnical Soil Investigation Report -Route-D (9061-9064) Review / Evaluation | 3 | C0SIR | E000 | 00E3 | E000#hrzk00E3
5918 | 5918 | 5918 | 5918 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Geotechnical Soil Investigation Report -Route-D (9061-9064) Approval with Comments | 4 | C0SIR | E000 | 00E4 | E000#hrzk00E4
5919 | 5919 | 5919 | 5919 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Geotechnical Soil Investigation Report -Route-D (9061-9064) FINAL Approval | 5 | C0SIR | E000 | 00E5 | E000#hrzk00E5
5920 | 5920 | 5920 | 5920 | SA24M005 | Extended Mix Design of Concrete Mix Concrete Trial mix design (150 min) |  | 5 | -1 | 0 |  |  | X | E000#hrzk
5921 | 5921 | 5921 | 5921 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Extended Mix Design of Concrete Mix Concrete Trial mix design (150 min) Drafting / Preparation | 1 | CEMDC | E000 | 00E1 | E000CEMDC00E1
5922 | 5922 | 5922 | 5922 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Extended Mix Design of Concrete Mix Concrete Trial mix design (150 min) Submission | 2 | CEMDC | E000 | 00E2 | E000CEMDC00E2
5923 | 5923 | 5923 | 5923 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Extended Mix Design of Concrete Mix Concrete Trial mix design (150 min) Review / Evaluation | 3 | CEMDC | E000 | 00E3 | E000CEMDC00E3
5924 | 5924 | 5924 | 5924 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Extended Mix Design of Concrete Mix Concrete Trial mix design (150 min) Approval with Comments | 4 | CEMDC | E000 | 00E4 | E000CEMDC00E4
5925 | 5925 | 5925 | 5925 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Extended Mix Design of Concrete Mix Concrete Trial mix design (150 min) FINAL Approval | 5 | CEMDC | E000 | 00E5 | E000CEMDC00E5
5926 | 5926 | 5926 | 5926 | SA24M005 | Foundation Design Calculations and Drawings -Route-A (9061-9010/9029) |  | 5 | -1 | 0 |  |  | X
5927 | 5927 | 5927 | 5927 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Foundation Design Calculations and Drawings -Route-A (9061-9010/9029) Drafting / Preparation | 1 | C0FDC | E000 | 00E1 | E000#ukfo00E1
5928 | 5928 | 5928 | 5928 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Foundation Design Calculations and Drawings -Route-A (9061-9010/9029) Submission | 2 | C0FDC | E000 | 00E2 | E000#ukfo00E2
5929 | 5929 | 5929 | 5929 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Foundation Design Calculations and Drawings -Route-A (9061-9010/9029) Review / Evaluation | 3 | C0FDC | E000 | 00E3 | E000#ukfo00E3
5930 | 5930 | 5930 | 5930 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Foundation Design Calculations and Drawings -Route-A (9061-9010/9029) Approval with Comments | 4 | C0FDC | E000 | 00E4 | E000#ukfo00E4
5931 | 5931 | 5931 | 5931 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Foundation Design Calculations and Drawings -Route-A (9061-9010/9029) FINAL Approval | 5 | C0FDC | E000 | 00E5 | E000#ukfo00E5
5932 | 5932 | 5932 | 5932 | SA24M005 | Foundation Design Calculations and Drawings -Route-B (9061-9010) |  | 5 | -1 | 0 |  |  | X | E000#ukfo
5933 | 5933 | 5933 | 5933 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Foundation Design Calculations and Drawings -Route-B (9061-9010) Drafting / Preparation | 1 | C0FDC | E000 | 00E1 | E000#AVWc00E1
5934 | 5934 | 5934 | 5934 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Foundation Design Calculations and Drawings -Route-B (9061-9010) Submission | 2 | C0FDC | E000 | 00E2 | E000#AVWc00E2
5935 | 5935 | 5935 | 5935 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Foundation Design Calculations and Drawings -Route-B (9061-9010) Review / Evaluation | 3 | C0FDC | E000 | 00E3 | E000#AVWc00E3
5936 | 5936 | 5936 | 5936 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Foundation Design Calculations and Drawings -Route-B (9061-9010) Approval with Comments | 4 | C0FDC | E000 | 00E4 | E000#AVWc00E4
5937 | 5937 | 5937 | 5937 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Foundation Design Calculations and Drawings -Route-B (9061-9010) FINAL Approval | 5 | C0FDC | E000 | 00E5 | E000#AVWc00E5
5938 | 5938 | 5938 | 5938 | SA24M005 | Foundation Design Calculations and Drawings -Route-C (9061-9006/9032) |  | 5 | -1 | 0 |  |  | X | E000#AVWc
5939 | 5939 | 5939 | 5939 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Foundation Design Calculations and Drawings -Route-C (9061-9006/9032) Drafting / Preparation | 1 | C0FDC | E000 | 00E1 | E000#RKDm00E1
5940 | 5940 | 5940 | 5940 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Foundation Design Calculations and Drawings -Route-C (9061-9006/9032) Submission | 2 | C0FDC | E000 | 00E2 | E000#RKDm00E2
5941 | 5941 | 5941 | 5941 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Foundation Design Calculations and Drawings -Route-C (9061-9006/9032) Review / Evaluation | 3 | C0FDC | E000 | 00E3 | E000#RKDm00E3
5942 | 5942 | 5942 | 5942 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Foundation Design Calculations and Drawings -Route-C (9061-9006/9032) Approval with Comments | 4 | C0FDC | E000 | 00E4 | E000#RKDm00E4
5943 | 5943 | 5943 | 5943 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Foundation Design Calculations and Drawings -Route-C (9061-9006/9032) FINAL Approval | 5 | C0FDC | E000 | 00E5 | E000#RKDm00E5
5944 | 5944 | 5944 | 5944 | SA24M005 | Foundation Design Calculations and Drawings -Route-D (9061-9064) |  | 5 | -1 | 0 |  |  | X | E000#RKDm
5945 | 5945 | 5945 | 5945 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Foundation Design Calculations and Drawings -Route-D (9061-9064) Drafting / Preparation | 1 | C0FDC | E000 | 00E1 | E000#xjss00E1
5946 | 5946 | 5946 | 5946 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Foundation Design Calculations and Drawings -Route-D (9061-9064) Submission | 2 | C0FDC | E000 | 00E2 | E000#xjss00E2
5947 | 5947 | 5947 | 5947 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Foundation Design Calculations and Drawings -Route-D (9061-9064) Review / Evaluation | 3 | C0FDC | E000 | 00E3 | E000#xjss00E3
5948 | 5948 | 5948 | 5948 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Foundation Design Calculations and Drawings -Route-D (9061-9064) Approval with Comments | 4 | C0FDC | E000 | 00E4 | E000#xjss00E4
5949 | 5949 | 5949 | 5949 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Foundation Design Calculations and Drawings -Route-D (9061-9064) FINAL Approval | 5 | C0FDC | E000 | 00E5 | E000#xjss00E5
5950 | 5950 | 5950 | 5950 | SA24M005 | Design Calculations and Drawings For Uplift Test foundation for Tangent Tower |  | 5 | -1 | 0 |  |  | X | E000#xjss
5951 | 5951 | 5951 | 5951 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Design Calculations and Drawings For Uplift Test foundation for Tangent Tower Drafting / Preparation | 1 | CUPTF | E000 | 00E1 | E000#iuYk00E1
5952 | 5952 | 5952 | 5952 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Design Calculations and Drawings For Uplift Test foundation for Tangent Tower Submission | 2 | CUPTF | E000 | 00E2 | E000#iuYk00E2
5953 | 5953 | 5953 | 5953 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Design Calculations and Drawings For Uplift Test foundation for Tangent Tower Review / Evaluation | 3 | CUPTF | E000 | 00E3 | E000#iuYk00E3
5954 | 5954 | 5954 | 5954 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Design Calculations and Drawings For Uplift Test foundation for Tangent Tower Approval with Comments | 4 | CUPTF | E000 | 00E4 | E000#iuYk00E4
5955 | 5955 | 5955 | 5955 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Design Calculations and Drawings For Uplift Test foundation for Tangent Tower FINAL Approval | 5 | CUPTF | E000 | 00E5 | E000#iuYk00E5
5956 | 5956 | 5956 | 5956 | SA24M005 | Design Calculations and Drawings For Uplift Test foundation for Heavy Angle Tower |  | 5 | -1 | 0 |  |  | X | E000#iuYk
5957 | 5957 | 5957 | 5957 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Design Calculations and Drawings For Uplift Test foundation for Heavy Angle Tower Drafting / Preparation | 1 | CUPTF | E000 | 00E1 | E000#UAZb00E1
5958 | 5958 | 5958 | 5958 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Design Calculations and Drawings For Uplift Test foundation for Heavy Angle Tower Submission | 2 | CUPTF | E000 | 00E2 | E000#UAZb00E2
5959 | 5959 | 5959 | 5959 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Design Calculations and Drawings For Uplift Test foundation for Heavy Angle Tower Review / Evaluation | 3 | CUPTF | E000 | 00E3 | E000#UAZb00E3
5960 | 5960 | 5960 | 5960 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Design Calculations and Drawings For Uplift Test foundation for Heavy Angle Tower Approval with Comments | 4 | CUPTF | E000 | 00E4 | E000#UAZb00E4
5961 | 5961 | 5961 | 5961 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Design Calculations and Drawings For Uplift Test foundation for Heavy Angle Tower FINAL Approval | 5 | CUPTF | E000 | 00E5 | E000#UAZb00E5
5962 | 5962 | 5962 | 5962 | SA24M005 | Uplift Test Procedure (full scale / uplift load test) for Tangent Tower foundation - "to be repeated |  | 5 | -1 | 0 |  |  | X | E000#UAZb
5963 | 5963 | 5963 | 5963 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Uplift Test Procedure (full scale / uplift load test) for Tangent Tower foundation - "to be repeated Drafting / Preparation | 1 | CUPT | E000 | 00E1 | E000CUPT00E1
5964 | 5964 | 5964 | 5964 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Uplift Test Procedure (full scale / uplift load test) for Tangent Tower foundation - "to be repeated Submission | 2 | CUPT | E000 | 00E2 | E000CUPT00E2
5965 | 5965 | 5965 | 5965 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Uplift Test Procedure (full scale / uplift load test) for Tangent Tower foundation - "to be repeated Review / Evaluation | 3 | CUPT | E000 | 00E3 | E000CUPT00E3
5966 | 5966 | 5966 | 5966 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Uplift Test Procedure (full scale / uplift load test) for Tangent Tower foundation - "to be repeated Approval with Comments | 4 | CUPT | E000 | 00E4 | E000CUPT00E4
5967 | 5967 | 5967 | 5967 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Uplift Test Procedure (full scale / uplift load test) for Tangent Tower foundation - "to be repeated FINAL Approval | 5 | CUPT | E000 | 00E5 | E000CUPT00E5
5968 | 5968 | 5968 | 5968 | SA24M005 | Uplift Test Reports for Heavy Angle Tower foundation- "to be repeated according to the foundation ty |  | 5 | -1 | 0 |  |  | X
5969 | 5969 | 5969 | 5969 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Uplift Test Reports for Heavy Angle Tower foundation- "to be repeated according to the foundation ty Drafting / Preparation | 1 | CUPTR | E000 | 00E1 | E000CUPTR00E1
5970 | 5970 | 5970 | 5970 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Uplift Test Reports for Heavy Angle Tower foundation- "to be repeated according to the foundation ty Submission | 2 | CUPTR | E000 | 00E2 | E000CUPTR00E2
5971 | 5971 | 5971 | 5971 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Uplift Test Reports for Heavy Angle Tower foundation- "to be repeated according to the foundation ty Review / Evaluation | 3 | CUPTR | E000 | 00E3 | E000CUPTR00E3
5972 | 5972 | 5972 | 5972 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Uplift Test Reports for Heavy Angle Tower foundation- "to be repeated according to the foundation ty Approval with Comments | 4 | CUPTR | E000 | 00E4 | E000CUPTR00E4
5973 | 5973 | 5973 | 5973 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Uplift Test Reports for Heavy Angle Tower foundation- "to be repeated according to the foundation ty FINAL Approval | 5 | CUPTR | E000 | 00E5 | E000CUPTR00E5
5974 | 5974 | 5974 | 5974 | SA24M005 | Layout and Details of Access Road and Structure -Route-A (9061-9010/9029) |  | 5 | -1 | 0 |  |  | X
5975 | 5975 | 5975 | 5975 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Layout and Details of Access Road and Structure -Route-A (9061-9010/9029) Drafting / Preparation | 1 | CL0AR | E000 | 00E1 | E000#QYfA00E1
5976 | 5976 | 5976 | 5976 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Layout and Details of Access Road and Structure -Route-A (9061-9010/9029) Submission | 2 | CL0AR | E000 | 00E2 | E000#QYfA00E2
5977 | 5977 | 5977 | 5977 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Layout and Details of Access Road and Structure -Route-A (9061-9010/9029) Review / Evaluation | 3 | CL0AR | E000 | 00E3 | E000#QYfA00E3
5978 | 5978 | 5978 | 5978 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Layout and Details of Access Road and Structure -Route-A (9061-9010/9029) Approval with Comments | 4 | CL0AR | E000 | 00E4 | E000#QYfA00E4
5979 | 5979 | 5979 | 5979 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Layout and Details of Access Road and Structure -Route-A (9061-9010/9029) FINAL Approval | 5 | CL0AR | E000 | 00E5 | E000#QYfA00E5
5980 | 5980 | 5980 | 5980 | SA24M005 | Layout and Details of Access Road and Structure -Route-B (9061-9010) |  | 5 | -1 | 0 |  |  | X | E000#QYfA
5981 | 5981 | 5981 | 5981 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Layout and Details of Access Road and Structure -Route-B (9061-9010) Drafting / Preparation | 1 | CL0AR | E000 | 00E1 | E000#RmeE00E1
5982 | 5982 | 5982 | 5982 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Layout and Details of Access Road and Structure -Route-B (9061-9010) Submission | 2 | CL0AR | E000 | 00E2 | E000#RmeE00E2
5983 | 5983 | 5983 | 5983 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Layout and Details of Access Road and Structure -Route-B (9061-9010) Review / Evaluation | 3 | CL0AR | E000 | 00E3 | E000#RmeE00E3
5984 | 5984 | 5984 | 5984 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Layout and Details of Access Road and Structure -Route-B (9061-9010) Approval with Comments | 4 | CL0AR | E000 | 00E4 | E000#RmeE00E4
5985 | 5985 | 5985 | 5985 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Layout and Details of Access Road and Structure -Route-B (9061-9010) FINAL Approval | 5 | CL0AR | E000 | 00E5 | E000#RmeE00E5
5986 | 5986 | 5986 | 5986 | SA24M005 | Layout and Details of Access Road and Structure -Route-C (9061-9006/9032) |  | 5 | -1 | 0 |  |  | X | E000#RmeE
5987 | 5987 | 5987 | 5987 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Layout and Details of Access Road and Structure -Route-C (9061-9006/9032) Drafting / Preparation | 1 | C00AR | E000 | 00E1 | E000C00AR00E1
5988 | 5988 | 5988 | 5988 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Layout and Details of Access Road and Structure -Route-C (9061-9006/9032) Submission | 2 | C00AR | E000 | 00E2 | E000C00AR00E2
5989 | 5989 | 5989 | 5989 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Layout and Details of Access Road and Structure -Route-C (9061-9006/9032) Review / Evaluation | 3 | C00AR | E000 | 00E3 | E000C00AR00E3
5990 | 5990 | 5990 | 5990 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Layout and Details of Access Road and Structure -Route-C (9061-9006/9032) Approval with Comments | 4 | C00AR | E000 | 00E4 | E000C00AR00E4
5991 | 5991 | 5991 | 5991 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Layout and Details of Access Road and Structure -Route-C (9061-9006/9032) FINAL Approval | 5 | C00AR | E000 | 00E5 | E000C00AR00E5
5992 | 5992 | 5992 | 5992 | SA24M005 | Layout and Details of Access Road and Structure -Route-D (9061-9064) |  | 5 | -1 | 0 |  |  | X
5993 | 5993 | 5993 | 5993 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Layout and Details of Access Road and Structure -Route-D (9061-9064) Drafting / Preparation | 1 | CL0AR | E000 | 00E1 | E000#oMeI00E1
5994 | 5994 | 5994 | 5994 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Layout and Details of Access Road and Structure -Route-D (9061-9064) Submission | 2 | CL0AR | E000 | 00E2 | E000#oMeI00E2
5995 | 5995 | 5995 | 5995 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Layout and Details of Access Road and Structure -Route-D (9061-9064) Review / Evaluation | 3 | CL0AR | E000 | 00E3 | E000#oMeI00E3
5996 | 5996 | 5996 | 5996 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Layout and Details of Access Road and Structure -Route-D (9061-9064) Approval with Comments | 4 | CL0AR | E000 | 00E4 | E000#oMeI00E4
5997 | 5997 | 5997 | 5997 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Layout and Details of Access Road and Structure -Route-D (9061-9064) FINAL Approval | 5 | CL0AR | E000 | 00E5 | E000#oMeI00E5
5998 | 5998 | 5998 | 5998 | SA24M005 | Analytical Vibration Damping Study and recommendations for Spacer Dampers & Stock Bridge Dampers |  | 5 | -1 | 0 |  |  | X | E000#oMeI
5999 | 5999 | 5999 | 5999 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Analytical Vibration Damping Study and recommendations for Spacer Dampers & Stock Bridge Dampers Drafting / Preparation | 1 | CAVDS | E000 | 00E1 | E000CAVDS00E1
6000 | 6000 | 6000 | 6000 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Analytical Vibration Damping Study and recommendations for Spacer Dampers & Stock Bridge Dampers Submission | 2 | CAVDS | E000 | 00E2 | E000CAVDS00E2
6001 | 6001 | 6001 | 6001 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Analytical Vibration Damping Study and recommendations for Spacer Dampers & Stock Bridge Dampers Review / Evaluation | 3 | CAVDS | E000 | 00E3 | E000CAVDS00E3
6002 | 6002 | 6002 | 6002 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Analytical Vibration Damping Study and recommendations for Spacer Dampers & Stock Bridge Dampers Approval with Comments | 4 | CAVDS | E000 | 00E4 | E000CAVDS00E4
6003 | 6003 | 6003 | 6003 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Analytical Vibration Damping Study and recommendations for Spacer Dampers & Stock Bridge Dampers FINAL Approval | 5 | CAVDS | E000 | 00E5 | E000CAVDS00E5
6004 | 6004 | 6004 | 6004 | SA24M005 | Field vibration test procedure including sub span oscillation measurement |  | 5 | -1 | 0 |  |  | X
6005 | 6005 | 6005 | 6005 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Field vibration test procedure including sub span oscillation measurement Drafting / Preparation | 1 | CFVTM | E000 | 00E1 | E000CFVTM00E1
6006 | 6006 | 6006 | 6006 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Field vibration test procedure including sub span oscillation measurement Submission | 2 | CFVTM | E000 | 00E2 | E000CFVTM00E2
6007 | 6007 | 6007 | 6007 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Field vibration test procedure including sub span oscillation measurement Review / Evaluation | 3 | CFVTM | E000 | 00E3 | E000CFVTM00E3
6008 | 6008 | 6008 | 6008 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Field vibration test procedure including sub span oscillation measurement Approval with Comments | 4 | CFVTM | E000 | 00E4 | E000CFVTM00E4
6009 | 6009 | 6009 | 6009 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Field vibration test procedure including sub span oscillation measurement FINAL Approval | 5 | CFVTM | E000 | 00E5 | E000CFVTM00E5
6010 | 6010 | 6010 | 6010 | SA24M005 | Field vibration test and sub span oscillation measurement result |  | 5 | -1 | 0 |  |  | X
6011 | 6011 | 6011 | 6011 | SA24M005 | Drafting / Preparation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Field vibration test and sub span oscillation measurement result Drafting / Preparation | 1 | CVFSRM | E000 | 00E1 | E000CVFSRM00E1
6012 | 6012 | 6012 | 6012 | SA24M005 | Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Field vibration test and sub span oscillation measurement result Submission | 2 | CVFSRM | E000 | 00E2 | E000CVFSRM00E2
6013 | 6013 | 6013 | 6013 | SA24M005 | Review / Evaluation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Field vibration test and sub span oscillation measurement result Review / Evaluation | 3 | CVFSRM | E000 | 00E3 | E000CVFSRM00E3
6014 | 6014 | 6014 | 6014 | SA24M005 | Approval with Comments |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Field vibration test and sub span oscillation measurement result Approval with Comments | 4 | CVFSRM | E000 | 00E4 | E000CVFSRM00E4
6015 | 6015 | 6015 | 6015 | SA24M005 | FINAL Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Engineering & Design Linewise Design (Phase- II) Civil Field vibration test and sub span oscillation measurement result FINAL Approval | 5 | CVFSRM | E000 | 00E5 | E000CVFSRM00E5
6016 | 6016 | 6016 | 6016 | SA24M005 | Material Procurement |  | 2 | -1 | 0 |  |  | X
6017 | 6017 | 6017 | 6017 | SA24M005 | Stubs for Tangent Tower (0 - 2 degree) |  | 3 | -1 | 0 |  |  | X
6018 | 6018 | 6018 | 6018 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Stubs for Tangent Tower (0 - 2 degree) Purchase Request to SCM | 1 | 0STRT | P000 | 00P1 | P0000STRT00P1
6019 | 6019 | 6019 | 6019 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Stubs for Tangent Tower (0 - 2 degree) Issue of RFQ | 2 | 0STRT | P000 | 00P2 | P0000STRT00P2
6020 | 6020 | 6020 | 6020 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Stubs for Tangent Tower (0 - 2 degree) Receipt of Technical offer from Vendor | 3 | 0STRT | P000 | 00P3 | P0000STRT00P3
6021 | 6021 | 6021 | 6021 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Stubs for Tangent Tower (0 - 2 degree) Technical Evaluation by EDRC | 4 | 0STRT | P000 | 00P4 | P0000STRT00P4
6022 | 6022 | 6022 | 6022 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Stubs for Tangent Tower (0 - 2 degree) Final technical compliance from Vendor | 5 | 0STRT | P000 | 00P5 | P0000STRT00P5
6023 | 6023 | 6023 | 6023 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Stubs for Tangent Tower (0 - 2 degree) Technical clearance by EDRC | 6 | 0STRT | P000 | 00P6 | P0000STRT00P6
6024 | 6024 | 6024 | 6024 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Stubs for Tangent Tower (0 - 2 degree) Commercial Evaluation by SCM | 7 | 0STRT | P000 | 00P7 | P0000STRT00P7
6025 | 6025 | 6025 | 6025 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Stubs for Tangent Tower (0 - 2 degree) Vendor negotiation & Finalization | 8 | 0STRT | P000 | 00P8 | P0000STRT00P8
6026 | 6026 | 6026 | 6026 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Stubs for Tangent Tower (0 - 2 degree) HPC Approval / PO release to vendor | 9 | 0STRT | P000 | 00P9 | P0000STRT00P9
6027 | 6027 | 6027 | 6027 | SA24M005 | Stubs for Dead-End / Terminal Tower (0 - 30 degree) |  | 3 | -1 | 0 |  |  | X
6028 | 6028 | 6028 | 6028 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Stubs for Dead-End / Terminal Tower (0 - 30 degree) Purchase Request to SCM | 1 | #Kmet | P000 | 00P1 | P000#Kmet00P1
6029 | 6029 | 6029 | 6029 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Stubs for Dead-End / Terminal Tower (0 - 30 degree) Issue of RFQ | 2 | #Kmet | P000 | 00P2 | P000#Kmet00P2
6030 | 6030 | 6030 | 6030 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Stubs for Dead-End / Terminal Tower (0 - 30 degree) Receipt of Technical offer from Vendor | 3 | #Kmet | P000 | 00P3 | P000#Kmet00P3
6031 | 6031 | 6031 | 6031 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Stubs for Dead-End / Terminal Tower (0 - 30 degree) Technical Evaluation by EDRC | 4 | #Kmet | P000 | 00P4 | P000#Kmet00P4
6032 | 6032 | 6032 | 6032 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Stubs for Dead-End / Terminal Tower (0 - 30 degree) Final technical compliance from Vendor | 5 | #Kmet | P000 | 00P5 | P000#Kmet00P5
6033 | 6033 | 6033 | 6033 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Stubs for Dead-End / Terminal Tower (0 - 30 degree) Technical clearance by EDRC | 6 | #Kmet | P000 | 00P6 | P000#Kmet00P6
6034 | 6034 | 6034 | 6034 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Stubs for Dead-End / Terminal Tower (0 - 30 degree) Commercial Evaluation by SCM | 7 | #Kmet | P000 | 00P7 | P000#Kmet00P7
6035 | 6035 | 6035 | 6035 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Stubs for Dead-End / Terminal Tower (0 - 30 degree) Vendor negotiation & Finalization | 8 | #Kmet | P000 | 00P8 | P000#Kmet00P8
6036 | 6036 | 6036 | 6036 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Stubs for Dead-End / Terminal Tower (0 - 30 degree) HPC Approval / PO release to vendor | 9 | #Kmet | P000 | 00P9 | P000#Kmet00P9
6037 | 6037 | 6037 | 6037 | SA24M005 | Stubs for Heavy Angle Tower (60 - 90 degree) |  | 3 | -1 | 0 |  |  | X
6038 | 6038 | 6038 | 6038 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Stubs for Heavy Angle Tower (60 - 90 degree) Purchase Request to SCM | 1 | 0SBHA | P000 | 00P1 | P0000SBHA00P1
6039 | 6039 | 6039 | 6039 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Stubs for Heavy Angle Tower (60 - 90 degree) Issue of RFQ | 2 | 0SBHA | P000 | 00P2 | P0000SBHA00P2
6040 | 6040 | 6040 | 6040 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Stubs for Heavy Angle Tower (60 - 90 degree) Receipt of Technical offer from Vendor | 3 | 0SBHA | P000 | 00P3 | P0000SBHA00P3
6041 | 6041 | 6041 | 6041 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Stubs for Heavy Angle Tower (60 - 90 degree) Technical Evaluation by EDRC | 4 | 0SBHA | P000 | 00P4 | P0000SBHA00P4
6042 | 6042 | 6042 | 6042 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Stubs for Heavy Angle Tower (60 - 90 degree) Final technical compliance from Vendor | 5 | 0SBHA | P000 | 00P5 | P0000SBHA00P5
6043 | 6043 | 6043 | 6043 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Stubs for Heavy Angle Tower (60 - 90 degree) Technical clearance by EDRC | 6 | 0SBHA | P000 | 00P6 | P0000SBHA00P6
6044 | 6044 | 6044 | 6044 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Stubs for Heavy Angle Tower (60 - 90 degree) Commercial Evaluation by SCM | 7 | 0SBHA | P000 | 00P7 | P0000SBHA00P7
6045 | 6045 | 6045 | 6045 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Stubs for Heavy Angle Tower (60 - 90 degree) Vendor negotiation & Finalization | 8 | 0SBHA | P000 | 00P8 | P0000SBHA00P8
6046 | 6046 | 6046 | 6046 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Stubs for Heavy Angle Tower (60 - 90 degree) HPC Approval / PO release to vendor | 9 | 0SBHA | P000 | 00P9 | P0000SBHA00P9
6047 | 6047 | 6047 | 6047 | SA24M005 | Lattice Structure for Tangent Tower (0 - 2 degree) |  | 3 | -1 | 0 |  |  | X
6048 | 6048 | 6048 | 6048 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Lattice Structure for Tangent Tower (0 - 2 degree) Purchase Request to SCM | 1 | 0LSTR | P000 | 00P1 | P0000LSTR00P1
6049 | 6049 | 6049 | 6049 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Lattice Structure for Tangent Tower (0 - 2 degree) Issue of RFQ | 2 | 0LSTR | P000 | 00P2 | P0000LSTR00P2
6050 | 6050 | 6050 | 6050 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Lattice Structure for Tangent Tower (0 - 2 degree) Receipt of Technical offer from Vendor | 3 | 0LSTR | P000 | 00P3 | P0000LSTR00P3
6051 | 6051 | 6051 | 6051 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Lattice Structure for Tangent Tower (0 - 2 degree) Technical Evaluation by EDRC | 4 | 0LSTR | P000 | 00P4 | P0000LSTR00P4
6052 | 6052 | 6052 | 6052 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Lattice Structure for Tangent Tower (0 - 2 degree) Final technical compliance from Vendor | 5 | 0LSTR | P000 | 00P5 | P0000LSTR00P5
6053 | 6053 | 6053 | 6053 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Lattice Structure for Tangent Tower (0 - 2 degree) Technical clearance by EDRC | 6 | 0LSTR | P000 | 00P6 | P0000LSTR00P6
6054 | 6054 | 6054 | 6054 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Lattice Structure for Tangent Tower (0 - 2 degree) Commercial Evaluation by SCM | 7 | 0LSTR | P000 | 00P7 | P0000LSTR00P7
6055 | 6055 | 6055 | 6055 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Lattice Structure for Tangent Tower (0 - 2 degree) Vendor negotiation & Finalization | 8 | 0LSTR | P000 | 00P8 | P0000LSTR00P8
6056 | 6056 | 6056 | 6056 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Lattice Structure for Tangent Tower (0 - 2 degree) HPC Approval / PO release to vendor | 9 | 0LSTR | P000 | 00P9 | P0000LSTR00P9
6057 | 6057 | 6057 | 6057 | SA24M005 | Lattice Structure for Dead-End / Terminal Tower (0 - 30 degree) |  | 3 | -1 | 0 |  |  | X
6058 | 6058 | 6058 | 6058 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Lattice Structure for Dead-End / Terminal Tower (0 - 30 degree) Purchase Request to SCM | 1 | #XmNy | P000 | 00P1 | P000#XmNy00P1
6059 | 6059 | 6059 | 6059 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Lattice Structure for Dead-End / Terminal Tower (0 - 30 degree) Issue of RFQ | 2 | #XmNy | P000 | 00P2 | P000#XmNy00P2
6060 | 6060 | 6060 | 6060 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Lattice Structure for Dead-End / Terminal Tower (0 - 30 degree) Receipt of Technical offer from Vendor | 3 | #XmNy | P000 | 00P3 | P000#XmNy00P3
6061 | 6061 | 6061 | 6061 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Lattice Structure for Dead-End / Terminal Tower (0 - 30 degree) Technical Evaluation by EDRC | 4 | #XmNy | P000 | 00P4 | P000#XmNy00P4
6062 | 6062 | 6062 | 6062 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Lattice Structure for Dead-End / Terminal Tower (0 - 30 degree) Final technical compliance from Vendor | 5 | #XmNy | P000 | 00P5 | P000#XmNy00P5
6063 | 6063 | 6063 | 6063 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Lattice Structure for Dead-End / Terminal Tower (0 - 30 degree) Technical clearance by EDRC | 6 | #XmNy | P000 | 00P6 | P000#XmNy00P6
6064 | 6064 | 6064 | 6064 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Lattice Structure for Dead-End / Terminal Tower (0 - 30 degree) Commercial Evaluation by SCM | 7 | #XmNy | P000 | 00P7 | P000#XmNy00P7
6065 | 6065 | 6065 | 6065 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Lattice Structure for Dead-End / Terminal Tower (0 - 30 degree) Vendor negotiation & Finalization | 8 | #XmNy | P000 | 00P8 | P000#XmNy00P8
6066 | 6066 | 6066 | 6066 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Lattice Structure for Dead-End / Terminal Tower (0 - 30 degree) HPC Approval / PO release to vendor | 9 | #XmNy | P000 | 00P9 | P000#XmNy00P9
6067 | 6067 | 6067 | 6067 | SA24M005 | Lattice Structure for Heavy Angle Tower (60 - 90 degree) |  | 3 | -1 | 0 |  |  | X
6068 | 6068 | 6068 | 6068 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Lattice Structure for Heavy Angle Tower (60 - 90 degree) Purchase Request to SCM | 1 | 0STRL | P000 | 00P1 | P0000STRL00P1
6069 | 6069 | 6069 | 6069 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Lattice Structure for Heavy Angle Tower (60 - 90 degree) Issue of RFQ | 2 | 0STRL | P000 | 00P2 | P0000STRL00P2
6070 | 6070 | 6070 | 6070 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Lattice Structure for Heavy Angle Tower (60 - 90 degree) Receipt of Technical offer from Vendor | 3 | 0STRL | P000 | 00P3 | P0000STRL00P3
6071 | 6071 | 6071 | 6071 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Lattice Structure for Heavy Angle Tower (60 - 90 degree) Technical Evaluation by EDRC | 4 | 0STRL | P000 | 00P4 | P0000STRL00P4
6072 | 6072 | 6072 | 6072 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Lattice Structure for Heavy Angle Tower (60 - 90 degree) Final technical compliance from Vendor | 5 | 0STRL | P000 | 00P5 | P0000STRL00P5
6073 | 6073 | 6073 | 6073 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Lattice Structure for Heavy Angle Tower (60 - 90 degree) Technical clearance by EDRC | 6 | 0STRL | P000 | 00P6 | P0000STRL00P6
6074 | 6074 | 6074 | 6074 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Lattice Structure for Heavy Angle Tower (60 - 90 degree) Commercial Evaluation by SCM | 7 | 0STRL | P000 | 00P7 | P0000STRL00P7
6075 | 6075 | 6075 | 6075 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Lattice Structure for Heavy Angle Tower (60 - 90 degree) Vendor negotiation & Finalization | 8 | 0STRL | P000 | 00P8 | P0000STRL00P8
6076 | 6076 | 6076 | 6076 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Lattice Structure for Heavy Angle Tower (60 - 90 degree) HPC Approval / PO release to vendor | 9 | 0STRL | P000 | 00P9 | P0000STRL00P9
6077 | 6077 | 6077 | 6077 | SA24M005 | Insulators for Tangent Tower (0 - 2 degree) |  | 3 | -1 | 0 |  |  | X
6078 | 6078 | 6078 | 6078 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Insulators for Tangent Tower (0 - 2 degree) Purchase Request to SCM | 1 | 0INSL | P000 | 00P1 | P0000INSL00P1
6079 | 6079 | 6079 | 6079 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Insulators for Tangent Tower (0 - 2 degree) Issue of RFQ | 2 | 0INSL | P000 | 00P2 | P0000INSL00P2
6080 | 6080 | 6080 | 6080 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Insulators for Tangent Tower (0 - 2 degree) Receipt of Technical offer from Vendor | 3 | 0INSL | P000 | 00P3 | P0000INSL00P3
6081 | 6081 | 6081 | 6081 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Insulators for Tangent Tower (0 - 2 degree) Technical Evaluation by EDRC | 4 | 0INSL | P000 | 00P4 | P0000INSL00P4
6082 | 6082 | 6082 | 6082 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Insulators for Tangent Tower (0 - 2 degree) Final technical compliance from Vendor | 5 | 0INSL | P000 | 00P5 | P0000INSL00P5
6083 | 6083 | 6083 | 6083 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Insulators for Tangent Tower (0 - 2 degree) Technical clearance by EDRC | 6 | 0INSL | P000 | 00P6 | P0000INSL00P6
6084 | 6084 | 6084 | 6084 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Insulators for Tangent Tower (0 - 2 degree) Commercial Evaluation by SCM | 7 | 0INSL | P000 | 00P7 | P0000INSL00P7
6085 | 6085 | 6085 | 6085 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Insulators for Tangent Tower (0 - 2 degree) Vendor negotiation & Finalization | 8 | 0INSL | P000 | 00P8 | P0000INSL00P8
6086 | 6086 | 6086 | 6086 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Insulators for Tangent Tower (0 - 2 degree) HPC Approval / PO release to vendor | 9 | 0INSL | P000 | 00P9 | P0000INSL00P9
6087 | 6087 | 6087 | 6087 | SA24M005 | Insulators for Dead-End / Terminal Tower (0 - 30 degree) |  | 3 | -1 | 0 |  |  | X
6088 | 6088 | 6088 | 6088 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Insulators for Dead-End / Terminal Tower (0 - 30 degree) Purchase Request to SCM | 1 | 0INSD | P000 | 00P1 | P0000INSD00P1
6089 | 6089 | 6089 | 6089 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Insulators for Dead-End / Terminal Tower (0 - 30 degree) Issue of RFQ | 2 | 0INSD | P000 | 00P2 | P0000INSD00P2
6090 | 6090 | 6090 | 6090 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Insulators for Dead-End / Terminal Tower (0 - 30 degree) Receipt of Technical offer from Vendor | 3 | 0INSD | P000 | 00P3 | P0000INSD00P3
6091 | 6091 | 6091 | 6091 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Insulators for Dead-End / Terminal Tower (0 - 30 degree) Technical Evaluation by EDRC | 4 | 0INSD | P000 | 00P4 | P0000INSD00P4
6092 | 6092 | 6092 | 6092 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Insulators for Dead-End / Terminal Tower (0 - 30 degree) Final technical compliance from Vendor | 5 | 0INSD | P000 | 00P5 | P0000INSD00P5
6093 | 6093 | 6093 | 6093 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Insulators for Dead-End / Terminal Tower (0 - 30 degree) Technical clearance by EDRC | 6 | 0INSD | P000 | 00P6 | P0000INSD00P6
6094 | 6094 | 6094 | 6094 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Insulators for Dead-End / Terminal Tower (0 - 30 degree) Commercial Evaluation by SCM | 7 | 0INSD | P000 | 00P7 | P0000INSD00P7
6095 | 6095 | 6095 | 6095 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Insulators for Dead-End / Terminal Tower (0 - 30 degree) Vendor negotiation & Finalization | 8 | 0INSD | P000 | 00P8 | P0000INSD00P8
6096 | 6096 | 6096 | 6096 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Insulators for Dead-End / Terminal Tower (0 - 30 degree) HPC Approval / PO release to vendor | 9 | 0INSD | P000 | 00P9 | P0000INSD00P9
6097 | 6097 | 6097 | 6097 | SA24M005 | Insulators for Heavy Angle Tower (60 - 90 degree) |  | 3 | -1 | 0 |  |  | X
6098 | 6098 | 6098 | 6098 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Insulators for Heavy Angle Tower (60 - 90 degree) Purchase Request to SCM | 1 | 0INSR | P000 | 00P1 | P0000INSR00P1
6099 | 6099 | 6099 | 6099 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Insulators for Heavy Angle Tower (60 - 90 degree) Issue of RFQ | 2 | 0INSR | P000 | 00P2 | P0000INSR00P2
6100 | 6100 | 6100 | 6100 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Insulators for Heavy Angle Tower (60 - 90 degree) Receipt of Technical offer from Vendor | 3 | 0INSR | P000 | 00P3 | P0000INSR00P3
6101 | 6101 | 6101 | 6101 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Insulators for Heavy Angle Tower (60 - 90 degree) Technical Evaluation by EDRC | 4 | 0INSR | P000 | 00P4 | P0000INSR00P4
6102 | 6102 | 6102 | 6102 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Insulators for Heavy Angle Tower (60 - 90 degree) Final technical compliance from Vendor | 5 | 0INSR | P000 | 00P5 | P0000INSR00P5
6103 | 6103 | 6103 | 6103 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Insulators for Heavy Angle Tower (60 - 90 degree) Technical clearance by EDRC | 6 | 0INSR | P000 | 00P6 | P0000INSR00P6
6104 | 6104 | 6104 | 6104 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Insulators for Heavy Angle Tower (60 - 90 degree) Commercial Evaluation by SCM | 7 | 0INSR | P000 | 00P7 | P0000INSR00P7
6105 | 6105 | 6105 | 6105 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Insulators for Heavy Angle Tower (60 - 90 degree) Vendor negotiation & Finalization | 8 | 0INSR | P000 | 00P8 | P0000INSR00P8
6106 | 6106 | 6106 | 6106 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Insulators for Heavy Angle Tower (60 - 90 degree) HPC Approval / PO release to vendor | 9 | 0INSR | P000 | 00P9 | P0000INSR00P9
6107 | 6107 | 6107 | 6107 | SA24M005 | Hardware & Accessories for Tangent Tower (0 - 2 degree) |  | 3 | -1 | 0 |  |  | X
6108 | 6108 | 6108 | 6108 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Hardware & Accessories for Tangent Tower (0 - 2 degree) Purchase Request to SCM | 1 | HTANG | P000 | 00P1 | P000HTANG00P1
6109 | 6109 | 6109 | 6109 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Hardware & Accessories for Tangent Tower (0 - 2 degree) Issue of RFQ | 2 | HTANG | P000 | 00P2 | P000HTANG00P2
6110 | 6110 | 6110 | 6110 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Hardware & Accessories for Tangent Tower (0 - 2 degree) Receipt of Technical offer from Vendor | 3 | HTANG | P000 | 00P3 | P000HTANG00P3
6111 | 6111 | 6111 | 6111 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Hardware & Accessories for Tangent Tower (0 - 2 degree) Technical Evaluation by EDRC | 4 | HTANG | P000 | 00P4 | P000HTANG00P4
6112 | 6112 | 6112 | 6112 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Hardware & Accessories for Tangent Tower (0 - 2 degree) Final technical compliance from Vendor | 5 | HTANG | P000 | 00P5 | P000HTANG00P5
6113 | 6113 | 6113 | 6113 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Hardware & Accessories for Tangent Tower (0 - 2 degree) Technical clearance by EDRC | 6 | HTANG | P000 | 00P6 | P000HTANG00P6
6114 | 6114 | 6114 | 6114 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Hardware & Accessories for Tangent Tower (0 - 2 degree) Commercial Evaluation by SCM | 7 | HTANG | P000 | 00P7 | P000HTANG00P7
6115 | 6115 | 6115 | 6115 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Hardware & Accessories for Tangent Tower (0 - 2 degree) Vendor negotiation & Finalization | 8 | HTANG | P000 | 00P8 | P000HTANG00P8
6116 | 6116 | 6116 | 6116 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Hardware & Accessories for Tangent Tower (0 - 2 degree) HPC Approval / PO release to vendor | 9 | HTANG | P000 | 00P9 | P000HTANG00P9
6117 | 6117 | 6117 | 6117 | SA24M005 | Hardware & Accessories for Dead-End / Terminal Tower (0 - 30 degree) |  | 3 | -1 | 0 |  |  | X
6118 | 6118 | 6118 | 6118 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Hardware & Accessories for Dead-End / Terminal Tower (0 - 30 degree) Purchase Request to SCM | 1 | HDEAD | P000 | 00P1 | P000HDEAD00P1
6119 | 6119 | 6119 | 6119 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Hardware & Accessories for Dead-End / Terminal Tower (0 - 30 degree) Issue of RFQ | 2 | HDEAD | P000 | 00P2 | P000HDEAD00P2
6120 | 6120 | 6120 | 6120 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Hardware & Accessories for Dead-End / Terminal Tower (0 - 30 degree) Receipt of Technical offer from Vendor | 3 | HDEAD | P000 | 00P3 | P000HDEAD00P3
6121 | 6121 | 6121 | 6121 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Hardware & Accessories for Dead-End / Terminal Tower (0 - 30 degree) Technical Evaluation by EDRC | 4 | HDEAD | P000 | 00P4 | P000HDEAD00P4
6122 | 6122 | 6122 | 6122 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Hardware & Accessories for Dead-End / Terminal Tower (0 - 30 degree) Final technical compliance from Vendor | 5 | HDEAD | P000 | 00P5 | P000HDEAD00P5
6123 | 6123 | 6123 | 6123 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Hardware & Accessories for Dead-End / Terminal Tower (0 - 30 degree) Technical clearance by EDRC | 6 | HDEAD | P000 | 00P6 | P000HDEAD00P6
6124 | 6124 | 6124 | 6124 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Hardware & Accessories for Dead-End / Terminal Tower (0 - 30 degree) Commercial Evaluation by SCM | 7 | HDEAD | P000 | 00P7 | P000HDEAD00P7
6125 | 6125 | 6125 | 6125 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Hardware & Accessories for Dead-End / Terminal Tower (0 - 30 degree) Vendor negotiation & Finalization | 8 | HDEAD | P000 | 00P8 | P000HDEAD00P8
6126 | 6126 | 6126 | 6126 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Hardware & Accessories for Dead-End / Terminal Tower (0 - 30 degree) HPC Approval / PO release to vendor | 9 | HDEAD | P000 | 00P9 | P000HDEAD00P9
6127 | 6127 | 6127 | 6127 | SA24M005 | Hardware & Accessories for Angle Tower (60 - 90 degree) |  | 3 | -1 | 0 |  |  | X
6128 | 6128 | 6128 | 6128 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Hardware & Accessories for Angle Tower (60 - 90 degree) Purchase Request to SCM | 1 | #ePET | P000 | 00P1 | P000#ePET00P1
6129 | 6129 | 6129 | 6129 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Hardware & Accessories for Angle Tower (60 - 90 degree) Issue of RFQ | 2 | #ePET | P000 | 00P2 | P000#ePET00P2
6130 | 6130 | 6130 | 6130 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Hardware & Accessories for Angle Tower (60 - 90 degree) Receipt of Technical offer from Vendor | 3 | #ePET | P000 | 00P3 | P000#ePET00P3
6131 | 6131 | 6131 | 6131 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Hardware & Accessories for Angle Tower (60 - 90 degree) Technical Evaluation by EDRC | 4 | #ePET | P000 | 00P4 | P000#ePET00P4
6132 | 6132 | 6132 | 6132 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Hardware & Accessories for Angle Tower (60 - 90 degree) Final technical compliance from Vendor | 5 | #ePET | P000 | 00P5 | P000#ePET00P5
6133 | 6133 | 6133 | 6133 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Hardware & Accessories for Angle Tower (60 - 90 degree) Technical clearance by EDRC | 6 | #ePET | P000 | 00P6 | P000#ePET00P6
6134 | 6134 | 6134 | 6134 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Hardware & Accessories for Angle Tower (60 - 90 degree) Commercial Evaluation by SCM | 7 | #ePET | P000 | 00P7 | P000#ePET00P7
6135 | 6135 | 6135 | 6135 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Hardware & Accessories for Angle Tower (60 - 90 degree) Vendor negotiation & Finalization | 8 | #ePET | P000 | 00P8 | P000#ePET00P8
6136 | 6136 | 6136 | 6136 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Hardware & Accessories for Angle Tower (60 - 90 degree) HPC Approval / PO release to vendor | 9 | #ePET | P000 | 00P9 | P000#ePET00P9
6137 | 6137 | 6137 | 6137 | SA24M005 | Quard Bundle Conductors |  | 3 | -1 | 0 |  |  | X
6138 | 6138 | 6138 | 6138 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Quard Bundle Conductors Purchase Request to SCM | 1 | 0QUAR | P000 | 00P1 | P0000QUAR00P1
6139 | 6139 | 6139 | 6139 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Quard Bundle Conductors Issue of RFQ | 2 | 0QUAR | P000 | 00P2 | P0000QUAR00P2
6140 | 6140 | 6140 | 6140 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Quard Bundle Conductors Receipt of Technical offer from Vendor | 3 | 0QUAR | P000 | 00P3 | P0000QUAR00P3
6141 | 6141 | 6141 | 6141 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Quard Bundle Conductors Technical Evaluation by EDRC | 4 | 0QUAR | P000 | 00P4 | P0000QUAR00P4
6142 | 6142 | 6142 | 6142 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Quard Bundle Conductors Final technical compliance from Vendor | 5 | 0QUAR | P000 | 00P5 | P0000QUAR00P5
6143 | 6143 | 6143 | 6143 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Quard Bundle Conductors Technical clearance by EDRC | 6 | 0QUAR | P000 | 00P6 | P0000QUAR00P6
6144 | 6144 | 6144 | 6144 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Quard Bundle Conductors Commercial Evaluation by SCM | 7 | 0QUAR | P000 | 00P7 | P0000QUAR00P7
6145 | 6145 | 6145 | 6145 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Quard Bundle Conductors Vendor negotiation & Finalization | 8 | 0QUAR | P000 | 00P8 | P0000QUAR00P8
6146 | 6146 | 6146 | 6146 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Quard Bundle Conductors HPC Approval / PO release to vendor | 9 | 0QUAR | P000 | 00P9 | P0000QUAR00P9
6147 | 6147 | 6147 | 6147 | SA24M005 | Hardware & Accessories for Conductor |  | 3 | -1 | 0 |  |  | X
6148 | 6148 | 6148 | 6148 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Hardware & Accessories for Conductor Purchase Request to SCM | 1 | HCND | P000 | 00P1 | P000HCND00P1
6149 | 6149 | 6149 | 6149 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Hardware & Accessories for Conductor Issue of RFQ | 2 | HCND | P000 | 00P2 | P000HCND00P2
6150 | 6150 | 6150 | 6150 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Hardware & Accessories for Conductor Receipt of Technical offer from Vendor | 3 | HCND | P000 | 00P3 | P000HCND00P3
6151 | 6151 | 6151 | 6151 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Hardware & Accessories for Conductor Technical Evaluation by EDRC | 4 | HCND | P000 | 00P4 | P000HCND00P4
6152 | 6152 | 6152 | 6152 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Hardware & Accessories for Conductor Final technical compliance from Vendor | 5 | HCND | P000 | 00P5 | P000HCND00P5
6153 | 6153 | 6153 | 6153 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Hardware & Accessories for Conductor Technical clearance by EDRC | 6 | HCND | P000 | 00P6 | P000HCND00P6
6154 | 6154 | 6154 | 6154 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Hardware & Accessories for Conductor Commercial Evaluation by SCM | 7 | HCND | P000 | 00P7 | P000HCND00P7
6155 | 6155 | 6155 | 6155 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Hardware & Accessories for Conductor Vendor negotiation & Finalization | 8 | HCND | P000 | 00P8 | P000HCND00P8
6156 | 6156 | 6156 | 6156 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Hardware & Accessories for Conductor HPC Approval / PO release to vendor | 9 | HCND | P000 | 00P9 | P000HCND00P9
6157 | 6157 | 6157 | 6157 | SA24M005 | Spacer Dampers of Main Conductor |  | 3 | -1 | 0 |  |  | X
6158 | 6158 | 6158 | 6158 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Spacer Dampers of Main Conductor Purchase Request to SCM | 1 | 0SPDM | P000 | 00P1 | P0000SPDM00P1
6159 | 6159 | 6159 | 6159 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Spacer Dampers of Main Conductor Issue of RFQ | 2 | 0SPDM | P000 | 00P2 | P0000SPDM00P2
6160 | 6160 | 6160 | 6160 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Spacer Dampers of Main Conductor Receipt of Technical offer from Vendor | 3 | 0SPDM | P000 | 00P3 | P0000SPDM00P3
6161 | 6161 | 6161 | 6161 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Spacer Dampers of Main Conductor Technical Evaluation by EDRC | 4 | 0SPDM | P000 | 00P4 | P0000SPDM00P4
6162 | 6162 | 6162 | 6162 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Spacer Dampers of Main Conductor Final technical compliance from Vendor | 5 | 0SPDM | P000 | 00P5 | P0000SPDM00P5
6163 | 6163 | 6163 | 6163 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Spacer Dampers of Main Conductor Technical clearance by EDRC | 6 | 0SPDM | P000 | 00P6 | P0000SPDM00P6
6164 | 6164 | 6164 | 6164 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Spacer Dampers of Main Conductor Commercial Evaluation by SCM | 7 | 0SPDM | P000 | 00P7 | P0000SPDM00P7
6165 | 6165 | 6165 | 6165 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Spacer Dampers of Main Conductor Vendor negotiation & Finalization | 8 | 0SPDM | P000 | 00P8 | P0000SPDM00P8
6166 | 6166 | 6166 | 6166 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Spacer Dampers of Main Conductor HPC Approval / PO release to vendor | 9 | 0SPDM | P000 | 00P9 | P0000SPDM00P9
6167 | 6167 | 6167 | 6167 | SA24M005 | OPGW |  | 3 | -1 | 0 |  |  | X
6168 | 6168 | 6168 | 6168 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement OPGW Purchase Request to SCM | 1 | OPGW | P000 | 00P1 | P000#Ysvs00P1
6169 | 6169 | 6169 | 6169 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement OPGW Issue of RFQ | 2 | OPGW | P000 | 00P2 | P000#Ysvs00P2
6170 | 6170 | 6170 | 6170 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement OPGW Receipt of Technical offer from Vendor | 3 | OPGW | P000 | 00P3 | P000#Ysvs00P3
6171 | 6171 | 6171 | 6171 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement OPGW Technical Evaluation by EDRC | 4 | OPGW | P000 | 00P4 | P000#Ysvs00P4
6172 | 6172 | 6172 | 6172 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement OPGW Final technical compliance from Vendor | 5 | OPGW | P000 | 00P5 | P000#Ysvs00P5
6173 | 6173 | 6173 | 6173 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement OPGW Technical clearance by EDRC | 6 | OPGW | P000 | 00P6 | P000#Ysvs00P6
6174 | 6174 | 6174 | 6174 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement OPGW Commercial Evaluation by SCM | 7 | OPGW | P000 | 00P7 | P000#Ysvs00P7
6175 | 6175 | 6175 | 6175 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement OPGW Vendor negotiation & Finalization | 8 | OPGW | P000 | 00P8 | P000#Ysvs00P8
6176 | 6176 | 6176 | 6176 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement OPGW HPC Approval / PO release to vendor | 9 | OPGW | P000 | 00P9 | P000#Ysvs00P9
6177 | 6177 | 6177 | 6177 | SA24M005 | OPGW / OGW Hardwares |  | 3 | -1 | 0 |  |  | X | P000#Ysvs
6178 | 6178 | 6178 | 6178 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement OPGW / OGW Hardwares Purchase Request to SCM | 1 | OPGW | P000 | 00P1 | P000#iHEV00P1
6179 | 6179 | 6179 | 6179 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement OPGW / OGW Hardwares Issue of RFQ | 2 | OPGW | P000 | 00P2 | P000#iHEV00P2
6180 | 6180 | 6180 | 6180 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement OPGW / OGW Hardwares Receipt of Technical offer from Vendor | 3 | OPGW | P000 | 00P3 | P000#iHEV00P3
6181 | 6181 | 6181 | 6181 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement OPGW / OGW Hardwares Technical Evaluation by EDRC | 4 | OPGW | P000 | 00P4 | P000#iHEV00P4
6182 | 6182 | 6182 | 6182 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement OPGW / OGW Hardwares Final technical compliance from Vendor | 5 | OPGW | P000 | 00P5 | P000#iHEV00P5
6183 | 6183 | 6183 | 6183 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement OPGW / OGW Hardwares Technical clearance by EDRC | 6 | OPGW | P000 | 00P6 | P000#iHEV00P6
6184 | 6184 | 6184 | 6184 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement OPGW / OGW Hardwares Commercial Evaluation by SCM | 7 | OPGW | P000 | 00P7 | P000#iHEV00P7
6185 | 6185 | 6185 | 6185 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement OPGW / OGW Hardwares Vendor negotiation & Finalization | 8 | OPGW | P000 | 00P8 | P000#iHEV00P8
6186 | 6186 | 6186 | 6186 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement OPGW / OGW Hardwares HPC Approval / PO release to vendor | 9 | OPGW | P000 | 00P9 | P000#iHEV00P9
6187 | 6187 | 6187 | 6187 | SA24M005 | Grounding Material (Earth wire, Roda & Connectors) |  | 3 | -1 | 0 |  |  | X | P000#iHEV
6188 | 6188 | 6188 | 6188 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Grounding Material (Earth wire, Roda & Connectors) Purchase Request to SCM | 1 | 0GRND | P000 | 00P1 | P0000GRND00P1
6189 | 6189 | 6189 | 6189 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Grounding Material (Earth wire, Roda & Connectors) Issue of RFQ | 2 | 0GRND | P000 | 00P2 | P0000GRND00P2
6190 | 6190 | 6190 | 6190 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Grounding Material (Earth wire, Roda & Connectors) Receipt of Technical offer from Vendor | 3 | 0GRND | P000 | 00P3 | P0000GRND00P3
6191 | 6191 | 6191 | 6191 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Grounding Material (Earth wire, Roda & Connectors) Technical Evaluation by EDRC | 4 | 0GRND | P000 | 00P4 | P0000GRND00P4
6192 | 6192 | 6192 | 6192 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Grounding Material (Earth wire, Roda & Connectors) Final technical compliance from Vendor | 5 | 0GRND | P000 | 00P5 | P0000GRND00P5
6193 | 6193 | 6193 | 6193 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Grounding Material (Earth wire, Roda & Connectors) Technical clearance by EDRC | 6 | 0GRND | P000 | 00P6 | P0000GRND00P6
6194 | 6194 | 6194 | 6194 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Grounding Material (Earth wire, Roda & Connectors) Commercial Evaluation by SCM | 7 | 0GRND | P000 | 00P7 | P0000GRND00P7
6195 | 6195 | 6195 | 6195 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Grounding Material (Earth wire, Roda & Connectors) Vendor negotiation & Finalization | 8 | 0GRND | P000 | 00P8 | P0000GRND00P8
6196 | 6196 | 6196 | 6196 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Grounding Material (Earth wire, Roda & Connectors) HPC Approval / PO release to vendor | 9 | 0GRND | P000 | 00P9 | P0000GRND00P9
6197 | 6197 | 6197 | 6197 | SA24M005 | Joint Boxes |  | 3 | -1 | 0 |  |  | X
6198 | 6198 | 6198 | 6198 | SA24M005 | Purchase Request to SCM |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Joint Boxes Purchase Request to SCM | 1 | 0JB0X | P000 | 00P1 | P0000JB0X00P1
6199 | 6199 | 6199 | 6199 | SA24M005 | Issue of RFQ |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Joint Boxes Issue of RFQ | 2 | 0JB0X | P000 | 00P2 | P0000JB0X00P2
6200 | 6200 | 6200 | 6200 | SA24M005 | Receipt of Technical offer from Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Joint Boxes Receipt of Technical offer from Vendor | 3 | 0JB0X | P000 | 00P3 | P0000JB0X00P3
6201 | 6201 | 6201 | 6201 | SA24M005 | Technical Evaluation by EDRC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Joint Boxes Technical Evaluation by EDRC | 4 | 0JB0X | P000 | 00P4 | P0000JB0X00P4
6202 | 6202 | 6202 | 6202 | SA24M005 | Final technical compliance from Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Joint Boxes Final technical compliance from Vendor | 5 | 0JB0X | P000 | 00P5 | P0000JB0X00P5
6203 | 6203 | 6203 | 6203 | SA24M005 | Technical clearance by EDRC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Joint Boxes Technical clearance by EDRC | 6 | 0JB0X | P000 | 00P6 | P0000JB0X00P6
6204 | 6204 | 6204 | 6204 | SA24M005 | Commercial Evaluation by SCM |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Joint Boxes Commercial Evaluation by SCM | 7 | 0JB0X | P000 | 00P7 | P0000JB0X00P7
6205 | 6205 | 6205 | 6205 | SA24M005 | Vendor negotiation & Finalization |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Joint Boxes Vendor negotiation & Finalization | 8 | 0JB0X | P000 | 00P8 | P0000JB0X00P8
6206 | 6206 | 6206 | 6206 | SA24M005 | HPC Approval / PO release to vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Material Procurement Joint Boxes HPC Approval / PO release to vendor | 9 | 0JB0X | P000 | 00P9 | P0000JB0X00P9
6207 | 6207 | 6207 | 6207 | SA24M005 | Inspection & Delivery |  | 2 | -1 | 0 |  |  | X
6208 | 6208 | 6208 | 6208 | SA24M005 | Stubs for Tangent Tower (0 - 2 degree) |  | 3 | -1 | 0 |  |  | X
6209 | 6209 | 6209 | 6209 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Stubs for Tangent Tower (0 - 2 degree) MQP / ITP Submission | 1 | 0STRT | I000 | 00I1 | I0000STRT00I1
6210 | 6210 | 6210 | 6210 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Stubs for Tangent Tower (0 - 2 degree) MQP / ITP Approval | 2 | 0STRT | I000 | 00I2 | I0000STRT00I2
6211 | 6211 | 6211 | 6211 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Stubs for Tangent Tower (0 - 2 degree) Issuance of MFC | 3 | 0STRT | I000 | 00I3 | I0000STRT00I3
6212 | 6212 | 6212 | 6212 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Stubs for Tangent Tower (0 - 2 degree) Lead Time For Manufacturing | 4 | 0STRT | I000 | 00I4 | I0000STRT00I4
6213 | 6213 | 6213 | 6213 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Stubs for Tangent Tower (0 - 2 degree) Material readiness / Inspection call | 5 | 0STRT | I000 | 00I5 | I0000STRT00I5
6214 | 6214 | 6214 | 6214 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Stubs for Tangent Tower (0 - 2 degree) Inspection by client personal / Third Party | 6 | 0STRT | I000 | 00I6 | I0000STRT00I6
6215 | 6215 | 6215 | 6215 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Stubs for Tangent Tower (0 - 2 degree) Submission of FAT Compliance by Vendor | 7 | 0STRT | I000 | 00I7 | I0000STRT00I7
6216 | 6216 | 6216 | 6216 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Stubs for Tangent Tower (0 - 2 degree) Dispatch Clearance to vendor | 8 | 0STRT | I000 | 00I8 | I0000STRT00I8
6217 | 6217 | 6217 | 6217 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Stubs for Tangent Tower (0 - 2 degree) Transportation and Custom clearance | 9 | 0STRT | I000 | 00I9 | I0000STRT00I9
6218 | 6218 | 6218 | 6218 | SA24M005 | Receipt at site |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Stubs for Tangent Tower (0 - 2 degree) Receipt at site | 10 | 0STRT | I000 | 0I10 | I0000STRT0I10
6219 | 6219 | 6219 | 6219 | SA24M005 | Stubs for Dead-End / Terminal Tower (0 - 30 degree) |  | 3 | -1 | 0 |  |  | X
6220 | 6220 | 6220 | 6220 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Stubs for Dead-End / Terminal Tower (0 - 30 degree) MQP / ITP Submission | 1 | 0STRB | I000 | 00I1 | I0000STRB00I1
6221 | 6221 | 6221 | 6221 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Stubs for Dead-End / Terminal Tower (0 - 30 degree) MQP / ITP Approval | 2 | 0STRB | I000 | 00I2 | I0000STRB00I2
6222 | 6222 | 6222 | 6222 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Stubs for Dead-End / Terminal Tower (0 - 30 degree) Issuance of MFC | 3 | 0STRB | I000 | 00I3 | I0000STRB00I3
6223 | 6223 | 6223 | 6223 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Stubs for Dead-End / Terminal Tower (0 - 30 degree) Lead Time For Manufacturing | 4 | 0STRB | I000 | 00I4 | I0000STRB00I4
6224 | 6224 | 6224 | 6224 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Stubs for Dead-End / Terminal Tower (0 - 30 degree) Material readiness / Inspection call | 5 | 0STRB | I000 | 00I5 | I0000STRB00I5
6225 | 6225 | 6225 | 6225 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Stubs for Dead-End / Terminal Tower (0 - 30 degree) Inspection by client personal / Third Party | 6 | 0STRB | I000 | 00I6 | I0000STRB00I6
6226 | 6226 | 6226 | 6226 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Stubs for Dead-End / Terminal Tower (0 - 30 degree) Submission of FAT Compliance by Vendor | 7 | 0STRB | I000 | 00I7 | I0000STRB00I7
6227 | 6227 | 6227 | 6227 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Stubs for Dead-End / Terminal Tower (0 - 30 degree) Dispatch Clearance to vendor | 8 | 0STRB | I000 | 00I8 | I0000STRB00I8
6228 | 6228 | 6228 | 6228 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Stubs for Dead-End / Terminal Tower (0 - 30 degree) Transportation and Custom clearance | 9 | 0STRB | I000 | 00I9 | I0000STRB00I9
6229 | 6229 | 6229 | 6229 | SA24M005 | Receipt at site |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Stubs for Dead-End / Terminal Tower (0 - 30 degree) Receipt at site | 10 | 0STRB | I000 | 0I10 | I0000STRB0I10
6230 | 6230 | 6230 | 6230 | SA24M005 | Stubs for Heavy Angle Tower (60 - 90 degree) |  | 3 | -1 | 0 |  |  | X
6231 | 6231 | 6231 | 6231 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Stubs for Heavy Angle Tower (60 - 90 degree) MQP / ITP Submission | 1 | 0SBHA | I000 | 00I1 | I0000SBHA00I1
6232 | 6232 | 6232 | 6232 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Stubs for Heavy Angle Tower (60 - 90 degree) MQP / ITP Approval | 2 | 0SBHA | I000 | 00I2 | I0000SBHA00I2
6233 | 6233 | 6233 | 6233 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Stubs for Heavy Angle Tower (60 - 90 degree) Issuance of MFC | 3 | 0SBHA | I000 | 00I3 | I0000SBHA00I3
6234 | 6234 | 6234 | 6234 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Stubs for Heavy Angle Tower (60 - 90 degree) Lead Time For Manufacturing | 4 | 0SBHA | I000 | 00I4 | I0000SBHA00I4
6235 | 6235 | 6235 | 6235 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Stubs for Heavy Angle Tower (60 - 90 degree) Material readiness / Inspection call | 5 | 0SBHA | I000 | 00I5 | I0000SBHA00I5
6236 | 6236 | 6236 | 6236 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Stubs for Heavy Angle Tower (60 - 90 degree) Inspection by client personal / Third Party | 6 | 0SBHA | I000 | 00I6 | I0000SBHA00I6
6237 | 6237 | 6237 | 6237 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Stubs for Heavy Angle Tower (60 - 90 degree) Submission of FAT Compliance by Vendor | 7 | 0SBHA | I000 | 00I7 | I0000SBHA00I7
6238 | 6238 | 6238 | 6238 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Stubs for Heavy Angle Tower (60 - 90 degree) Dispatch Clearance to vendor | 8 | 0SBHA | I000 | 00I8 | I0000SBHA00I8
6239 | 6239 | 6239 | 6239 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Stubs for Heavy Angle Tower (60 - 90 degree) Transportation and Custom clearance | 9 | 0SBHA | I000 | 00I9 | I0000SBHA00I9
6240 | 6240 | 6240 | 6240 | SA24M005 | Receipt at site |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Stubs for Heavy Angle Tower (60 - 90 degree) Receipt at site | 10 | 0SBHA | I000 | 0I10 | I0000SBHA0I10
6241 | 6241 | 6241 | 6241 | SA24M005 | Lattice Structure for Tangent Tower (0 - 2 degree) |  | 3 | -1 | 0 |  |  | X
6242 | 6242 | 6242 | 6242 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Lattice Structure for Tangent Tower (0 - 2 degree) MQP / ITP Submission | 1 | 0LSTR | I000 | 00I1 | I0000LSTR00I1
6243 | 6243 | 6243 | 6243 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Lattice Structure for Tangent Tower (0 - 2 degree) MQP / ITP Approval | 2 | 0LSTR | I000 | 00I2 | I0000LSTR00I2
6244 | 6244 | 6244 | 6244 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Lattice Structure for Tangent Tower (0 - 2 degree) Issuance of MFC | 3 | 0LSTR | I000 | 00I3 | I0000LSTR00I3
6245 | 6245 | 6245 | 6245 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Lattice Structure for Tangent Tower (0 - 2 degree) Lead Time For Manufacturing | 4 | 0LSTR | I000 | 00I4 | I0000LSTR00I4
6246 | 6246 | 6246 | 6246 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Lattice Structure for Tangent Tower (0 - 2 degree) Material readiness / Inspection call | 5 | 0LSTR | I000 | 00I5 | I0000LSTR00I5
6247 | 6247 | 6247 | 6247 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Lattice Structure for Tangent Tower (0 - 2 degree) Inspection by client personal / Third Party | 6 | 0LSTR | I000 | 00I6 | I0000LSTR00I6
6248 | 6248 | 6248 | 6248 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Lattice Structure for Tangent Tower (0 - 2 degree) Submission of FAT Compliance by Vendor | 7 | 0LSTR | I000 | 00I7 | I0000LSTR00I7
6249 | 6249 | 6249 | 6249 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Lattice Structure for Tangent Tower (0 - 2 degree) Dispatch Clearance to vendor | 8 | 0LSTR | I000 | 00I8 | I0000LSTR00I8
6250 | 6250 | 6250 | 6250 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Lattice Structure for Tangent Tower (0 - 2 degree) Transportation and Custom clearance | 9 | 0LSTR | I000 | 00I9 | I0000LSTR00I9
6251 | 6251 | 6251 | 6251 | SA24M005 | Receipt at site |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Lattice Structure for Tangent Tower (0 - 2 degree) Receipt at site | 10 | 0LSTR | I000 | 0I10 | I0000LSTR0I10
6252 | 6252 | 6252 | 6252 | SA24M005 | Lattice Structure for Dead-End / Terminal Tower (0 - 30 degree) |  | 3 | -1 | 0 |  |  | X
6253 | 6253 | 6253 | 6253 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Lattice Structure for Dead-End / Terminal Tower (0 - 30 degree) MQP / ITP Submission | 1 | #knPL | I000 | 00I1 | I000#knPL00I1
6254 | 6254 | 6254 | 6254 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Lattice Structure for Dead-End / Terminal Tower (0 - 30 degree) MQP / ITP Approval | 2 | #knPL | I000 | 00I2 | I000#knPL00I2
6255 | 6255 | 6255 | 6255 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Lattice Structure for Dead-End / Terminal Tower (0 - 30 degree) Issuance of MFC | 3 | #knPL | I000 | 00I3 | I000#knPL00I3
6256 | 6256 | 6256 | 6256 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Lattice Structure for Dead-End / Terminal Tower (0 - 30 degree) Lead Time For Manufacturing | 4 | #knPL | I000 | 00I4 | I000#knPL00I4
6257 | 6257 | 6257 | 6257 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Lattice Structure for Dead-End / Terminal Tower (0 - 30 degree) Material readiness / Inspection call | 5 | #knPL | I000 | 00I5 | I000#knPL00I5
6258 | 6258 | 6258 | 6258 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Lattice Structure for Dead-End / Terminal Tower (0 - 30 degree) Inspection by client personal / Third Party | 6 | #knPL | I000 | 00I6 | I000#knPL00I6
6259 | 6259 | 6259 | 6259 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Lattice Structure for Dead-End / Terminal Tower (0 - 30 degree) Submission of FAT Compliance by Vendor | 7 | #knPL | I000 | 00I7 | I000#knPL00I7
6260 | 6260 | 6260 | 6260 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Lattice Structure for Dead-End / Terminal Tower (0 - 30 degree) Dispatch Clearance to vendor | 8 | #knPL | I000 | 00I8 | I000#knPL00I8
6261 | 6261 | 6261 | 6261 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Lattice Structure for Dead-End / Terminal Tower (0 - 30 degree) Transportation and Custom clearance | 9 | #knPL | I000 | 00I9 | I000#knPL00I9
6262 | 6262 | 6262 | 6262 | SA24M005 | Receipt at site |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Lattice Structure for Dead-End / Terminal Tower (0 - 30 degree) Receipt at site | 10 | #knPL | I000 | 0I10 | I000#knPL0I10
6263 | 6263 | 6263 | 6263 | SA24M005 | Lattice Structure for Heavy Angle Tower (60 - 90 degree) |  | 3 | -1 | 0 |  |  | X
6264 | 6264 | 6264 | 6264 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Lattice Structure for Heavy Angle Tower (60 - 90 degree) MQP / ITP Submission | 1 | 00LSR | I000 | 00I1 | I000#ISDV00I1
6265 | 6265 | 6265 | 6265 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Lattice Structure for Heavy Angle Tower (60 - 90 degree) MQP / ITP Approval | 2 | 00LSR | I000 | 00I2 | I000#ISDV00I2
6266 | 6266 | 6266 | 6266 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Lattice Structure for Heavy Angle Tower (60 - 90 degree) Issuance of MFC | 3 | 00LSR | I000 | 00I3 | I000#ISDV00I3
6267 | 6267 | 6267 | 6267 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Lattice Structure for Heavy Angle Tower (60 - 90 degree) Lead Time For Manufacturing | 4 | 00LSR | I000 | 00I4 | I000#ISDV00I4
6268 | 6268 | 6268 | 6268 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Lattice Structure for Heavy Angle Tower (60 - 90 degree) Material readiness / Inspection call | 5 | 00LSR | I000 | 00I5 | I000#ISDV00I5
6269 | 6269 | 6269 | 6269 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Lattice Structure for Heavy Angle Tower (60 - 90 degree) Inspection by client personal / Third Party | 6 | 00LSR | I000 | 00I6 | I000#ISDV00I6
6270 | 6270 | 6270 | 6270 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Lattice Structure for Heavy Angle Tower (60 - 90 degree) Submission of FAT Compliance by Vendor | 7 | 00LSR | I000 | 00I7 | I000#ISDV00I7
6271 | 6271 | 6271 | 6271 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Lattice Structure for Heavy Angle Tower (60 - 90 degree) Dispatch Clearance to vendor | 8 | 00LSR | I000 | 00I8 | I000#ISDV00I8
6272 | 6272 | 6272 | 6272 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Lattice Structure for Heavy Angle Tower (60 - 90 degree) Transportation and Custom clearance | 9 | 00LSR | I000 | 00I9 | I000#ISDV00I9
6273 | 6273 | 6273 | 6273 | SA24M005 | Receipt at site |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Lattice Structure for Heavy Angle Tower (60 - 90 degree) Receipt at site | 10 | 00LSR | I000 | 0I10 | I000#ISDV0I10
6274 | 6274 | 6274 | 6274 | SA24M005 | Insulators for Tangent Tower (0 - 2 degree) |  | 3 | -1 | 0 |  |  | X | I000#ISDV
6275 | 6275 | 6275 | 6275 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Insulators for Tangent Tower (0 - 2 degree) MQP / ITP Submission | 1 | IN0TAN | I000 | 00I1 | I000IN0TAN00I1
6276 | 6276 | 6276 | 6276 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Insulators for Tangent Tower (0 - 2 degree) MQP / ITP Approval | 2 | IN0TAN | I000 | 00I2 | I000IN0TAN00I2
6277 | 6277 | 6277 | 6277 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Insulators for Tangent Tower (0 - 2 degree) Issuance of MFC | 3 | IN0TAN | I000 | 00I3 | I000IN0TAN00I3
6278 | 6278 | 6278 | 6278 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Insulators for Tangent Tower (0 - 2 degree) Lead Time For Manufacturing | 4 | IN0TAN | I000 | 00I4 | I000IN0TAN00I4
6279 | 6279 | 6279 | 6279 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Insulators for Tangent Tower (0 - 2 degree) Material readiness / Inspection call | 5 | IN0TAN | I000 | 00I5 | I000IN0TAN00I5
6280 | 6280 | 6280 | 6280 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Insulators for Tangent Tower (0 - 2 degree) Inspection by client personal / Third Party | 6 | IN0TAN | I000 | 00I6 | I000IN0TAN00I6
6281 | 6281 | 6281 | 6281 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Insulators for Tangent Tower (0 - 2 degree) Submission of FAT Compliance by Vendor | 7 | IN0TAN | I000 | 00I7 | I000IN0TAN00I7
6282 | 6282 | 6282 | 6282 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Insulators for Tangent Tower (0 - 2 degree) Dispatch Clearance to vendor | 8 | IN0TAN | I000 | 00I8 | I000IN0TAN00I8
6283 | 6283 | 6283 | 6283 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Insulators for Tangent Tower (0 - 2 degree) Transportation and Custom clearance | 9 | IN0TAN | I000 | 00I9 | I000IN0TAN00I9
6284 | 6284 | 6284 | 6284 | SA24M005 | Receipt at site |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Insulators for Tangent Tower (0 - 2 degree) Receipt at site | 10 | IN0TAN | I000 | 0I10 | I000IN0TAN0I10
6285 | 6285 | 6285 | 6285 | SA24M005 | Insulators for Dead-End / Terminal Tower (0 - 30 degree) |  | 3 | -1 | 0 |  |  | X
6286 | 6286 | 6286 | 6286 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Insulators for Dead-End / Terminal Tower (0 - 30 degree) MQP / ITP Submission | 1 | MQP | I000 | 00I1 | I000MQP00I1
6287 | 6287 | 6287 | 6287 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Insulators for Dead-End / Terminal Tower (0 - 30 degree) MQP / ITP Approval | 2 | MQP | I000 | 00I2 | I000MQP00I2
6288 | 6288 | 6288 | 6288 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Insulators for Dead-End / Terminal Tower (0 - 30 degree) Issuance of MFC | 3 | MQP | I000 | 00I3 | I000MQP00I3
6289 | 6289 | 6289 | 6289 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Insulators for Dead-End / Terminal Tower (0 - 30 degree) Lead Time For Manufacturing | 4 | MQP | I000 | 00I4 | I000MQP00I4
6290 | 6290 | 6290 | 6290 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Insulators for Dead-End / Terminal Tower (0 - 30 degree) Material readiness / Inspection call | 5 | MQP | I000 | 00I5 | I000MQP00I5
6291 | 6291 | 6291 | 6291 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Insulators for Dead-End / Terminal Tower (0 - 30 degree) Inspection by client personal / Third Party | 6 | MQP | I000 | 00I6 | I000MQP00I6
6292 | 6292 | 6292 | 6292 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Insulators for Dead-End / Terminal Tower (0 - 30 degree) Submission of FAT Compliance by Vendor | 7 | MQP | I000 | 00I7 | I000MQP00I7
6293 | 6293 | 6293 | 6293 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Insulators for Dead-End / Terminal Tower (0 - 30 degree) Dispatch Clearance to vendor | 8 | MQP | I000 | 00I8 | I000MQP00I8
6294 | 6294 | 6294 | 6294 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Insulators for Dead-End / Terminal Tower (0 - 30 degree) Transportation and Custom clearance | 9 | MQP | I000 | 00I9 | I000MQP00I9
6295 | 6295 | 6295 | 6295 | SA24M005 | Receipt at site |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Insulators for Dead-End / Terminal Tower (0 - 30 degree) Receipt at site | 10 | MQP | I000 | 0I10 | I000MQP0I10
6296 | 6296 | 6296 | 6296 | SA24M005 | Insulators for Heavy Angle Tower (60 - 90 degree) |  | 3 | -1 | 0 |  |  | X
6297 | 6297 | 6297 | 6297 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Insulators for Heavy Angle Tower (60 - 90 degree) MQP / ITP Submission | 1 | IHAT | I000 | 00I1 | I000IHAT00I1
6298 | 6298 | 6298 | 6298 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Insulators for Heavy Angle Tower (60 - 90 degree) MQP / ITP Approval | 2 | IHAT | I000 | 00I2 | I000IHAT00I2
6299 | 6299 | 6299 | 6299 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Insulators for Heavy Angle Tower (60 - 90 degree) Issuance of MFC | 3 | IHAT | I000 | 00I3 | I000IHAT00I3
6300 | 6300 | 6300 | 6300 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Insulators for Heavy Angle Tower (60 - 90 degree) Lead Time For Manufacturing | 4 | IHAT | I000 | 00I4 | I000IHAT00I4
6301 | 6301 | 6301 | 6301 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Insulators for Heavy Angle Tower (60 - 90 degree) Material readiness / Inspection call | 5 | IHAT | I000 | 00I5 | I000IHAT00I5
6302 | 6302 | 6302 | 6302 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Insulators for Heavy Angle Tower (60 - 90 degree) Inspection by client personal / Third Party | 6 | IHAT | I000 | 00I6 | I000IHAT00I6
6303 | 6303 | 6303 | 6303 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Insulators for Heavy Angle Tower (60 - 90 degree) Submission of FAT Compliance by Vendor | 7 | IHAT | I000 | 00I7 | I000IHAT00I7
6304 | 6304 | 6304 | 6304 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Insulators for Heavy Angle Tower (60 - 90 degree) Dispatch Clearance to vendor | 8 | IHAT | I000 | 00I8 | I000IHAT00I8
6305 | 6305 | 6305 | 6305 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Insulators for Heavy Angle Tower (60 - 90 degree) Transportation and Custom clearance | 9 | IHAT | I000 | 00I9 | I000IHAT00I9
6306 | 6306 | 6306 | 6306 | SA24M005 | Receipt at site |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Insulators for Heavy Angle Tower (60 - 90 degree) Receipt at site | 10 | IHAT | I000 | 0I10 | I000IHAT0I10
6307 | 6307 | 6307 | 6307 | SA24M005 | Hardware & Accessories for Tangent Tower (0 - 2 degree) |  | 3 | -1 | 0 |  |  | X
6308 | 6308 | 6308 | 6308 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Hardware & Accessories for Tangent Tower (0 - 2 degree) MQP / ITP Submission | 1 | 0HWTA | I000 | 00I1 | I0000HWTA00I1
6309 | 6309 | 6309 | 6309 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Hardware & Accessories for Tangent Tower (0 - 2 degree) MQP / ITP Approval | 2 | 0HWTA | I000 | 00I2 | I0000HWTA00I2
6310 | 6310 | 6310 | 6310 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Hardware & Accessories for Tangent Tower (0 - 2 degree) Issuance of MFC | 3 | 0HWTA | I000 | 00I3 | I0000HWTA00I3
6311 | 6311 | 6311 | 6311 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Hardware & Accessories for Tangent Tower (0 - 2 degree) Lead Time For Manufacturing | 4 | 0HWTA | I000 | 00I4 | I0000HWTA00I4
6312 | 6312 | 6312 | 6312 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Hardware & Accessories for Tangent Tower (0 - 2 degree) Material readiness / Inspection call | 5 | 0HWTA | I000 | 00I5 | I0000HWTA00I5
6313 | 6313 | 6313 | 6313 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Hardware & Accessories for Tangent Tower (0 - 2 degree) Inspection by client personal / Third Party | 6 | 0HWTA | I000 | 00I6 | I0000HWTA00I6
6314 | 6314 | 6314 | 6314 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Hardware & Accessories for Tangent Tower (0 - 2 degree) Submission of FAT Compliance by Vendor | 7 | 0HWTA | I000 | 00I7 | I0000HWTA00I7
6315 | 6315 | 6315 | 6315 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Hardware & Accessories for Tangent Tower (0 - 2 degree) Dispatch Clearance to vendor | 8 | 0HWTA | I000 | 00I8 | I0000HWTA00I8
6316 | 6316 | 6316 | 6316 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Hardware & Accessories for Tangent Tower (0 - 2 degree) Transportation and Custom clearance | 9 | 0HWTA | I000 | 00I9 | I0000HWTA00I9
6317 | 6317 | 6317 | 6317 | SA24M005 | Receipt at site |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Hardware & Accessories for Tangent Tower (0 - 2 degree) Receipt at site | 10 | 0HWTA | I000 | 0I10 | I0000HWTA0I10
6318 | 6318 | 6318 | 6318 | SA24M005 | Hardware & Accessories for Dead-End / Terminal Tower (0 - 30 degree) |  | 3 | -1 | 0 |  |  | X
6319 | 6319 | 6319 | 6319 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Hardware & Accessories for Dead-End / Terminal Tower (0 - 30 degree) MQP / ITP Submission | 1 | 0HWAC | I000 | 00I1 | I0000HWAC00I1
6320 | 6320 | 6320 | 6320 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Hardware & Accessories for Dead-End / Terminal Tower (0 - 30 degree) MQP / ITP Approval | 2 | 0HWAC | I000 | 00I2 | I0000HWAC00I2
6321 | 6321 | 6321 | 6321 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Hardware & Accessories for Dead-End / Terminal Tower (0 - 30 degree) Issuance of MFC | 3 | 0HWAC | I000 | 00I3 | I0000HWAC00I3
6322 | 6322 | 6322 | 6322 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Hardware & Accessories for Dead-End / Terminal Tower (0 - 30 degree) Lead Time For Manufacturing | 4 | 0HWAC | I000 | 00I4 | I0000HWAC00I4
6323 | 6323 | 6323 | 6323 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Hardware & Accessories for Dead-End / Terminal Tower (0 - 30 degree) Material readiness / Inspection call | 5 | 0HWAC | I000 | 00I5 | I0000HWAC00I5
6324 | 6324 | 6324 | 6324 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Hardware & Accessories for Dead-End / Terminal Tower (0 - 30 degree) Inspection by client personal / Third Party | 6 | 0HWAC | I000 | 00I6 | I0000HWAC00I6
6325 | 6325 | 6325 | 6325 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Hardware & Accessories for Dead-End / Terminal Tower (0 - 30 degree) Submission of FAT Compliance by Vendor | 7 | 0HWAC | I000 | 00I7 | I0000HWAC00I7
6326 | 6326 | 6326 | 6326 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Hardware & Accessories for Dead-End / Terminal Tower (0 - 30 degree) Dispatch Clearance to vendor | 8 | 0HWAC | I000 | 00I8 | I0000HWAC00I8
6327 | 6327 | 6327 | 6327 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Hardware & Accessories for Dead-End / Terminal Tower (0 - 30 degree) Transportation and Custom clearance | 9 | 0HWAC | I000 | 00I9 | I0000HWAC00I9
6328 | 6328 | 6328 | 6328 | SA24M005 | Receipt at site |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Hardware & Accessories for Dead-End / Terminal Tower (0 - 30 degree) Receipt at site | 10 | 0HWAC | I000 | 0I10 | I0000HWAC0I10
6329 | 6329 | 6329 | 6329 | SA24M005 | Hardware & Accessories for Angle Tower (60 - 90 degree) |  | 3 | -1 | 0 |  |  | X
6330 | 6330 | 6330 | 6330 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Hardware & Accessories for Angle Tower (60 - 90 degree) MQP / ITP Submission | 1 | #trmH | I000 | 00I1 | I000#trmH00I1
6331 | 6331 | 6331 | 6331 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Hardware & Accessories for Angle Tower (60 - 90 degree) MQP / ITP Approval | 2 | #trmH | I000 | 00I2 | I000#trmH00I2
6332 | 6332 | 6332 | 6332 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Hardware & Accessories for Angle Tower (60 - 90 degree) Issuance of MFC | 3 | #trmH | I000 | 00I3 | I000#trmH00I3
6333 | 6333 | 6333 | 6333 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Hardware & Accessories for Angle Tower (60 - 90 degree) Lead Time For Manufacturing | 4 | #trmH | I000 | 00I4 | I000#trmH00I4
6334 | 6334 | 6334 | 6334 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Hardware & Accessories for Angle Tower (60 - 90 degree) Material readiness / Inspection call | 5 | #trmH | I000 | 00I5 | I000#trmH00I5
6335 | 6335 | 6335 | 6335 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Hardware & Accessories for Angle Tower (60 - 90 degree) Inspection by client personal / Third Party | 6 | #trmH | I000 | 00I6 | I000#trmH00I6
6336 | 6336 | 6336 | 6336 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Hardware & Accessories for Angle Tower (60 - 90 degree) Submission of FAT Compliance by Vendor | 7 | #trmH | I000 | 00I7 | I000#trmH00I7
6337 | 6337 | 6337 | 6337 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Hardware & Accessories for Angle Tower (60 - 90 degree) Dispatch Clearance to vendor | 8 | #trmH | I000 | 00I8 | I000#trmH00I8
6338 | 6338 | 6338 | 6338 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Hardware & Accessories for Angle Tower (60 - 90 degree) Transportation and Custom clearance | 9 | #trmH | I000 | 00I9 | I000#trmH00I9
6339 | 6339 | 6339 | 6339 | SA24M005 | Receipt at site |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Hardware & Accessories for Angle Tower (60 - 90 degree) Receipt at site | 10 | #trmH | I000 | 0I10 | I000#trmH0I10
6340 | 6340 | 6340 | 6340 | SA24M005 | Quard Bundle Conductors |  | 3 | -1 | 0 |  |  | X
6341 | 6341 | 6341 | 6341 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Quard Bundle Conductors MQP / ITP Submission | 1 | 0QUAR | I000 | 00I1 | I0000QUAR00I1
6342 | 6342 | 6342 | 6342 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Quard Bundle Conductors MQP / ITP Approval | 2 | 0QUAR | I000 | 00I2 | I0000QUAR00I2
6343 | 6343 | 6343 | 6343 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Quard Bundle Conductors Issuance of MFC | 3 | 0QUAR | I000 | 00I3 | I0000QUAR00I3
6344 | 6344 | 6344 | 6344 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Quard Bundle Conductors Lead Time For Manufacturing | 4 | 0QUAR | I000 | 00I4 | I0000QUAR00I4
6345 | 6345 | 6345 | 6345 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Quard Bundle Conductors Material readiness / Inspection call | 5 | 0QUAR | I000 | 00I5 | I0000QUAR00I5
6346 | 6346 | 6346 | 6346 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Quard Bundle Conductors Inspection by client personal / Third Party | 6 | 0QUAR | I000 | 00I6 | I0000QUAR00I6
6347 | 6347 | 6347 | 6347 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Quard Bundle Conductors Submission of FAT Compliance by Vendor | 7 | 0QUAR | I000 | 00I7 | I0000QUAR00I7
6348 | 6348 | 6348 | 6348 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Quard Bundle Conductors Dispatch Clearance to vendor | 8 | 0QUAR | I000 | 00I8 | I0000QUAR00I8
6349 | 6349 | 6349 | 6349 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Quard Bundle Conductors Transportation and Custom clearance | 9 | 0QUAR | I000 | 00I9 | I0000QUAR00I9
6350 | 6350 | 6350 | 6350 | SA24M005 | Receipt at site |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Quard Bundle Conductors Receipt at site | 10 | 0QUAR | I000 | 0I10 | I0000QUAR0I10
6351 | 6351 | 6351 | 6351 | SA24M005 | Hardware & Accessories for Conductor |  | 3 | -1 | 0 |  |  | X
6352 | 6352 | 6352 | 6352 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Hardware & Accessories for Conductor MQP / ITP Submission | 1 | HCND | I000 | 00I1 | I000HCND00I1
6353 | 6353 | 6353 | 6353 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Hardware & Accessories for Conductor MQP / ITP Approval | 2 | HCND | I000 | 00I2 | I000HCND00I2
6354 | 6354 | 6354 | 6354 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Hardware & Accessories for Conductor Issuance of MFC | 3 | HCND | I000 | 00I3 | I000HCND00I3
6355 | 6355 | 6355 | 6355 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Hardware & Accessories for Conductor Lead Time For Manufacturing | 4 | HCND | I000 | 00I4 | I000HCND00I4
6356 | 6356 | 6356 | 6356 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Hardware & Accessories for Conductor Material readiness / Inspection call | 5 | HCND | I000 | 00I5 | I000HCND00I5
6357 | 6357 | 6357 | 6357 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Hardware & Accessories for Conductor Inspection by client personal / Third Party | 6 | HCND | I000 | 00I6 | I000HCND00I6
6358 | 6358 | 6358 | 6358 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Hardware & Accessories for Conductor Submission of FAT Compliance by Vendor | 7 | HCND | I000 | 00I7 | I000HCND00I7
6359 | 6359 | 6359 | 6359 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Hardware & Accessories for Conductor Dispatch Clearance to vendor | 8 | HCND | I000 | 00I8 | I000HCND00I8
6360 | 6360 | 6360 | 6360 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Hardware & Accessories for Conductor Transportation and Custom clearance | 9 | HCND | I000 | 00I9 | I000HCND00I9
6361 | 6361 | 6361 | 6361 | SA24M005 | Receipt at site |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Hardware & Accessories for Conductor Receipt at site | 10 | HCND | I000 | 0I10 | I000HCND0I10
6362 | 6362 | 6362 | 6362 | SA24M005 | Spacer Dampers of Main Conductor |  | 3 | -1 | 0 |  |  | X
6363 | 6363 | 6363 | 6363 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Spacer Dampers of Main Conductor MQP / ITP Submission | 1 | 0SPMC | I000 | 00I1 | I0000SPMC00I1
6364 | 6364 | 6364 | 6364 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Spacer Dampers of Main Conductor MQP / ITP Approval | 2 | 0SPMC | I000 | 00I2 | I0000SPMC00I2
6365 | 6365 | 6365 | 6365 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Spacer Dampers of Main Conductor Issuance of MFC | 3 | 0SPMC | I000 | 00I3 | I0000SPMC00I3
6366 | 6366 | 6366 | 6366 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Spacer Dampers of Main Conductor Lead Time For Manufacturing | 4 | 0SPMC | I000 | 00I4 | I0000SPMC00I4
6367 | 6367 | 6367 | 6367 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Spacer Dampers of Main Conductor Material readiness / Inspection call | 5 | 0SPMC | I000 | 00I5 | I0000SPMC00I5
6368 | 6368 | 6368 | 6368 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Spacer Dampers of Main Conductor Inspection by client personal / Third Party | 6 | 0SPMC | I000 | 00I6 | I0000SPMC00I6
6369 | 6369 | 6369 | 6369 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Spacer Dampers of Main Conductor Submission of FAT Compliance by Vendor | 7 | 0SPMC | I000 | 00I7 | I0000SPMC00I7
6370 | 6370 | 6370 | 6370 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Spacer Dampers of Main Conductor Dispatch Clearance to vendor | 8 | 0SPMC | I000 | 00I8 | I0000SPMC00I8
6371 | 6371 | 6371 | 6371 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Spacer Dampers of Main Conductor Transportation and Custom clearance | 9 | 0SPMC | I000 | 00I9 | I0000SPMC00I9
6372 | 6372 | 6372 | 6372 | SA24M005 | Receipt at site |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Spacer Dampers of Main Conductor Receipt at site | 10 | 0SPMC | I000 | 0I10 | I0000SPMC0I10
6373 | 6373 | 6373 | 6373 | SA24M005 | OPGW |  | 3 | -1 | 0 |  |  | X
6374 | 6374 | 6374 | 6374 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery OPGW MQP / ITP Submission | 1 | OPGW | I000 | 00I1 | I000#AtER00I1
6375 | 6375 | 6375 | 6375 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery OPGW MQP / ITP Approval | 2 | OPGW | I000 | 00I2 | I000#AtER00I2
6376 | 6376 | 6376 | 6376 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery OPGW Issuance of MFC | 3 | OPGW | I000 | 00I3 | I000#AtER00I3
6377 | 6377 | 6377 | 6377 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery OPGW Lead Time For Manufacturing | 4 | OPGW | I000 | 00I4 | I000#AtER00I4
6378 | 6378 | 6378 | 6378 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery OPGW Material readiness / Inspection call | 5 | OPGW | I000 | 00I5 | I000#AtER00I5
6379 | 6379 | 6379 | 6379 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery OPGW Inspection by client personal / Third Party | 6 | OPGW | I000 | 00I6 | I000#AtER00I6
6380 | 6380 | 6380 | 6380 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery OPGW Submission of FAT Compliance by Vendor | 7 | OPGW | I000 | 00I7 | I000#AtER00I7
6381 | 6381 | 6381 | 6381 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery OPGW Dispatch Clearance to vendor | 8 | OPGW | I000 | 00I8 | I000#AtER00I8
6382 | 6382 | 6382 | 6382 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery OPGW Transportation and Custom clearance | 9 | OPGW | I000 | 00I9 | I000#AtER00I9
6383 | 6383 | 6383 | 6383 | SA24M005 | Receipt at site |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery OPGW Receipt at site | 10 | OPGW | I000 | 0I10 | I000#AtER0I10
6384 | 6384 | 6384 | 6384 | SA24M005 | OPGW / OGW Hardwares |  | 3 | -1 | 0 |  |  | X | I000#AtER
6385 | 6385 | 6385 | 6385 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery OPGW / OGW Hardwares MQP / ITP Submission | 1 | OPGW | I000 | 00I1 | I000#mCSp00I1
6386 | 6386 | 6386 | 6386 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery OPGW / OGW Hardwares MQP / ITP Approval | 2 | OPGW | I000 | 00I2 | I000#mCSp00I2
6387 | 6387 | 6387 | 6387 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery OPGW / OGW Hardwares Issuance of MFC | 3 | OPGW | I000 | 00I3 | I000#mCSp00I3
6388 | 6388 | 6388 | 6388 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery OPGW / OGW Hardwares Lead Time For Manufacturing | 4 | OPGW | I000 | 00I4 | I000#mCSp00I4
6389 | 6389 | 6389 | 6389 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery OPGW / OGW Hardwares Material readiness / Inspection call | 5 | OPGW | I000 | 00I5 | I000#mCSp00I5
6390 | 6390 | 6390 | 6390 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery OPGW / OGW Hardwares Inspection by client personal / Third Party | 6 | OPGW | I000 | 00I6 | I000#mCSp00I6
6391 | 6391 | 6391 | 6391 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery OPGW / OGW Hardwares Submission of FAT Compliance by Vendor | 7 | OPGW | I000 | 00I7 | I000#mCSp00I7
6392 | 6392 | 6392 | 6392 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery OPGW / OGW Hardwares Dispatch Clearance to vendor | 8 | OPGW | I000 | 00I8 | I000#mCSp00I8
6393 | 6393 | 6393 | 6393 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery OPGW / OGW Hardwares Transportation and Custom clearance | 9 | OPGW | I000 | 00I9 | I000#mCSp00I9
6394 | 6394 | 6394 | 6394 | SA24M005 | Receipt at site |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery OPGW / OGW Hardwares Receipt at site | 10 | OPGW | I000 | 0I10 | I000#mCSp0I10
6395 | 6395 | 6395 | 6395 | SA24M005 | Grounding Material (Earth wire, Roda & Connectors) |  | 3 | -1 | 0 |  |  | X | I000#mCSp
6396 | 6396 | 6396 | 6396 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Grounding Material (Earth wire, Roda & Connectors) MQP / ITP Submission | 1 | GRND | I000 | 00I1 | I000#ZvJr00I1
6397 | 6397 | 6397 | 6397 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Grounding Material (Earth wire, Roda & Connectors) MQP / ITP Approval | 2 | GRND | I000 | 00I2 | I000#ZvJr00I2
6398 | 6398 | 6398 | 6398 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Grounding Material (Earth wire, Roda & Connectors) Issuance of MFC | 3 | GRND | I000 | 00I3 | I000#ZvJr00I3
6399 | 6399 | 6399 | 6399 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Grounding Material (Earth wire, Roda & Connectors) Lead Time For Manufacturing | 4 | GRND | I000 | 00I4 | I000#ZvJr00I4
6400 | 6400 | 6400 | 6400 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Grounding Material (Earth wire, Roda & Connectors) Material readiness / Inspection call | 5 | GRND | I000 | 00I5 | I000#ZvJr00I5
6401 | 6401 | 6401 | 6401 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Grounding Material (Earth wire, Roda & Connectors) Inspection by client personal / Third Party | 6 | GRND | I000 | 00I6 | I000#ZvJr00I6
6402 | 6402 | 6402 | 6402 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Grounding Material (Earth wire, Roda & Connectors) Submission of FAT Compliance by Vendor | 7 | GRND | I000 | 00I7 | I000#ZvJr00I7
6403 | 6403 | 6403 | 6403 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Grounding Material (Earth wire, Roda & Connectors) Dispatch Clearance to vendor | 8 | GRND | I000 | 00I8 | I000#ZvJr00I8
6404 | 6404 | 6404 | 6404 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Grounding Material (Earth wire, Roda & Connectors) Transportation and Custom clearance | 9 | GRND | I000 | 00I9 | I000#ZvJr00I9
6405 | 6405 | 6405 | 6405 | SA24M005 | Receipt at site |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Grounding Material (Earth wire, Roda & Connectors) Receipt at site | 10 | GRND | I000 | 0I10 | I000#ZvJr0I10
6406 | 6406 | 6406 | 6406 | SA24M005 | Joint Boxes |  | 3 | -1 | 0 |  |  | X | I000#ZvJr
6407 | 6407 | 6407 | 6407 | SA24M005 | MQP / ITP Submission |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Joint Boxes MQP / ITP Submission | 1 | 0JB0M | I000 | 00I1 | I0000JB0M00I1
6408 | 6408 | 6408 | 6408 | SA24M005 | MQP / ITP Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Joint Boxes MQP / ITP Approval | 2 | 0JB0M | I000 | 00I2 | I0000JB0M00I2
6409 | 6409 | 6409 | 6409 | SA24M005 | Issuance of MFC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Joint Boxes Issuance of MFC | 3 | 0JB0M | I000 | 00I3 | I0000JB0M00I3
6410 | 6410 | 6410 | 6410 | SA24M005 | Lead Time For Manufacturing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Joint Boxes Lead Time For Manufacturing | 4 | 0JB0M | I000 | 00I4 | I0000JB0M00I4
6411 | 6411 | 6411 | 6411 | SA24M005 | Material readiness / Inspection call |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Joint Boxes Material readiness / Inspection call | 5 | 0JB0M | I000 | 00I5 | I0000JB0M00I5
6412 | 6412 | 6412 | 6412 | SA24M005 | Inspection by client personal / Third Party |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Joint Boxes Inspection by client personal / Third Party | 6 | 0JB0M | I000 | 00I6 | I0000JB0M00I6
6413 | 6413 | 6413 | 6413 | SA24M005 | Submission of FAT Compliance by Vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Joint Boxes Submission of FAT Compliance by Vendor | 7 | 0JB0M | I000 | 00I7 | I0000JB0M00I7
6414 | 6414 | 6414 | 6414 | SA24M005 | Dispatch Clearance to vendor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Joint Boxes Dispatch Clearance to vendor | 8 | 0JB0M | I000 | 00I8 | I0000JB0M00I8
6415 | 6415 | 6415 | 6415 | SA24M005 | Transportation and Custom clearance |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Joint Boxes Transportation and Custom clearance | 9 | 0JB0M | I000 | 00I9 | I0000JB0M00I9
6416 | 6416 | 6416 | 6416 | SA24M005 | Receipt at site |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Inspection & Delivery Joint Boxes Receipt at site | 10 | 0JB0M | I000 | 0I10 | I0000JB0M0I10
6417 | 6417 | 6417 | 6417 | SA24M005 | Construction & Installation Works |  | 2 | -1 | 0 |  |  | X
6418 | 6418 | 6418 | 6418 | SA24M005 | Line 1 |  | 3 | -1 | 0 |  |  | X
6419 | 6419 | 6419 | 6419 | SA24M005 | General Works |  | 4 | -1 | 0 |  |  | X
6420 | 6420 | 6420 | 6420 | SA24M005 | Route Survey |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 General Works Route Survey | 1 | LGWRS | C000 | 00C1 | C000LGWRS00C1
6421 | 6421 | 6421 | 6421 | SA24M005 | Detailed Survey |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 General Works Detailed Survey | 2 | LGWRS | C000 | 00C2 | C000LGWRS00C2
6422 | 6422 | 6422 | 6422 | SA24M005 | Check Survey |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 General Works Check Survey | 3 | LGWRS | C000 | 00C3 | C000LGWRS00C3
6423 | 6423 | 6423 | 6423 | SA24M005 | Soil Investigation & Thermal Resistivity Measurement |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 General Works Soil Investigation & Thermal Resistivity Measurement | 4 | LGWRS | C000 | 00C4 | C000LGWRS00C4
6424 | 6424 | 6424 | 6424 | SA24M005 | Access Road- Sub Grade |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 General Works Access Road- Sub Grade | 5 | LGWRS | C000 | 00C5 | C000LGWRS00C5
6425 | 6425 | 6425 | 6425 | SA24M005 | Access Road- Sub Base |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 General Works Access Road- Sub Base | 6 | LGWRS | C000 | 00C6 | C000LGWRS00C6
6426 | 6426 | 6426 | 6426 | SA24M005 | Access Road- Final Layer |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 General Works Access Road- Final Layer | 7 | LGWRS | C000 | 00C7 | C000LGWRS00C7
6427 | 6427 | 6427 | 6427 | SA24M005 | Civil Works |  | 4 | -1 | 0 |  |  | X
6428 | 6428 | 6428 | 6428 | SA24M005 | Tower 1 |  | 5 | -1 | 0 |  |  | X
6429 | 6429 | 6429 | 6429 | SA24M005 | ROW / Work Permit |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 1 ROW / Work Permit | 1 | CW00TR | C000 | 00C1 | C000#bNzQ00C1
6430 | 6430 | 6430 | 6430 | SA24M005 | Excavation / Piping |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 1 Excavation / Piping | 2 | CW00TR | C000 | 00C2 | C000#bNzQ00C2
6431 | 6431 | 6431 | 6431 | SA24M005 | Stub Setting |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 1 Stub Setting | 3 | CW00TR | C000 | 00C3 | C000#bNzQ00C3
6432 | 6432 | 6432 | 6432 | SA24M005 | Placement of PCC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 1 Placement of PCC | 4 | CW00TR | C000 | 00C4 | C000#bNzQ00C4
6433 | 6433 | 6433 | 6433 | SA24M005 | Reinforcement Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 1 Reinforcement Works | 5 | CW00TR | C000 | 00C5 | C000#bNzQ00C5
6434 | 6434 | 6434 | 6434 | SA24M005 | Concreting / RCC Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 1 Concreting / RCC Works | 6 | CW00TR | C000 | 00C6 | C000#bNzQ00C6
6435 | 6435 | 6435 | 6435 | SA24M005 | Backfilling |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 1 Backfilling | 7 | CW00TR | C000 | 00C7 | C000#bNzQ00C7
6436 | 6436 | 6436 | 6436 | SA24M005 | Tower 2 |  | 5 | -1 | 0 |  |  | X | C000#bNzQ
6437 | 6437 | 6437 | 6437 | SA24M005 | ROW / Work Permit |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 2 ROW / Work Permit | 1 | CW00TR | C000 | 00C1 | C000#hyBf00C1
6438 | 6438 | 6438 | 6438 | SA24M005 | Excavation / Piping |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 2 Excavation / Piping | 2 | CW00TR | C000 | 00C2 | C000#hyBf00C2
6439 | 6439 | 6439 | 6439 | SA24M005 | Stub Setting |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 2 Stub Setting | 3 | CW00TR | C000 | 00C3 | C000#hyBf00C3
6440 | 6440 | 6440 | 6440 | SA24M005 | Placement of PCC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 2 Placement of PCC | 4 | CW00TR | C000 | 00C4 | C000#hyBf00C4
6441 | 6441 | 6441 | 6441 | SA24M005 | Reinforcement Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 2 Reinforcement Works | 5 | CW00TR | C000 | 00C5 | C000#hyBf00C5
6442 | 6442 | 6442 | 6442 | SA24M005 | Concreting / RCC Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 2 Concreting / RCC Works | 6 | CW00TR | C000 | 00C6 | C000#hyBf00C6
6443 | 6443 | 6443 | 6443 | SA24M005 | Backfilling |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 2 Backfilling | 7 | CW00TR | C000 | 00C7 | C000#hyBf00C7
6444 | 6444 | 6444 | 6444 | SA24M005 | Tower 3 |  | 5 | -1 | 0 |  |  | X | C000#hyBf
6445 | 6445 | 6445 | 6445 | SA24M005 | ROW / Work Permit |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 3 ROW / Work Permit | 1 | CW003 | C000 | 00C1 | C000#rDAU00C1
6446 | 6446 | 6446 | 6446 | SA24M005 | Excavation / Piping |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 3 Excavation / Piping | 2 | CW003 | C000 | 00C2 | C000#rDAU00C2
6447 | 6447 | 6447 | 6447 | SA24M005 | Stub Setting |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 3 Stub Setting | 3 | CW003 | C000 | 00C3 | C000#rDAU00C3
6448 | 6448 | 6448 | 6448 | SA24M005 | Placement of PCC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 3 Placement of PCC | 4 | CW003 | C000 | 00C4 | C000#rDAU00C4
6449 | 6449 | 6449 | 6449 | SA24M005 | Reinforcement Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 3 Reinforcement Works | 5 | CW003 | C000 | 00C5 | C000#rDAU00C5
6450 | 6450 | 6450 | 6450 | SA24M005 | Concreting / RCC Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 3 Concreting / RCC Works | 6 | CW003 | C000 | 00C6 | C000#rDAU00C6
6451 | 6451 | 6451 | 6451 | SA24M005 | Backfilling |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 3 Backfilling | 7 | CW003 | C000 | 00C7 | C000#rDAU00C7
6452 | 6452 | 6452 | 6452 | SA24M005 | Tower 4 |  | 5 | -1 | 0 |  |  | X | C000#rDAU
6453 | 6453 | 6453 | 6453 | SA24M005 | ROW / Work Permit |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 4 ROW / Work Permit | 1 | CW004 | C000 | 00C1 | C000CW00400C1
6454 | 6454 | 6454 | 6454 | SA24M005 | Excavation / Piping |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 4 Excavation / Piping | 2 | CW004 | C000 | 00C2 | C000CW00400C2
6455 | 6455 | 6455 | 6455 | SA24M005 | Stub Setting |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 4 Stub Setting | 3 | CW004 | C000 | 00C3 | C000CW00400C3
6456 | 6456 | 6456 | 6456 | SA24M005 | Placement of PCC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 4 Placement of PCC | 4 | CW004 | C000 | 00C4 | C000CW00400C4
6457 | 6457 | 6457 | 6457 | SA24M005 | Reinforcement Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 4 Reinforcement Works | 5 | CW004 | C000 | 00C5 | C000CW00400C5
6458 | 6458 | 6458 | 6458 | SA24M005 | Concreting / RCC Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 4 Concreting / RCC Works | 6 | CW004 | C000 | 00C6 | C000CW00400C6
6459 | 6459 | 6459 | 6459 | SA24M005 | Backfilling |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 4 Backfilling | 7 | CW004 | C000 | 00C7 | C000CW00400C7
6460 | 6460 | 6460 | 6460 | SA24M005 | Tower 5 |  | 5 | -1 | 0 |  |  | X
6461 | 6461 | 6461 | 6461 | SA24M005 | ROW / Work Permit |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 5 ROW / Work Permit | 1 | C0TW5 | C000 | 00C1 | C000C0TW500C1
6462 | 6462 | 6462 | 6462 | SA24M005 | Excavation / Piping |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 5 Excavation / Piping | 2 | C0TW5 | C000 | 00C2 | C000C0TW500C2
6463 | 6463 | 6463 | 6463 | SA24M005 | Stub Setting |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 5 Stub Setting | 3 | C0TW5 | C000 | 00C3 | C000C0TW500C3
6464 | 6464 | 6464 | 6464 | SA24M005 | Placement of PCC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 5 Placement of PCC | 4 | C0TW5 | C000 | 00C4 | C000C0TW500C4
6465 | 6465 | 6465 | 6465 | SA24M005 | Reinforcement Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 5 Reinforcement Works | 5 | C0TW5 | C000 | 00C5 | C000C0TW500C5
6466 | 6466 | 6466 | 6466 | SA24M005 | Concreting / RCC Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 5 Concreting / RCC Works | 6 | C0TW5 | C000 | 00C6 | C000C0TW500C6
6467 | 6467 | 6467 | 6467 | SA24M005 | Backfilling |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 5 Backfilling | 7 | C0TW5 | C000 | 00C7 | C000C0TW500C7
6468 | 6468 | 6468 | 6468 | SA24M005 | Tower 6 |  | 5 | -1 | 0 |  |  | X
6469 | 6469 | 6469 | 6469 | SA24M005 | ROW / Work Permit |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 6 ROW / Work Permit | 1 | C0TW6 | C000 | 00C1 | C000C0TW600C1
6470 | 6470 | 6470 | 6470 | SA24M005 | Excavation / Piping |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 6 Excavation / Piping | 2 | C0TW6 | C000 | 00C2 | C000C0TW600C2
6471 | 6471 | 6471 | 6471 | SA24M005 | Stub Setting |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 6 Stub Setting | 3 | C0TW6 | C000 | 00C3 | C000C0TW600C3
6472 | 6472 | 6472 | 6472 | SA24M005 | Placement of PCC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 6 Placement of PCC | 4 | C0TW6 | C000 | 00C4 | C000C0TW600C4
6473 | 6473 | 6473 | 6473 | SA24M005 | Reinforcement Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 6 Reinforcement Works | 5 | C0TW6 | C000 | 00C5 | C000C0TW600C5
6474 | 6474 | 6474 | 6474 | SA24M005 | Concreting / RCC Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 6 Concreting / RCC Works | 6 | C0TW6 | C000 | 00C6 | C000C0TW600C6
6475 | 6475 | 6475 | 6475 | SA24M005 | Backfilling |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 6 Backfilling | 7 | C0TW6 | C000 | 00C7 | C000C0TW600C7
6476 | 6476 | 6476 | 6476 | SA24M005 | Tower 7 |  | 5 | -1 | 0 |  |  | X
6477 | 6477 | 6477 | 6477 | SA24M005 | ROW / Work Permit |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 7 ROW / Work Permit | 1 | CW007 | C000 | 00C1 | C000CW00700C1
6478 | 6478 | 6478 | 6478 | SA24M005 | Excavation / Piping |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 7 Excavation / Piping | 2 | CW007 | C000 | 00C2 | C000CW00700C2
6479 | 6479 | 6479 | 6479 | SA24M005 | Stub Setting |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 7 Stub Setting | 3 | CW007 | C000 | 00C3 | C000CW00700C3
6480 | 6480 | 6480 | 6480 | SA24M005 | Placement of PCC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 7 Placement of PCC | 4 | CW007 | C000 | 00C4 | C000CW00700C4
6481 | 6481 | 6481 | 6481 | SA24M005 | Reinforcement Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 7 Reinforcement Works | 5 | CW007 | C000 | 00C5 | C000CW00700C5
6482 | 6482 | 6482 | 6482 | SA24M005 | Concreting / RCC Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 7 Concreting / RCC Works | 6 | CW007 | C000 | 00C6 | C000CW00700C6
6483 | 6483 | 6483 | 6483 | SA24M005 | Backfilling |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 7 Backfilling | 7 | CW007 | C000 | 00C7 | C000CW00700C7
6484 | 6484 | 6484 | 6484 | SA24M005 | Tower 8 |  | 5 | -1 | 0 |  |  | X
6485 | 6485 | 6485 | 6485 | SA24M005 | ROW / Work Permit |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 8 ROW / Work Permit | 1 | CW0TW | C000 | 00C1 | C000#UZAp00C1
6486 | 6486 | 6486 | 6486 | SA24M005 | Excavation / Piping |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 8 Excavation / Piping | 2 | CW0TW | C000 | 00C2 | C000#UZAp00C2
6487 | 6487 | 6487 | 6487 | SA24M005 | Stub Setting |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 8 Stub Setting | 3 | CW0TW | C000 | 00C3 | C000#UZAp00C3
6488 | 6488 | 6488 | 6488 | SA24M005 | Placement of PCC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 8 Placement of PCC | 4 | CW0TW | C000 | 00C4 | C000#UZAp00C4
6489 | 6489 | 6489 | 6489 | SA24M005 | Reinforcement Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 8 Reinforcement Works | 5 | CW0TW | C000 | 00C5 | C000#UZAp00C5
6490 | 6490 | 6490 | 6490 | SA24M005 | Concreting / RCC Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 8 Concreting / RCC Works | 6 | CW0TW | C000 | 00C6 | C000#UZAp00C6
6491 | 6491 | 6491 | 6491 | SA24M005 | Backfilling |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 8 Backfilling | 7 | CW0TW | C000 | 00C7 | C000#UZAp00C7
6492 | 6492 | 6492 | 6492 | SA24M005 | Tower 9 |  | 5 | -1 | 0 |  |  | X | C000#UZAp
6493 | 6493 | 6493 | 6493 | SA24M005 | ROW / Work Permit |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 9 ROW / Work Permit | 1 | CW009 | C000 | 00C1 | C000CW00900C1
6494 | 6494 | 6494 | 6494 | SA24M005 | Excavation / Piping |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 9 Excavation / Piping | 2 | CW009 | C000 | 00C2 | C000CW00900C2
6495 | 6495 | 6495 | 6495 | SA24M005 | Stub Setting |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 9 Stub Setting | 3 | CW009 | C000 | 00C3 | C000CW00900C3
6496 | 6496 | 6496 | 6496 | SA24M005 | Placement of PCC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 9 Placement of PCC | 4 | CW009 | C000 | 00C4 | C000CW00900C4
6497 | 6497 | 6497 | 6497 | SA24M005 | Reinforcement Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 9 Reinforcement Works | 5 | CW009 | C000 | 00C5 | C000CW00900C5
6498 | 6498 | 6498 | 6498 | SA24M005 | Concreting / RCC Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 9 Concreting / RCC Works | 6 | CW009 | C000 | 00C6 | C000CW00900C6
6499 | 6499 | 6499 | 6499 | SA24M005 | Backfilling |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 9 Backfilling | 7 | CW009 | C000 | 00C7 | C000CW00900C7
6500 | 6500 | 6500 | 6500 | SA24M005 | Tower 10 |  | 5 | -1 | 0 |  |  | X
6501 | 6501 | 6501 | 6501 | SA24M005 | ROW / Work Permit |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 10 ROW / Work Permit | 1 | CW0TW | C000 | 00C1 | C000#JlVh00C1
6502 | 6502 | 6502 | 6502 | SA24M005 | Excavation / Piping |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 10 Excavation / Piping | 2 | CW0TW | C000 | 00C2 | C000#JlVh00C2
6503 | 6503 | 6503 | 6503 | SA24M005 | Stub Setting |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 10 Stub Setting | 3 | CW0TW | C000 | 00C3 | C000#JlVh00C3
6504 | 6504 | 6504 | 6504 | SA24M005 | Placement of PCC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 10 Placement of PCC | 4 | CW0TW | C000 | 00C4 | C000#JlVh00C4
6505 | 6505 | 6505 | 6505 | SA24M005 | Reinforcement Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 10 Reinforcement Works | 5 | CW0TW | C000 | 00C5 | C000#JlVh00C5
6506 | 6506 | 6506 | 6506 | SA24M005 | Concreting / RCC Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 10 Concreting / RCC Works | 6 | CW0TW | C000 | 00C6 | C000#JlVh00C6
6507 | 6507 | 6507 | 6507 | SA24M005 | Backfilling |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 10 Backfilling | 7 | CW0TW | C000 | 00C7 | C000#JlVh00C7
6508 | 6508 | 6508 | 6508 | SA24M005 | Tower 11 |  | 5 | -1 | 0 |  |  | X | C000#JlVh
6509 | 6509 | 6509 | 6509 | SA24M005 | ROW / Work Permit |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 11 ROW / Work Permit | 1 | CW0TW | C000 | 00C1 | C000#Uqvg00C1
6510 | 6510 | 6510 | 6510 | SA24M005 | Excavation / Piping |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 11 Excavation / Piping | 2 | CW0TW | C000 | 00C2 | C000#Uqvg00C2
6511 | 6511 | 6511 | 6511 | SA24M005 | Stub Setting |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 11 Stub Setting | 3 | CW0TW | C000 | 00C3 | C000#Uqvg00C3
6512 | 6512 | 6512 | 6512 | SA24M005 | Placement of PCC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 11 Placement of PCC | 4 | CW0TW | C000 | 00C4 | C000#Uqvg00C4
6513 | 6513 | 6513 | 6513 | SA24M005 | Reinforcement Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 11 Reinforcement Works | 5 | CW0TW | C000 | 00C5 | C000#Uqvg00C5
6514 | 6514 | 6514 | 6514 | SA24M005 | Concreting / RCC Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 11 Concreting / RCC Works | 6 | CW0TW | C000 | 00C6 | C000#Uqvg00C6
6515 | 6515 | 6515 | 6515 | SA24M005 | Backfilling |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 11 Backfilling | 7 | CW0TW | C000 | 00C7 | C000#Uqvg00C7
6516 | 6516 | 6516 | 6516 | SA24M005 | Tower 12 |  | 5 | -1 | 0 |  |  | X | C000#Uqvg
6517 | 6517 | 6517 | 6517 | SA24M005 | ROW / Work Permit |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 12 ROW / Work Permit | 1 | CW0012ROW | C000 | 00C1 | C000CW0012ROW00C1
6518 | 6518 | 6518 | 6518 | SA24M005 | Excavation / Piping |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 12 Excavation / Piping | 2 | CW0012ROW | C000 | 00C2 | C000CW0012ROW00C2
6519 | 6519 | 6519 | 6519 | SA24M005 | Stub Setting |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 12 Stub Setting | 3 | CW0012ROW | C000 | 00C3 | C000CW0012ROW00C3
6520 | 6520 | 6520 | 6520 | SA24M005 | Placement of PCC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 12 Placement of PCC | 4 | CW0012ROW | C000 | 00C4 | C000CW0012ROW00C4
6521 | 6521 | 6521 | 6521 | SA24M005 | Reinforcement Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 12 Reinforcement Works | 5 | CW0012ROW | C000 | 00C5 | C000CW0012ROW00C5
6522 | 6522 | 6522 | 6522 | SA24M005 | Concreting / RCC Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 12 Concreting / RCC Works | 6 | CW0012ROW | C000 | 00C6 | C000CW0012ROW00C6
6523 | 6523 | 6523 | 6523 | SA24M005 | Backfilling |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 12 Backfilling | 7 | CW0012ROW | C000 | 00C7 | C000CW0012ROW00C7
6524 | 6524 | 6524 | 6524 | SA24M005 | Tower 13 |  | 5 | -1 | 0 |  |  | X
6525 | 6525 | 6525 | 6525 | SA24M005 | ROW / Work Permit |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 13 ROW / Work Permit | 1 | CW0TW | C000 | 00C1 | C000#obBy00C1
6526 | 6526 | 6526 | 6526 | SA24M005 | Excavation / Piping |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 13 Excavation / Piping | 2 | CW0TW | C000 | 00C2 | C000#obBy00C2
6527 | 6527 | 6527 | 6527 | SA24M005 | Stub Setting |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 13 Stub Setting | 3 | CW0TW | C000 | 00C3 | C000#obBy00C3
6528 | 6528 | 6528 | 6528 | SA24M005 | Placement of PCC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 13 Placement of PCC | 4 | CW0TW | C000 | 00C4 | C000#obBy00C4
6529 | 6529 | 6529 | 6529 | SA24M005 | Reinforcement Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 13 Reinforcement Works | 5 | CW0TW | C000 | 00C5 | C000#obBy00C5
6530 | 6530 | 6530 | 6530 | SA24M005 | Concreting / RCC Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 13 Concreting / RCC Works | 6 | CW0TW | C000 | 00C6 | C000#obBy00C6
6531 | 6531 | 6531 | 6531 | SA24M005 | Backfilling |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 13 Backfilling | 7 | CW0TW | C000 | 00C7 | C000#obBy00C7
6532 | 6532 | 6532 | 6532 | SA24M005 | Tower 14 |  | 5 | -1 | 0 |  |  | X | C000#obBy
6533 | 6533 | 6533 | 6533 | SA24M005 | ROW / Work Permit |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 14 ROW / Work Permit | 1 | CW0TW | C000 | 00C1 | C000#TXkU00C1
6534 | 6534 | 6534 | 6534 | SA24M005 | Excavation / Piping |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 14 Excavation / Piping | 2 | CW0TW | C000 | 00C2 | C000#TXkU00C2
6535 | 6535 | 6535 | 6535 | SA24M005 | Stub Setting |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 14 Stub Setting | 3 | CW0TW | C000 | 00C3 | C000#TXkU00C3
6536 | 6536 | 6536 | 6536 | SA24M005 | Placement of PCC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 14 Placement of PCC | 4 | CW0TW | C000 | 00C4 | C000#TXkU00C4
6537 | 6537 | 6537 | 6537 | SA24M005 | Reinforcement Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 14 Reinforcement Works | 5 | CW0TW | C000 | 00C5 | C000#TXkU00C5
6538 | 6538 | 6538 | 6538 | SA24M005 | Concreting / RCC Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 14 Concreting / RCC Works | 6 | CW0TW | C000 | 00C6 | C000#TXkU00C6
6539 | 6539 | 6539 | 6539 | SA24M005 | Backfilling |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 14 Backfilling | 7 | CW0TW | C000 | 00C7 | C000#TXkU00C7
6540 | 6540 | 6540 | 6540 | SA24M005 | Tower 15 |  | 5 | -1 | 0 |  |  | X | C000#TXkU
6541 | 6541 | 6541 | 6541 | SA24M005 | ROW / Work Permit |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 15 ROW / Work Permit | 1 | CW0TW | C000 | 00C1 | C000#LBDA00C1
6542 | 6542 | 6542 | 6542 | SA24M005 | Excavation / Piping |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 15 Excavation / Piping | 2 | CW0TW | C000 | 00C2 | C000#LBDA00C2
6543 | 6543 | 6543 | 6543 | SA24M005 | Stub Setting |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 15 Stub Setting | 3 | CW0TW | C000 | 00C3 | C000#LBDA00C3
6544 | 6544 | 6544 | 6544 | SA24M005 | Placement of PCC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 15 Placement of PCC | 4 | CW0TW | C000 | 00C4 | C000#LBDA00C4
6545 | 6545 | 6545 | 6545 | SA24M005 | Reinforcement Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 15 Reinforcement Works | 5 | CW0TW | C000 | 00C5 | C000#LBDA00C5
6546 | 6546 | 6546 | 6546 | SA24M005 | Concreting / RCC Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 15 Concreting / RCC Works | 6 | CW0TW | C000 | 00C6 | C000#LBDA00C6
6547 | 6547 | 6547 | 6547 | SA24M005 | Backfilling |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 15 Backfilling | 7 | CW0TW | C000 | 00C7 | C000#LBDA00C7
6548 | 6548 | 6548 | 6548 | SA24M005 | Tower 16 |  | 5 | -1 | 0 |  |  | X | C000#LBDA
6549 | 6549 | 6549 | 6549 | SA24M005 | ROW / Work Permit |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 16 ROW / Work Permit | 1 | CW0TW | C000 | 00C1 | C000#hwQz00C1
6550 | 6550 | 6550 | 6550 | SA24M005 | Excavation / Piping |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 16 Excavation / Piping | 2 | CW0TW | C000 | 00C2 | C000#hwQz00C2
6551 | 6551 | 6551 | 6551 | SA24M005 | Stub Setting |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 16 Stub Setting | 3 | CW0TW | C000 | 00C3 | C000#hwQz00C3
6552 | 6552 | 6552 | 6552 | SA24M005 | Placement of PCC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 16 Placement of PCC | 4 | CW0TW | C000 | 00C4 | C000#hwQz00C4
6553 | 6553 | 6553 | 6553 | SA24M005 | Reinforcement Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 16 Reinforcement Works | 5 | CW0TW | C000 | 00C5 | C000#hwQz00C5
6554 | 6554 | 6554 | 6554 | SA24M005 | Concreting / RCC Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 16 Concreting / RCC Works | 6 | CW0TW | C000 | 00C6 | C000#hwQz00C6
6555 | 6555 | 6555 | 6555 | SA24M005 | Backfilling |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 16 Backfilling | 7 | CW0TW | C000 | 00C7 | C000#hwQz00C7
6556 | 6556 | 6556 | 6556 | SA24M005 | Tower 17 |  | 5 | -1 | 0 |  |  | X | C000#hwQz
6557 | 6557 | 6557 | 6557 | SA24M005 | ROW / Work Permit |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 17 ROW / Work Permit | 1 | CW0TW | C000 | 00C1 | C000#YCtG00C1
6558 | 6558 | 6558 | 6558 | SA24M005 | Excavation / Piping |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 17 Excavation / Piping | 2 | CW0TW | C000 | 00C2 | C000#YCtG00C2
6559 | 6559 | 6559 | 6559 | SA24M005 | Stub Setting |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 17 Stub Setting | 3 | CW0TW | C000 | 00C3 | C000#YCtG00C3
6560 | 6560 | 6560 | 6560 | SA24M005 | Placement of PCC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 17 Placement of PCC | 4 | CW0TW | C000 | 00C4 | C000#YCtG00C4
6561 | 6561 | 6561 | 6561 | SA24M005 | Reinforcement Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 17 Reinforcement Works | 5 | CW0TW | C000 | 00C5 | C000#YCtG00C5
6562 | 6562 | 6562 | 6562 | SA24M005 | Concreting / RCC Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 17 Concreting / RCC Works | 6 | CW0TW | C000 | 00C6 | C000#YCtG00C6
6563 | 6563 | 6563 | 6563 | SA24M005 | Backfilling |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 17 Backfilling | 7 | CW0TW | C000 | 00C7 | C000#YCtG00C7
6564 | 6564 | 6564 | 6564 | SA24M005 | Tower 18 |  | 5 | -1 | 0 |  |  | X | C000#YCtG
6565 | 6565 | 6565 | 6565 | SA24M005 | ROW / Work Permit |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 18 ROW / Work Permit | 1 | CW0TW | C000 | 00C1 | C000#dxJw00C1
6566 | 6566 | 6566 | 6566 | SA24M005 | Excavation / Piping |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 18 Excavation / Piping | 2 | CW0TW | C000 | 00C2 | C000#dxJw00C2
6567 | 6567 | 6567 | 6567 | SA24M005 | Stub Setting |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 18 Stub Setting | 3 | CW0TW | C000 | 00C3 | C000#dxJw00C3
6568 | 6568 | 6568 | 6568 | SA24M005 | Placement of PCC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 18 Placement of PCC | 4 | CW0TW | C000 | 00C4 | C000#dxJw00C4
6569 | 6569 | 6569 | 6569 | SA24M005 | Reinforcement Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 18 Reinforcement Works | 5 | CW0TW | C000 | 00C5 | C000#dxJw00C5
6570 | 6570 | 6570 | 6570 | SA24M005 | Concreting / RCC Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 18 Concreting / RCC Works | 6 | CW0TW | C000 | 00C6 | C000#dxJw00C6
6571 | 6571 | 6571 | 6571 | SA24M005 | Backfilling |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 18 Backfilling | 7 | CW0TW | C000 | 00C7 | C000#dxJw00C7
6572 | 6572 | 6572 | 6572 | SA24M005 | Tower 19 |  | 5 | -1 | 0 |  |  | X | C000#dxJw
6573 | 6573 | 6573 | 6573 | SA24M005 | ROW / Work Permit |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 19 ROW / Work Permit | 1 | CW0TW | C000 | 00C1 | C000#ifoY00C1
6574 | 6574 | 6574 | 6574 | SA24M005 | Excavation / Piping |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 19 Excavation / Piping | 2 | CW0TW | C000 | 00C2 | C000#ifoY00C2
6575 | 6575 | 6575 | 6575 | SA24M005 | Stub Setting |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 19 Stub Setting | 3 | CW0TW | C000 | 00C3 | C000#ifoY00C3
6576 | 6576 | 6576 | 6576 | SA24M005 | Placement of PCC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 19 Placement of PCC | 4 | CW0TW | C000 | 00C4 | C000#ifoY00C4
6577 | 6577 | 6577 | 6577 | SA24M005 | Reinforcement Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 19 Reinforcement Works | 5 | CW0TW | C000 | 00C5 | C000#ifoY00C5
6578 | 6578 | 6578 | 6578 | SA24M005 | Concreting / RCC Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 19 Concreting / RCC Works | 6 | CW0TW | C000 | 00C6 | C000#ifoY00C6
6579 | 6579 | 6579 | 6579 | SA24M005 | Backfilling |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 19 Backfilling | 7 | CW0TW | C000 | 00C7 | C000#ifoY00C7
6580 | 6580 | 6580 | 6580 | SA24M005 | Tower 20 |  | 5 | -1 | 0 |  |  | X | C000#ifoY
6581 | 6581 | 6581 | 6581 | SA24M005 | ROW / Work Permit |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 20 ROW / Work Permit | 1 | CW0TW | C000 | 00C1 | C000#NcQk00C1
6582 | 6582 | 6582 | 6582 | SA24M005 | Excavation / Piping |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 20 Excavation / Piping | 2 | CW0TW | C000 | 00C2 | C000#NcQk00C2
6583 | 6583 | 6583 | 6583 | SA24M005 | Stub Setting |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 20 Stub Setting | 3 | CW0TW | C000 | 00C3 | C000#NcQk00C3
6584 | 6584 | 6584 | 6584 | SA24M005 | Placement of PCC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 20 Placement of PCC | 4 | CW0TW | C000 | 00C4 | C000#NcQk00C4
6585 | 6585 | 6585 | 6585 | SA24M005 | Reinforcement Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 20 Reinforcement Works | 5 | CW0TW | C000 | 00C5 | C000#NcQk00C5
6586 | 6586 | 6586 | 6586 | SA24M005 | Concreting / RCC Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 20 Concreting / RCC Works | 6 | CW0TW | C000 | 00C6 | C000#NcQk00C6
6587 | 6587 | 6587 | 6587 | SA24M005 | Backfilling |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 20 Backfilling | 7 | CW0TW | C000 | 00C7 | C000#NcQk00C7
6588 | 6588 | 6588 | 6588 | SA24M005 | Tower 21 |  | 5 | -1 | 0 |  |  | X | C000#NcQk
6589 | 6589 | 6589 | 6589 | SA24M005 | ROW / Work Permit |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 21 ROW / Work Permit | 1 | CW0TW | C000 | 00C1 | C000#IoNP00C1
6590 | 6590 | 6590 | 6590 | SA24M005 | Excavation / Piping |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 21 Excavation / Piping | 2 | CW0TW | C000 | 00C2 | C000#IoNP00C2
6591 | 6591 | 6591 | 6591 | SA24M005 | Stub Setting |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 21 Stub Setting | 3 | CW0TW | C000 | 00C3 | C000#IoNP00C3
6592 | 6592 | 6592 | 6592 | SA24M005 | Placement of PCC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 21 Placement of PCC | 4 | CW0TW | C000 | 00C4 | C000#IoNP00C4
6593 | 6593 | 6593 | 6593 | SA24M005 | Reinforcement Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 21 Reinforcement Works | 5 | CW0TW | C000 | 00C5 | C000#IoNP00C5
6594 | 6594 | 6594 | 6594 | SA24M005 | Concreting / RCC Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 21 Concreting / RCC Works | 6 | CW0TW | C000 | 00C6 | C000#IoNP00C6
6595 | 6595 | 6595 | 6595 | SA24M005 | Backfilling |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Civil Works Tower 21 Backfilling | 7 | CW0TW | C000 | 00C7 | C000#IoNP00C7
6596 | 6596 | 6596 | 6596 | SA24M005 | Structure Pad Works |  | 4 | -1 | 0 |  |  | X | C000#IoNP
6597 | 6597 | 6597 | 6597 | SA24M005 | Tower 1 |  | 5 | -1 | 0 |  |  | X | C000#IoNP
6598 | 6598 | 6598 | 6598 | SA24M005 | Sub Grade |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 1 Sub Grade | 1 | STRPAD | C000 | 00C1 | C000#YCEL00C1
6599 | 6599 | 6599 | 6599 | SA24M005 | Sub Base |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 1 Sub Base | 2 | STRPAD | C000 | 00C2 | C000#YCEL00C2
6600 | 6600 | 6600 | 6600 | SA24M005 | Final Layer |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 1 Final Layer | 3 | STRPAD | C000 | 00C3 | C000#YCEL00C3
6601 | 6601 | 6601 | 6601 | SA24M005 | Tower 2 |  | 5 | -1 | 0 |  |  | X | C000#YCEL
6602 | 6602 | 6602 | 6602 | SA24M005 | Sub Grade |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 2 Sub Grade | 1 | STRPAD | C000 | 00C1 | C000#WthD00C1
6603 | 6603 | 6603 | 6603 | SA24M005 | Sub Base |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 2 Sub Base | 2 | STRPAD | C000 | 00C2 | C000#WthD00C2
6604 | 6604 | 6604 | 6604 | SA24M005 | Final Layer |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 2 Final Layer | 3 | STRPAD | C000 | 00C3 | C000#WthD00C3
6605 | 6605 | 6605 | 6605 | SA24M005 | Tower 3 |  | 5 | -1 | 0 |  |  | X | C000#WthD
6606 | 6606 | 6606 | 6606 | SA24M005 | Sub Grade |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 3 Sub Grade | 1 | STRPAD | C000 | 00C1 | C000#BKCm00C1
6607 | 6607 | 6607 | 6607 | SA24M005 | Sub Base |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 3 Sub Base | 2 | STRPAD | C000 | 00C2 | C000#BKCm00C2
6608 | 6608 | 6608 | 6608 | SA24M005 | Final Layer |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 3 Final Layer | 3 | STRPAD | C000 | 00C3 | C000#BKCm00C3
6609 | 6609 | 6609 | 6609 | SA24M005 | Tower 4 |  | 5 | -1 | 0 |  |  | X | C000#BKCm
6610 | 6610 | 6610 | 6610 | SA24M005 | Sub Grade |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 4 Sub Grade | 1 | L1STRP | C000 | 00C1 | C000#LUqH00C1
6611 | 6611 | 6611 | 6611 | SA24M005 | Sub Base |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 4 Sub Base | 2 | L1STRP | C000 | 00C2 | C000#LUqH00C2
6612 | 6612 | 6612 | 6612 | SA24M005 | Final Layer |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 4 Final Layer | 3 | L1STRP | C000 | 00C3 | C000#LUqH00C3
6613 | 6613 | 6613 | 6613 | SA24M005 | Tower 5 |  | 5 | -1 | 0 |  |  | X | C000#LUqH
6614 | 6614 | 6614 | 6614 | SA24M005 | Sub Grade |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 5 Sub Grade | 1 | L1STRP | C000 | 00C1 | C000#ahtQ00C1
6615 | 6615 | 6615 | 6615 | SA24M005 | Sub Base |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 5 Sub Base | 2 | L1STRP | C000 | 00C2 | C000#ahtQ00C2
6616 | 6616 | 6616 | 6616 | SA24M005 | Final Layer |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 5 Final Layer | 3 | L1STRP | C000 | 00C3 | C000#ahtQ00C3
6617 | 6617 | 6617 | 6617 | SA24M005 | Tower 6 |  | 5 | -1 | 0 |  |  | X | C000#ahtQ
6618 | 6618 | 6618 | 6618 | SA24M005 | Sub Grade |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 6 Sub Grade | 1 | L1STRP | C000 | 00C1 | C000#PcXe00C1
6619 | 6619 | 6619 | 6619 | SA24M005 | Sub Base |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 6 Sub Base | 2 | L1STRP | C000 | 00C2 | C000#PcXe00C2
6620 | 6620 | 6620 | 6620 | SA24M005 | Final Layer |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 6 Final Layer | 3 | L1STRP | C000 | 00C3 | C000#PcXe00C3
6621 | 6621 | 6621 | 6621 | SA24M005 | Tower 7 |  | 5 | -1 | 0 |  |  | X | C000#PcXe
6622 | 6622 | 6622 | 6622 | SA24M005 | Sub Grade |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 7 Sub Grade | 1 | L1STRP | C000 | 00C1 | C000#NfKb00C1
6623 | 6623 | 6623 | 6623 | SA24M005 | Sub Base |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 7 Sub Base | 2 | L1STRP | C000 | 00C2 | C000#NfKb00C2
6624 | 6624 | 6624 | 6624 | SA24M005 | Final Layer |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 7 Final Layer | 3 | L1STRP | C000 | 00C3 | C000#NfKb00C3
6625 | 6625 | 6625 | 6625 | SA24M005 | Tower 8 |  | 5 | -1 | 0 |  |  | X | C000#NfKb
6626 | 6626 | 6626 | 6626 | SA24M005 | Sub Grade |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 8 Sub Grade | 1 | L1STRP008 | C000 | 00C1 | C000L1STRP00800C1
6627 | 6627 | 6627 | 6627 | SA24M005 | Sub Base |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 8 Sub Base | 2 | L1STRP008 | C000 | 00C2 | C000L1STRP00800C2
6628 | 6628 | 6628 | 6628 | SA24M005 | Final Layer |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 8 Final Layer | 3 | L1STRP008 | C000 | 00C3 | C000L1STRP00800C3
6629 | 6629 | 6629 | 6629 | SA24M005 | Tower 9 |  | 5 | -1 | 0 |  |  | X
6630 | 6630 | 6630 | 6630 | SA24M005 | Sub Grade |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 9 Sub Grade | 1 | L1STRP | C000 | 00C1 | C000#haPS00C1
6631 | 6631 | 6631 | 6631 | SA24M005 | Sub Base |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 9 Sub Base | 2 | L1STRP | C000 | 00C2 | C000#haPS00C2
6632 | 6632 | 6632 | 6632 | SA24M005 | Final Layer |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 9 Final Layer | 3 | L1STRP | C000 | 00C3 | C000#haPS00C3
6633 | 6633 | 6633 | 6633 | SA24M005 | Tower 10 |  | 5 | -1 | 0 |  |  | X | C000#haPS
6634 | 6634 | 6634 | 6634 | SA24M005 | Sub Grade |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 10 Sub Grade | 1 | STRPAD0010 | C000 | 00C1 | C000STRPAD001000C1
6635 | 6635 | 6635 | 6635 | SA24M005 | Sub Base |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 10 Sub Base | 2 | STRPAD0010 | C000 | 00C2 | C000STRPAD001000C2
6636 | 6636 | 6636 | 6636 | SA24M005 | Final Layer |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 10 Final Layer | 3 | STRPAD0010 | C000 | 00C3 | C000STRPAD001000C3
6637 | 6637 | 6637 | 6637 | SA24M005 | Tower 11 |  | 5 | -1 | 0 |  |  | X
6638 | 6638 | 6638 | 6638 | SA24M005 | Sub Grade |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 11 Sub Grade | 1 | STRPAD | C000 | 00C1 | C000#oVoQ00C1
6639 | 6639 | 6639 | 6639 | SA24M005 | Sub Base |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 11 Sub Base | 2 | STRPAD | C000 | 00C2 | C000#oVoQ00C2
6640 | 6640 | 6640 | 6640 | SA24M005 | Final Layer |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 11 Final Layer | 3 | STRPAD | C000 | 00C3 | C000#oVoQ00C3
6641 | 6641 | 6641 | 6641 | SA24M005 | Tower 12 |  | 5 | -1 | 0 |  |  | X | C000#oVoQ
6642 | 6642 | 6642 | 6642 | SA24M005 | Sub Grade |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 12 Sub Grade | 1 | L1STRP | C000 | 00C1 | C000#mmUK00C1
6643 | 6643 | 6643 | 6643 | SA24M005 | Sub Base |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 12 Sub Base | 2 | L1STRP | C000 | 00C2 | C000#mmUK00C2
6644 | 6644 | 6644 | 6644 | SA24M005 | Final Layer |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 12 Final Layer | 3 | L1STRP | C000 | 00C3 | C000#mmUK00C3
6645 | 6645 | 6645 | 6645 | SA24M005 | Tower 13 |  | 5 | -1 | 0 |  |  | X | C000#mmUK
6646 | 6646 | 6646 | 6646 | SA24M005 | Sub Grade |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 13 Sub Grade | 1 | STRPAD0013 | C000 | 00C1 | C000STRPAD001300C1
6647 | 6647 | 6647 | 6647 | SA24M005 | Sub Base |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 13 Sub Base | 2 | STRPAD0013 | C000 | 00C2 | C000STRPAD001300C2
6648 | 6648 | 6648 | 6648 | SA24M005 | Final Layer |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 13 Final Layer | 3 | STRPAD0013 | C000 | 00C3 | C000STRPAD001300C3
6649 | 6649 | 6649 | 6649 | SA24M005 | Tower 14 |  | 5 | -1 | 0 |  |  | X
6650 | 6650 | 6650 | 6650 | SA24M005 | Sub Grade |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 14 Sub Grade | 1 | STRPAD0014 | C000 | 00C1 | C000STRPAD001400C1
6651 | 6651 | 6651 | 6651 | SA24M005 | Sub Base |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 14 Sub Base | 2 | STRPAD0014 | C000 | 00C2 | C000STRPAD001400C2
6652 | 6652 | 6652 | 6652 | SA24M005 | Final Layer |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 14 Final Layer | 3 | STRPAD0014 | C000 | 00C3 | C000STRPAD001400C3
6653 | 6653 | 6653 | 6653 | SA24M005 | Tower 15 |  | 5 | -1 | 0 |  |  | X
6654 | 6654 | 6654 | 6654 | SA24M005 | Sub Grade |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 15 Sub Grade | 1 | STRPAD0015 | C000 | 00C1 | C000STRPAD001500C1
6655 | 6655 | 6655 | 6655 | SA24M005 | Sub Base |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 15 Sub Base | 2 | STRPAD0015 | C000 | 00C2 | C000STRPAD001500C2
6656 | 6656 | 6656 | 6656 | SA24M005 | Final Layer |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 15 Final Layer | 3 | STRPAD0015 | C000 | 00C3 | C000STRPAD001500C3
6657 | 6657 | 6657 | 6657 | SA24M005 | Tower 16 |  | 5 | -1 | 0 |  |  | X
6658 | 6658 | 6658 | 6658 | SA24M005 | Sub Grade |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 16 Sub Grade | 1 | STRPAD0016 | C000 | 00C1 | C000STRPAD001600C1
6659 | 6659 | 6659 | 6659 | SA24M005 | Sub Base |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 16 Sub Base | 2 | STRPAD0016 | C000 | 00C2 | C000STRPAD001600C2
6660 | 6660 | 6660 | 6660 | SA24M005 | Final Layer |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 16 Final Layer | 3 | STRPAD0016 | C000 | 00C3 | C000STRPAD001600C3
6661 | 6661 | 6661 | 6661 | SA24M005 | Tower 17 |  | 5 | -1 | 0 |  |  | X
6662 | 6662 | 6662 | 6662 | SA24M005 | Sub Grade |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 17 Sub Grade | 1 | STRPAD0017 | C000 | 00C1 | C000STRPAD001700C1
6663 | 6663 | 6663 | 6663 | SA24M005 | Sub Base |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 17 Sub Base | 2 | STRPAD0017 | C000 | 00C2 | C000STRPAD001700C2
6664 | 6664 | 6664 | 6664 | SA24M005 | Final Layer |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 17 Final Layer | 3 | STRPAD0017 | C000 | 00C3 | C000STRPAD001700C3
6665 | 6665 | 6665 | 6665 | SA24M005 | Tower 18 |  | 5 | -1 | 0 |  |  | X
6666 | 6666 | 6666 | 6666 | SA24M005 | Sub Grade |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 18 Sub Grade | 1 | STRPAD0018 | C000 | 00C1 | C000STRPAD001800C1
6667 | 6667 | 6667 | 6667 | SA24M005 | Sub Base |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 18 Sub Base | 2 | STRPAD0018 | C000 | 00C2 | C000STRPAD001800C2
6668 | 6668 | 6668 | 6668 | SA24M005 | Final Layer |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 18 Final Layer | 3 | STRPAD0018 | C000 | 00C3 | C000STRPAD001800C3
6669 | 6669 | 6669 | 6669 | SA24M005 | Tower 19 |  | 5 | -1 | 0 |  |  | X
6670 | 6670 | 6670 | 6670 | SA24M005 | Sub Grade |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 19 Sub Grade | 1 | STRPAD0019 | C000 | 00C1 | C000STRPAD001900C1
6671 | 6671 | 6671 | 6671 | SA24M005 | Sub Base |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 19 Sub Base | 2 | STRPAD0019 | C000 | 00C2 | C000STRPAD001900C2
6672 | 6672 | 6672 | 6672 | SA24M005 | Final Layer |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 19 Final Layer | 3 | STRPAD0019 | C000 | 00C3 | C000STRPAD001900C3
6673 | 6673 | 6673 | 6673 | SA24M005 | Tower 20 |  | 5 | -1 | 0 |  |  | X
6674 | 6674 | 6674 | 6674 | SA24M005 | Sub Grade |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 20 Sub Grade | 1 | STRPAD00TW | C000 | 00C1 | C000STRPAD00TW00C1
6675 | 6675 | 6675 | 6675 | SA24M005 | Sub Base |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 20 Sub Base | 2 | STRPAD00TW | C000 | 00C2 | C000STRPAD00TW00C2
6676 | 6676 | 6676 | 6676 | SA24M005 | Final Layer |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 20 Final Layer | 3 | STRPAD00TW | C000 | 00C3 | C000STRPAD00TW00C3
6677 | 6677 | 6677 | 6677 | SA24M005 | Tower 21 |  | 5 | -1 | 0 |  |  | X
6678 | 6678 | 6678 | 6678 | SA24M005 | Sub Grade |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 21 Sub Grade | 1 | STRPAD0021 | C000 | 00C1 | C000STRPAD002100C1
6679 | 6679 | 6679 | 6679 | SA24M005 | Sub Base |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 21 Sub Base | 2 | STRPAD0021 | C000 | 00C2 | C000STRPAD002100C2
6680 | 6680 | 6680 | 6680 | SA24M005 | Final Layer |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Structure Pad Works Tower 21 Final Layer | 3 | STRPAD0021 | C000 | 00C3 | C000STRPAD002100C3
6681 | 6681 | 6681 | 6681 | SA24M005 | Erection Works |  | 4 | -1 | 0 |  |  | X
6682 | 6682 | 6682 | 6682 | SA24M005 | Tower 1 |  | 5 | -1 | 0 |  |  | X
6683 | 6683 | 6683 | 6683 | SA24M005 | Tower Earthing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 1 Tower Earthing | 1 | E0TW1 | C000 | 00C1 | C000E0TW100C1
6684 | 6684 | 6684 | 6684 | SA24M005 | Tower Ground assembly |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 1 Tower Ground assembly | 2 | E0TW1 | C000 | 00C2 | C000E0TW100C2
6685 | 6685 | 6685 | 6685 | SA24M005 | Tower Erection |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 1 Tower Erection | 3 | E0TW1 | C000 | 00C3 | C000E0TW100C3
6686 | 6686 | 6686 | 6686 | SA24M005 | Tower Torque check |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 1 Tower Torque check | 4 | E0TW1 | C000 | 00C4 | C000E0TW100C4
6687 | 6687 | 6687 | 6687 | SA24M005 | Palnut Fixing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 1 Palnut Fixing | 5 | E0TW1 | C000 | 00C5 | C000E0TW100C5
6688 | 6688 | 6688 | 6688 | SA24M005 | Tower Platform installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 1 Tower Platform installation | 6 | E0TW1 | C000 | 00C6 | C000E0TW100C6
6689 | 6689 | 6689 | 6689 | SA24M005 | Tower accessories installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 1 Tower accessories installation | 7 | E0TW1 | C000 | 00C7 | C000E0TW100C7
6690 | 6690 | 6690 | 6690 | SA24M005 | Anti climbing device installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 1 Anti climbing device installation | 8 | E0TW1 | C000 | 00C8 | C000E0TW100C8
6691 | 6691 | 6691 | 6691 | SA24M005 | Final Checking |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 1 Final Checking | 9 | E0TW1 | C000 | 00C9 | C000E0TW100C9
6692 | 6692 | 6692 | 6692 | SA24M005 | Tower 2 |  | 5 | -1 | 0 |  |  | X
6693 | 6693 | 6693 | 6693 | SA24M005 | Tower Earthing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 2 Tower Earthing | 1 | E0TW2 | C000 | 00C1 | C000E0TW200C1
6694 | 6694 | 6694 | 6694 | SA24M005 | Tower Ground assembly |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 2 Tower Ground assembly | 2 | E0TW2 | C000 | 00C2 | C000E0TW200C2
6695 | 6695 | 6695 | 6695 | SA24M005 | Tower Erection |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 2 Tower Erection | 3 | E0TW2 | C000 | 00C3 | C000E0TW200C3
6696 | 6696 | 6696 | 6696 | SA24M005 | Tower Torque check |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 2 Tower Torque check | 4 | E0TW2 | C000 | 00C4 | C000E0TW200C4
6697 | 6697 | 6697 | 6697 | SA24M005 | Palnut Fixing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 2 Palnut Fixing | 5 | E0TW2 | C000 | 00C5 | C000E0TW200C5
6698 | 6698 | 6698 | 6698 | SA24M005 | Tower Platform installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 2 Tower Platform installation | 6 | E0TW2 | C000 | 00C6 | C000E0TW200C6
6699 | 6699 | 6699 | 6699 | SA24M005 | Tower accessories installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 2 Tower accessories installation | 7 | E0TW2 | C000 | 00C7 | C000E0TW200C7
6700 | 6700 | 6700 | 6700 | SA24M005 | Anti climbing device installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 2 Anti climbing device installation | 8 | E0TW2 | C000 | 00C8 | C000E0TW200C8
6701 | 6701 | 6701 | 6701 | SA24M005 | Final Checking |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 2 Final Checking | 9 | E0TW2 | C000 | 00C9 | C000E0TW200C9
6702 | 6702 | 6702 | 6702 | SA24M005 | Tower 3 |  | 5 | -1 | 0 |  |  | X
6703 | 6703 | 6703 | 6703 | SA24M005 | Tower Earthing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 3 Tower Earthing | 1 | E0TW3 | C000 | 00C1 | C000#RnJz00C1
6704 | 6704 | 6704 | 6704 | SA24M005 | Tower Ground assembly |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 3 Tower Ground assembly | 2 | E0TW3 | C000 | 00C2 | C000#RnJz00C2
6705 | 6705 | 6705 | 6705 | SA24M005 | Tower Erection |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 3 Tower Erection | 3 | E0TW3 | C000 | 00C3 | C000#RnJz00C3
6706 | 6706 | 6706 | 6706 | SA24M005 | Tower Torque check |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 3 Tower Torque check | 4 | E0TW3 | C000 | 00C4 | C000#RnJz00C4
6707 | 6707 | 6707 | 6707 | SA24M005 | Palnut Fixing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 3 Palnut Fixing | 5 | E0TW3 | C000 | 00C5 | C000#RnJz00C5
6708 | 6708 | 6708 | 6708 | SA24M005 | Tower Platform installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 3 Tower Platform installation | 6 | E0TW3 | C000 | 00C6 | C000#RnJz00C6
6709 | 6709 | 6709 | 6709 | SA24M005 | Tower accessories installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 3 Tower accessories installation | 7 | E0TW3 | C000 | 00C7 | C000#RnJz00C7
6710 | 6710 | 6710 | 6710 | SA24M005 | Anti climbing device installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 3 Anti climbing device installation | 8 | E0TW3 | C000 | 00C8 | C000#RnJz00C8
6711 | 6711 | 6711 | 6711 | SA24M005 | Final Checking |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 3 Final Checking | 9 | E0TW3 | C000 | 00C9 | C000#RnJz00C9
6712 | 6712 | 6712 | 6712 | SA24M005 | Tower 4 |  | 5 | -1 | 0 |  |  | X | C000#RnJz
6713 | 6713 | 6713 | 6713 | SA24M005 | Tower Earthing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 4 Tower Earthing | 1 | E0TW4 | C000 | 00C1 | C000E0TW400C1
6714 | 6714 | 6714 | 6714 | SA24M005 | Tower Ground assembly |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 4 Tower Ground assembly | 2 | E0TW4 | C000 | 00C2 | C000E0TW400C2
6715 | 6715 | 6715 | 6715 | SA24M005 | Tower Erection |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 4 Tower Erection | 3 | E0TW4 | C000 | 00C3 | C000E0TW400C3
6716 | 6716 | 6716 | 6716 | SA24M005 | Tower Torque check |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 4 Tower Torque check | 4 | E0TW4 | C000 | 00C4 | C000E0TW400C4
6717 | 6717 | 6717 | 6717 | SA24M005 | Palnut Fixing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 4 Palnut Fixing | 5 | E0TW4 | C000 | 00C5 | C000E0TW400C5
6718 | 6718 | 6718 | 6718 | SA24M005 | Tower Platform installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 4 Tower Platform installation | 6 | E0TW4 | C000 | 00C6 | C000E0TW400C6
6719 | 6719 | 6719 | 6719 | SA24M005 | Tower accessories installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 4 Tower accessories installation | 7 | E0TW4 | C000 | 00C7 | C000E0TW400C7
6720 | 6720 | 6720 | 6720 | SA24M005 | Anti climbing device installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 4 Anti climbing device installation | 8 | E0TW4 | C000 | 00C8 | C000E0TW400C8
6721 | 6721 | 6721 | 6721 | SA24M005 | Final Checking |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 4 Final Checking | 9 | E0TW4 | C000 | 00C9 | C000E0TW400C9
6722 | 6722 | 6722 | 6722 | SA24M005 | Tower 5 |  | 5 | -1 | 0 |  |  | X
6723 | 6723 | 6723 | 6723 | SA24M005 | Tower Earthing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 5 Tower Earthing | 1 | E0TW5 | C000 | 00C1 | C000E0TW500C1
6724 | 6724 | 6724 | 6724 | SA24M005 | Tower Ground assembly |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 5 Tower Ground assembly | 2 | E0TW5 | C000 | 00C2 | C000E0TW500C2
6725 | 6725 | 6725 | 6725 | SA24M005 | Tower Erection |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 5 Tower Erection | 3 | E0TW5 | C000 | 00C3 | C000E0TW500C3
6726 | 6726 | 6726 | 6726 | SA24M005 | Tower Torque check |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 5 Tower Torque check | 4 | E0TW5 | C000 | 00C4 | C000E0TW500C4
6727 | 6727 | 6727 | 6727 | SA24M005 | Palnut Fixing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 5 Palnut Fixing | 5 | E0TW5 | C000 | 00C5 | C000E0TW500C5
6728 | 6728 | 6728 | 6728 | SA24M005 | Tower Platform installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 5 Tower Platform installation | 6 | E0TW5 | C000 | 00C6 | C000E0TW500C6
6729 | 6729 | 6729 | 6729 | SA24M005 | Tower accessories installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 5 Tower accessories installation | 7 | E0TW5 | C000 | 00C7 | C000E0TW500C7
6730 | 6730 | 6730 | 6730 | SA24M005 | Anti climbing device installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 5 Anti climbing device installation | 8 | E0TW5 | C000 | 00C8 | C000E0TW500C8
6731 | 6731 | 6731 | 6731 | SA24M005 | Final Checking |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 5 Final Checking | 9 | E0TW5 | C000 | 00C9 | C000E0TW500C9
6732 | 6732 | 6732 | 6732 | SA24M005 | Tower 6 |  | 5 | -1 | 0 |  |  | X
6733 | 6733 | 6733 | 6733 | SA24M005 | Tower Earthing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 6 Tower Earthing | 1 | E0TW6 | C000 | 00C1 | C000E0TW600C1
6734 | 6734 | 6734 | 6734 | SA24M005 | Tower Ground assembly |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 6 Tower Ground assembly | 2 | E0TW6 | C000 | 00C2 | C000E0TW600C2
6735 | 6735 | 6735 | 6735 | SA24M005 | Tower Erection |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 6 Tower Erection | 3 | E0TW6 | C000 | 00C3 | C000E0TW600C3
6736 | 6736 | 6736 | 6736 | SA24M005 | Tower Torque check |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 6 Tower Torque check | 4 | E0TW6 | C000 | 00C4 | C000E0TW600C4
6737 | 6737 | 6737 | 6737 | SA24M005 | Palnut Fixing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 6 Palnut Fixing | 5 | E0TW6 | C000 | 00C5 | C000E0TW600C5
6738 | 6738 | 6738 | 6738 | SA24M005 | Tower Platform installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 6 Tower Platform installation | 6 | E0TW6 | C000 | 00C6 | C000E0TW600C6
6739 | 6739 | 6739 | 6739 | SA24M005 | Tower accessories installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 6 Tower accessories installation | 7 | E0TW6 | C000 | 00C7 | C000E0TW600C7
6740 | 6740 | 6740 | 6740 | SA24M005 | Anti climbing device installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 6 Anti climbing device installation | 8 | E0TW6 | C000 | 00C8 | C000E0TW600C8
6741 | 6741 | 6741 | 6741 | SA24M005 | Final Checking |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 6 Final Checking | 9 | E0TW6 | C000 | 00C9 | C000E0TW600C9
6742 | 6742 | 6742 | 6742 | SA24M005 | Tower 7 |  | 5 | -1 | 0 |  |  | X
6743 | 6743 | 6743 | 6743 | SA24M005 | Tower Earthing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 7 Tower Earthing | 1 | E0TW7 | C000 | 00C1 | C000E0TW700C1
6744 | 6744 | 6744 | 6744 | SA24M005 | Tower Ground assembly |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 7 Tower Ground assembly | 2 | E0TW7 | C000 | 00C2 | C000E0TW700C2
6745 | 6745 | 6745 | 6745 | SA24M005 | Tower Erection |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 7 Tower Erection | 3 | E0TW7 | C000 | 00C3 | C000E0TW700C3
6746 | 6746 | 6746 | 6746 | SA24M005 | Tower Torque check |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 7 Tower Torque check | 4 | E0TW7 | C000 | 00C4 | C000E0TW700C4
6747 | 6747 | 6747 | 6747 | SA24M005 | Palnut Fixing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 7 Palnut Fixing | 5 | E0TW7 | C000 | 00C5 | C000E0TW700C5
6748 | 6748 | 6748 | 6748 | SA24M005 | Tower Platform installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 7 Tower Platform installation | 6 | E0TW7 | C000 | 00C6 | C000E0TW700C6
6749 | 6749 | 6749 | 6749 | SA24M005 | Tower accessories installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 7 Tower accessories installation | 7 | E0TW7 | C000 | 00C7 | C000E0TW700C7
6750 | 6750 | 6750 | 6750 | SA24M005 | Anti climbing device installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 7 Anti climbing device installation | 8 | E0TW7 | C000 | 00C8 | C000E0TW700C8
6751 | 6751 | 6751 | 6751 | SA24M005 | Final Checking |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 7 Final Checking | 9 | E0TW7 | C000 | 00C9 | C000E0TW700C9
6752 | 6752 | 6752 | 6752 | SA24M005 | Tower 8 |  | 5 | -1 | 0 |  |  | X
6753 | 6753 | 6753 | 6753 | SA24M005 | Tower Earthing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 8 Tower Earthing | 1 | E0TW8 | C000 | 00C1 | C000E0TW800C1
6754 | 6754 | 6754 | 6754 | SA24M005 | Tower Ground assembly |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 8 Tower Ground assembly | 2 | E0TW8 | C000 | 00C2 | C000E0TW800C2
6755 | 6755 | 6755 | 6755 | SA24M005 | Tower Erection |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 8 Tower Erection | 3 | E0TW8 | C000 | 00C3 | C000E0TW800C3
6756 | 6756 | 6756 | 6756 | SA24M005 | Tower Torque check |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 8 Tower Torque check | 4 | E0TW8 | C000 | 00C4 | C000E0TW800C4
6757 | 6757 | 6757 | 6757 | SA24M005 | Palnut Fixing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 8 Palnut Fixing | 5 | E0TW8 | C000 | 00C5 | C000E0TW800C5
6758 | 6758 | 6758 | 6758 | SA24M005 | Tower Platform installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 8 Tower Platform installation | 6 | E0TW8 | C000 | 00C6 | C000E0TW800C6
6759 | 6759 | 6759 | 6759 | SA24M005 | Tower accessories installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 8 Tower accessories installation | 7 | E0TW8 | C000 | 00C7 | C000E0TW800C7
6760 | 6760 | 6760 | 6760 | SA24M005 | Anti climbing device installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 8 Anti climbing device installation | 8 | E0TW8 | C000 | 00C8 | C000E0TW800C8
6761 | 6761 | 6761 | 6761 | SA24M005 | Final Checking |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 8 Final Checking | 9 | E0TW8 | C000 | 00C9 | C000E0TW800C9
6762 | 6762 | 6762 | 6762 | SA24M005 | Tower 9 |  | 5 | -1 | 0 |  |  | X
6763 | 6763 | 6763 | 6763 | SA24M005 | Tower Earthing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 9 Tower Earthing | 1 | E0TW9 | C000 | 00C1 | C000E0TW900C1
6764 | 6764 | 6764 | 6764 | SA24M005 | Tower Ground assembly |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 9 Tower Ground assembly | 2 | E0TW9 | C000 | 00C2 | C000E0TW900C2
6765 | 6765 | 6765 | 6765 | SA24M005 | Tower Erection |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 9 Tower Erection | 3 | E0TW9 | C000 | 00C3 | C000E0TW900C3
6766 | 6766 | 6766 | 6766 | SA24M005 | Tower Torque check |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 9 Tower Torque check | 4 | E0TW9 | C000 | 00C4 | C000E0TW900C4
6767 | 6767 | 6767 | 6767 | SA24M005 | Palnut Fixing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 9 Palnut Fixing | 5 | E0TW9 | C000 | 00C5 | C000E0TW900C5
6768 | 6768 | 6768 | 6768 | SA24M005 | Tower Platform installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 9 Tower Platform installation | 6 | E0TW9 | C000 | 00C6 | C000E0TW900C6
6769 | 6769 | 6769 | 6769 | SA24M005 | Tower accessories installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 9 Tower accessories installation | 7 | E0TW9 | C000 | 00C7 | C000E0TW900C7
6770 | 6770 | 6770 | 6770 | SA24M005 | Anti climbing device installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 9 Anti climbing device installation | 8 | E0TW9 | C000 | 00C8 | C000E0TW900C8
6771 | 6771 | 6771 | 6771 | SA24M005 | Final Checking |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 9 Final Checking | 9 | E0TW9 | C000 | 00C9 | C000E0TW900C9
6772 | 6772 | 6772 | 6772 | SA24M005 | Tower 10 |  | 5 | -1 | 0 |  |  | X
6773 | 6773 | 6773 | 6773 | SA24M005 | Tower Earthing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 10 Tower Earthing | 1 | E0TW10 | C000 | 00C1 | C000E0TW1000C1
6774 | 6774 | 6774 | 6774 | SA24M005 | Tower Ground assembly |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 10 Tower Ground assembly | 2 | E0TW10 | C000 | 00C2 | C000E0TW1000C2
6775 | 6775 | 6775 | 6775 | SA24M005 | Tower Erection |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 10 Tower Erection | 3 | E0TW10 | C000 | 00C3 | C000E0TW1000C3
6776 | 6776 | 6776 | 6776 | SA24M005 | Tower Torque check |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 10 Tower Torque check | 4 | E0TW10 | C000 | 00C4 | C000E0TW1000C4
6777 | 6777 | 6777 | 6777 | SA24M005 | Palnut Fixing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 10 Palnut Fixing | 5 | E0TW10 | C000 | 00C5 | C000E0TW1000C5
6778 | 6778 | 6778 | 6778 | SA24M005 | Tower Platform installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 10 Tower Platform installation | 6 | E0TW10 | C000 | 00C6 | C000E0TW1000C6
6779 | 6779 | 6779 | 6779 | SA24M005 | Tower accessories installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 10 Tower accessories installation | 7 | E0TW10 | C000 | 00C7 | C000E0TW1000C7
6780 | 6780 | 6780 | 6780 | SA24M005 | Anti climbing device installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 10 Anti climbing device installation | 8 | E0TW10 | C000 | 00C8 | C000E0TW1000C8
6781 | 6781 | 6781 | 6781 | SA24M005 | Final Checking |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 10 Final Checking | 9 | E0TW10 | C000 | 00C9 | C000E0TW1000C9
6782 | 6782 | 6782 | 6782 | SA24M005 | Tower 11 |  | 5 | -1 | 0 |  |  | X
6783 | 6783 | 6783 | 6783 | SA24M005 | Tower Earthing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 11 Tower Earthing | 1 | E0TW11 | C000 | 00C1 | C000E0TW1100C1
6784 | 6784 | 6784 | 6784 | SA24M005 | Tower Ground assembly |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 11 Tower Ground assembly | 2 | E0TW11 | C000 | 00C2 | C000E0TW1100C2
6785 | 6785 | 6785 | 6785 | SA24M005 | Tower Erection |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 11 Tower Erection | 3 | E0TW11 | C000 | 00C3 | C000E0TW1100C3
6786 | 6786 | 6786 | 6786 | SA24M005 | Tower Torque check |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 11 Tower Torque check | 4 | E0TW11 | C000 | 00C4 | C000E0TW1100C4
6787 | 6787 | 6787 | 6787 | SA24M005 | Palnut Fixing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 11 Palnut Fixing | 5 | E0TW11 | C000 | 00C5 | C000E0TW1100C5
6788 | 6788 | 6788 | 6788 | SA24M005 | Tower Platform installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 11 Tower Platform installation | 6 | E0TW11 | C000 | 00C6 | C000E0TW1100C6
6789 | 6789 | 6789 | 6789 | SA24M005 | Tower accessories installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 11 Tower accessories installation | 7 | E0TW11 | C000 | 00C7 | C000E0TW1100C7
6790 | 6790 | 6790 | 6790 | SA24M005 | Anti climbing device installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 11 Anti climbing device installation | 8 | E0TW11 | C000 | 00C8 | C000E0TW1100C8
6791 | 6791 | 6791 | 6791 | SA24M005 | Final Checking |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 11 Final Checking | 9 | E0TW11 | C000 | 00C9 | C000E0TW1100C9
6792 | 6792 | 6792 | 6792 | SA24M005 | Tower 12 |  | 5 | -1 | 0 |  |  | X
6793 | 6793 | 6793 | 6793 | SA24M005 | Tower Earthing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 12 Tower Earthing | 1 | E0TW12 | C000 | 00C1 | C000E0TW1200C1
6794 | 6794 | 6794 | 6794 | SA24M005 | Tower Ground assembly |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 12 Tower Ground assembly | 2 | E0TW12 | C000 | 00C2 | C000E0TW1200C2
6795 | 6795 | 6795 | 6795 | SA24M005 | Tower Erection |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 12 Tower Erection | 3 | E0TW12 | C000 | 00C3 | C000E0TW1200C3
6796 | 6796 | 6796 | 6796 | SA24M005 | Tower Torque check |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 12 Tower Torque check | 4 | E0TW12 | C000 | 00C4 | C000E0TW1200C4
6797 | 6797 | 6797 | 6797 | SA24M005 | Palnut Fixing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 12 Palnut Fixing | 5 | E0TW12 | C000 | 00C5 | C000E0TW1200C5
6798 | 6798 | 6798 | 6798 | SA24M005 | Tower Platform installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 12 Tower Platform installation | 6 | E0TW12 | C000 | 00C6 | C000E0TW1200C6
6799 | 6799 | 6799 | 6799 | SA24M005 | Tower accessories installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 12 Tower accessories installation | 7 | E0TW12 | C000 | 00C7 | C000E0TW1200C7
6800 | 6800 | 6800 | 6800 | SA24M005 | Anti climbing device installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 12 Anti climbing device installation | 8 | E0TW12 | C000 | 00C8 | C000E0TW1200C8
6801 | 6801 | 6801 | 6801 | SA24M005 | Final Checking |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 12 Final Checking | 9 | E0TW12 | C000 | 00C9 | C000E0TW1200C9
6802 | 6802 | 6802 | 6802 | SA24M005 | Tower 13 |  | 5 | -1 | 0 |  |  | X
6803 | 6803 | 6803 | 6803 | SA24M005 | Tower Earthing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 13 Tower Earthing | 1 | E0TW13 | C000 | 00C1 | C000E0TW1300C1
6804 | 6804 | 6804 | 6804 | SA24M005 | Tower Ground assembly |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 13 Tower Ground assembly | 2 | E0TW13 | C000 | 00C2 | C000E0TW1300C2
6805 | 6805 | 6805 | 6805 | SA24M005 | Tower Erection |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 13 Tower Erection | 3 | E0TW13 | C000 | 00C3 | C000E0TW1300C3
6806 | 6806 | 6806 | 6806 | SA24M005 | Tower Torque check |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 13 Tower Torque check | 4 | E0TW13 | C000 | 00C4 | C000E0TW1300C4
6807 | 6807 | 6807 | 6807 | SA24M005 | Palnut Fixing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 13 Palnut Fixing | 5 | E0TW13 | C000 | 00C5 | C000E0TW1300C5
6808 | 6808 | 6808 | 6808 | SA24M005 | Tower Platform installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 13 Tower Platform installation | 6 | E0TW13 | C000 | 00C6 | C000E0TW1300C6
6809 | 6809 | 6809 | 6809 | SA24M005 | Tower accessories installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 13 Tower accessories installation | 7 | E0TW13 | C000 | 00C7 | C000E0TW1300C7
6810 | 6810 | 6810 | 6810 | SA24M005 | Anti climbing device installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 13 Anti climbing device installation | 8 | E0TW13 | C000 | 00C8 | C000E0TW1300C8
6811 | 6811 | 6811 | 6811 | SA24M005 | Final Checking |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 13 Final Checking | 9 | E0TW13 | C000 | 00C9 | C000E0TW1300C9
6812 | 6812 | 6812 | 6812 | SA24M005 | Tower 14 |  | 5 | -1 | 0 |  |  | X
6813 | 6813 | 6813 | 6813 | SA24M005 | Tower Earthing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 14 Tower Earthing | 1 | E0TW14 | C000 | 00C1 | C000E0TW1400C1
6814 | 6814 | 6814 | 6814 | SA24M005 | Tower Ground assembly |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 14 Tower Ground assembly | 2 | E0TW14 | C000 | 00C2 | C000E0TW1400C2
6815 | 6815 | 6815 | 6815 | SA24M005 | Tower Erection |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 14 Tower Erection | 3 | E0TW14 | C000 | 00C3 | C000E0TW1400C3
6816 | 6816 | 6816 | 6816 | SA24M005 | Tower Torque check |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 14 Tower Torque check | 4 | E0TW14 | C000 | 00C4 | C000E0TW1400C4
6817 | 6817 | 6817 | 6817 | SA24M005 | Palnut Fixing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 14 Palnut Fixing | 5 | E0TW14 | C000 | 00C5 | C000E0TW1400C5
6818 | 6818 | 6818 | 6818 | SA24M005 | Tower Platform installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 14 Tower Platform installation | 6 | E0TW14 | C000 | 00C6 | C000E0TW1400C6
6819 | 6819 | 6819 | 6819 | SA24M005 | Tower accessories installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 14 Tower accessories installation | 7 | E0TW14 | C000 | 00C7 | C000E0TW1400C7
6820 | 6820 | 6820 | 6820 | SA24M005 | Anti climbing device installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 14 Anti climbing device installation | 8 | E0TW14 | C000 | 00C8 | C000E0TW1400C8
6821 | 6821 | 6821 | 6821 | SA24M005 | Final Checking |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 14 Final Checking | 9 | E0TW14 | C000 | 00C9 | C000E0TW1400C9
6822 | 6822 | 6822 | 6822 | SA24M005 | Tower 15 |  | 5 | -1 | 0 |  |  | X
6823 | 6823 | 6823 | 6823 | SA24M005 | Tower Earthing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 15 Tower Earthing | 1 | E0TW15 | C000 | 00C1 | C000E0TW1500C1
6824 | 6824 | 6824 | 6824 | SA24M005 | Tower Ground assembly |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 15 Tower Ground assembly | 2 | E0TW15 | C000 | 00C2 | C000E0TW1500C2
6825 | 6825 | 6825 | 6825 | SA24M005 | Tower Erection |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 15 Tower Erection | 3 | E0TW15 | C000 | 00C3 | C000E0TW1500C3
6826 | 6826 | 6826 | 6826 | SA24M005 | Tower Torque check |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 15 Tower Torque check | 4 | E0TW15 | C000 | 00C4 | C000E0TW1500C4
6827 | 6827 | 6827 | 6827 | SA24M005 | Palnut Fixing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 15 Palnut Fixing | 5 | E0TW15 | C000 | 00C5 | C000E0TW1500C5
6828 | 6828 | 6828 | 6828 | SA24M005 | Tower Platform installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 15 Tower Platform installation | 6 | E0TW15 | C000 | 00C6 | C000E0TW1500C6
6829 | 6829 | 6829 | 6829 | SA24M005 | Tower accessories installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 15 Tower accessories installation | 7 | E0TW15 | C000 | 00C7 | C000E0TW1500C7
6830 | 6830 | 6830 | 6830 | SA24M005 | Anti climbing device installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 15 Anti climbing device installation | 8 | E0TW15 | C000 | 00C8 | C000E0TW1500C8
6831 | 6831 | 6831 | 6831 | SA24M005 | Final Checking |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 15 Final Checking | 9 | E0TW15 | C000 | 00C9 | C000E0TW1500C9
6832 | 6832 | 6832 | 6832 | SA24M005 | Tower 16 |  | 5 | -1 | 0 |  |  | X
6833 | 6833 | 6833 | 6833 | SA24M005 | Tower Earthing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 16 Tower Earthing | 1 | E0TW16 | C000 | 00C1 | C000E0TW1600C1
6834 | 6834 | 6834 | 6834 | SA24M005 | Tower Ground assembly |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 16 Tower Ground assembly | 2 | E0TW16 | C000 | 00C2 | C000E0TW1600C2
6835 | 6835 | 6835 | 6835 | SA24M005 | Tower Erection |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 16 Tower Erection | 3 | E0TW16 | C000 | 00C3 | C000E0TW1600C3
6836 | 6836 | 6836 | 6836 | SA24M005 | Tower Torque check |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 16 Tower Torque check | 4 | E0TW16 | C000 | 00C4 | C000E0TW1600C4
6837 | 6837 | 6837 | 6837 | SA24M005 | Palnut Fixing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 16 Palnut Fixing | 5 | E0TW16 | C000 | 00C5 | C000E0TW1600C5
6838 | 6838 | 6838 | 6838 | SA24M005 | Tower Platform installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 16 Tower Platform installation | 6 | E0TW16 | C000 | 00C6 | C000E0TW1600C6
6839 | 6839 | 6839 | 6839 | SA24M005 | Tower accessories installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 16 Tower accessories installation | 7 | E0TW16 | C000 | 00C7 | C000E0TW1600C7
6840 | 6840 | 6840 | 6840 | SA24M005 | Anti climbing device installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 16 Anti climbing device installation | 8 | E0TW16 | C000 | 00C8 | C000E0TW1600C8
6841 | 6841 | 6841 | 6841 | SA24M005 | Final Checking |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 16 Final Checking | 9 | E0TW16 | C000 | 00C9 | C000E0TW1600C9
6842 | 6842 | 6842 | 6842 | SA24M005 | Tower 17 |  | 5 | -1 | 0 |  |  | X
6843 | 6843 | 6843 | 6843 | SA24M005 | Tower Earthing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 17 Tower Earthing | 1 | E0TW17 | C000 | 00C1 | C000E0TW1700C1
6844 | 6844 | 6844 | 6844 | SA24M005 | Tower Ground assembly |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 17 Tower Ground assembly | 2 | E0TW17 | C000 | 00C2 | C000E0TW1700C2
6845 | 6845 | 6845 | 6845 | SA24M005 | Tower Erection |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 17 Tower Erection | 3 | E0TW17 | C000 | 00C3 | C000E0TW1700C3
6846 | 6846 | 6846 | 6846 | SA24M005 | Tower Torque check |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 17 Tower Torque check | 4 | E0TW17 | C000 | 00C4 | C000E0TW1700C4
6847 | 6847 | 6847 | 6847 | SA24M005 | Palnut Fixing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 17 Palnut Fixing | 5 | E0TW17 | C000 | 00C5 | C000E0TW1700C5
6848 | 6848 | 6848 | 6848 | SA24M005 | Tower Platform installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 17 Tower Platform installation | 6 | E0TW17 | C000 | 00C6 | C000E0TW1700C6
6849 | 6849 | 6849 | 6849 | SA24M005 | Tower accessories installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 17 Tower accessories installation | 7 | E0TW17 | C000 | 00C7 | C000E0TW1700C7
6850 | 6850 | 6850 | 6850 | SA24M005 | Anti climbing device installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 17 Anti climbing device installation | 8 | E0TW17 | C000 | 00C8 | C000E0TW1700C8
6851 | 6851 | 6851 | 6851 | SA24M005 | Final Checking |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 17 Final Checking | 9 | E0TW17 | C000 | 00C9 | C000E0TW1700C9
6852 | 6852 | 6852 | 6852 | SA24M005 | Tower 18 |  | 5 | -1 | 0 |  |  | X
6853 | 6853 | 6853 | 6853 | SA24M005 | Tower Earthing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 18 Tower Earthing | 1 | E0TW18 | C000 | 00C1 | C000E0TW1800C1
6854 | 6854 | 6854 | 6854 | SA24M005 | Tower Ground assembly |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 18 Tower Ground assembly | 2 | E0TW18 | C000 | 00C2 | C000E0TW1800C2
6855 | 6855 | 6855 | 6855 | SA24M005 | Tower Erection |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 18 Tower Erection | 3 | E0TW18 | C000 | 00C3 | C000E0TW1800C3
6856 | 6856 | 6856 | 6856 | SA24M005 | Tower Torque check |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 18 Tower Torque check | 4 | E0TW18 | C000 | 00C4 | C000E0TW1800C4
6857 | 6857 | 6857 | 6857 | SA24M005 | Palnut Fixing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 18 Palnut Fixing | 5 | E0TW18 | C000 | 00C5 | C000E0TW1800C5
6858 | 6858 | 6858 | 6858 | SA24M005 | Tower Platform installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 18 Tower Platform installation | 6 | E0TW18 | C000 | 00C6 | C000E0TW1800C6
6859 | 6859 | 6859 | 6859 | SA24M005 | Tower accessories installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 18 Tower accessories installation | 7 | E0TW18 | C000 | 00C7 | C000E0TW1800C7
6860 | 6860 | 6860 | 6860 | SA24M005 | Anti climbing device installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 18 Anti climbing device installation | 8 | E0TW18 | C000 | 00C8 | C000E0TW1800C8
6861 | 6861 | 6861 | 6861 | SA24M005 | Final Checking |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 18 Final Checking | 9 | E0TW18 | C000 | 00C9 | C000E0TW1800C9
6862 | 6862 | 6862 | 6862 | SA24M005 | Tower 19 |  | 5 | -1 | 0 |  |  | X
6863 | 6863 | 6863 | 6863 | SA24M005 | Tower Earthing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 19 Tower Earthing | 1 | E0TW19 | C000 | 00C1 | C000E0TW1900C1
6864 | 6864 | 6864 | 6864 | SA24M005 | Tower Ground assembly |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 19 Tower Ground assembly | 2 | E0TW19 | C000 | 00C2 | C000E0TW1900C2
6865 | 6865 | 6865 | 6865 | SA24M005 | Tower Erection |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 19 Tower Erection | 3 | E0TW19 | C000 | 00C3 | C000E0TW1900C3
6866 | 6866 | 6866 | 6866 | SA24M005 | Tower Torque check |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 19 Tower Torque check | 4 | E0TW19 | C000 | 00C4 | C000E0TW1900C4
6867 | 6867 | 6867 | 6867 | SA24M005 | Palnut Fixing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 19 Palnut Fixing | 5 | E0TW19 | C000 | 00C5 | C000E0TW1900C5
6868 | 6868 | 6868 | 6868 | SA24M005 | Tower Platform installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 19 Tower Platform installation | 6 | E0TW19 | C000 | 00C6 | C000E0TW1900C6
6869 | 6869 | 6869 | 6869 | SA24M005 | Tower accessories installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 19 Tower accessories installation | 7 | E0TW19 | C000 | 00C7 | C000E0TW1900C7
6870 | 6870 | 6870 | 6870 | SA24M005 | Anti climbing device installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 19 Anti climbing device installation | 8 | E0TW19 | C000 | 00C8 | C000E0TW1900C8
6871 | 6871 | 6871 | 6871 | SA24M005 | Final Checking |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 19 Final Checking | 9 | E0TW19 | C000 | 00C9 | C000E0TW1900C9
6872 | 6872 | 6872 | 6872 | SA24M005 | Tower 20 |  | 5 | -1 | 0 |  |  | X
6873 | 6873 | 6873 | 6873 | SA24M005 | Tower Earthing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 20 Tower Earthing | 1 | E0TW20 | C000 | 00C1 | C000E0TW2000C1
6874 | 6874 | 6874 | 6874 | SA24M005 | Tower Ground assembly |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 20 Tower Ground assembly | 2 | E0TW20 | C000 | 00C2 | C000E0TW2000C2
6875 | 6875 | 6875 | 6875 | SA24M005 | Tower Erection |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 20 Tower Erection | 3 | E0TW20 | C000 | 00C3 | C000E0TW2000C3
6876 | 6876 | 6876 | 6876 | SA24M005 | Tower Torque check |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 20 Tower Torque check | 4 | E0TW20 | C000 | 00C4 | C000E0TW2000C4
6877 | 6877 | 6877 | 6877 | SA24M005 | Palnut Fixing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 20 Palnut Fixing | 5 | E0TW20 | C000 | 00C5 | C000E0TW2000C5
6878 | 6878 | 6878 | 6878 | SA24M005 | Tower Platform installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 20 Tower Platform installation | 6 | E0TW20 | C000 | 00C6 | C000E0TW2000C6
6879 | 6879 | 6879 | 6879 | SA24M005 | Tower accessories installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 20 Tower accessories installation | 7 | E0TW20 | C000 | 00C7 | C000E0TW2000C7
6880 | 6880 | 6880 | 6880 | SA24M005 | Anti climbing device installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 20 Anti climbing device installation | 8 | E0TW20 | C000 | 00C8 | C000E0TW2000C8
6881 | 6881 | 6881 | 6881 | SA24M005 | Final Checking |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 20 Final Checking | 9 | E0TW20 | C000 | 00C9 | C000E0TW2000C9
6882 | 6882 | 6882 | 6882 | SA24M005 | Tower 21 |  | 5 | -1 | 0 |  |  | X
6883 | 6883 | 6883 | 6883 | SA24M005 | Tower Earthing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 21 Tower Earthing | 1 | E0TW21 | C000 | 00C1 | C000E0TW2100C1
6884 | 6884 | 6884 | 6884 | SA24M005 | Tower Ground assembly |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 21 Tower Ground assembly | 2 | E0TW21 | C000 | 00C2 | C000E0TW2100C2
6885 | 6885 | 6885 | 6885 | SA24M005 | Tower Erection |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 21 Tower Erection | 3 | E0TW21 | C000 | 00C3 | C000E0TW2100C3
6886 | 6886 | 6886 | 6886 | SA24M005 | Tower Torque check |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 21 Tower Torque check | 4 | E0TW21 | C000 | 00C4 | C000E0TW2100C4
6887 | 6887 | 6887 | 6887 | SA24M005 | Palnut Fixing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 21 Palnut Fixing | 5 | E0TW21 | C000 | 00C5 | C000E0TW2100C5
6888 | 6888 | 6888 | 6888 | SA24M005 | Tower Platform installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 21 Tower Platform installation | 6 | E0TW21 | C000 | 00C6 | C000E0TW2100C6
6889 | 6889 | 6889 | 6889 | SA24M005 | Tower accessories installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 21 Tower accessories installation | 7 | E0TW21 | C000 | 00C7 | C000E0TW2100C7
6890 | 6890 | 6890 | 6890 | SA24M005 | Anti climbing device installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 21 Anti climbing device installation | 8 | E0TW21 | C000 | 00C8 | C000E0TW2100C8
6891 | 6891 | 6891 | 6891 | SA24M005 | Final Checking |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Erection Works Tower 21 Final Checking | 9 | E0TW21 | C000 | 00C9 | C000E0TW2100C9
6892 | 6892 | 6892 | 6892 | SA24M005 | Stringing Conductor |  | 4 | -1 | 0 |  |  | X
6893 | 6893 | 6893 | 6893 | SA24M005 | Insulator Hoisting |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Stringing Conductor Insulator Hoisting | 1 | L1COND | C000 | 00C1 | C000L1COND00C1
6894 | 6894 | 6894 | 6894 | SA24M005 | Pilot Wire paying Out |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Stringing Conductor Pilot Wire paying Out | 2 | L1COND | C000 | 00C2 | C000L1COND00C2
6895 | 6895 | 6895 | 6895 | SA24M005 | Conductor Paying Out |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Stringing Conductor Conductor Paying Out | 3 | L1COND | C000 | 00C3 | C000L1COND00C3
6896 | 6896 | 6896 | 6896 | SA24M005 | Conductor Clipping |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Stringing Conductor Conductor Clipping | 4 | L1COND | C000 | 00C4 | C000L1COND00C4
6897 | 6897 | 6897 | 6897 | SA24M005 | Spacer Installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Stringing Conductor Spacer Installation | 5 | L1COND | C000 | 00C5 | C000L1COND00C5
6898 | 6898 | 6898 | 6898 | SA24M005 | Jumper Installation |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Stringing Conductor Jumper Installation | 6 | L1COND | C000 | 00C6 | C000L1COND00C6
6899 | 6899 | 6899 | 6899 | SA24M005 | Conductor Final Sagging |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Stringing Conductor Conductor Final Sagging | 7 | L1COND | C000 | 00C7 | C000L1COND00C7
6900 | 6900 | 6900 | 6900 | SA24M005 | Stringing OPGW |  | 4 | -1 | 0 |  |  | X
6901 | 6901 | 6901 | 6901 | SA24M005 | Pilot Wire Paying out |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Stringing OPGW Pilot Wire Paying out | 1 | LGOPG | C000 | 00C1 | C000LGOPG00C1
6902 | 6902 | 6902 | 6902 | SA24M005 | OPGW paying out |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Stringing OPGW OPGW paying out | 2 | LGOPG | C000 | 00C2 | C000LGOPG00C2
6903 | 6903 | 6903 | 6903 | SA24M005 | OPGW Clipping |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Stringing OPGW OPGW Clipping | 3 | LGOPG | C000 | 00C3 | C000LGOPG00C3
6904 | 6904 | 6904 | 6904 | SA24M005 | OPGW Final Sagging |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Stringing OPGW OPGW Final Sagging | 4 | LGOPG | C000 | 00C4 | C000LGOPG00C4
6905 | 6905 | 6905 | 6905 | SA24M005 | Joint Box fixing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Stringing OPGW Joint Box fixing | 5 | LGOPG | C000 | 00C5 | C000LGOPG00C5
6906 | 6906 | 6906 | 6906 | SA24M005 | Splicing of OPGW |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Stringing OPGW Splicing of OPGW | 6 | LGOPG | C000 | 00C6 | C000LGOPG00C6
6907 | 6907 | 6907 | 6907 | SA24M005 | Joint box fixing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Stringing OPGW Joint box fixing | 7 | LGOPG | C000 | 00C7 | C000LGOPG00C7
6908 | 6908 | 6908 | 6908 | SA24M005 | Spliceing of OPGW |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Stringing OPGW Spliceing of OPGW | 8 | LGOPG | C000 | 00C8 | C000LGOPG00C8
6909 | 6909 | 6909 | 6909 | SA24M005 | Clearance / Shutdown availability |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 1 Stringing OPGW Clearance / Shutdown availability | 9 | LGOPG | C000 | 00C9 | C000LGOPG00C9
6910 | 6910 | 6910 | 6910 | SA24M005 | Line 2 |  | 3 | -1 | 0 |  |  | X
6911 | 6911 | 6911 | 6911 | SA24M005 | General Works |  | 4 | -1 | 0 |  |  | X
6912 | 6912 | 6912 | 6912 | SA24M005 | Soil Investigation & Thermal Resistivity Measurement |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 General Works Soil Investigation & Thermal Resistivity Measurement | 1 | LGW0SRM | C000 | 00C1 | C000#oeRW00C1
6913 | 6913 | 6913 | 6913 | SA24M005 | Construction of Access Road |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 General Works Construction of Access Road | 2 | LGW0SRM | C000 | 00C2 | C000#oeRW00C2
6914 | 6914 | 6914 | 6914 | SA24M005 | Route Survey |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 General Works Route Survey | 3 | LGW0SRM | C000 | 00C3 | C000#oeRW00C3
6915 | 6915 | 6915 | 6915 | SA24M005 | Civil Works |  | 4 | -1 | 0 |  |  | X | C000#oeRW
6916 | 6916 | 6916 | 6916 | SA24M005 | Tower 1 |  | 5 | -1 | 0 |  |  | X | C000#oeRW
6917 | 6917 | 6917 | 6917 | SA24M005 | ROW / Work Permit |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Civil Works Tower 1 ROW / Work Permit | 1 | C0TW1 | C000 | 00C1 | C000C0TW100C1
6918 | 6918 | 6918 | 6918 | SA24M005 | Excavation / Piping |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Civil Works Tower 1 Excavation / Piping | 2 | C0TW1 | C000 | 00C2 | C000C0TW100C2
6919 | 6919 | 6919 | 6919 | SA24M005 | Stub Setting |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Civil Works Tower 1 Stub Setting | 3 | C0TW1 | C000 | 00C3 | C000C0TW100C3
6920 | 6920 | 6920 | 6920 | SA24M005 | Placement of PCC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Civil Works Tower 1 Placement of PCC | 4 | C0TW1 | C000 | 00C4 | C000C0TW100C4
6921 | 6921 | 6921 | 6921 | SA24M005 | Reinforcement Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Civil Works Tower 1 Reinforcement Works | 5 | C0TW1 | C000 | 00C5 | C000C0TW100C5
6922 | 6922 | 6922 | 6922 | SA24M005 | Concreting / RCC Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Civil Works Tower 1 Concreting / RCC Works | 6 | C0TW1 | C000 | 00C6 | C000C0TW100C6
6923 | 6923 | 6923 | 6923 | SA24M005 | Backfilling |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Civil Works Tower 1 Backfilling | 7 | C0TW1 | C000 | 00C7 | C000C0TW100C7
6924 | 6924 | 6924 | 6924 | SA24M005 | Tower 2 |  | 5 | -1 | 0 |  |  | X
6925 | 6925 | 6925 | 6925 | SA24M005 | ROW / Work Permit |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Civil Works Tower 2 ROW / Work Permit | 1 | C0TW0ROW | C000 | 00C1 | C000C0TW0ROW00C1
6926 | 6926 | 6926 | 6926 | SA24M005 | Excavation / Piping |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Civil Works Tower 2 Excavation / Piping | 2 | C0TW0ROW | C000 | 00C2 | C000C0TW0ROW00C2
6927 | 6927 | 6927 | 6927 | SA24M005 | Stub Setting |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Civil Works Tower 2 Stub Setting | 3 | C0TW0ROW | C000 | 00C3 | C000C0TW0ROW00C3
6928 | 6928 | 6928 | 6928 | SA24M005 | Placement of PCC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Civil Works Tower 2 Placement of PCC | 4 | C0TW0ROW | C000 | 00C4 | C000C0TW0ROW00C4
6929 | 6929 | 6929 | 6929 | SA24M005 | Reinforcement Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Civil Works Tower 2 Reinforcement Works | 5 | C0TW0ROW | C000 | 00C5 | C000C0TW0ROW00C5
6930 | 6930 | 6930 | 6930 | SA24M005 | Concreting / RCC Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Civil Works Tower 2 Concreting / RCC Works | 6 | C0TW0ROW | C000 | 00C6 | C000C0TW0ROW00C6
6931 | 6931 | 6931 | 6931 | SA24M005 | Backfilling |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Civil Works Tower 2 Backfilling | 7 | C0TW0ROW | C000 | 00C7 | C000C0TW0ROW00C7
6932 | 6932 | 6932 | 6932 | SA24M005 | Tower 3 |  | 5 | -1 | 0 |  |  | X
6933 | 6933 | 6933 | 6933 | SA24M005 | ROW / Work Permit |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Civil Works Tower 3 ROW / Work Permit | 1 | CW003 | C000 | 00C1 | C000#Nwgv00C1
6934 | 6934 | 6934 | 6934 | SA24M005 | Excavation / Piping |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Civil Works Tower 3 Excavation / Piping | 2 | CW003 | C000 | 00C2 | C000#Nwgv00C2
6935 | 6935 | 6935 | 6935 | SA24M005 | Stub Setting |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Civil Works Tower 3 Stub Setting | 3 | CW003 | C000 | 00C3 | C000#Nwgv00C3
6936 | 6936 | 6936 | 6936 | SA24M005 | Placement of PCC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Civil Works Tower 3 Placement of PCC | 4 | CW003 | C000 | 00C4 | C000#Nwgv00C4
6937 | 6937 | 6937 | 6937 | SA24M005 | Reinforcement Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Civil Works Tower 3 Reinforcement Works | 5 | CW003 | C000 | 00C5 | C000#Nwgv00C5
6938 | 6938 | 6938 | 6938 | SA24M005 | Concreting / RCC Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Civil Works Tower 3 Concreting / RCC Works | 6 | CW003 | C000 | 00C6 | C000#Nwgv00C6
6939 | 6939 | 6939 | 6939 | SA24M005 | Backfilling |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Civil Works Tower 3 Backfilling | 7 | CW003 | C000 | 00C7 | C000#Nwgv00C7
6940 | 6940 | 6940 | 6940 | SA24M005 | Structure Pad Works |  | 4 | -1 | 0 |  |  | X | C000#Nwgv
6941 | 6941 | 6941 | 6941 | SA24M005 | Tower 1 |  | 5 | -1 | 0 |  |  | X | C000#Nwgv
6942 | 6942 | 6942 | 6942 | SA24M005 | Sub Grade |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Structure Pad Works Tower 1 Sub Grade | 1 | L2STRP | C000 | 00C1 | C000L2STRP00C1
6943 | 6943 | 6943 | 6943 | SA24M005 | Sub Base |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Structure Pad Works Tower 1 Sub Base | 2 | L2STRP | C000 | 00C2 | C000L2STRP00C2
6944 | 6944 | 6944 | 6944 | SA24M005 | Final Layer |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Structure Pad Works Tower 1 Final Layer | 3 | L2STRP | C000 | 00C3 | C000L2STRP00C3
6945 | 6945 | 6945 | 6945 | SA24M005 | Tower 2 |  | 5 | -1 | 0 |  |  | X
6946 | 6946 | 6946 | 6946 | SA24M005 | Sub Grade |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Structure Pad Works Tower 2 Sub Grade | 1 | L2STRG | C000 | 00C1 | C000L2STRG00C1
6947 | 6947 | 6947 | 6947 | SA24M005 | Sub Base |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Structure Pad Works Tower 2 Sub Base | 2 | L2STRG | C000 | 00C2 | C000L2STRG00C2
6948 | 6948 | 6948 | 6948 | SA24M005 | Final Layer |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Structure Pad Works Tower 2 Final Layer | 3 | L2STRG | C000 | 00C3 | C000L2STRG00C3
6949 | 6949 | 6949 | 6949 | SA24M005 | Tower 3 |  | 5 | -1 | 0 |  |  | X
6950 | 6950 | 6950 | 6950 | SA24M005 | Sub Grade |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Structure Pad Works Tower 3 Sub Grade | 1 | STRPAD | C000 | 00C1 | C000#uIfI00C1
6951 | 6951 | 6951 | 6951 | SA24M005 | Sub Base |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Structure Pad Works Tower 3 Sub Base | 2 | STRPAD | C000 | 00C2 | C000#uIfI00C2
6952 | 6952 | 6952 | 6952 | SA24M005 | Final Layer |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Structure Pad Works Tower 3 Final Layer | 3 | STRPAD | C000 | 00C3 | C000#uIfI00C3
6953 | 6953 | 6953 | 6953 | SA24M005 | Erection Works |  | 4 | -1 | 0 |  |  | X | C000#uIfI
6954 | 6954 | 6954 | 6954 | SA24M005 | Tower 1 |  | 5 | -1 | 0 |  |  | X | C000#uIfI
6955 | 6955 | 6955 | 6955 | SA24M005 | Tower Earthing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Erection Works Tower 1 Tower Earthing | 1 | E0TW0 | C000 | 00C1 | C000#gUlV00C1
6956 | 6956 | 6956 | 6956 | SA24M005 | Tower Erection |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Erection Works Tower 1 Tower Erection | 2 | E0TW0 | C000 | 00C2 | C000#gUlV00C2
6957 | 6957 | 6957 | 6957 | SA24M005 | Tack Welding / Tower Tightning & Pal nut Fixing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Erection Works Tower 1 Tack Welding / Tower Tightning & Pal nut Fixing | 3 | E0TW0 | C000 | 00C3 | C000#gUlV00C3
6958 | 6958 | 6958 | 6958 | SA24M005 | Tower 2 |  | 5 | -1 | 0 |  |  | X | C000#gUlV
6959 | 6959 | 6959 | 6959 | SA24M005 | Tower Earthing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Erection Works Tower 2 Tower Earthing | 1 | E0TW | C000 | 00C1 | C000#hdQC00C1
6960 | 6960 | 6960 | 6960 | SA24M005 | Tower Erection |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Erection Works Tower 2 Tower Erection | 2 | E0TW | C000 | 00C2 | C000#hdQC00C2
6961 | 6961 | 6961 | 6961 | SA24M005 | Tack welding / Tower Tightning & Pal nut Fixing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Erection Works Tower 2 Tack welding / Tower Tightning & Pal nut Fixing | 3 | E0TW | C000 | 00C3 | C000#hdQC00C3
6962 | 6962 | 6962 | 6962 | SA24M005 | Tower 3 |  | 5 | -1 | 0 |  |  | X | C000#hdQC
6963 | 6963 | 6963 | 6963 | SA24M005 | Tower Earthing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Erection Works Tower 3 Tower Earthing | 1 | E0TW3 | C000 | 00C1 | C000#RnvW00C1
6964 | 6964 | 6964 | 6964 | SA24M005 | Tower Erection |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Erection Works Tower 3 Tower Erection | 2 | E0TW3 | C000 | 00C2 | C000#RnvW00C2
6965 | 6965 | 6965 | 6965 | SA24M005 | Tack welding / Tower Tightning & Pal nut Fixing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Erection Works Tower 3 Tack welding / Tower Tightning & Pal nut Fixing | 3 | E0TW3 | C000 | 00C3 | C000#RnvW00C3
6966 | 6966 | 6966 | 6966 | SA24M005 | Stringing |  | 4 | -1 | 0 |  |  | X | C000#RnvW
6967 | 6967 | 6967 | 6967 | SA24M005 | Insulator Hoisting |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Stringing Insulator Hoisting | 1 | #TwNx | C000 | 00C1 | C000#TwNx00C1
6968 | 6968 | 6968 | 6968 | SA24M005 | Stringing of Conductor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Stringing Stringing of Conductor | 2 | #TwNx | C000 | 00C2 | C000#TwNx00C2
6969 | 6969 | 6969 | 6969 | SA24M005 | Stringing of OPGW |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Stringing Stringing of OPGW | 3 | #TwNx | C000 | 00C3 | C000#TwNx00C3
6970 | 6970 | 6970 | 6970 | SA24M005 | Paying out & Rough Sag |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Stringing Paying out & Rough Sag | 4 | #TwNx | C000 | 00C4 | C000#TwNx00C4
6971 | 6971 | 6971 | 6971 | SA24M005 | Final Sag of Conductor & OPGW |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Stringing Final Sag of Conductor & OPGW | 5 | #TwNx | C000 | 00C5 | C000#TwNx00C5
6972 | 6972 | 6972 | 6972 | SA24M005 | Spacer Damper fixing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Stringing Spacer Damper fixing | 6 | #TwNx | C000 | 00C6 | C000#TwNx00C6
6973 | 6973 | 6973 | 6973 | SA24M005 | Joint box fixing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Stringing Joint box fixing | 7 | #TwNx | C000 | 00C7 | C000#TwNx00C7
6974 | 6974 | 6974 | 6974 | SA24M005 | Spliceing of OPGW |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 2 Stringing Spliceing of OPGW | 8 | #TwNx | C000 | 00C8 | C000#TwNx00C8
6975 | 6975 | 6975 | 6975 | SA24M005 | Line 3 |  | 3 | -1 | 0 |  |  | X
6976 | 6976 | 6976 | 6976 | SA24M005 | General Works |  | 4 | -1 | 0 |  |  | X
6977 | 6977 | 6977 | 6977 | SA24M005 | Soil Investigation & Thermal Resistivity Measurement |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 General Works Soil Investigation & Thermal Resistivity Measurement | 1 | LGW0SRM | C000 | 00C1 | C000#iTzK00C1
6978 | 6978 | 6978 | 6978 | SA24M005 | Construction of Access Road |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 General Works Construction of Access Road | 2 | LGW0SRM | C000 | 00C2 | C000#iTzK00C2
6979 | 6979 | 6979 | 6979 | SA24M005 | Route Survey |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 General Works Route Survey | 3 | LGW0SRM | C000 | 00C3 | C000#iTzK00C3
6980 | 6980 | 6980 | 6980 | SA24M005 | Civil Works |  | 4 | -1 | 0 |  |  | X | C000#iTzK
6981 | 6981 | 6981 | 6981 | SA24M005 | Tower 1 |  | 5 | -1 | 0 |  |  | X | C000#iTzK
6982 | 6982 | 6982 | 6982 | SA24M005 | ROW / Work Permit |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Civil Works Tower 1 ROW / Work Permit | 1 | CW0TW | C000 | 00C1 | C000#dmyF00C1
6983 | 6983 | 6983 | 6983 | SA24M005 | Excavation / Piping |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Civil Works Tower 1 Excavation / Piping | 2 | CW0TW | C000 | 00C2 | C000#dmyF00C2
6984 | 6984 | 6984 | 6984 | SA24M005 | Stub Setting |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Civil Works Tower 1 Stub Setting | 3 | CW0TW | C000 | 00C3 | C000#dmyF00C3
6985 | 6985 | 6985 | 6985 | SA24M005 | Placement of PCC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Civil Works Tower 1 Placement of PCC | 4 | CW0TW | C000 | 00C4 | C000#dmyF00C4
6986 | 6986 | 6986 | 6986 | SA24M005 | Reinforcement Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Civil Works Tower 1 Reinforcement Works | 5 | CW0TW | C000 | 00C5 | C000#dmyF00C5
6987 | 6987 | 6987 | 6987 | SA24M005 | Concreting / RCC Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Civil Works Tower 1 Concreting / RCC Works | 6 | CW0TW | C000 | 00C6 | C000#dmyF00C6
6988 | 6988 | 6988 | 6988 | SA24M005 | Backfilling |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Civil Works Tower 1 Backfilling | 7 | CW0TW | C000 | 00C7 | C000#dmyF00C7
6989 | 6989 | 6989 | 6989 | SA24M005 | Tower 2 |  | 5 | -1 | 0 |  |  | X | C000#dmyF
6990 | 6990 | 6990 | 6990 | SA24M005 | ROW / Work Permit |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Civil Works Tower 2 ROW / Work Permit | 1 | CW00TR | C000 | 00C1 | C000#Wxme00C1
6991 | 6991 | 6991 | 6991 | SA24M005 | Excavation / Piping |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Civil Works Tower 2 Excavation / Piping | 2 | CW00TR | C000 | 00C2 | C000#Wxme00C2
6992 | 6992 | 6992 | 6992 | SA24M005 | Stub Setting |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Civil Works Tower 2 Stub Setting | 3 | CW00TR | C000 | 00C3 | C000#Wxme00C3
6993 | 6993 | 6993 | 6993 | SA24M005 | Placement of PCC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Civil Works Tower 2 Placement of PCC | 4 | CW00TR | C000 | 00C4 | C000#Wxme00C4
6994 | 6994 | 6994 | 6994 | SA24M005 | Reinforcement Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Civil Works Tower 2 Reinforcement Works | 5 | CW00TR | C000 | 00C5 | C000#Wxme00C5
6995 | 6995 | 6995 | 6995 | SA24M005 | Concreting / RCC Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Civil Works Tower 2 Concreting / RCC Works | 6 | CW00TR | C000 | 00C6 | C000#Wxme00C6
6996 | 6996 | 6996 | 6996 | SA24M005 | Backfilling |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Civil Works Tower 2 Backfilling | 7 | CW00TR | C000 | 00C7 | C000#Wxme00C7
6997 | 6997 | 6997 | 6997 | SA24M005 | Tower 3 |  | 5 | -1 | 0 |  |  | X | C000#Wxme
6998 | 6998 | 6998 | 6998 | SA24M005 | ROW / Work Permit |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Civil Works Tower 3 ROW / Work Permit | 1 | C0TW0 | C000 | 00C1 | C000C0TW000C1
6999 | 6999 | 6999 | 6999 | SA24M005 | Excavation / Piping |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Civil Works Tower 3 Excavation / Piping | 2 | C0TW0 | C000 | 00C2 | C000C0TW000C2
7000 | 7000 | 7000 | 7000 | SA24M005 | Stub Setting |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Civil Works Tower 3 Stub Setting | 3 | C0TW0 | C000 | 00C3 | C000C0TW000C3
7001 | 7001 | 7001 | 7001 | SA24M005 | Placement of PCC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Civil Works Tower 3 Placement of PCC | 4 | C0TW0 | C000 | 00C4 | C000C0TW000C4
7002 | 7002 | 7002 | 7002 | SA24M005 | Reinforcement Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Civil Works Tower 3 Reinforcement Works | 5 | C0TW0 | C000 | 00C5 | C000C0TW000C5
7003 | 7003 | 7003 | 7003 | SA24M005 | Concreting / RCC Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Civil Works Tower 3 Concreting / RCC Works | 6 | C0TW0 | C000 | 00C6 | C000C0TW000C6
7004 | 7004 | 7004 | 7004 | SA24M005 | Backfilling |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Civil Works Tower 3 Backfilling | 7 | C0TW0 | C000 | 00C7 | C000C0TW000C7
7005 | 7005 | 7005 | 7005 | SA24M005 | Structure Pad Works |  | 4 | -1 | 0 |  |  | X
7006 | 7006 | 7006 | 7006 | SA24M005 | Tower 1 |  | 5 | -1 | 0 |  |  | X
7007 | 7007 | 7007 | 7007 | SA24M005 | Sub Grade |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Structure Pad Works Tower 1 Sub Grade | 1 | L3STRP1 | C000 | 00C1 | C000L3STRP100C1
7008 | 7008 | 7008 | 7008 | SA24M005 | Sub Base |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Structure Pad Works Tower 1 Sub Base | 2 | L3STRP1 | C000 | 00C2 | C000L3STRP100C2
7009 | 7009 | 7009 | 7009 | SA24M005 | Final Layer |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Structure Pad Works Tower 1 Final Layer | 3 | L3STRP1 | C000 | 00C3 | C000L3STRP100C3
7010 | 7010 | 7010 | 7010 | SA24M005 | Tower 2 |  | 5 | -1 | 0 |  |  | X
7011 | 7011 | 7011 | 7011 | SA24M005 | Sub Grade |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Structure Pad Works Tower 2 Sub Grade | 1 | STRPAD2 | C000 | 00C1 | C000STRPAD200C1
7012 | 7012 | 7012 | 7012 | SA24M005 | Sub Base |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Structure Pad Works Tower 2 Sub Base | 2 | STRPAD2 | C000 | 00C2 | C000STRPAD200C2
7013 | 7013 | 7013 | 7013 | SA24M005 | Final Layer |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Structure Pad Works Tower 2 Final Layer | 3 | STRPAD2 | C000 | 00C3 | C000STRPAD200C3
7014 | 7014 | 7014 | 7014 | SA24M005 | Tower 3 |  | 5 | -1 | 0 |  |  | X
7015 | 7015 | 7015 | 7015 | SA24M005 | Sub Grade |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Structure Pad Works Tower 3 Sub Grade | 1 | STRPAD3 | C000 | 00C1 | C000STRPAD300C1
7016 | 7016 | 7016 | 7016 | SA24M005 | Sub Base |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Structure Pad Works Tower 3 Sub Base | 2 | STRPAD3 | C000 | 00C2 | C000STRPAD300C2
7017 | 7017 | 7017 | 7017 | SA24M005 | Final Layer |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Structure Pad Works Tower 3 Final Layer | 3 | STRPAD3 | C000 | 00C3 | C000STRPAD300C3
7018 | 7018 | 7018 | 7018 | SA24M005 | Erection Works |  | 4 | -1 | 0 |  |  | X
7019 | 7019 | 7019 | 7019 | SA24M005 | Tower 1 |  | 5 | -1 | 0 |  |  | X
7020 | 7020 | 7020 | 7020 | SA24M005 | Tower Earthing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Erection Works Tower 1 Tower Earthing | 1 | E0TW0 | C000 | 00C1 | C000#tUNO00C1
7021 | 7021 | 7021 | 7021 | SA24M005 | Tower Erection |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Erection Works Tower 1 Tower Erection | 2 | E0TW0 | C000 | 00C2 | C000#tUNO00C2
7022 | 7022 | 7022 | 7022 | SA24M005 | Tack Welding / Tower Tightning & Pal nut Fixing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Erection Works Tower 1 Tack Welding / Tower Tightning & Pal nut Fixing | 3 | E0TW0 | C000 | 00C3 | C000#tUNO00C3
7023 | 7023 | 7023 | 7023 | SA24M005 | Tower 2 |  | 5 | -1 | 0 |  |  | X | C000#tUNO
7024 | 7024 | 7024 | 7024 | SA24M005 | Tower Earthing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Erection Works Tower 2 Tower Earthing | 1 | E0TW | C000 | 00C1 | C000#JETJ00C1
7025 | 7025 | 7025 | 7025 | SA24M005 | Tower Erection |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Erection Works Tower 2 Tower Erection | 2 | E0TW | C000 | 00C2 | C000#JETJ00C2
7026 | 7026 | 7026 | 7026 | SA24M005 | Tack welding / Tower Tightning & Pal nut Fixing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Erection Works Tower 2 Tack welding / Tower Tightning & Pal nut Fixing | 3 | E0TW | C000 | 00C3 | C000#JETJ00C3
7027 | 7027 | 7027 | 7027 | SA24M005 | Tower 3 |  | 5 | -1 | 0 |  |  | X | C000#JETJ
7028 | 7028 | 7028 | 7028 | SA24M005 | Tower Earthing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Erection Works Tower 3 Tower Earthing | 1 | E0TW | C000 | 00C1 | C000#GiEm00C1
7029 | 7029 | 7029 | 7029 | SA24M005 | Tower Erection |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Erection Works Tower 3 Tower Erection | 2 | E0TW | C000 | 00C2 | C000#GiEm00C2
7030 | 7030 | 7030 | 7030 | SA24M005 | Tack welding / Tower Tightning & Pal nut Fixing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Erection Works Tower 3 Tack welding / Tower Tightning & Pal nut Fixing | 3 | E0TW | C000 | 00C3 | C000#GiEm00C3
7031 | 7031 | 7031 | 7031 | SA24M005 | Stringing |  | 4 | -1 | 0 |  |  | X | C000#GiEm
7032 | 7032 | 7032 | 7032 | SA24M005 | Insulator Hoisting |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Stringing Insulator Hoisting | 1 | #KSUa | C000 | 00C1 | C000#KSUa00C1
7033 | 7033 | 7033 | 7033 | SA24M005 | Stringing of Conductor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Stringing Stringing of Conductor | 2 | #KSUa | C000 | 00C2 | C000#KSUa00C2
7034 | 7034 | 7034 | 7034 | SA24M005 | Stringing of OPGW |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Stringing Stringing of OPGW | 3 | #KSUa | C000 | 00C3 | C000#KSUa00C3
7035 | 7035 | 7035 | 7035 | SA24M005 | Paying out & Rough Sag |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Stringing Paying out & Rough Sag | 4 | #KSUa | C000 | 00C4 | C000#KSUa00C4
7036 | 7036 | 7036 | 7036 | SA24M005 | Final Sag of Conductor & OPGW |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Stringing Final Sag of Conductor & OPGW | 5 | #KSUa | C000 | 00C5 | C000#KSUa00C5
7037 | 7037 | 7037 | 7037 | SA24M005 | Spacer Damper fixing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Stringing Spacer Damper fixing | 6 | #KSUa | C000 | 00C6 | C000#KSUa00C6
7038 | 7038 | 7038 | 7038 | SA24M005 | Joint box fixing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Stringing Joint box fixing | 7 | #KSUa | C000 | 00C7 | C000#KSUa00C7
7039 | 7039 | 7039 | 7039 | SA24M005 | Spliceing of OPGW |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 3 Stringing Spliceing of OPGW | 8 | #KSUa | C000 | 00C8 | C000#KSUa00C8
7040 | 7040 | 7040 | 7040 | SA24M005 | Line 4 |  | 3 | -1 | 0 |  |  | X
7041 | 7041 | 7041 | 7041 | SA24M005 | General Works |  | 4 | -1 | 0 |  |  | X
7042 | 7042 | 7042 | 7042 | SA24M005 | Soil Investigation & Thermal Resistivity Measurement |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 General Works Soil Investigation & Thermal Resistivity Measurement | 1 | LGW0SRM | C000 | 00C1 | C000#pVLy00C1
7043 | 7043 | 7043 | 7043 | SA24M005 | Construction of Access Road |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 General Works Construction of Access Road | 2 | LGW0SRM | C000 | 00C2 | C000#pVLy00C2
7044 | 7044 | 7044 | 7044 | SA24M005 | Route Survey |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 General Works Route Survey | 3 | LGW0SRM | C000 | 00C3 | C000#pVLy00C3
7045 | 7045 | 7045 | 7045 | SA24M005 | Civil Works |  | 4 | -1 | 0 |  |  | X | C000#pVLy
7046 | 7046 | 7046 | 7046 | SA24M005 | Tower 1 |  | 5 | -1 | 0 |  |  | X | C000#pVLy
7047 | 7047 | 7047 | 7047 | SA24M005 | ROW / Work Permit |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Civil Works Tower 1 ROW / Work Permit | 1 | CW0TW1 | C000 | 00C1 | C000CW0TW100C1
7048 | 7048 | 7048 | 7048 | SA24M005 | Excavation / Piping |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Civil Works Tower 1 Excavation / Piping | 2 | CW0TW1 | C000 | 00C2 | C000CW0TW100C2
7049 | 7049 | 7049 | 7049 | SA24M005 | Stub Setting |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Civil Works Tower 1 Stub Setting | 3 | CW0TW1 | C000 | 00C3 | C000CW0TW100C3
7050 | 7050 | 7050 | 7050 | SA24M005 | Placement of PCC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Civil Works Tower 1 Placement of PCC | 4 | CW0TW1 | C000 | 00C4 | C000CW0TW100C4
7051 | 7051 | 7051 | 7051 | SA24M005 | Reinforcement Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Civil Works Tower 1 Reinforcement Works | 5 | CW0TW1 | C000 | 00C5 | C000CW0TW100C5
7052 | 7052 | 7052 | 7052 | SA24M005 | Concreting / RCC Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Civil Works Tower 1 Concreting / RCC Works | 6 | CW0TW1 | C000 | 00C6 | C000CW0TW100C6
7053 | 7053 | 7053 | 7053 | SA24M005 | Backfilling |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Civil Works Tower 1 Backfilling | 7 | CW0TW1 | C000 | 00C7 | C000CW0TW100C7
7054 | 7054 | 7054 | 7054 | SA24M005 | Tower 2 |  | 5 | -1 | 0 |  |  | X
7055 | 7055 | 7055 | 7055 | SA24M005 | ROW / Work Permit |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Civil Works Tower 2 ROW / Work Permit | 1 | CW00TR2 | C000 | 00C1 | C000CW00TR200C1
7056 | 7056 | 7056 | 7056 | SA24M005 | Excavation / Piping |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Civil Works Tower 2 Excavation / Piping | 2 | CW00TR2 | C000 | 00C2 | C000CW00TR200C2
7057 | 7057 | 7057 | 7057 | SA24M005 | Stub Setting |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Civil Works Tower 2 Stub Setting | 3 | CW00TR2 | C000 | 00C3 | C000CW00TR200C3
7058 | 7058 | 7058 | 7058 | SA24M005 | Placement of PCC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Civil Works Tower 2 Placement of PCC | 4 | CW00TR2 | C000 | 00C4 | C000CW00TR200C4
7059 | 7059 | 7059 | 7059 | SA24M005 | Reinforcement Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Civil Works Tower 2 Reinforcement Works | 5 | CW00TR2 | C000 | 00C5 | C000CW00TR200C5
7060 | 7060 | 7060 | 7060 | SA24M005 | Concreting / RCC Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Civil Works Tower 2 Concreting / RCC Works | 6 | CW00TR2 | C000 | 00C6 | C000CW00TR200C6
7061 | 7061 | 7061 | 7061 | SA24M005 | Backfilling |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Civil Works Tower 2 Backfilling | 7 | CW00TR2 | C000 | 00C7 | C000CW00TR200C7
7062 | 7062 | 7062 | 7062 | SA24M005 | Tower 3 |  | 5 | -1 | 0 |  |  | X
7063 | 7063 | 7063 | 7063 | SA24M005 | ROW / Work Permit |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Civil Works Tower 3 ROW / Work Permit | 1 | CW0TW | C000 | 00C1 | C000#OXcS00C1
7064 | 7064 | 7064 | 7064 | SA24M005 | Excavation / Piping |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Civil Works Tower 3 Excavation / Piping | 2 | CW0TW | C000 | 00C2 | C000#OXcS00C2
7065 | 7065 | 7065 | 7065 | SA24M005 | Stub Setting |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Civil Works Tower 3 Stub Setting | 3 | CW0TW | C000 | 00C3 | C000#OXcS00C3
7066 | 7066 | 7066 | 7066 | SA24M005 | Placement of PCC |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Civil Works Tower 3 Placement of PCC | 4 | CW0TW | C000 | 00C4 | C000#OXcS00C4
7067 | 7067 | 7067 | 7067 | SA24M005 | Reinforcement Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Civil Works Tower 3 Reinforcement Works | 5 | CW0TW | C000 | 00C5 | C000#OXcS00C5
7068 | 7068 | 7068 | 7068 | SA24M005 | Concreting / RCC Works |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Civil Works Tower 3 Concreting / RCC Works | 6 | CW0TW | C000 | 00C6 | C000#OXcS00C6
7069 | 7069 | 7069 | 7069 | SA24M005 | Backfilling |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Civil Works Tower 3 Backfilling | 7 | CW0TW | C000 | 00C7 | C000#OXcS00C7
7070 | 7070 | 7070 | 7070 | SA24M005 | Structure Pad Works |  | 4 | -1 | 0 |  |  | X | C000#OXcS
7071 | 7071 | 7071 | 7071 | SA24M005 | Tower 1 |  | 5 | -1 | 0 |  |  | X | C000#OXcS
7072 | 7072 | 7072 | 7072 | SA24M005 | Sub Grade |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Structure Pad Works Tower 1 Sub Grade | 1 | STRPAD | C000 | 00C1 | C000#smpa00C1
7073 | 7073 | 7073 | 7073 | SA24M005 | Sub Base |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Structure Pad Works Tower 1 Sub Base | 2 | STRPAD | C000 | 00C2 | C000#smpa00C2
7074 | 7074 | 7074 | 7074 | SA24M005 | Final Layer |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Structure Pad Works Tower 1 Final Layer | 3 | STRPAD | C000 | 00C3 | C000#smpa00C3
7075 | 7075 | 7075 | 7075 | SA24M005 | Tower 2 |  | 5 | -1 | 0 |  |  | X | C000#smpa
7076 | 7076 | 7076 | 7076 | SA24M005 | Sub Grade |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Structure Pad Works Tower 2 Sub Grade | 1 | STRPAD | C000 | 00C1 | C000#URAf00C1
7077 | 7077 | 7077 | 7077 | SA24M005 | Sub Base |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Structure Pad Works Tower 2 Sub Base | 2 | STRPAD | C000 | 00C2 | C000#URAf00C2
7078 | 7078 | 7078 | 7078 | SA24M005 | Final Layer |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Structure Pad Works Tower 2 Final Layer | 3 | STRPAD | C000 | 00C3 | C000#URAf00C3
7079 | 7079 | 7079 | 7079 | SA24M005 | Tower 3 |  | 5 | -1 | 0 |  |  | X | C000#URAf
7080 | 7080 | 7080 | 7080 | SA24M005 | Sub Grade |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Structure Pad Works Tower 3 Sub Grade | 1 | STRPAD003 | C000 | 00C1 | C000STRPAD00300C1
7081 | 7081 | 7081 | 7081 | SA24M005 | Sub Base |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Structure Pad Works Tower 3 Sub Base | 2 | STRPAD003 | C000 | 00C2 | C000STRPAD00300C2
7082 | 7082 | 7082 | 7082 | SA24M005 | Final Layer |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Structure Pad Works Tower 3 Final Layer | 3 | STRPAD003 | C000 | 00C3 | C000STRPAD00300C3
7083 | 7083 | 7083 | 7083 | SA24M005 | Erection Works |  | 4 | -1 | 0 |  |  | X
7084 | 7084 | 7084 | 7084 | SA24M005 | Tower 1 |  | 5 | -1 | 0 |  |  | X
7085 | 7085 | 7085 | 7085 | SA24M005 | Tower Earthing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Erection Works Tower 1 Tower Earthing | 1 | E0TW0 | C000 | 00C1 | C000#FCtq00C1
7086 | 7086 | 7086 | 7086 | SA24M005 | Tower Erection |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Erection Works Tower 1 Tower Erection | 2 | E0TW0 | C000 | 00C2 | C000#FCtq00C2
7087 | 7087 | 7087 | 7087 | SA24M005 | Tack Welding / Tower Tightning & Pal nut Fixing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Erection Works Tower 1 Tack Welding / Tower Tightning & Pal nut Fixing | 3 | E0TW0 | C000 | 00C3 | C000#FCtq00C3
7088 | 7088 | 7088 | 7088 | SA24M005 | Tower 2 |  | 5 | -1 | 0 |  |  | X | C000#FCtq
7089 | 7089 | 7089 | 7089 | SA24M005 | Tower Earthing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Erection Works Tower 2 Tower Earthing | 1 | E0TW | C000 | 00C1 | C000#WbSt00C1
7090 | 7090 | 7090 | 7090 | SA24M005 | Tower Erection |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Erection Works Tower 2 Tower Erection | 2 | E0TW | C000 | 00C2 | C000#WbSt00C2
7091 | 7091 | 7091 | 7091 | SA24M005 | Tack welding / Tower Tightning & Pal nut Fixing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Erection Works Tower 2 Tack welding / Tower Tightning & Pal nut Fixing | 3 | E0TW | C000 | 00C3 | C000#WbSt00C3
7092 | 7092 | 7092 | 7092 | SA24M005 | Tower 3 |  | 5 | -1 | 0 |  |  | X | C000#WbSt
7093 | 7093 | 7093 | 7093 | SA24M005 | Tower Earthing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Erection Works Tower 3 Tower Earthing | 1 | E0TW3 | X | 00X1 | XE0TW300X1
7094 | 7094 | 7094 | 7094 | SA24M005 | Tower Erection |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Erection Works Tower 3 Tower Erection | 2 | E0TW3 | X | 00X2 | XE0TW300X2
7095 | 7095 | 7095 | 7095 | SA24M005 | Tack welding / Tower Tightning & Pal nut Fixing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Erection Works Tower 3 Tack welding / Tower Tightning & Pal nut Fixing | 3 | E0TW3 | X | 00X3 | XE0TW300X3
7096 | 7096 | 7096 | 7096 | SA24M005 | Stringing |  | 4 | -1 | 0 |  |  | X
7097 | 7097 | 7097 | 7097 | SA24M005 | Insulator Hoisting |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Stringing Insulator Hoisting | 1 | LINS | C000 | 00C1 | C000LINS00C1
7098 | 7098 | 7098 | 7098 | SA24M005 | Stringing of Conductor |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Stringing Stringing of Conductor | 2 | LINS | C000 | 00C2 | C000LINS00C2
7099 | 7099 | 7099 | 7099 | SA24M005 | Stringing of OPGW |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Stringing Stringing of OPGW | 3 | LINS | C000 | 00C3 | C000LINS00C3
7100 | 7100 | 7100 | 7100 | SA24M005 | Paying out & Rough Sag |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Stringing Paying out & Rough Sag | 4 | LINS | C000 | 00C4 | C000LINS00C4
7101 | 7101 | 7101 | 7101 | SA24M005 | Final Sag of Conductor & OPGW |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Stringing Final Sag of Conductor & OPGW | 5 | LINS | C000 | 00C5 | C000LINS00C5
7102 | 7102 | 7102 | 7102 | SA24M005 | Spacer Damper fixing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Stringing Spacer Damper fixing | 6 | LINS | C000 | 00C6 | C000LINS00C6
7103 | 7103 | 7103 | 7103 | SA24M005 | Joint box fixing |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Stringing Joint box fixing | 7 | LINS | C000 | 00C7 | C000LINS00C7
7104 | 7104 | 7104 | 7104 | SA24M005 | Spliceing of OPGW |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Construction & Installation Works Line 4 Stringing Spliceing of OPGW | 8 | LINS | C000 | 00C8 | C000LINS00C8
7105 | 7105 | 7105 | 7105 | SA24M005 | Testing & Commissioning |  | 2 | -1 | 0 |  |  | X
7106 | 7106 | 7106 | 7106 | SA24M005 | Line 1 (North Qassim # 9061 - Qassim 1 # 9010 / Qassim 3 # 9029) |  | 3 | -1 | 0 |  |  | X
7107 | 7107 | 7107 | 7107 | SA24M005 | Electrical Tests |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Testing & Commissioning Line 1 (North Qassim # 9061 - Qassim 1 # 9010 / Qassim 3 # 9029) Electrical Tests | 1 | E0LGT1 | E000 | 00E1 | E000E0LGT100E1
7108 | 7108 | 7108 | 7108 | SA24M005 | Communication Tests |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Testing & Commissioning Line 1 (North Qassim # 9061 - Qassim 1 # 9010 / Qassim 3 # 9029) Communication Tests | 2 | E0LGT1 | E000 | 00E2 | E000E0LGT100E2
7109 | 7109 | 7109 | 7109 | SA24M005 | Line 2 (North Qassim # 9061 - AL Zulfi # 9064) |  | 3 | -1 | 0 |  |  | X
7110 | 7110 | 7110 | 7110 | SA24M005 | Electrical Tests |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Testing & Commissioning Line 2 (North Qassim # 9061 - AL Zulfi # 9064) Electrical Tests | 1 | E0LGT2 | E000 | 00E1 | E000E0LGT200E1
7111 | 7111 | 7111 | 7111 | SA24M005 | Communication Tests |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Testing & Commissioning Line 2 (North Qassim # 9061 - AL Zulfi # 9064) Communication Tests | 2 | E0LGT2 | E000 | 00E2 | E000E0LGT200E2
7112 | 7112 | 7112 | 7112 | SA24M005 | Line 3 (North Qassim # 9061 - Qassim 1 # 9010) |  | 3 | -1 | 0 |  |  | X
7113 | 7113 | 7113 | 7113 | SA24M005 | Electrical Tests |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Testing & Commissioning Line 3 (North Qassim # 9061 - Qassim 1 # 9010) Electrical Tests | 1 | E0LGT3 | E000 | 00E1 | E000E0LGT300E1
7114 | 7114 | 7114 | 7114 | SA24M005 | Communication Tests |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Testing & Commissioning Line 3 (North Qassim # 9061 - Qassim 1 # 9010) Communication Tests | 2 | E0LGT3 | E000 | 00E2 | E000E0LGT300E2
7115 | 7115 | 7115 | 7115 | SA24M005 | Line 4 (North Qassim # 9061 - Khuf # 9006 / Qassim 4 # 9032) |  | 3 | -1 | 0 |  |  | X
7116 | 7116 | 7116 | 7116 | SA24M005 | Electrical Tests |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Testing & Commissioning Line 4 (North Qassim # 9061 - Khuf # 9006 / Qassim 4 # 9032) Electrical Tests | 1 | E0LGT4 | E000 | 00E1 | E000E0LGT400E1
7117 | 7117 | 7117 | 7117 | SA24M005 | Communication Tests |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Testing & Commissioning Line 4 (North Qassim # 9061 - Khuf # 9006 / Qassim 4 # 9032) Communication Tests | 2 | E0LGT4 | E000 | 00E2 | E000E0LGT400E2
7118 | 7118 | 7118 | 7118 | SA24M005 | Prechecks |  | 4 | -1 | 0 |  |  | X
7119 | 7119 | 7119 | 7119 | SA24M005 | Remote End-4(BSP# 9032 OHTL Lines) 380kV |  | 5 | -1 | 0 |  |  | X
7120 | 7120 | 7120 | 7120 | SA24M005 | MCB Test In Control And Protection Panels |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Testing & Commissioning Line 4 (North Qassim # 9061 - Khuf # 9006 / Qassim 4 # 9032) Prechecks Remote End-4(BSP# 9032 OHTL Lines) 380kV MCB Test In Control And Protection Panels | 1 | MCBP | E000 | 00E1 | E000MCBP00E1
7121 | 7121 | 7121 | 7121 | SA24M005 | Auxiliary/Trip Relay Test In Control And Protection Panels |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Testing & Commissioning Line 4 (North Qassim # 9061 - Khuf # 9006 / Qassim 4 # 9032) Prechecks Remote End-4(BSP# 9032 OHTL Lines) 380kV Auxiliary/Trip Relay Test In Control And Protection Panels | 2 | MCBP | E000 | 00E2 | E000MCBP00E2
7122 | 7122 | 7122 | 7122 | SA24M005 | VT Secondary Circuit Injection & Loop Resistance |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Testing & Commissioning Line 4 (North Qassim # 9061 - Khuf # 9006 / Qassim 4 # 9032) Prechecks Remote End-4(BSP# 9032 OHTL Lines) 380kV VT Secondary Circuit Injection & Loop Resistance | 3 | MCBP | E000 | 00E3 | E000MCBP00E3
7123 | 7123 | 7123 | 7123 | SA24M005 | CT Loop Resistance and Single Earth Point |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Testing & Commissioning Line 4 (North Qassim # 9061 - Khuf # 9006 / Qassim 4 # 9032) Prechecks Remote End-4(BSP# 9032 OHTL Lines) 380kV CT Loop Resistance and Single Earth Point | 4 | MCBP | E000 | 00E4 | E000MCBP00E4
7124 | 7124 | 7124 | 7124 | SA24M005 | Scheme Check For Line Protection |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Testing & Commissioning Line 4 (North Qassim # 9061 - Khuf # 9006 / Qassim 4 # 9032) Prechecks Remote End-4(BSP# 9032 OHTL Lines) 380kV Scheme Check For Line Protection | 5 | MCBP | E000 | 00E5 | E000MCBP00E5
7125 | 7125 | 7125 | 7125 | SA24M005 | Set 1 Line Differential Relay Acceptance Test |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Testing & Commissioning Line 4 (North Qassim # 9061 - Khuf # 9006 / Qassim 4 # 9032) Prechecks Remote End-4(BSP# 9032 OHTL Lines) 380kV Set 1 Line Differential Relay Acceptance Test | 6 | MCBP | E000 | 00E6 | E000MCBP00E6
7126 | 7126 | 7126 | 7126 | SA24M005 | Set 2 Line Differential Relay Acceptance Test |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Testing & Commissioning Line 4 (North Qassim # 9061 - Khuf # 9006 / Qassim 4 # 9032) Prechecks Remote End-4(BSP# 9032 OHTL Lines) 380kV Set 2 Line Differential Relay Acceptance Test | 7 | MCBP | E000 | 00E7 | E000MCBP00E7
7127 | 7127 | 7127 | 7127 | SA24M005 | Commissioning |  | 4 | -1 | 0 |  |  | X
7128 | 7128 | 7128 | 7128 | SA24M005 | Remote End-4(BSP# 9032 OHTL Lines) 380kV |  | 5 | -1 | 0 |  |  | X
7129 | 7129 | 7129 | 7129 | SA24M005 | MCB Test In Control And Protection Panels |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Testing & Commissioning Line 4 (North Qassim # 9061 - Khuf # 9006 / Qassim 4 # 9032) Commissioning Remote End-4(BSP# 9032 OHTL Lines) 380kV MCB Test In Control And Protection Panels | 1 | MCBC | E000 | 00E1 | E000MCBC00E1
7130 | 7130 | 7130 | 7130 | SA24M005 | Auxiliary/Trip Relay Test In Control And Protection Panels |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Testing & Commissioning Line 4 (North Qassim # 9061 - Khuf # 9006 / Qassim 4 # 9032) Commissioning Remote End-4(BSP# 9032 OHTL Lines) 380kV Auxiliary/Trip Relay Test In Control And Protection Panels | 2 | MCBC | E000 | 00E2 | E000MCBC00E2
7131 | 7131 | 7131 | 7131 | SA24M005 | VT Secondary Circuit Injection & Loop Resistance |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Testing & Commissioning Line 4 (North Qassim # 9061 - Khuf # 9006 / Qassim 4 # 9032) Commissioning Remote End-4(BSP# 9032 OHTL Lines) 380kV VT Secondary Circuit Injection & Loop Resistance | 3 | MCBC | E000 | 00E3 | E000MCBC00E3
7132 | 7132 | 7132 | 7132 | SA24M005 | CT Loop Resistance and Single Earth Point |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Testing & Commissioning Line 4 (North Qassim # 9061 - Khuf # 9006 / Qassim 4 # 9032) Commissioning Remote End-4(BSP# 9032 OHTL Lines) 380kV CT Loop Resistance and Single Earth Point | 4 | MCBC | E000 | 00E4 | E000MCBC00E4
7133 | 7133 | 7133 | 7133 | SA24M005 | Scheme Check For Line Protection |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Testing & Commissioning Line 4 (North Qassim # 9061 - Khuf # 9006 / Qassim 4 # 9032) Commissioning Remote End-4(BSP# 9032 OHTL Lines) 380kV Scheme Check For Line Protection | 5 | MCBC | E000 | 00E5 | E000MCBC00E5
7134 | 7134 | 7134 | 7134 | SA24M005 | Set 1 Line Differential Relay Acceptance Test |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Testing & Commissioning Line 4 (North Qassim # 9061 - Khuf # 9006 / Qassim 4 # 9032) Commissioning Remote End-4(BSP# 9032 OHTL Lines) 380kV Set 1 Line Differential Relay Acceptance Test | 6 | MCBC | E000 | 00E6 | E000MCBC00E6
7135 | 7135 | 7135 | 7135 | SA24M005 | Set 2 Line Differential Relay Acceptance Test |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Testing & Commissioning Line 4 (North Qassim # 9061 - Khuf # 9006 / Qassim 4 # 9032) Commissioning Remote End-4(BSP# 9032 OHTL Lines) 380kV Set 2 Line Differential Relay Acceptance Test | 7 | MCBC | E000 | 00E7 | E000MCBC00E7
7136 | 7136 | 7136 | 7136 | SA24M005 | Main 1 Multifunction Relay Final Setting Test |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Testing & Commissioning Line 4 (North Qassim # 9061 - Khuf # 9006 / Qassim 4 # 9032) Commissioning Remote End-4(BSP# 9032 OHTL Lines) 380kV Main 1 Multifunction Relay Final Setting Test | 8 | MCBC | E000 | 00E8 | E000MCBC00E8
7137 | 7137 | 7137 | 7137 | SA24M005 | Main 2 Multifunction Relay Final setting Test |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Testing & Commissioning Line 4 (North Qassim # 9061 - Khuf # 9006 / Qassim 4 # 9032) Commissioning Remote End-4(BSP# 9032 OHTL Lines) 380kV Main 2 Multifunction Relay Final setting Test | 9 | MCBC | E000 | 00E9 | E000MCBC00E9
7138 | 7138 | 7138 | 7138 | SA24M005 | Alarm And Indication Check Up To SAS HMI And Gateway For EHV |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Testing & Commissioning Line 4 (North Qassim # 9061 - Khuf # 9006 / Qassim 4 # 9032) Commissioning Remote End-4(BSP# 9032 OHTL Lines) 380kV Alarm And Indication Check Up To SAS HMI And Gateway For EHV | 10 | MCBC | E000 | 0E10 | E000MCBC0E10
7139 | 7139 | 7139 | 7139 | SA24M005 | Closed Loop Test EHV |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Testing & Commissioning Line 4 (North Qassim # 9061 - Khuf # 9006 / Qassim 4 # 9032) Commissioning Remote End-4(BSP# 9032 OHTL Lines) 380kV Closed Loop Test EHV | 11 | MCBC | E000 | 0E11 | E000MCBC0E11
7140 | 7140 | 7140 | 7140 | SA24M005 | EHV Line Feeder Set 1 Multifunction Relay |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Testing & Commissioning Line 4 (North Qassim # 9061 - Khuf # 9006 / Qassim 4 # 9032) Commissioning Remote End-4(BSP# 9032 OHTL Lines) 380kV EHV Line Feeder Set 1 Multifunction Relay | 12 | MCBC | E000 | 0E12 | E000MCBC0E12
7141 | 7141 | 7141 | 7141 | SA24M005 | EHV Line Feeder Set 2 Multifunction Relay |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Testing & Commissioning Line 4 (North Qassim # 9061 - Khuf # 9006 / Qassim 4 # 9032) Commissioning Remote End-4(BSP# 9032 OHTL Lines) 380kV EHV Line Feeder Set 2 Multifunction Relay | 13 | MCBC | E000 | 0E13 | E000MCBC0E13
7142 | 7142 | 7142 | 7142 | SA24M005 | Final Trip Test for EHV |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Testing & Commissioning Line 4 (North Qassim # 9061 - Khuf # 9006 / Qassim 4 # 9032) Commissioning Remote End-4(BSP# 9032 OHTL Lines) 380kV Final Trip Test for EHV | 14 | MCBC | E000 | 0E14 | E000MCBC0E14
7143 | 7143 | 7143 | 7143 | SA24M005 | Relay Final settings Review for EHV |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Testing & Commissioning Line 4 (North Qassim # 9061 - Khuf # 9006 / Qassim 4 # 9032) Commissioning Remote End-4(BSP# 9032 OHTL Lines) 380kV Relay Final settings Review for EHV | 15 | MCBC | E000 | 0E15 | E000MCBC0E15
7144 | 7144 | 7144 | 7144 | SA24M005 | Normalization Before Energization EHV |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Testing & Commissioning Line 4 (North Qassim # 9061 - Khuf # 9006 / Qassim 4 # 9032) Commissioning Remote End-4(BSP# 9032 OHTL Lines) 380kV Normalization Before Energization EHV | 16 | MCBC | E000 | 0E16 | E000MCBC0E16
7145 | 7145 | 7145 | 7145 | SA24M005 | Post Energization In Service Test for EHV |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Testing & Commissioning Line 4 (North Qassim # 9061 - Khuf # 9006 / Qassim 4 # 9032) Commissioning Remote End-4(BSP# 9032 OHTL Lines) 380kV Post Energization In Service Test for EHV | 17 | MCBC | E000 | 0E17 | E000MCBC0E17
7146 | 7146 | 7146 | 7146 | SA24M005 | Energization for EHV |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Testing & Commissioning Line 4 (North Qassim # 9061 - Khuf # 9006 / Qassim 4 # 9032) Commissioning Remote End-4(BSP# 9032 OHTL Lines) 380kV Energization for EHV | 18 | MCBC | E000 | 0E18 | E000MCBC0E18
7147 | 7147 | 7147 | 7147 | SA24M005 | Project Close Out Activities |  | 2 | -1 | 0 |  |  | X
7148 | 7148 | 7148 | 7148 | SA24M005 | As Built Drawings |  | 3 | -1 | 0 |  |  | X
7149 | 7149 | 7149 | 7149 | SA24M005 | Preparation of Red Mark Up From Site |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Project Close Out Activities As Built Drawings Preparation of Red Mark Up From Site | 1 | A0RMR | C000 | 00C1 | C000#WFPM00C1
7150 | 7150 | 7150 | 7150 | SA24M005 | Preparation of Draft As Built Drawings |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Project Close Out Activities As Built Drawings Preparation of Draft As Built Drawings | 2 | A0RMR | C000 | 00C2 | C000#WFPM00C2
7151 | 7151 | 7151 | 7151 | SA24M005 | As Built Review and Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Project Close Out Activities As Built Drawings As Built Review and Approval | 3 | A0RMR | C000 | 00C3 | C000#WFPM00C3
7152 | 7152 | 7152 | 7152 | SA24M005 | SEED II - Drawings Submittal & Approval |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Project Close Out Activities As Built Drawings SEED II - Drawings Submittal & Approval | 4 | A0RMR | C000 | 00C4 | C000#WFPM00C4
7153 | 7153 | 7153 | 7153 | SA24M005 | Demobilization |  | 3 | -1 | 0 |  |  | X | C000#WFPM
7154 | 7154 | 7154 | 7154 | SA24M005 | Removal of Temporary Facilities |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Project Close Out Activities Demobilization Removal of Temporary Facilities | 1 | DTEMF | C000 | 00C1 | C000#jTiw00C1
7155 | 7155 | 7155 | 7155 | SA24M005 | Removal of Camp Facilities |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Project Close Out Activities Demobilization Removal of Camp Facilities | 2 | DTEMF | C000 | 00C2 | C000#jTiw00C2
7156 | 7156 | 7156 | 7156 | SA24M005 | Demobilization & Clean up |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Project Close Out Activities Demobilization Demobilization & Clean up | 3 | DTEMF | C000 | 00C3 | C000#jTiw00C3
7157 | 7157 | 7157 | 7157 | SA24M005 | Acceptance Certificate |  | 2 | -1 | 0 |  |  | X | C000#jTiw
7158 | 7158 | 7158 | 7158 | SA24M005 | TCC (Technical Completion Certificate) |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Acceptance Certificate TCC (Technical Completion Certificate) | 1 | DECL | C000 | 00C1 | C000DECL00C1
7159 | 7159 | 7159 | 7159 | SA24M005 | PAC (Preliminary Completion Certificate) |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Acceptance Certificate PAC (Preliminary Completion Certificate) | 2 | DECL | C000 | 00C2 | C000DECL00C2
7160 | 7160 | 7160 | 7160 | SA24M005 | FAC (Final Acceptance Certificate) |  | 0 | Project Portion- II (Construction of 380kV OHTL's) Acceptance Certificate FAC (Final Acceptance Certificate) | 3 | DECL | C000 | 00C3 | C000DECL00C3
7161 | 7161 | 7161 | 7161 | SA24M005 | Remote Normalization Before Energization |  | 1 | -1 | 0 |  |  | X
7162 | 7162 | 7162 | 7162 | SA24M005 | Normalization Before Energization EHV |  | 0 | Remote Normalization Before Energization Normalization Before Energization EHV | 1 | E0RNB | E000 | 00E1 | E000E0RNB00E1
7163 | 7163 | 7163 | 7163 | SA24M005 | Energization for EHV |  | 0 | Remote Normalization Before Energization Energization for EHV | 2 | E0RNB | E000 | 00E2 | E000E0RNB00E2
7164 | 7164 | 7164 | 7164 | SA24M005 | Post Energization In Service Test for EHV |  | 0 | Remote Normalization Before Energization Post Energization In Service Test for EHV | 3 | E0RNB | E000 | 00E3 | E000E0RNB00E3